## CAT DE55E0 GENSETS (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 15.03.2021 | COMMENTS 16.03.2021 | COMMENTS 28.04.2021 | COMMENTS 29.04.2021 | COMMENTS 30.04.2021 | COMMENTS 03.05.2021 | COMMENTS 05.05.2021 | COMMENTS 06.05.2021 | COMMENTS 07.05.2021 | COMMENTS 10.05.2021 | COMMENTS 11.05.2021 | COMMENTS 12.05.2021 | COMMENTS 13.05.2021 | COMMENTS 14.05.2021 | COMMENTS 17.05.2021 | COMMENTS 18.05.2021 | COMMENTS 19.05.2021 | COMMENTS 20.05.2021 | COMMENTS 24.05.2021
BA1599 | CAT DE55E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4985384 * 5011555 * 5897314 | * EC506529 * E3S09450 * M2500600 | FML2103DSI1076 | COD 2021 162495 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1076 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KASUMBALESA AS OF 17.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1600 | CAT DE55E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4985384 * 5011555 * 5897314 | * EC506526 * E3S09445 * M2500599 | FML2103DSI1076 | COD 2021 165921 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1076 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KASUMBALESA AS OF 17.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1601 | CAT DE55E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4985384 * 5011555 * 5897314 | * EC506527 * E3S09444 * M2500598 | FML2103DSI1076 | COD 2021 162488 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1076 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KASUMBALESA AS OF 17.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1602 | CAT DE55E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4985384 * 5011555 * 5897314 | * EC506520 * E3S09453 * M2500592 | FML2103DSI1076 | COD 2021 162493 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1076 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KASUMBALESA AS OF 17.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1603 | CAT DE55E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4985384 * 5011555 * 5897315 | * EC506525 * E3S09449 * M2500596 | FML2103DSI1076 | COD 2021 162512 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1076 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KASUMBALESA AS OF 17.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1604 | CAT DE65E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4985384 * 5011555 * 5897315 | * EC506528 * E3S09441 * M2500605 | FML2103DSI1076 | COD 2021 162513 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1076 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * THE VESSEL SHANGAI IS DUE TO ARRIVE IN DURBAN PORT ON THE 20.04.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KASUMBALESA AS OF 17.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021

## CAT DE88E0 GENSETS (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 28.04.2021 | COMMENTS 29.04.2021 | COMMENTS 30.04.2021 | COMMENTS 03.05.2021 | COMMENTS 05.05.2021 | COMMENTS 06.05.2021 | COMMENTS 07.05.2021 | COMMENTS 10.05.2021 | COMMENTS 11.05.2021 | COMMENTS 12.05.2021 | COMMENTS 13.05.2021 | COMMENTS 14.05.2021 | COMMENTS 17.05.2021 | COMMENTS 18.05.2021 | COMMENTS 19.05.2021 | COMMENTS 20.05.2021 | COMMENTS 24.05.2021
BA1605 | CAT DE88E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512502 * 4508025 * 5897316 | * EC902601 * ZRE02460 * M2800663 | FML2103DSI1077 | COD 2021 162501 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1077 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1606 | CAT DE55E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512502 * 4508025 * 5897316 | * EC902602 * ZRE02462 * M2800664 | FML2103DSI1077 | COD 2021 162492 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1077 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1607 | CAT DE55E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512502 * 4508025 * 5897316 | * EC902603 * ZRE02458 * M2800661 | FML2103DSI1077 | COD 2021 165916 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1077 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1608 | CAT DE55E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512502 * 4508025 * 5897316 | * EC902600 * ZRE02459 * M2800662 | FML2103DSI1077 | COD 2021 165917 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1077 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021
BA1613 | CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 5854458 * 5787141 * 5029783 | * LXJ05900 * LXL00742 * LWL04021 | FML2103DSI1077 | COD 2021 162511 | ACR6803 | ACR7931T/ACR7781T | 2103DSI1077 | 06.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021 | 28.04.2021 | 01.05.2021 | 03.05.2021 | 05.05.2021 | 08.05.2021 | 09.05.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 20.05.2021 | 20.05.2021 | 21.05.2021 | 23.05.2021 | 24.05.2021 | * VEHICLE ON STANDBY TO COLLECT THE CONTAINER FROM PORT TOMMORW THE 29.04.2021 | * TRUCK IS AT OUR DURBAN FACILITY AWAITING BV TO BE DONE ON THE 30.04.2021 | * AWAITING BV TO BE DONE TODAY.TRUCK TO DIPACTH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 03.05.2021 EN-ROUTE TO BEITBRIDGE BORDER. | * TRUCK CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 TRUCK TO DISPATCH TODAY EN ROUTE TO BEITBRIDGE BORDER | * TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE AS OF 06.05.2021 | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE BORDER AS OF 07.05.2021 | * TRUCK AT BANKET MASHOLAND WEST. ZIMBABWE EN-ROUTE TO CHIRUNDU AS OF 10.05.2021 | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT CHIRUNDU AS OF 11.05.2021 UNDERGOING CUSTOM FORMALITIES | * TRUCK AT NDOLA AS OF 13.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT KONKOLA AS OF 14.05.2021 EN-ROUTE TO KASUMBALESA | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * TRUCK AT WHISKEY PARKING AREA AWAITING FINAL RELEASE AS OF 19.05.2021 | * VEHICLE OFFLOADED AS OF 24.05.2021

## 1 X 140K (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 29.04.2021 | COMMENTS 30.04.2021 | COMMENTS 03.05.2021 | COMMENTS 04.05.2021 | COMMENTS 05.05.2021 | COMMENTS 06.05.2021 | COMMENTS 10.05.2021 | COMMENTS 11.05.2021 | COMMENTS 12.05.2021 | COMMENTS 13.05.2021 | COMMENTS 14.05.2021 | COMMENTS 17.05.2021 | COMMENTS 18.05.2021 | COMMENTS 19.05.2021 | COMMENTS 20.05.2021 | COMMENTS 22.05.2021
BA1573 | 1 X NEW CAT 140K MOTOR GRADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | SZL20494 | TX710797 | 2103DSI1081 | COD 2021 185549 | ND834401 | ND854241 | ND59099 | 06/05/2021 | * VEHICLE OFFLOADED AS OF 22.05.2021 | 28.04.2021 | 03.05.2021 | 05.05.2021 | 07.05.2021 | 08.05.2021 | 10.05.2021 | 11.05.2021 | 12.05.2021 | 13.05.2021 | 14.05.2021 | 16.05.2021 | 17.05.2021 | 19.05.2021 | 20.05.2021 | 22.05.2021 | * VEHCILE AT OUR DURBAN FACILITY AS OF 29.04.2021 BV BOOKED FOR THE 30.04.2021 | * BV BOOKED FOR TODAY.PLANNING TO DISPATCH THE TRUCK EN-ROUTE TO BEITBRIDGE TODAY | * TRUCK TO DISPACTH TODAY EN-ROUTE TO BEIT BRIDGE BORDER AS OF 03.05.2021 | * TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER AS OF 05.05.2021 | * TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER AS OF 05.05.2021 | * TRUCK AT ROEDTAN EN-ROUTE TO BEITBRIDGE BORDER AS OF 06.05.2021 | * TRUCK AT BEITBRIDGE RSA SIDE AS OF 10.05.2021 UNDERGOING FINAL CLEARANCE | * TRUCK AT CHIRUNDU ZIM SIDE AS OF 11.05.2021 | * TRUCK AT CHIRUNDU ZAM SIDE AS OF 12.05.2021 | * TRUCK AT CHIRUNDU ZAM SIDE AS OF 12.05.2021 | * TRUCK AT CHIBOMBO EN-ROUTE TO KASUMBALESA BORDER AS OF 14.05.2021 | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * VEHICLE OFFLOADED AS OF 22.05.2021
BA1610 | CAT DE165E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4594468 * 4551479 * 5897319 | * ECW04896 * KRG09293 * M2800659 | 2103DSI1076 | COD 2021 162509 | ND834401 | ND854241 | ND59099 | 06/05/2021 | * VEHICLE OFFLOADED AS OF 22.05.2021 | 28.04.2021 | 03.05.2021 | 05.05.2021 | 07.05.2021 | 08.05.2021 | 10.05.2021 | 11.05.2021 | 12.05.2021 | 13.05.2021 | 14.05.2021 | 16.05.2021 | 17.05.2021 | 19.05.2021 | 20.05.2021 | 22.05.2021 | * VEHCILE AT OUR DURBAN FACILITY AS OF 29.04.2021 BV BOOKED FOR THE 30.04.2021 | * BV BOOKED FOR TODAY.PLANNING TO DISPATCH THE TRUCK EN-ROUTE TO BEITBRIDGE TODAY | * TRUCK TO DISPACTH TODAY EN-ROUTE TO BEIT BRIDGE BORDER AS OF 03.05.2021 | * TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER AS OF 05.05.2021 | * TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER AS OF 05.05.2021 | * TRUCK AT ROEDTAN EN-ROUTE TO BEITBRIDGE BORDER AS OF 06.05.2021 | * TRUCK AT BEITBRIDGE RSA SIDE AS OF 10.05.2021 UNDERGOING FINAL CLEARANCE | * TRUCK AT CHIRUNDU ZIM SIDE AS OF 11.05.2021 | * TRUCK AT CHIRUNDU ZAM SIDE AS OF 12.05.2021 | * TRUCK AT CHIRUNDU ZAM SIDE AS OF 12.05.2021 | * TRUCK AT CHIBOMBO EN-ROUTE TO KASUMBALESA BORDER AS OF 14.05.2021 | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * VEHICLE OFFLOADED AS OF 22.05.2021
BA1611 | CAT DE165E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4594468 * 4551479 * 5897319 | * ECW04897 * KRG09294 * M2800658 | 2103DSI1076 | COD 2021 162505 | ND834401 | ND854241 | ND59099 | 06/05/2021 | * VEHICLE OFFLOADED AS OF 22.05.2021 | 28.04.2021 | 03.05.2021 | 05.05.2021 | 07.05.2021 | 08.05.2021 | 10.05.2021 | 11.05.2021 | 12.05.2021 | 13.05.2021 | 14.05.2021 | 16.05.2021 | 17.05.2021 | 19.05.2021 | 20.05.2021 | 22.05.2021 | * VEHCILE AT OUR DURBAN FACILITY AS OF 29.04.2021 BV BOOKED FOR THE 30.04.2021 | * BV BOOKED FOR TODAY.PLANNING TO DISPATCH THE TRUCK EN-ROUTE TO BEITBRIDGE TODAY | * TRUCK TO DISPACTH TODAY EN-ROUTE TO BEIT BRIDGE BORDER AS OF 03.05.2021 | * TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER AS OF 05.05.2021 | * TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER AS OF 05.05.2021 | * TRUCK AT ROEDTAN EN-ROUTE TO BEITBRIDGE BORDER AS OF 06.05.2021 | * TRUCK AT BEITBRIDGE RSA SIDE AS OF 10.05.2021 UNDERGOING FINAL CLEARANCE | * TRUCK AT CHIRUNDU ZIM SIDE AS OF 11.05.2021 | * TRUCK AT CHIRUNDU ZAM SIDE AS OF 12.05.2021 | * TRUCK AT CHIRUNDU ZAM SIDE AS OF 12.05.2021 | * TRUCK AT CHIBOMBO EN-ROUTE TO KASUMBALESA BORDER AS OF 14.05.2021 | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * TRUCK AT WHISKEY AS OF 17.05.2021 AWAITING FINAL FORMALITIES | * VEHICLE OFFLOADED AS OF 22.05.2021

## 1 x CAT 390 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 29.04.2021 | COMMENTS 30.04.2021 | COMMENTS 03.05.2021 | COMMENTS 04.05.2021 | COMMENTS 05.05.2021 | COMMENTS 06.05.2021 | COMMENTS 07.05.2021 | COMMENTS 10.05.2021 | COMMENTS 11.05.2021 | COMMENTS 12.05.2021 | COMMENTS 13.05.2021 | COMMENTS 14.05.2021 | COMMENTS 17.05.2021 | COMMENTS 18.05.2021 | COMMENTS 19.05.2021 | COMMENTS 20.05.2021 | COMMENTS 24.05.2021 | COMMENTS 25.05.2021 | COMMENTS 26.05.2021 | COMMENTS 27.05.2021 | COMMENTS 28.05.2021
BA1565 | 1 X NEW CAT 390FL HYDRAULIC EXCAVATOR MAIN BODY | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GAY20225 | CAT0390FTGAY20225 | TXW05809 | 210DSI1031 | COD 2021 185550 | CR83TPGP | DH27VWGP/DH06WWGP | ND59697 | 06/05/2021 | * VEHICLE OFFLOADED AS OF 17.05.2021 | 02.02.2021 | 30.04.2021 | 04.05.2021 | 05.05.2021 | 06.05.2021 | 08.05.2021 | 09.05.2021 | 12.05.2021 | 13.05.2021 | 14.05.2021 | 14.05.2021 | 15.05.2021 | 15.05.2021 | 16.05.2021 | 17.05.2021 | LOADING TODAY AS OF 29.04.2021. PLANNING TO DISPATCH THE 30.04.2021 | LOADING TODAY AS OF 29.04.2021. PLANNING TO DISPATCH THE 30.04.2022 | * TRUCK CURTRENTLY AT JOHANNESBURG AS OF 03.05.2021 | * TRUCK CURTRENTLY AT JOHANNESBURG AS OF 04.05.2021.AWAITING PERMIT | * TRUCK SHOULD BE AT BEITBRIDGE SHORTLEY | * TRUCK CURTRENTLY AT BEITBRIDGE RSA SIDE AS OF 06.05.2021 | * TRUCK CURTRENTLY BUBI EN-ROUTE TO CHIRUNDU AS OF 07.05.2021 | * TRUCK CURRENTLY AT CHIRUNDU ZAM SIDE AS OF 10.05.2021 | * TRUCK CURRENTLY AT KAFUE EN-ROUTE TO KASUMBALESA AS OF 11.05.2021 | * TRUCK CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA AS OF 12.05.2021 | * TRUCK CURRENTLY AT KASUMBALESA ZAM SIDE AS OF 13.05.2021 | * AWAITING CUSTOM FORMALITIES | * TRUCK OFFLOADED AS OF 17.05.2021 | * TRUCK OFFLOADED AS OF 17.05.2021 | * TRUCK OFFLOADED AS OF 17.05.2021 | * TRUCK OFFLOADED AS OF 17.05.2021 | * TRUCK OFFLOADED AS OF 17.05.2021 | * TRUCK OFFLOADED AS OF 17.05.2021 | * TRUCK OFFLOADED AS OF 17.05.2021 | * TRUCK OFFLOADED AS OF 17.05.2021 | * VEHICLE OFFLOADED AS OF 17.05.2021
BA1565 | * CYLINDER * COUNTER WEIGHT * PLATEN * BOOM * PARTS * STICK | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GAY20225 | CAT0390FTGAY20225 | TXW05809 | 210DSI1031 | COD 2021 185550 | AAV3878 | ACG7257T/ACG7258T | ND59697-2 | 06/05/2021 | * VEHICLE OFFLOADED AS OF 27.05.2021 | 02.02.2021 | 30.04.2021 | 04.05.2021 | 05.05.2021 | 06.05.2021 | 08.05.2021 | 12.05.2021 | 12.05.2021 | 13.05.2021 | 21.05.2021 | 25.05.2021 | 26.05.2021 | 26.05.2021 | 27.05.2021 | 27.05.2021 | LOADING TODAY AS OF 29.04.2021. PLANNING TO DISPATCH THE 30.04.2021 | LOADING TODAY AS OF 29.04.2021. PLANNING TO DISPATCH THE 30.04.2022 | * TRUCK CURTRENTLY AT JOHANNESBURG AS OF 03.05.2021 | * TRUCK CURTRENTLY AT JOHANNESBURG AS OF 04.05.2021 EN-ROUTE TO BEITBRIDGE | * TRUCK SHOULD BE AT BEITBRIDGE SHORTLEY | * TRUCK CURTRENTLY AT BEITBRIDGE RSA SIDE AS OF 06.05.2021 | * TRUCK CURTRENTLY RUTENGA EN-ROUTE TO CHIRUNDU AS OF 07.05.2021 | * TRUCK CURRENTLY AT CHIRUNDU ZIM SIDE AS OF 10.05.2021 | * TRUCK CURRENTLY AT CHIRUNDU ZIM SIDE AS OF 10.05.2021 | * TRUCK CURRENTLY AT CHIRUNDU ZAM SIDE AS OF 12.05.2021 | * AWAITING FINAL CUSTOM FORMALITIES | * TRUCK TO DISPATCH CHIRUNDU TODAY THE 14.05.2021 | * TRUCK AT NDOLA EN-ROUTE TO SITE AS OF 17.05.2021 | * TRUCK ON SITE AWAITING TO OFFLOAD AS OF 17.05.2021 | * TRUCK CURRENTLY AT KASUMBALESA ZAM AS OF 19.05.2021 | * TRUCK CURRENTLY ON SITE AS OF 20.05.2021 | * VEHICLE CURRENTLY AT KAUMBALESA DRC SIDE WAITING RELEASE AS OF 24.05.2021 | * VEHICLE CURRENTLY AT KAUMBALESA DRC SIDE WAITING RELEASE AS OF 25.05.2021 | * VEHICLE CURRENTLY AT WHISKY AS OF 26.05.2021 | * VEHICLE ON SITE WAITING TO OFFLOAD AS OF 27.05.2021 | * VEHICLE OFFLOADED AS OF 27.05.2021

## CAT DE13.5E3 GENSETS (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 07.05.2021 | COMMENTS 10.05.2021 | COMMENTS 11.05.2021 | COMMENTS 12.05.2021 | COMMENTS 12.05.2021 | COMMENTS 14.05.2021 | COMMENTS 17.05.2021 | COMMENTS 18.05.2021 | COMMENTS 19.05.2021 | COMMENTS 20.05.2021 | COMMENTS 24.05.2021 | COMMENTS 25.05.2021 | COMMENTS 26.05.2021 | COMMENTS 27.05.2021 | COMMENTS 28.05.2021 | COMMENTS 28.05.2021 | COMMENTS 31.05.2021 | COMMENTS 01.06.2021 | COMMENTS 02.06.2021 | COMMENTS 03.06.2021 | COMMENTS 04.06.2021
BA1592 | CAT DE13.5E3 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512481 * 4488966 * 5849904 | * GB903759 * W2203636 * TT901883 | 2104DSI1106 | COD 2021 174466 | 471-JF50LRGP | NLN116GP | 2104DSI1106 | 20/05/2021 | * VEHICLE OFFLOADED AS OF 03.06.2021 | 09.05.2021 | 20.05.2021 | 22.05.2021 | 24.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 30.05.2021 | 31.05.2021 | 01.06.2021 | 03.04.2021 | 03.04.2021 | 03.04.2021 | * THE VESSEL JEAN MERMOZ IS DUE TO ARRIVE IN DURBAN PORT ON THE 09.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 10.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 11.05.2021 | * CUSTOMS INSPECTION BOOKED FOR TODAY THE 12.05.2021. ONCE DONE THE CONTAINER WILL BE TRANSPORTER TO OUR FACILITY | * CUSTOMS INSPECTION WILL BE BOOKED ONCE AT OUR FACILITY | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.CUSTOMS INSPECTION TO BE DONE TODAY 18.05.2021 | * TRUCK LOADED.AWAITING XE CUSTOMS RELEASE IN ORDER TO DISPACTH THE TRUCK AS OF 19.05.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO JOHANNESBURG AS OF 20.05.2021 | * VEHILE CURRENT AT BEITBRIDGE. ZIM SIDE. WAITING CLEARANCE AS OF 24.05.2021 | * VEHILE CURRENT AT MASVINGO - ENROUTE HARARE AS OF 25.05.2021 | * VEHILE ENROUTE HARARE AS OF 26.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 27.05.2021 | * VEHICLE AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 01.06.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 02.06.2021 | * VEHILCE CURRENTLY ENROUTE LUBUMBASHI AS OF 03.06.2021 | * VEHICLE OFFLOADED AS OF 03.06.2021
BA1593 | CAT DE13.5E3 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512481 * 4488966 * 5849904 | * GB903760 * W2203635 * TT901880 | 2104DSI1106 | COD 2021 174466 | 471-JF50LRGP | NLN116GP | 2104DSI1106 | 20/05/2021 | * VEHICLE OFFLOADED AS OF 03.06.2021 | 09.05.2021 | 20.05.2021 | 22.05.2021 | 24.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 30.05.2021 | 31.05.2021 | 01.06.2021 | 03.04.2021 | 03.04.2021 | 03.04.2021 | * THE VESSEL JEAN MERMOZ IS DUE TO ARRIVE IN DURBAN PORT ON THE 09.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 10.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 11.05.2021 | * CUSTOMS INSPECTION BOOKED FOR TODAY THE 12.05.2021. ONCE DONE THE CONTAINER WILL BE TRANSPORTER TO OUR FACILITY | * CUSTOMS INSPECTION WILL BE BOOKED ONCE AT OUR FACILITY | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.CUSTOMS INSPECTION TO BE DONE TODAY 18.05.2021 | * TRUCK LOADED.AWAITING XE CUSTOMS RELEASE IN ORDER TO DISPACTH THE TRUCK AS OF 19.05.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO JOHANNESBURG AS OF 20.05.2021 | * VEHILE CURRENT AT BEITBRIDGE. ZIM SIDE. WAITING CLEARANCE AS OF 24.05.2021 | * VEHILE CURRENT AT MASVINGO - ENROUTE HARARE AS OF 25.05.2021 | * VEHILE ENROUTE HARARE AS OF 26.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 27.05.2021 | * VEHICLE AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 01.06.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 02.06.2021 | * VEHILCE CURRENTLY ENROUTE LUBUMBASHI AS OF 03.06.2021 | * VEHICLE OFFLOADED AS OF 03.06.2021
BA1594 | CAT DE22E3 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512485 * 4489035 * 5849908 | * GBY11486 * SM811419 * TT901943 | 2104DSI1106 | COD 2021 174466 | 471-JF50LRGP | NLN116GP | 2104DSI1106 | 20/05/2021 | * VEHICLE OFFLOADED AS OF 03.06.2021 | 09.05.2021 | 20.05.2021 | 22.05.2021 | 24.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 30.05.2021 | 31.05.2021 | 01.06.2021 | 03.04.2021 | 03.04.2021 | 03.04.2021 | * THE VESSEL JEAN MERMOZ IS DUE TO ARRIVE IN DURBAN PORT ON THE 09.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 10.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 11.05.2021 | * CUSTOMS INSPECTION BOOKED FOR TODAY THE 12.05.2021. ONCE DONE THE CONTAINER WILL BE TRANSPORTER TO OUR FACILITY | * CUSTOMS INSPECTION WILL BE BOOKED ONCE AT OUR FACILITY | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.CUSTOMS INSPECTION TO BE DONE TODAY 18.05.2021 | * TRUCK LOADED.AWAITING XE CUSTOMS RELEASE IN ORDER TO DISPACTH THE TRUCK AS OF 19.05.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO JOHANNESBURG AS OF 20.05.2021 | * VEHILE CURRENT AT BEITBRIDGE. ZIM SIDE. WAITING CLEARANCE AS OF 24.05.2021 | * VEHILE CURRENT AT MASVINGO - ENROUTE HARARE AS OF 25.05.2021 | * VEHILE ENROUTE HARARE AS OF 26.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 27.05.2021 | * VEHICLE AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 01.06.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 02.06.2021 | * VEHILCE CURRENTLY ENROUTE LUBUMBASHI AS OF 03.06.2021 | * VEHICLE OFFLOADED AS OF 03.06.2021
BA1595 | CAT DE22E3 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512485 * 4489035 * 5849908 | * GBY11484 * SM811418 * TT901948 | 2104DSI1106 | COD 2021 174466 | 471-JF50LRGP | NLN116GP | 2104DSI1106 | 20/05/2021 | * VEHICLE OFFLOADED AS OF 03.06.2021 | 09.05.2021 | 20.05.2021 | 22.05.2021 | 24.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 30.05.2021 | 31.05.2021 | 01.06.2021 | 03.04.2021 | 03.04.2021 | 03.04.2021 | * THE VESSEL JEAN MERMOZ IS DUE TO ARRIVE IN DURBAN PORT ON THE 09.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 10.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 11.05.2021 | * CUSTOMS INSPECTION BOOKED FOR TODAY THE 12.05.2021. ONCE DONE THE CONTAINER WILL BE TRANSPORTER TO OUR FACILITY | * CUSTOMS INSPECTION WILL BE BOOKED ONCE AT OUR FACILITY | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.CUSTOMS INSPECTION TO BE DONE TODAY 18.05.2021 | * TRUCK LOADED.AWAITING XE CUSTOMS RELEASE IN ORDER TO DISPACTH THE TRUCK AS OF 19.05.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO JOHANNESBURG AS OF 20.05.2021 | * VEHILE CURRENT AT BEITBRIDGE. ZIM SIDE. WAITING CLEARANCE AS OF 24.05.2021 | * VEHILE CURRENT AT MASVINGO - ENROUTE HARARE AS OF 25.05.2021 | * VEHILE ENROUTE HARARE AS OF 26.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 27.05.2021 | * VEHICLE AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 01.06.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 02.06.2021 | * VEHILCE CURRENTLY ENROUTE LUBUMBASHI AS OF 03.06.2021 | * VEHICLE OFFLOADED AS OF 03.06.2021
BA1596 | CAT DE22E3 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4512485 * 4489035 * 5849908 | * GBY11485 * SM811415 * TT901950 | 2104DSI1106 | COD 2021 174466 | 471-JF50LRGP | NLN116GP | 2104DSI1106 | 20/05/2021 | * VEHICLE OFFLOADED AS OF 03.06.2021 | 09.05.2021 | 20.05.2021 | 22.05.2021 | 24.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 30.05.2021 | 31.05.2021 | 01.06.2021 | 03.04.2021 | 03.04.2021 | 03.04.2021 | * THE VESSEL JEAN MERMOZ IS DUE TO ARRIVE IN DURBAN PORT ON THE 09.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 10.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 11.05.2021 | * CUSTOMS INSPECTION BOOKED FOR TODAY THE 12.05.2021. ONCE DONE THE CONTAINER WILL BE TRANSPORTER TO OUR FACILITY | * CUSTOMS INSPECTION WILL BE BOOKED ONCE AT OUR FACILITY | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.CUSTOMS INSPECTION TO BE DONE TODAY 18.05.2021 | * TRUCK LOADED.AWAITING XE CUSTOMS RELEASE IN ORDER TO DISPACTH THE TRUCK AS OF 19.05.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO JOHANNESBURG AS OF 20.05.2021 | * VEHILE CURRENT AT BEITBRIDGE. ZIM SIDE. WAITING CLEARANCE AS OF 24.05.2021 | * VEHILE CURRENT AT MASVINGO - ENROUTE HARARE AS OF 25.05.2021 | * VEHILE ENROUTE HARARE AS OF 26.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 27.05.2021 | * VEHICLE AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 01.06.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 02.06.2021 | * VEHILCE CURRENTLY ENROUTE LUBUMBASHI AS OF 03.06.2021 | * VEHICLE OFFLOADED AS OF 03.06.2021
BA1597 | CAT DE33E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4985380 * 5010890 * 5897312 | * EC304826 * E3S09653 * M2500672 | 2104DSI1106 | COD 2021 174466 | 471-JF50LRGP | NLN116GP | 2104DSI1106 | 20/05/2021 | * VEHICLE OFFLOADED AS OF 03.06.2021 | 09.05.2021 | 20.05.2021 | 22.05.2021 | 24.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 30.05.2021 | 31.05.2021 | 01.06.2021 | 03.04.2021 | 03.04.2021 | 03.04.2021 | * THE VESSEL JEAN MERMOZ IS DUE TO ARRIVE IN DURBAN PORT ON THE 09.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 10.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 11.05.2021 | * CUSTOMS INSPECTION BOOKED FOR TODAY THE 12.05.2021. ONCE DONE THE CONTAINER WILL BE TRANSPORTER TO OUR FACILITY | * CUSTOMS INSPECTION WILL BE BOOKED ONCE AT OUR FACILITY | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.CUSTOMS INSPECTION TO BE DONE TODAY 18.05.2021 | * TRUCK LOADED.AWAITING XE CUSTOMS RELEASE IN ORDER TO DISPACTH THE TRUCK AS OF 19.05.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO JOHANNESBURG AS OF 20.05.2021 | * VEHILE CURRENT AT BEITBRIDGE. ZIM SIDE. WAITING CLEARANCE AS OF 24.05.2021 | * VEHILE CURRENT AT MASVINGO - ENROUTE HARARE AS OF 25.05.2021 | * VEHILE ENROUTE HARARE AS OF 26.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 27.05.2021 | * VEHICLE AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 01.06.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 02.06.2021 | * VEHILCE CURRENTLY ENROUTE LUBUMBASHI AS OF 03.06.2021 | * VEHICLE OFFLOADED AS OF 03.06.2021
BA1598 | CAT DE33E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4985380 * 5010890 * 5897312 | * EC304827 * E3S09654 * M2500673 | 2104DSI1106 | COD 2021 174466 | 471-JF50LRGP | NLN116GP | 2104DSI1106 | 20/05/2021 | * VEHICLE OFFLOADED AS OF 03.06.2021 | 09.05.2021 | 20.05.2021 | 22.05.2021 | 24.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 30.05.2021 | 31.05.2021 | 01.06.2021 | 03.04.2021 | 03.04.2021 | 03.04.2021 | * THE VESSEL JEAN MERMOZ IS DUE TO ARRIVE IN DURBAN PORT ON THE 09.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 10.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 11.05.2021 | * CUSTOMS INSPECTION BOOKED FOR TODAY THE 12.05.2021. ONCE DONE THE CONTAINER WILL BE TRANSPORTER TO OUR FACILITY | * CUSTOMS INSPECTION WILL BE BOOKED ONCE AT OUR FACILITY | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.CUSTOMS INSPECTION TO BE DONE TODAY 18.05.2021 | * TRUCK LOADED.AWAITING XE CUSTOMS RELEASE IN ORDER TO DISPACTH THE TRUCK AS OF 19.05.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO JOHANNESBURG AS OF 20.05.2021 | * VEHILE CURRENT AT BEITBRIDGE. ZIM SIDE. WAITING CLEARANCE AS OF 24.05.2021 | * VEHILE CURRENT AT MASVINGO - ENROUTE HARARE AS OF 25.05.2021 | * VEHILE ENROUTE HARARE AS OF 26.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 27.05.2021 | * VEHICLE AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 01.06.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 02.06.2021 | * VEHILCE CURRENTLY ENROUTE LUBUMBASHI AS OF 03.06.2021 | * VEHICLE OFFLOADED AS OF 03.06.2021
BA1609 | CAT DE150E0 GENSETS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | * 4677716 * 4643099 * 5897318 | * GTY01329 * KRG09324 * M2800751 | 2104DSI1106 | COD 2021 174466 | 471-JF50LRGP | NLN116GP | 2104DSI1106 | 20/05/2021 | * VEHICLE OFFLOADED AS OF 03.06.2021 | 09.05.2021 | 20.05.2021 | 22.05.2021 | 24.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 30.05.2021 | 31.05.2021 | 01.06.2021 | 03.04.2021 | 03.04.2021 | 03.04.2021 | * THE VESSEL JEAN MERMOZ IS DUE TO ARRIVE IN DURBAN PORT ON THE 09.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 10.05.2021 | * THE VESSEL JEAN MERMOZ HAS BERTH DURBAN PORT.AWAITING CUSTOMS INSPECTION ONCE CONTAINER IS GROUNDED AS OF 11.05.2021 | * CUSTOMS INSPECTION BOOKED FOR TODAY THE 12.05.2021. ONCE DONE THE CONTAINER WILL BE TRANSPORTER TO OUR FACILITY | * CUSTOMS INSPECTION WILL BE BOOKED ONCE AT OUR FACILITY | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.BV AND INSPECTION WILL TAKE PLACE ON MONDAY THE 17.05.2021 | * CONTAINER IS AT OUR FACILITY.CUSTOMS INSPECTION TO BE DONE TODAY 18.05.2021 | * TRUCK LOADED.AWAITING XE CUSTOMS RELEASE IN ORDER TO DISPACTH THE TRUCK AS OF 19.05.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO JOHANNESBURG AS OF 20.05.2021 | * VEHILE CURRENT AT BEITBRIDGE. ZIM SIDE. WAITING CLEARANCE AS OF 24.05.2021 | * VEHILE CURRENT AT MASVINGO - ENROUTE HARARE AS OF 25.05.2021 | * VEHILE ENROUTE HARARE AS OF 26.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 27.05.2021 | * VEHICLE AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE AS OF 31.05.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 01.06.2021 | * VEHILCE CURRENTLY AT WHISKY AWAITING RELEASE AS OF 02.06.2021 | * VEHILCE CURRENTLY ENROUTE LUBUMBASHI AS OF 03.06.2021 | * VEHICLE OFFLOADED AS OF 03.06.2021

## 2 X CAT 395 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 30.04.2021 | COMMENTS 03.05.2021 | COMMENTS 04.05.2021 | COMMENTS 05.05.2021 | COMMENTS 06.05.2021 | COMMENTS 07.05.2021 | COMMENTS 10.05.2021 | COMMENTS 11.05.2021 | COMMENTS 12.05.2021 | COMMENTS 13.05.2021 | COMMENTS 14.05.2021 | COMMENTS 17.05.2021 | COMMENTS 18.05.2021 | COMMENTS 19.05.2021 | COMMENTS 20.05.2021 | COMEMNTS 24.05.2021 | COMMENTS 25.05.2021 | COMMENTS 26.05.2021 | COMMENTS 27.05.2021 | COMMENTS 28.05.2021 | COMMENTS 31.05.2021 | COMMENTS 01.06.2021 | COMMENTS 02.06.2021 | COMMENTS 03.06.2021
BA1581 | 1 X NEW CAT 395-07A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | SGD00225 | CAT00395ESGD00225 | H4E00113 | 2104DSI1091 | COD 2021 187705 | ND754967 | ND654346 | ND526680 | 06/05/2021 | * VEHICLE OFFLOAD 02.06.2021 | 28.04.2021 | 11.05.2021 | 12.05.2021 | 15.05.2021 | 17.05.2021 | 17.05.2022 | 21.05.2021 | 22.05.2021 | 23.05.2021 | 24.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 01.06.2021 | 02.06.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR MONDAY | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 03.05.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 04.05.2021 | * TRUCKS TO DISPATCH ON MONDAY THE 10.05.2021 | * TRUCKS TO DISPATCH ON MONDAY THE 10.05.2021 | * TRUCKS TO DISPATCH ON MONDAY THE 10.05.2021 | * TRUCKS TO DISPATCH ON TEUSDAY THE 11.05.2021 | * TRUCKS DISPATCH DURBAN TODAY AS OF 11.05.2021 | * TRUCKS AT COLENSO AS OF 12.05.2021 EN-ROUTE TO BEITBRIDGE BORDER | * TRUCKS AT COLENSO AS OF 12.05.2021 EN-ROUTE TO BEITBRIDGE BORDER | * TRUCKS AT MIDDELBURG AS OF 14.05.2021 EN-ROUTE TO BEITBRIDGE | * TRUCKS AT BEITBRIDGE RSA SIDE AS OF 17.05.2021 | * TRUCKS AT BEITBRIDGE RSA SIDE AS OF 17.05.2021 | * TRUCKS AT MASVINGO EN-ROUTE TO CHIRUNDU AS OF 19.05.2021 | * TRUCKS AT HARARE EN-ROUTE TO CHIRUNDU AS OF 20.05.2021 | * KASUMBALESA ZAMBIA - WAITING CLEARANCE AS OF 24.05.2021 | * KASUMBALESA ZAMBIA - WAITING CLEARANCE AS OF 25.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 26.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 27.05.2021 | * VEHICLE ENROUTE WHISKY AS OF 28.05.2021 | * VEHILCE ENROUTE KOLWEZI AS OF 31.05.2021 | * VEHILCE ENROUTE SITE TO OFFLOAD AS OF 01.06.2021 | * VEHILCE ENROUTE SITE TO OFFLOAD AS OF 02.06.2021 | * VEHILCE OFFLOADED 02.06.2021
BA1582 | 1 X NEW CAT 395-07A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | SGD00226 | CAT00395CSGD00226 | H4E00120 | 2104DSI1091 | COD 2021 187705 | ND760431 | ND760424 | ND760428 | 06/05/2021 | * VEHICLE OFFLOAD 28.05.2021 | 28.04.2021 | 11.05.2021 | 12.05.2021 | 14.05.2021 | 16.05.2021 | 18.05.2021 | 20.05.2021 | 22.05.2021 | 23.05.2021 | 24.05.2021 | 27.05.2021 | 28.05.2021 | 28.05.2021 | 28.05.2021 | 28.05.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR MONDAY | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 03.05.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 04.05.2021 | * TRUCKS TO DISPATCH ON MONDAY THE 10.05.2021 | * TRUCKS TO DISPATCH ON MONDAY THE 10.05.2021 | * TRUCKS TO DISPATCH ON MONDAY THE 10.05.2021 | * TRUCKS TO DISPATCH ON TEUSDAY THE 11.05.2021 | * TRUCKS DISPATCH DURBAN TODAY AS OF 11.05.2021 | * TRUCKS AT MOOIRIVER AS OF 12.05.2021 EN-ROUTE TO BEITBRIDGE BORDER | * TRUCKS AT MOOIRIVER AS OF 12.05.2021 EN-ROUTE TO BEITBRIDGE BORDER | * TRUCKS AT MIDDELBURG AS OF 14.05.2021 EN-ROUTE TO BEITBRIDGE | * TRUCKS AT BUBI EN-ROUTE TO CHIRUNDU AS OF 17.05.2021 | * TRUCKS AT HARARE AS OF 18.05.2021 EN-ROUTE TO CHIRUNDU | * TRUCKS AT MAKUTI EN-ROUTE TO CHIRUNDU AS OF 19.05.2021 | * TRUCKS CURRENTLY AT CHIRUNDU ZIM AS OF 20.05.2021 | * KASUMBALESA ZAMBIA - WAITING CLEARANCE AS OF 24.05.2021 | * KASUMBALESA ZAMBIA - WAITING CLEARANCE AS OF 25.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 26.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 27.05.2021 | * VEHICLE AT WHISKY AWAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE OFFLOAD 28.05.2021 | * VEHICLE OFFLOAD 28.05.2021 | * VEHICLE OFFLOAD 28.05.2021 | * VEHICLE OFFLOAD 28.05.2021
BA1581 | * BUCKET * BOOM * CYLINDER * BOX * WALKWAY | BARTRAC EQUIPMENT / CONGO EQUIPMENT | SGD00225 | CAT00395ESGD00225 | H4E00113 | 2104DSI1091 | COD 2021 187705 | ACK1474 | ACG4891T | ACG4892T | 06/05/2021 | * VEHICLE OFFLOAD 01.06.2021 | 28.04.2021 | 04.05.2021 | 11.05.2021 | 14.05.2021 | 16.05.2021 | 18.05.2021 | 19.05.2021 | 20.05.2021 | 22.05.2021 | 25.05.2021 | 27.05.2021 | 28.05.2021 | 28.05.2021 | 28.05.2021 | 01.06.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR MONDAY | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 03.05.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 04.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 06.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 06.05.2021 | * TRUCKS TO DISPATCH JNB TODAY EN ROUTE TO BEITBRIDGE AS OF 10.05.2021 | * TRUCKS CURRENTLY AT MUSINA AS OF 11.05.2021 EN-ROUTE TO BEITBRIDGE | * TRUCKS CURRENTLY AT MUSINA AS OF 12.05.2021 EN-ROUTE TO BEITBRIDGE | * AWAITING MAIN MACHINES TO TRAVEL IN CONVOY | * AWAITING MAIN MACHINES TO TRAVEL IN CONVOY | * TRUCKS CURRENTLY AT LUNDE EN-ROUTE TO CHIRUNDU AS OF 17.05.2021 | * TRUCKS CURRENTLY AT CHEGUTU EN-ROUTE TO CHIRUNDU AS OF 18.05.2021 | * TRUCKS CURRENTLY AT CHIRUNDU ZIM AS OF 19.05.2021 | * TRUCKS CURRENTLY AT CHIRUNDU ZIM AS OF 20.05.2021 | * VEHICLE CURRENTLY AT CHINGOLA AS OF 24.05.2021 | * KASUMBALESA ZAMBIA - WAITING CLEARANCE AS OF 25.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 26.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 27.05.2021 | * VEHICLE AT WHISKY AWAITING CLEARANCE AS OF 28.05.2021 | * VEHILCE ON SITE WAITING TO OFFLOAD AS OF 31.05.2021 | * VEHILCE ON SITE WAITING TO OFFLOAD AS OF 01.06.2021 | * VEHICLE OFFLOAD 01.06.2021 | * VEHICLE OFFLOAD 01.06.2021
BA1581/BA1582 | 2 X COUNTERWEIGHTS | BARTRAC EQUIPMENT / CONGO EQUIPMENT | SGD00225/SGD00226 | CAT00395ESGD00225 CAT00395CSGD00226 | H4E00113 H4E00120 | 2104DSI1091 | COD 2021 187705 | ABC6607 | ACG8213T | ACG8214T | 06/05/2021 | * VEHICLE OFFLOAD 01.06.2021 | 28.04.2021 | 04.05.2021 | 11.05.2021 | 14.05.2021 | 16.05.2021 | 18.05.2021 | 19.05.2021 | 20.05.2021 | 22.05.2021 | 25.05.2021 | 27.05.2021 | 28.05.2021 | 28.05.2021 | 28.05.2021 | 01.06.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR MONDAY | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 03.05.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 04.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 06.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 06.05.2021 | * TRUCKS TO DISPATCH JNB TODAY EN ROUTE TO BEITBRIDGE AS OF 10.05.2021 | * TRUCKS CURRENTLY AT MUSINA AS OF 11.05.2021 EN-ROUTE TO BEITBRIDGE | * TRUCKS CURRENTLY AT MUSINA AS OF 12.05.2021 EN-ROUTE TO BEITBRIDGE | * AWAITING MAIN MACHINES TO TRAVEL IN CONVOY | * AWAITING MAIN MACHINES TO TRAVEL IN CONVOY | * TRUCKS CURRENTLY AT LUNDE EN-ROUTE TO CHIRUNDU AS OF 17.05.2021 | * TRUCKS CURRENTLY AT CHEGUTU EN-ROUTE TO CHIRUNDU AS OF 18.05.2021 | * TRUCKS CURRENTLY AT CHIRUNDU ZIM AS OF 19.05.2021 | * TRUCKS CURRENTLY AT CHIRUNDU ZIM AS OF 20.05.2021 | * VEHICLE CURRENTLY AT CHINGOLA AS OF 24.05.2021 | * KASUMBALESA ZAMBIA - WAITING CLEARANCE AS OF 25.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 26.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 27.05.2021 | * VEHICLE AT WHISKY AWAITING CLEARANCE AS OF 28.05.2021 | * VEHILCE ON SITE WAITING TO OFFLOAD AS OF 31.05.2021 | * VEHILCE ON SITE WAITING TO OFFLOAD AS OF 01.06.2021 | * VEHICLE OFFLOAD 01.06.2021 | * VEHICLE OFFLOAD 01.06.2021
BA1582 | * BUCKET * BOOM * CYLINDER * BOX * WALKWAY | BARTRAC EQUIPMENT / CONGO EQUIPMENT | SGD00226 | CAT00395CSGD00226 | H4E00120 | 2104DSI1091 | COD 2021 187705 | AAZ4570 | ABE4576T | AAM8154T | 06/05/2021 | * VEHICLE OFFLOAD 01.06.2021 | 28.04.2021 | 04.05.2021 | 11.05.2021 | 14.05.2021 | 16.05.2021 | 18.05.2021 | 19.05.2021 | 20.05.2021 | 22.05.2021 | 25.05.2021 | 27.05.2021 | 28.05.2021 | 28.05.2021 | 28.05.2021 | 01.06.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR MONDAY | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 03.05.2021 | * TRUCKS AT OUR FACILITY.BV BOOKED FOR TODAY THE 04.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 05.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 06.05.2021 | * TRUCKS CURRENTLY AT JOHANNESBURG AS OF 06.05.2021 | * TRUCKS TO DISPATCH JNB TODAY EN ROUTE TO BEITBRIDGE AS OF 10.05.2021 | * TRUCKS CURRENTLY AT MUSINA AS OF 11.05.2021 EN-ROUTE TO BEITBRIDGE | * TRUCKS CURRENTLY AT MUSINA AS OF 12.05.2021 EN-ROUTE TO BEITBRIDGE | * AWAITING MAIN MACHINES TO TRAVEL IN CONVOY | * AWAITING MAIN MACHINES TO TRAVEL IN CONVOY | * TRUCKS CURRENTLY AT LUNDE EN-ROUTE TO CHIRUNDU AS OF 17.05.2021 | * TRUCKS CURRENTLY AT CHEGUTU EN-ROUTE TO CHIRUNDU AS OF 18.05.2021 | * TRUCKS CURRENTLY AT CHIRUNDU ZIM AS OF 19.05.2021 | * TRUCKS CURRENTLY AT CHIRUNDU ZIM AS OF 20.05.2021 | * VEHICLE CURRENTLY AT CHINGOLA AS OF 24.05.2021 | * KASUMBALESA ZAMBIA - WAITING CLEARANCE AS OF 25.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 26.05.2021 | * VEHICLE DISPATCHING KASUMBALESA TODAY ENROUTE WHISKY AS OF 27.05.2021 | * VEHICLE AT WHISKY AWAITING CLEARANCE AS OF 28.05.2021 | * VEHILCE ON SITE WAITING TO OFFLOAD AS OF 31.05.2021 | * VEHILCE ON SITE WAITING TO OFFLOAD AS OF 01.06.2021 | * VEHICLE OFFLOAD 01.06.2021 | * VEHICLE OFFLOAD 01.06.2021

## 2 X 140GC (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 05.05.2021 | COMMENTS 07.05.2021 | COMMENTS 11.05.2021 | COMMENTS 12.05.2021 | COMMENTS 13.05.2021 | COMMENTS 14.05.2021 | COMMENTS 17.05.2021 | COMMENTS 18.05.2021 | COMMENTS 19.05.2021 | COMMENTS 24.05.2021 | COMMENTS 25.05.2021 | COMMENTS 26.05.2021 | COMMENTS 27.05.2021 | COMMENTS 28.05.2021 | COMMENTS 31.05.2021 | COMMENTS 01.06.2021 | COMMENTS 02.06.2021 | COMMENTS 03.06.2021 | COMMENTS 04.06.2021 | COMMENTS 07.06.2021
BA1575 | 1 X NEW CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9200694 | CAT00140LW9200694 | E7A42121 | 2104DSI1094 | COD 2021 190154 | ACK5989 | AAZ4509 | ND59100 | 20.05.2021 | * VEHILCE OFFLOADED AS OF 31.05.2021 | 02.05.2021 | 08.05.2021 | 10.05.2021 | 12.05.2021 | 14.05.2021 | 15.05.2021 | 17.05.2021 | 18.05.2021 | 19.05.2021 | 21.05.2021 | 25.05.2021 | 27.05.2021 | 28.05.2021 | 29.05.2021 | 31.05.2021 | VEHICLE ON STANDBY TO COLLECT THE CONTAINER AT THE PORT ON THE 04.05.2021 | * TRUCK TO DISPATCH ON MONDAY THE 10.05.2021 | * TRUCK CURRENTLY MUSINA EN-ROUTE TO BEITBRIDGE AS OF 11.05.2021 | * TRUCK CURRENTLY BEITBRIDGE RSA SIDE AS OF 12.05.2021 | * TRUCK CURRENTLY BUSY WITH CUSTOMS | * TRUCK CURRENTLY BEITBRIDGE ZIM SIDE AS OF 14.05.2021 | * TRUCK CURRENTLY BEITBRIDGE ZIM SIDE AS OF 14.05.2022 | * TRUCK CURRENTLY AT WHISKEY AS OF 18.05.2021 AWAITING FINAL CLEARANCE | * TRUCK CURRENTLY AT NDOLA AS OF 19.05.2021 EN-ROUTE TO KASUMBALESA BORDER | * VEHICL ECURRENTLY AT KASUMBALESA DRC - TO DISPATCH TODAY 24.05.2021 | * VEHICLE CURRENTLY AT KASUMBALESA DRC WAITING RELEASE AS OF 25.05.2021 | * VEHICLE CURENTLY WAITING TO ENTER WHISKY AS OF 26.05.2021 | * VEHICLE CURRENTLY AT WHISKY. WAITING CLEARANCE AS OF 27.05.2021 | * VEHICLE CURRENTLY AT WHISKY - DECLARATION RECEIVED THIS MORNING. WAITING CLEARANCE AS OF 28.05.2021 | * VEHICLE ON SITE - WAIITNG TO OFFLOAD AS OF 31.05.2021 | * VEHILCE OFFLOADED AS OF 31.05.2021 | * VEHILCE OFFLOADED AS OF 31.05.2021 | * VEHILCE OFFLOADED AS OF 31.05.2021 | * VEHILCE OFFLOADED AS OF 31.05.2021 | * VEHILCE OFFLOADED AS OF 31.05.2021
BA1574 | 1 X NEW CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9200692 | CAT00140VW9200692 | E7A39547 | 2104DSI1093 | COD 2021 190154 | CY70RYGP | NHD170GP | JOB032615 | 20.05.2021 | VEHICLE OFFLOADED AS OF 06.06.2021 | 10.05.2021 | 19.05.2021 | 20.05.2021 | 22.03.2021 | 23.05.2021 | 24.05.2021 | 26.05.2021 | 27.05.2021 | 28.05.2021 | 30.05.2021 | 01.06.2021 | 02.06.2021 | 04.06.2021 | 06.06.2021 | 06.06.2021 | VESSEL DUE TO ARRIVE ON THE 08.05.2021 | VESSEL DUE TO ARRIVE ON THE 10.05.2021 | VESSEL DUE TO ARRIVE ON THE 10.05.2021. AWAITING COINTAINER TO GROUND | VESSEL DUE TO ARRIVE ON THE 10.05.2021. AWAITING COINTAINER TO GROUND | * VESSEL IS BUSY WORKING. AWAITING CONTAINER TO BE GROUNDED AS OF 13.05.2021 | * CONTAINER IS AT OUR FACILITY BV IS BOOKED FOR MONDAY THE 14.05.2021 | * CONTAINER IS AT OUR FACILITY BV IS BOOKED FOR MONDAY THE 17.05.2021 | * COLLECTING CONTAINER TODAY THE 18.05.2021. BV IS BOOKED FOR WEDNESDAY THE 19.05.2021 | * CONTAINER AT DEPO. BV TO BE DONE TODAY THE 19.05.2021 | * VEHICLE ENROUTE HARARE AS OF 24.05.2021 | * VEHICLE ENROUTE CHIRUNDU AS OF 25.04.2021 | * VEHICLE AT HARARE TO DISPATCH FOR CHIRUNDU AS OF 26.05.2021 | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE DOCUMENTS AS OF 27.05.2021 | * VEHILCE ENROUTE KASUMBALESA AS OF 28.05.2021 | * VEHICLE CURRENTLY AT KASUMBALSEA ZAMBIA SIDE - WAITING RELEASE | * VEHILCE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE AWAITING RELEASE | * VEHILCE CURRENTLY AT KASUMBALESA ZAMBIAN UNDER CLEARANCE AS OF 02.06.2021 | * VEHILCE CURRENTLY AT WHISKY - AWAITING CLEARANCE AS OF 03.06.2021 | * VEHILCE CURRENTLY AT WHISKY - UNDER CLEARANCE AS OF 04.06.2021 | VEHICLE OFFLOADED AS OF 06.06.2021

## CURRENT SHIPMENTS
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | VESSEL DETAILS & ETA | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | ESTIMATED DATE OF ARRIVAL ON SITE | BV RECEIVED | BV COMPLETE | DATE PRELIMINARY NOTIFICATE RECEIVED | CRF ISSUE DATE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | MUSINA ARR | MUSINA DISPATCH | BBR ARR | BBR DSP | HARARE ARR | HARARE DISP | CHIRUNDU ZIM ARR | CHIRUNDU ZIM DISP | CHIRUNDU ZAM ARR | CHIRUNDU ZAM DISP | LUSAKA ARR | LUSAKA DISP | KABWE | CHINGOLA ARR | CHINGOLA DISP | KASUMBALESA / MOKAMBO ARR | KASUMBALESA / MOKAMBO DSP | WHISKY ARR | WHISKY DISP | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 03-01-2025 | COMMENTS 06-01-2025 | COMMENTS 07-01-2025 | COMMENTS 08-01-2025 | COMMENTS 09-01-2025 | COMMENTS 10-01-2025 | COMMENTS 13-01-2025 | COMMENTS 14-01-2025 | COMMENTS 15-01-2025 | COMMENTS 16-01-2025 | COMMENTS 17-01-2025 | COMMENTS 20-01-2025 | COMMENTS 21-01-2025 | COMMENTS 22-01-2025 | COMMENTS 23-01-2025 | COMMENTS 24-01-2025 | COMMENTS 27-01-2025 | COMMENTS 28-01-2025 | COMMENTS 29-01-2025 | COMMENTS 30-01-2025 | COMMENTS 31-01-2025 | COMMENTS 03-02-2025 | COMMENTS 04-02-2025 | COMMENTS 05-02-2025 | COMMENTS 06-02-2025 | COMMENTS 07-02-2025 | COMMENTS 10-02-2025 | COMMENTS 11-02-2025 | COMMENTS 12-02-2025 | COMMENTS 13-02-2025 | COMMENTS 14-02-2025 | COMMENTS 17-02-2025 | COMMENTS 18-02-2025 | COMMENTS 19-02-2025 | COMMENTS 20-02-2025 | COMMENTS 21-02-2025 | COMMENTS 24-02-2025 | COMMENTS 25-02-2025 | COMMENTS 26-02-2025 | COMMENTS 27-02-2025 | COMMENTS 28-02-2025 | COMMENTS 03-03-2025 | COMMENTS 04-03-2025 | COMMENTS 05-03-2025 | COMMENTS 06-03-2025 | COMMENTS 07-03-2025 | COMMENTS 10-03-2025 | COMMENTS 11-03-2025 | COMMENTS 12-03-2025 | COMMENTS 13-03-2025 | COMMENTS 14-03-2025 | COMMENTS 17-03-2025 | COMMENTS 18-03-2025 | COMMENTS 19-03-2025 | COMMENTS 20-03-2025 | COMMENTS 24-03-2025 | COMMENTS 25-03-2025 | COMMENTS 26-03-2025 | COMMENTS 27-03-2025 | COMMENTS 28-03-2025 | COMMENTS 31-03-2025 | COMMENTS 01-04-2025 | COMMENTS 02-04-2025 | COMMENTS 03-04-2025 | COMMENTS 04-04-2025 | COMMENTS 07-04-2025 | COMMENTS 08-04-2025 | COMMENTS 09-04-2025 | COMMENTS 10-04-2025 | COMMENTS 11-04-2025 | COMMENTS 14-04-2025 | COMMENTS 15-04-2025 | COMMENTS 16-04-2025 | COMMENTS 17-04-2025 | COMMENTS 22-04-2025 | COMMENTS 23-04-2025 | COMMENTS 24-04-2025 | COMMENTS 25-04-2025 | COMMENTS 29-04-2025 | COMMENTS 30-04-2025 | COMMENTS 02-05-2025 | COMMENTS 05-05-2025 | COMMENTS 06-05-2025 | COMMENTS 07-05-2025 | COMMENTS 08-05-2025 | COMMENTS 09-05-2025 | COMMENTS 12-05-2025 | COMMENTS 13-05-2025 | COMMENTS 14-05-2025 | COMMENTS 15-05-2025 | COMMENTS 16-05-2025 | COMMENTS 19-05-2025 | COMMENTS 20-05-2025 | COMMENTS 21-05-2025 | COMMENTS 22-05-2025 | COMMENTS 23-05-2025 | COMMENTS 26-05-2025 | COMMENTS 27-05-2025 | COMMENTS 28-05-2025 | COMMENTS 29-05-2025 | COMMENTS 30-05-2025 | COMMENTS 02-06-2025 | COMMENTS 03-06-2025 | COMMENTS 04-06-2025 | COMMENTS 05-06-2025 | COMMENTS 06-06-2025 | COMMENTS 09-06-2025 | COMMENTS 10-06-2025 | COMMENTS 11-06-2025 | COMMENTS 12-06-2025 | COMMENTS 13-06-2025 | COMMENTS 17-06-2025 | COMMENTS 18-06-2025 | COMMENTS 19-06-2025 | COMMENTS 20-06-2025 | COMMENTS 23-06-2025 | COMMENTS 24-06-2025 | COMMENTS 25-06-2025 | COMMENTS 26-06-2025 | COMMENTS 27-06-2025 | COMMENTS 30-06-2025 | COMMENTS 01-07-2025 | COMMENTS 02-07-2025 | COMMENTS 03-07-2025 | COMMENTS 04-07-2025 | COMMENTS 07-07-2025 | COMMENTS 08-07-2025 | COMMENTS 09-07-2025 | COMMENTS 10-07-2025 | COMMENTS 11-07-2025 | COMMENTS 14-07-2025 | COMMENTS 15-07-2025 | COMMENTS 16-07-2025 | COMMENTS 17-07-2025 | COMMENTS 18-07-2025 | COMMENTS 21-07-2025 | COMMENTS 22-07-2025 | COMMENTS 23-07-2025 | COMMENTS 24-07-2025 | COMMENTS 25-07-2025 | COMMENTS 28-07-2025 | COMMENTS 29-07-2025 | COMMENTS 30-07-2025 | COMMENTS 31-07-2025 | COMMENTS 01-08-2025 | COMMENTS 04-08-2025 | COMMENTS 05-08-2025 | COMMENTS 06-08-2025 | COMMENTS 07-08-2025 | COMMENTS 08-08-2025 | COMMENTS 11-08-2025 | COMMENTS 12-08-2025 | COMMENTS 13-08-2025 | COMMENTS 14-08-2025 | COMMENTS 15-08-2025 | COMMENTS 18-08-2025 | COMMENTS 19-08-2025 | COMMENTS 20-08-2025 | COMMENTS 21-08-2025 | COMMENTS 22-08-2025 | COMMENTS 25-08-2025 | COMMENTS 26-08-2025 | COMMENTS 27-08-2025 | COMMENTS 28-08-2025 | COMMENTS 29-08-2025 | COMMENTS 01-09-2025 | COMMENTS 02-09-2025 | COMMENTS 03-09-2025 | COMMENTS 04-09-2025 | COMMENTS 05-09-2025 | COMMENTS 08-09-2025 | COMMENTS 09-09-2025 | COMMENTS 10-09-2025 | COMMENTS 11-09-2025 | COMMENTS 12-09-2025 | COMMENTS 15-09-2025 | COMMENTS 16-09-2025 | COMMENTS 17-09-2025 | COMMENTS 18-09-2025 | COMMENTS 19-09-2025 | COMMENTS 22-09-2025 | COMMENTS 23-09-2025 | COMMENTS 25-09-2025 | COMMENTS 26-09-2025 | COMMENTS 29-09-2025 | COMMENTS 30-09-2025 | COMMENTS 01-10-2025 | COMMENTS 02-10-2025 | COMMENTS 03-10-2025 | COMMENTS 06-10-2025 | COMMENTS 07-10-2025 | COMMENTS 08-10-2025 | COMMENTS 09-10-2025 | COMMENTS 10-10-2025 | COMMENTS 13-10-2025 | COMMENTS 14-10-2025 | COMMENTS 15-10-2025 | COMMENTS 16-10-2025 | COMMENTS 17-10-2025 | COMMENTS 20-10-2025 | COMMENTS 21-10-2025 | COMMENTS 22-10-2025 | COMMENTS 23-10-2025 | COMMENTS 24-10-2025 | COMMENTS 27-10-2025 | COMMENTS 28-10-2025 | COMMENTS 29-10-2025 | COMMENTS 30-10-2025 | COMMENTS 03-11-2025 | COMMENTS 04-11-2025 | COMMENTS 05-11-2025 | COMMENTS 06-11-2025 | COMMENTS 07-11-2025 | COMMENTS 10-11-2025 | COMMENTS 11-11-2025 | COMMENTS 12-11-2025 | COMMENTS 13-11-2025 | COMMENTS 18-11-2025 | COMMENTS 19-11-2025 | COMMENTS 20-11-2025 | COMMENTS 21-11-2025 | COMMENTS 24-11-2025 | COMMENTS 25-11-2025 | COMMENTS 26-11-2025 | COMMENTS 27-11-2025 | COMMENTS 28-11-2025 | COMMENTS 01-12-2025 | COMMENTS 02-12-2025 | COMMENTS 03-12-2025 | COMMENTS 04-12-2025 | COMMENTS 05-12-2025 | COMMENTS 08-12-2025 | COMMENTS 09-12-2025 | COMMENTS 10-12-2025 | COMMENTS 11-12-2025 | COMMENTS 12-12-2025 | COMMENTS 15-12-2025 | COMMENTS 17-12-2025 | COMMENTS 18-12-2025 | COMMENTS 19-12-2025 | COMMENTS 22-12-2025 | COMMENTS 23-12-2025 | COMMENTS 24-12-2025 | COMMENTS 29-12-2025 | COMMENTS 30-12-2025 | COMMENTS 31-12-2025 | COMMENTS 02-01-2026 | COMMENTS 05-01-2026 | COMMENTS 06-01-2026 | COMMENTS 07-01-2026 | COMMENTS 08-01-2026 | COMMENTS 09-01-2026 | COMMENTS 12-01-2026 | COMMENTS 13-01-2026 | COMMENTS 14-01-2026 | COMMENTS 15-01-2026 | COMMENTS 16-01-2026 | COMMENTS 19-01-2026 | COMMENTS 20-01-2026 | COMMENTS 22-01-2026 | COMMENTS 21-01-2026 | COMMENTS 22-01-2026 | COMMENTS 23-01-2026 | COMMENTS 26-01-2026 | COMMENTS 27-01-2026 | COMMENTS 28-01-2026 | COMMENTS 29-01-2026 | COMMENTS 30-01-2026 | COMMENTS 02-02-2026 | COMMENTS 03-02-2026 | COMMENTS 04-02-2026 | COMMENTS 05-02-2026 | COMMENTS 06-02-2026 | COMMENTS 09-02-2026 | COMMENTS 10-02-2026 | COMMENTS 11-02-2026 | COMMENTS 12-02-2026 | COMMENTS 13-02-2026 | COMMENTS 16-02-2026 | COMMENTS 17-02-2026 | COMMENTS 18-02-2026 | COMMENTS 19-02-2026 | COMMENTS 20-02-2026 | COMMENTS 23-02-2026 | COMMENTS 24-02-2026 | COMMENTS 25-02-2026 | COMMENTS 26-02-2026 | COMMENTS 27-02-2026 | COMMENTS 02-03-2026 | COMMENTS 03-03-2026 | COMMENTS 04-03-2026 | COMMENTS 05-03-2026 | COMMENTS 06-03-2026 | COMMENTS 09-03-2026 | COMMENTS 10-03-2026 | COMMENTS 11-03-2026 | COMMENTS 12-03-2026 | COMMENTS 13-03-2026 | COMMENTS 16-03-2026 | COMMENTS 17-03-2026 | COMMENTS 18-03-2026 | COMMENTS 19-03-2026 | COMMENTS 20-03-2026 | COMMENTS 23-03-2026 | COMMENTS 24-03-2026 | COMMENTS 25-03-2026 | COMMENTS 26-03-2026 | COMMENTS 27-03-2026 | COMMENTS 30-03-2026 | COMMENTS 31-03-2026 | COMMENTS 01-04-2026 | COMMENTS 02-04-2026 | COMMENTS 08-04-2026 | COMMENTS 09-04-2026 | COMMENTS 10-04-2026
BA2960 | CAT C15 ENGINE | BARTRAC EQUIPMENT / CONGO EQUIPMENT |  |  |  | 2601DSI2752 | VESSEL: MSC ANTIGUE Voy. MG552E - Transhipment Vessel: MSC ORNELLA Voy UF601A - ETA DURBAN 13-02-2026 | COD 2026 113668 | BCG909ZM | BCG995ZM | 2601DSI2752 | 25-02-2026 | OFFLOADED |  | 28-01-2026 | 24-02-2026 | 25-02-2026 | 25-02-2026 | CRF ISSUED 25-02-2026 | 13-02-2026 | 18-03-2026 | 19-03-2026 | 19-03-2026 | GRB 19-03-2026 | GRB 20-03-2026 | MARTINS DRIFT 20-03-2026 | MARTINS DRIFT 21-03-2026 | FRANCISTOWN 21-03-2026 | FRANCISTOWN 22-03-2025 | KAZ BW 22-03-2026 | KAZ BW 22-03-2026 | KAZ ZM 22-03-2026 | KAZ ZM 23-03-2026 | LIVINGSTONE 24-03-2026 | 2026-03-25 | 2026-03-25 | NDOLA 26-03-2026 | CHINGOLA 28-03-2026 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-04-05 | 2026-04-05 | 2026-04-06 | 2026-04-09 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-02-2026 | VESSEL ARRIVED 14-02-2026 - AWAITING CONFIRMATION TO COLLECT CONTAINER FROM PORT | VESSEL ARRIVED 14-02-2026 - AWAITING CONFIRMATION TO COLLECT CONTAINER FROM PORT | CONTAINER CUSTOMS STOPPED FOR PHYSICAL INSPECTION - RELEASED 17/02/2026 AFTERNOON - CONTAINER TO BE COLLECTED 19/02/2026 FOR UNPACK | CONTAINER AT FML FACILITY WAITING UNPACK | AT FML FACILITY - BV INSPECTION PLANNED FOR NEXT WEEK - DATE TO BE CONFIMRED | AT FML FACILITY - BV INSPECTION BOOKED TOMORROW 24-02-2026 - AWAITING CONSOLIDATION LOAD | AT FML FACILITY - BV INSPECTION BOOKED TODAY 24-02-2026 - AWAITING CONSOLIDATION LOAD | AT FML FACILITY - BV INSPECTION DONE - AWAITING CONSOLIDATION LOAD | AT FML FACILITY - BV INSPECTION DONE - AWAITING CONSOLIDATION LOAD | AT FML FACILITY - BV INSPECTION DONE - AWAITING CONSOLIDATION LOAD | AT FML FACILITY - BV INSPECTION DONE - AWAITING CONSOLIDATION LOAD | AT FML FACILITY - BV INSPECTION DONE - AWAITING CONSOLIDATION LOAD | AT FML FACILITY - BV INSPECTION DONE - AWAITING CONSOLIDATION LOAD | AT FML FACILITY - BV INSPECTION DONE - LOADING NEXT WEEK | AT FML FACILITY - BV INSPECTION DONE - LOADING NEXT WEEK | AT FML FACILITY - BV INSPECTION DONE - LOADING THIS WEEK - LOADING DATE TO FOLLOW | AT FML FACILITY - BV INSPECTION DONE - LOADING THIS WEEK - LOADING DATE TO FOLLOW | AT FML FACILITY - BV INSPECTION DONE - LOADING THIS WEEK - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | AT FML FACILITY - BV INSPECTION DONE - LOADING THIS WEEK - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | AT FML FACILITY - BV INSPECTION DONE - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | AT FML FACILITY - BV INSPECTION DONE - LOADING WEDNESDAY | AT FML FACILITY - BV INSPECTION DONE - LOADING WEDNESDAY | LOADING TODAY | LOADED, TO DISPATCH FOR GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | KAZANGULA BRIDGE BORDER CLEARING | LIVINGSTONE - IN TRANSIT | LIVINGSTONE - IN TRANSIT | NDOLA - WAITING TO DISPATCH | NDOLA - BUSY WITH MAINTENANCE CHECKS BEFORE DISPATCHING FOR THE BORDER | WHISKEY | WHISKEY - UNDER CLEARANCE | WHISKEY - UNDER CLEARANCE - DAY 4 | ONSITE - WAIITNG TO OFFLOAD | ONSITE - WAIITNG TO OFFLOAD - DAY 2 | ONSITE - WAIITNG TO OFFLOAD - DAY 3 | OFFLOADED
BA2965 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMENT | 3F606534 | CAT00745A3F606534 | TXW08467 | 2510DSI2728 | VESSEL: HOEGH TARGET Voy. 60 - ETA DURBAN: 24-11-2026 | COD 2026 159901 | TBA | TBA | TBA | TBA | BV INSPECTION COMPLETED. LOADING NEXT WEEK |  | 07-04-2026 | 08-04-2026 | 09-04-2026 | 08-04-2026 | CRF ISSUE DATE 08-04-2026 | [333 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED. LOADING NEXT WEEK | BV INSPECTION COMPLETED. LOADING NEXT WEEK
BA2982 | CAT333-07H HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TJT30316 | CAT00333HTJT30316 | E7A67512 | 2510DSI2723 | VESSEL: HAN WU KOU Voy. 003 - ETA DURBAN: 16-11-2025 | COD 2026 156905 | TBA | TBA | TBA | TBA | PIETERMARITZBURG |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED |  | 2026-04-10 | [327 empty] | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | PIETERMARITZBURG
BA2983 | CAT333-07H HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TJT30315 | CAT00333LTJT30315 | E7A67514 | 2510DSI2723 | VESSEL: HAN WU KOU Voy. 003 - ETA DURBAN: 16-11-2025 | COD 2026 156905 | TBA | TBA | TBA | TBA | PIETERMARITZBURG |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED |  | 2026-04-10 | [327 empty] | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | PIETERMARITZBURG
BA2984 | CAT333-07H HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TJT30317 | CAT00333ETJT30317 | E7A67516 | 2510DSI2723 | VESSEL: HAN WU KOU Voy. 003 - ETA DURBAN: 16-11-2025 | COD 2026 156905 | TBA | TBA | TBA | TBA | LOADED DISPATCHING MONDAY 13-04-2026 |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | [329 empty] | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | LOADED DISPATCHING MONDAY 13-04-2026
BA2985 | CAT333-07H HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TJT30314 | CAT00333ATJT30314 | E7A67527 | 2510DSI2723 | VESSEL: HAN WU KOU Voy. 003 - ETA DURBAN: 16-11-2025 | COD 2026 156905 | TBA | TBA | TBA | TBA | BV INSPECTION COMPLETED LOADING NEXT WEEK |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | [329 empty] | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | BV INSPECTION COMPLETED LOADING NEXT WEEK | BV INSPECTION COMPLETED LOADING NEXT WEEK | BV INSPECTION COMPLETED LOADING NEXT WEEK
BA2974 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JZ404200 | CAT00426JJZ404200 | CC210767 | 2511DSI2736 | VESSEL: APL CAIRO Voy. 549S - ETA DURBAN: 28-12-2026 | COD 2026 141043 PT02 | CAH7929ZM | BBE2333ZM | 2511DSI2736 | 23-03-2026 | WHISKEY - DAY 3 |  | 09-03-2026 | 11-03-2026 | 11-03-2026 |  | PN RECEIVED | 28-12-2025 | 2026-03-23 | 2026-03-24 |  |  |  |  | MARTINS 27-03-2026 |  |  |  | KAZUNGULA 28-03-2026 | KAZUNGULA 30-03-2026 | KAZUNGULA - 03-04-2026 | 04-04-2-26 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-05 | 2026-04-07 | 2026-04-07 | [294 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING CONFIRMATION FROM BV RSA ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING DATE TO FOLLOW | BV INSPECTION DONE - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | BV INSPECTION DONE - LOADING WEDNESDAY | BV INSPECTION DONE - LOADING WEDNESDAY/THURSDAY | BV INSPECTION DONE - LOADING WEDNESDAY/THURSDAY | VEHICLE DELAYED - LOADING MONDAY | VEHICLE DELAYED - LOADING MONDAY | LOADING TODAY | JHB - EN ROUTE GRB | PRETORIA - EN ROUTE GRB | GRB - UNDER CLEARANCE | MARTINS DRIFT - UNDER CLEARANCE | KAZUNGULA | KAZUNGULA - BW SIDE - WAITING TO CROSS | KAZUNGULA - ZAM SIDE - WAITING FOR DOCUMENTS | KASUMBALESA - WAITING TO CROSS | WHISKEY | WHISKEY - DAY 2 | WHISKEY - DAY 3
BA2975 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JZ404212 | CAT00426PJZ404212 | CC210779 | 2511DSI2736 | VESSEL: APL CAIRO Voy. 549S - ETA DURBAN: 28-12-2026 | COD 2026 141043 PT02 | CAH7929ZM | BBE2333ZM | 2511DSI2736 | 23-03-2026 | WHISKEY - DAY 3 |  | 09-03-2026 | 11-03-2026 | 11-03-2026 |  | PN RECEIVED | 28-12-2025 | 2026-03-23 | 2026-03-24 |  |  |  |  | MARTINS 27-03-2026 |  |  |  | KAZUNGULA 28-03-2026 | KAZANGULA 30-03-2026 | KAZUNGULA - 03-04-2026 | 04-04-2-26 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-05 | 2026-04-07 | 2026-04-07 | [294 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING CONFIRMATION FROM BV RSA ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING DATE TO FOLLOW | BV INSPECTION DONE - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | BV INSPECTION DONE - LOADING WEDNESDAY | BV INSPECTION DONE - LOADING WEDNESDAY/THURSDAY | BV INSPECTION DONE - LOADING WEDNESDAY/THURSDAY | VEHICLE DELAYED - LOADING MONDAY | VEHICLE DELAYED - LOADING MONDAY | LOADING TODAY | JHB - EN ROUTE GRB | PRETORIA - EN ROUTE GRB | GRB - UNDER CLEARANCE | MARTINS DRIFT - UNDER CLEARANCE | KAZUNGULA | KAZUNGULA - BW SIDE - WAITING TO CROSS | KAZUNGULA - ZAM SIDE - WAITING FOR DOCUMENTS | KASUMBALESA - WAITING TO CROSS | WHISKEY | WHISKEY - DAY 2 | WHISKEY - DAY 3
BA3032 | CAT333-07H HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TJT30346 | CAT00333LTJT30346 | E7A67554 | 2511DSI2730 | VESSEL: TOSCA Voy. 053 - ETA DURBAN: 04-12-2025 | COD 2026 156905 | TBA | TBA | TBA | TBA | LOADED DISPATCHING MONDAY 13-04-2026 |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | [329 empty] | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | AWAITING BV NUMER | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | LOADED DISPATCHING MONDAY 13-04-2026
BA3053 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A01099 | CAT0DE33EN7A01099 |  | 2601DSI2763 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 150859 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - TO COLLECT CONTAINER FROM PORT | COLLECTED FROM PORT - AWAITING UNPACK | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3054 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A01098 | CAT0DE33HN7A01098 |  | 2601DSI2763 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 150859 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - TO COLLECT CONTAINER FROM PORT | COLLECTED FROM PORT - AWAITING UNPACK | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3055 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A01101 | CAT0DE33AN7A01101 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152870 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3056 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A01100 | CAT0DE33VN7A01100 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152870 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3057 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A01103 | CAT0DE33HN7A01103 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152870 | BCH9942ZM | BCB9847ZM / BCB9862ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3058 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A01102 | CAT0DE33LN7A01102 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152870 | BCH9944ZM | BCE5712ZM / BCE5708ZM | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3059 | CAT DE16E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | YMG00350 | CAT00C15AUMG00350 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 155339 | BCH9942ZM | BCB9847ZM / BCB9862ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 07-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3067 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7301123 | CAT0DE65EN7301123 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152885 | BCH9944ZM | BCE5712ZM / BCE5708ZM | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3069 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N73301124 | CAT0DE65CN7301124 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152885 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3079 | CAT DE110GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7E01349 | CATDE110VN7E01349 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147876 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3080 | CAT DE110GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7E01348 | CATDE110CN7E01348 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147876 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3081 | CAT DE110GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7E01347 | CATDE110JN7E01347 |  | 2601DSI2766 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147876 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3089 | CAT AD63-03A UNDERGROUND MINING TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TNW00231 | CAT0AD63ATNW00231 |  | 2601DSI2754 | VESSEL: VENUS LEADER Voy. 076 - Transhipment Vessel: DELPHINUS LEADER Voy. 063 - ETA DURBAN: 19-02-2026 | COD 2026 111222 | CT37XKZN | MS36RJGP / MS36RDGP | ND61054 | 05-03-2026 | LIKASI |  | 21-01-2026 | 26-02-2026 | 05-03-2026 | 28-02-2026 | CRF ISSUED 28-02-2026 | 2026-02-27 | 2026-03-05 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-12 | 2026-02-13 | 2026-03-17 | 18-03-2026 - CHIBI | 2026-03-20 | 2026-03-22 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | LUANSHYA 26-03-2026 | LUANSHYA 26-03-2026 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-04-01 | 2026-04-10 | [264 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-02-2026 | COLLECTING - 23-02-2026 | LOADED FROM PORT - AWATING PERMIT TO PROCEED TO BV INSPECITON LOACTION. - BV INSPECTION BOOKED FOR WEDNESDAY 25-02-2026 | BV INSPECITON BOOKED FOR TOMORROW 26-02-2026 | BV INSPECITON BOOKED FOR TOMORROW 26-02-2026 | DISPATCHING - 01-03-2026 | AWAITING PERMIT - DISPATCHING TOMORROW | DISPATCHING TODAY - 03-03-2026 | DISPATCHING TODAY - ISSUING ROAD PERMIT - 04-03-2026 | DISPATCHING - DURBAN | WARDEN | JNB ENROUTE BEIT BRIDGE BORDER | MOKOPANE ENROUTE BEIT BRIDGE BORDER | MUSINA - ENROUTE BEIT BRIDGE BORDER | MUSINA DAY 2 - ENROUTE BEIT BRIDGE BORDER | BBR - SA SIDE | BBR SA SIDE - AWAITING ABNORMAL PERMIT - IN QUEUE TO CROSS INTO ZIM | BBR ZIM SIDE | CHIBI - EN ROUTE HARARE | HARARE - EN ROUTE CHIRUNDU | HARARE DISPATCHING DELAY - NO DIESEL AT DEPOT - EN ROUTE CHIRUNDU | CHIRUNDU - ZAM SIDE | CHIRUNDU - ZAM SIDE - DISPATCHING | LUSAKA | LUANSHYA - EN ROUTE - CHINGOLA | KASUMBALESA - 27-03-2026 | WHISKEY | WHISKEY | WHISKEY - DAY 6 | LUBUMBASHI - DAY 4 | LUBUMBASHI - DAY 4 | LUBUMBASHI - DAY 5 | LIKASI
BA3091 | CAT R2900XE-09A LOAD HAUL DUMP | BARTRAC EQUIPMENT / CONGO EQUIPMENT | PLK00338 | CATR2900TPLK00338 | E4T01096 | 2602DSI2778 | VESSEL: WORLD SPIRIT Voy, 0330A - Transhipment Vessel: PROGRESS ACE Voy. 0175A - ETA DURBAN : 06-03-2026 | COD 2026 141907 | ML 50 MH GP | CS 71 TP GP / CS 88 PX GP | ND61117 | 13-03-2026 | LIKUNI |  | 09-03-2026 | 12-03-2026 | 13-03-2026 |  | PN RECEIVED | 10-03-2026 | 12-03-2026 | 13 03 2026 - COLENSO | 2026-03-14 | 16 03 2026 - PERDEKOP | 17 03 2026 - HAMMANSKRAAL | 2026-03-18 | 2026-03-18 | 19-03-2026 - GWERU | 20-03-2026 - CHINHOYI | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-25 | KAFUE 28-03-2026 | KAFUE 28-03-2026 | KAPIRI MPOSE 29-03-2026 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-02 | LIKUNI 10-04-2026 | [292 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 06-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 06-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 06-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 09-03-2026 | VESSEL ARRIVED - AWAITING DISCHARGE OF UNIT | VESSEL ARRIVED - AWAITING DISCHARGE OF UNIT | BV INSPECTION BOOKED FOR TODAY | COLLENSO ENROUTE BEIT BRIDGE | PERDEKOP ENROUTE BEIT BRIDGE BORDER | HAMMANSKRAAL - ENROUTE BEIT BRIDGE BORDER | BBR - ZIM SIDE | GWERU - EN ROUTE HARARE | CHINHOYI - EN ROUTE TO CHIRUNDU | CHIRUNDU - ZAM SIDE | CHIRUNDU - ZAM SIDE - WAITING ASSESSMENT | CHIRUNDU - ZAM SIDE - ASSESSMENT DONE - WAITING RELEASE | CHIRUNDU - ZAM SIDE - WAITING RELEASE | CHIRUNDU - ZAM SIDE - WAITING RELEASE - DAY 2 | CHINGOLA | KASUMBALESA - ZAM SIDE | WHISKEY | LUBUMBASHI - DAY 5 | LUBUMBASHI - DAY 6 | LUBUMBASHI - DAY 6 | LIKUNI
BA3092 | CAT R2900XE-09A LOAD HAUL DUMP | BARTRAC EQUIPMENT / CONGO EQUIPMENT | PLK00342 | CATR2900PPLK00342 | E4T01097 | 2603DSI2786 | VESSEL: CHANG AN KOU Voy. 160 - ETA DURBAN: 21-03-2026 | COD 2026 156928 | HC64KLGP | HN30BBGP / HN30BFGP | 2603DSI2786 | TBA | BV INSPECTION COMPLETED - WAITING FOR ROAD PERMIT - DAY 2 |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 20-03-2026 | 25-03-2026 | PRETORIA 27-03-2026 | [325 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-03-2026 | COLLECTED FROM PORT ENROUTE PRETORIA - PLEASE ASSIST WITH BV NUMBER | COLLECTED FROM PORT ENROUTE PRETORIA - PLEASE ASSIST WITH BV NUMBER | COLLECTED FROM PORT ENROUTE PRETORIA - PLEASE ASSIST WITH BV NUMBER | UNIT AT TRANSPORTER YARD IN PRETORIA - AWAITING BV NUMBER & INSPECTION | UNIT AT TRANSPORTER YARD IN PRETORIA - AWAITING BV NUMBER & INSPECTION | UNIT AT TRANSPORTER YARD IN PRETORIA - AWAITING BV NUMBER & INSPECTION | UNIT AT TRANSPORTER YARD IN PRETORIA - AWAITING BV NUMBER & INSPECTION | UNIT AT TRANSPORTER YARD IN PRETORIA - AWAITING BV NUMBER & INSPECTION | BV INSPECTION COMPLETED - WAITING FOR ROAD PERMIT | BV INSPECTION COMPLETED - WAITING FOR ROAD PERMIT - DAY 2 | BV INSPECTION COMPLETED - WAITING FOR ROAD PERMIT - DAY 2
BA3060 | CAT DE16E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | YMG00351 | CAT00C15LYMG00351 |  | 2601DSI2767 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 155339 | BCH9942ZM | BCB9847ZM / BCB9862ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 07-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3083 | CAT DE150GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7F00536 | CATDE150CN7F00536 |  | 2601DSI2767 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 148401 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3103 | CAT DE150GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7F00537 | CATDE150VN7F00537 |  | 2601DSI2767 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 148401 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3104 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7500604 | CATDE220TN7500604 |  | 2601DSI2767 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147860 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3105 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7500605 | CATDE220PN7500605 |  | 2601DSI2767 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147860 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3106 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7500607 | CATDE220JN7500607 |  | 2601DSI2767 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147860 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3107 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7500606 | CATDE220KN7500606 |  | 2601DSI2767 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147860 | BCH9942ZM | BCB9847ZM / BCB9862ZM | TBA | TBA | LOADING |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3061 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00984 | CAT0DE50JN7B00984 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 153013 | BCH9942ZM | BCB9847ZM / BCB9862ZM | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3062 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00983 | CAT0DE50KN7B00983 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 153013 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3063 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00982 | CAT0DE50PN7B00982 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 153013 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3064 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00985 | CAT0DE50CN7B00985 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 153013 | BCH9942ZM | BCB9847ZM / BCB9862ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3065 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00981 | CAT0DE50TN7B00981 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 153013 | BCH9944ZM | BCE5712ZM / BCE5708ZM | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3066 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00986 | CAT0DE50VN7B00986 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 153013 | BCH9944ZM | BCE5712ZM / BCE5708ZM | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3068 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7301125 | CAT0DE65TN7301125 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152885 | BCH9944ZM | BCE5712ZM / BCE5708ZM | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3070 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7301128 | CAT0DE65JN7301128 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152885 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3071 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7301127 | CAT0DE65KN7301127 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152885 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3072 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7301126 | CAT0DE65PN7301126 |  | 2601DSI2768 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 152885 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | CONTAINER ARRIVED AT UNPACK DEPOT - AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT UNPACK DEPOT AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3073 | CAT DE88GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7C00998 | CAT0DE88TN7C00998 |  | 2601DSI2769 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147872 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3074 | CAT DE88GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7C01000 | CAT0DE88LN7C01000 |  | 2601DSI2769 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147872 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3075 | CAT DE88GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7C00999 | CATDE88PN7C00999 |  | 2601DSI2769 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147872 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3076 | CAT DE88GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7C01001 | CAT0DE88HN7C01001 |  | 2601DSI2769 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147872 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3077 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | ECL07369 | CAT00C44AECL07369 |  | 2601DSI2769 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147873 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3078 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | ECL07368 | CAT00C44VECL7368 |  | 2601DSI2769 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147873 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3082 | CAT DE110GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7E01346 | CATDE110KN7E01346 |  | 2601DSI2769 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 147876 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3102 | CAT DE150GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7F00538 | CATDE150AN7F00538 |  | 2601DSI2769 | VESSEL: SEASPAN GANGES Voy. 605W - Transhipment VESSEL: COSCO VALENCIA Voy. 087W - ETA DURBAN: 17-03-2026 | COD 2026 148401 | BCJ1335ZM | BCD2932ZM / BCD2931ZM | TBA | TBA | BV INSPECTION DONE - LOADING TODAY/TOMORROW |  | 02-04-2026 |  |  |  | BV NUMBER RECEIVED | 17-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 17-03-2026 | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY | AT BONDED FACILTIY - AWAITING BV NUMBER | AT BONDED FACILTIY - AWAITING BV NUMBER | AT BONDED FACILTIY - AWAITING BV NUMBER | AT BONDED FACILTIY - AWAITING BV NUMBER | AT BONDED FACILTIY - AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW
BA3108 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LX906253 | CAT000C9JLX906253 |  | 2602DSI2773 | VESSEL: VUNG TAU EXPRESS Voy. 607W - Transhipment VESSEL: COSCO AQABA Voy. 091W - ETA DURBAN: 29-03-2026 | COD 2026 148347 | ADE7991ZM | ADE7982ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 31-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3110 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LX906252 | CAT000C9KLX906252 |  | 2602DSI2773 | VESSEL: VUNG TAU EXPRESS Voy. 607W - Transhipment VESSEL: COSCO AQABA Voy. 091W - ETA DURBAN: 29-03-2026 | COD 2026 148347 | ADE7991ZM | ADE7982ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 18-03-2026 |  |  |  | BV NUMBER RECEIVED | 31-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 29-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3111 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LX906251 | CAT000C9PLX906251 |  | 2602DSI2772 | VESSEL: EVER LIVELY Voy. 073W - Transhipment VESSEL: NAVIOS LAPIS Voy. 012W - ETA DURBAN 25-03-2026 | COFD 2026 150864 | ADE7991ZM | ADE7982ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 23-03-2026 |  |  |  | BV NUMBER RECEIVED | 27-03-2026 | [322 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER ARRIVED AT BONDED FACILITY FOR UNPACKING | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3112 | CAT DE400GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RZB00456 | CATDE400TRZB00456 |  | 2601DSI2758 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 142626 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 14-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK AT WAREHOUSE | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK AT WAREHOUSE | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3113 | CAT DE400GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RZB00455 | CATDE400CRZB00455 |  | 2601DSI2758 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 142626 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 14-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK AT WAREHOUSE | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK AT WAREHOUSE | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3114 | CAT DE450E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | DH405099 | CAT00C13VDH405099 |  | 2601DSI2764 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 142524 | BCH9944ZM | BCE5712ZM / BCE5708ZM | TBA | TBA | LOADING |  | 14-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK AT WAREHOUSE | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK AT WAREHOUSE | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK AT WAREHOUSE | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3115 | CAT DE450E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | DH405091 | CAT00C13HD405091 |  | 2601DSI2759 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 142524 | BCH9944ZM | BCE5712ZM / BCE5708ZM | TBA | TBA | LOADING |  | 14-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - TO COLLECT CONTAINER FROM PORT | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3116 | CAT DE450E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | DH405090 | CAT00C13LDH405090 |  | 2601DSI2759 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 142524 | BCJ1334ZM | AJD2807T / AJD2810T | TBA | TBA | LOADING |  | 14-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - TO COLLECT CONTAINER FROM PORT | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | AT BONDED FACILITY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3117 | CAT DE500E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LXJ08377 | CAT00C15CLXJ08377 |  | 2601DSI2756 | VESSEL: NANSHA EXPRESS Voy. 603W - Transhipmnet Vessel: DELPHINUS C Voy. 107W - ETA 22-01-2026 | COD 2026 135653 | BCG909ZM | BCG995ZM | 2601DSI2752 | 11-03-2026 | OFFLOADED |  | 09-03-2026 | 10-03-2026 | 11-03-2026 |  | PN RECEIVED | 22-02-2026 | 18-03-2026 | 19-03-2026 | 19-03-2026 | GRB 19-03-2026 | GRB 20-03-2026 | MARTINS DRIFT 20-03-2026 | MARTINS DRIFT 21-03-2026 | FRANCISTOWN 21-03-2026 | FRANCISTOWN 22-03-2025 | KAZ BW 22-03-2026 | KAZ BW 22-03-2026 | KAZ ZM 22-03-2026 | KAZ ZM 23-03-2026 | LIVINGSTONE 24-03-2026 | 0 | 2026-03-25 | NDOLA 26-03-2026 | CHINGOLA 28-03-2026 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-04-05 | 2026-04-05 | 2026-04-06 | 2026-04-09 | [283 empty] | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | BV INSPECTION DONE - LOADING DATE TO FOLLOW | BV INSPECTION DONE - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | BV INSPECTION DONE - LOADING WEDNESDAY | BV INSPECTION DONE - LOADING WEDNESDAY | LOADED, TO DISPATCH FOR GROBLERS BRIDGE BORDER | LOADED, TO DISPATCH FOR GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | KAZUNGULA - UNDER CLEARANCE | LIVINGSTONE - IN TRANSIT | LIVINGSTONE - IN TRANSIT | NDOLA - WAITING TO DISPATCH | NDOLA - BUSY WITH MAINTENANCE CHECKS BEFORE DISPATCHING FOR THE BORDER | WHISKEY | WHISKEY - UNDER CLEARANCE | WHISKEY - UNDER CLEARANCE - DAY 4 | ONSITE - WAIITNG TO OFFLOAD | ONSITE - WAIITNG TO OFFLOAD - DAY 2 | ONSITE - WAIITNG TO OFFLOAD - DAY 3 | OFFLOADED
BA3118 | CAT DE500E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LXJ08372 | CAT00C15VLXJ08372 |  | 2601DSI2756 | VESSEL: NANSHA EXPRESS Voy. 603W - Transhipmnet Vessel: DELPHINUS C Voy. 107W - ETA 22-01-2026 | COD 2026 135653 | BCG909ZM | BCG995ZM | 2601DSI2752 | 11-03-2026 | OFFLOADED |  | 09-03-2026 | 10-03-2026 | 11-03-2026 |  | PN RECEIVED | 22-02-2026 | 18-03-2026 | 19-03-2026 | 19-03-2026 | GRB 19-03-2026 | GRB 20-03-2026 | MARTINS DRIFT 20-03-2026 | MARTINS DRIFT 21-03-2026 | FRANCISTOWN 21-03-2026 | FRANCISTOWN 22-03-2025 | KAZ BW 22-03-2026 | KAZ BW 22-03-2026 | KAZ ZM 22-03-2026 | KAZ ZM 23-03-2026 | LIVINGSTONE 24-03-2026 | 2026-03-25 | 2026-03-25 | NDOLA 26-03-2026 | CHINGOLA 28-03-2026 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-04-05 | 2026-04-05 | 2026-04-06 | 2026-04-09 | [283 empty] | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | VESSEL ARRIVED 22-02-2026 - TO COLLECT CONTAINER FROM PORT ONCE RELEASED | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | UNIT AT BONDED FACILITY - AWATING BV NUMBER | BV INSPECTION DONE - LOADING DATE TO FOLLOW | BV INSPECTION DONE - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | BV INSPECTION DONE - LOADING WEDNESDAY | BV INSPECTION DONE - LOADING WEDNESDAY | LOADED, TO DISPATCH FOR GROBLERS BRIDGE BORDER | LOADED, TO DISPATCH FOR GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | KAZUNGULA - UNDER CLEARANCE | LIVINGSTONE - IN TRANSIT | LIVINGSTONE - IN TRANSIT | NDOLA - WAITING TO DISPATCH | NDOLA - BUSY WITH MAINTENANCE CHECKS BEFORE DISPATCHING FOR THE BORDER | WHISKEY | WHISKEY - UNDER CLEARANCE | WHISKEY - UNDER CLEARANCE - DAY 4 | ONSITE - WAIITNG TO OFFLOAD | ONSITE - WAIITNG TO OFFLOAD - DAY 2 | ONSITE - WAIITNG TO OFFLOAD - DAY 3 | OFFLOADED
BA3119 | CAT DE500GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RZ400336 | CATDE500ERZ400336 |  | 601DSI2763 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 142820 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 14-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - TO COLLECT CONTAINER FROM PORT | COLLECTED FROM PORT - AWAITING UNPACK | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3120 | CAT DE500GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RZ400335 | CATDE500HRZ400335 |  | 2601DSI2763 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 142820 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 14-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - TO COLLECT CONTAINER FROM PORT | COLLECTED FROM PORT - AWAITING UNPACK | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3121 | CAT DE660E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LXK06729 | CAT00C18CLXK06729 |  | 2601DSI2764 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 142822 | BCH9942ZM | BCB9847ZM / BCB9862ZM | TBA | TBA | LOADING |  | 14-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK AT WAREHOUSE | COLLECTED FROM PORT - AWAITING UNPACK | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3122 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LXK06726 | CAT00C18PLXK06726 |  | 2601DSI2765 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 147939 | BCJ1181ZM | BBC7625ZM / BBC7624ZM | TBA | TBA | LOADED - DISPATCHING FOR BORDER |  | 23-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - TO COLLECT CONTAINER FROM PORT | COLLECTED FROM PORT - AWAITING UNPACK | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADED - DISPATCHING FOR BORDER
BA3123 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LXK06725 | CAT00C18TLXK06725 |  | 2601DSI2765 | VESSEL: HAIPONG EXPRESS Voy. 604W - Transhipment Vessel: BAY BRIDGE Voy. 214W - ETA DURBAN: 11-03-2026 | COD 2026 147939 | BCH9942ZM | BCB9847ZM / BCB9862ZM | TBA | TBA | LOADING |  | 23-03-2026 |  |  |  | BV NUMBER RECEIVED | [319 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 11-03-2026 | VESSEL IN AND WORKING | VESSEL IN AND WORKING - TO COLLECT CONTAINER FROM PORT | COLLECTED FROM PORT - AWAITING UNPACK | COLLECTED FROM PORT - AWAITING UNPACK | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY - AWAITING BV NUMBER | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | AT BONDED FACILTY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING TODAY/TOMORROW | LOADING
BA3132 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A00984 | CAT0DE33LN7A00984 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | JZ76ZPGP | YSN885GP / YSY203GP | 2512DSI2749A | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 02-04-2026 | KOPFONTEIN BORDER 03-04-2026 | KOPFONTEIN BORDER 05-04-2026 | TLOKWENG BW 05-04-2026 | TLOKWENG BW 05-04-2026 | NATA 05-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 07-04-2026 | KAZ BW 07-04-2026 | KALOMO 08-04-2026 | KAMILONGA 08-04-2026 | KAMILONGA 08-04-2026 | 2026-04-09 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KALOMO | KAMILONGA | CHINGOLA
BA3133 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A01013 | CAT0DE33KN7A01013 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | JZ76ZPGP | YSN885GP / YSY203GP | 2512DSI2749A | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 02-04-2026 | KOPFONTEIN BORDER 03-04-2026 | KOPFONTEIN BORDER 05-04-2026 | TLOKWENG BW 05-04-2026 | TLOKWENG BW 05-04-2026 | NATA 05-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 07-04-2026 | KAZ BW 07-04-2026 | KALOMO 08-04-2026 | KAMILONGA 08-04-2026 | KAMILONGA 08-04-2026 | 2026-04-09 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KALOMO | KAMILONGA | CHINGOLA
BA3138 | CAT DE450GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RZE00311 | CATDE450HRZE00311 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | JZ76ZPGP | YSN885GP / YSY203GP | 2512DSI2749A | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 02-04-2026 | KOPFONTEIN BORDER 03-04-2026 | KOPFONTEIN BORDER 05-04-2026 | TLOKWENG BW 05-04-2026 | TLOKWENG BW 05-04-2026 | NATA 05-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 07-04-2026 | KAZ BW 07-04-2026 | KALOMO 08-04-2026 | KAMILONGA 08-04-2026 | KAMILONGA 08-04-2026 | 2026-04-09 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KALOMO | KAMILONGA | CHINGOLA
BA3139 | CAT DE450GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RZE00313 | CATDE450CRZE00313 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | JZ76ZPGP | YSN885GP / YSY203GP | 2512DSI2749A | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 02-04-2026 | KOPFONTEIN BORDER 03-04-2026 | KOPFONTEIN BORDER 05-04-2026 | TLOKWENG BW 05-04-2026 | TLOKWENG BW 05-04-2026 | NATA 05-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 07-04-2026 | KAZ BW 07-04-2026 | KALOMO 08-04-2026 | KAMILONGA 08-04-2026 | KAMILONGA 08-04-2026 | 2026-04-09 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KALOMO | KAMILONGA | CHINGOLA
BA3149 | CAT DE500GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RZ400310 | CATDE500TRZ400310 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | JZ76ZPGP | YSN885GP / YSY203GP | 2512DSI2749A | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 02-04-2026 | KOPFONTEIN BORDER 03-04-2026 | KOPFONTEIN BORDER 05-04-2026 | TLOKWENG BW 05-04-2026 | TLOKWENG BW 05-04-2026 | NATA 05-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 07-04-2026 | KAZ BW 07-04-2026 | KALOMO 08-04-2026 | KAMILONGA 08-04-2026 | KAMILONGA 08-04-2026 | 2026-04-09 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KALOMO | KAMILONGA | CHINGOLA
BA3134 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A00980 | CAT0DE33JN7A00980 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | LH12NZGP | FS47DCGP / FS47DLGP | 2512DSI2749B | 23-03-2026 | LUSAKA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 08-04-2026 | 2026-04-08 | 2026-04-10 | [264 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - DISPATCHING | LUSAKA | LUSAKA
BA3136 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00867 | CAT0DE50PN7B00867 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | LH12NZGP | FS47DCGP / FS47DLGP | 2512DSI2749B | 23-03-2026 | LUSAKA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 08-04-2026 | 2026-04-08 | 2026-04-10 | [264 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - DISPATCHING | LUSAKA | LUSAKA
BA3137 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00843 | CAT0DE50VN7B00843 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | LH12NZGP | FS47DCGP / FS47DLGP | 2512DSI2749B | 23-03-2026 | LUSAKA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 08-04-2026 | 2026-04-08 | 2026-04-10 | [264 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - DISPATCHING | LUSAKA | LUSAKA
BA3147 | CAT DE500GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RZ400314 | CATDE500CRZ400314 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | LH12NZGP | FS47DCGP / FS47DLGP | 2512DSI2749B | 23-03-2026 | LUSAKA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 08-04-2026 | 2026-04-08 | 2026-04-10 | [264 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - DISPATCHING | LUSAKA | LUSAKA
BA3148 | CAT DE450E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | 2W900287 | CAT00C13C2W900287 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | LH12NZGP | FS47DCGP / FS47DLGP | 2512DSI2749B | 23-03-2026 | LUSAKA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 08-04-2026 | 2026-04-08 | 2026-04-10 | [264 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - DISPATCHING | LUSAKA | LUSAKA
BA3150 | CAT DE500E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | 2S300494 | CAT00C15K2S300494 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | LH12NZGP | FS47DCGP / FS47DLGP | 2512DSI2749B | 23-03-2026 | LUSAKA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 07-04-2026 | KAZ ZM 08-04-2026 | 2026-04-08 | 2026-04-10 | [264 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - DISPATCHING | LUSAKA | LUSAKA
BA3135 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7B00848 | CAT0DE50CN7B00848 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | KT12MTGP | KT53PGGP / KT53PJGP | 2512DSI2749C | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 08-04-2026 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - UNDER CLEARANCE | LUSAKA | CHINGOLA
BA3140 | CAT DE88GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | EC904010 | CAT00C44HEC904010 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | KT12MTGP | KT53PGGP / KT53PJGP | 2512DSI2749C | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 08-04-2026 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - UNDER CLEARANCE | LUSAKA | CHINGOLA
BA3141 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | ECL06956 | CAT00C44TECL06956 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | KT12MTGP | KT53PGGP / KT53PJGP | 2512DSI2749C | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 08-04-2026 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - UNDER CLEARANCE | LUSAKA | CHINGOLA
BA3142 | CAT DE150GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7F00493 | CATDE150HN7F00493 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | KT12MTGP | KT53PGGP / KT53PJGP | 2512DSI2749C | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 08-04-2026 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - UNDER CLEARANCE | LUSAKA | CHINGOLA
BA3143 | CAT DE110GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7E01238 | CATDE110AN7E01238 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | KT12MTGP | KT53PGGP / KT53PJGP | 2512DSI2749C | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 08-04-2026 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - UNDER CLEARANCE | LUSAKA | CHINGOLA
BA3144 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7500532 | CATDE220AN7500532 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | KT12MTGP | KT53PGGP / KT53PJGP | 2512DSI2749C | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 08-04-2026 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - UNDER CLEARANCE | LUSAKA | CHINGOLA
BA3145 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7500533 | CATDE220LN7500533 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | KT12MTGP | KT53PGGP / KT53PJGP | 2512DSI2749C | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 08-04-2026 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - UNDER CLEARANCE | LUSAKA | CHINGOLA
BA3146 | CAT DE110GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7E01239 | CATDE110LN7E01239 |  | 2512DSI2749 | VESSEL: MSC INES Voy. NZ551A - ETA DURBAN: 25-01-2026 | COD 2026 114780 | KT12MTGP | KT53PGGP / KT53PJGP | 2512DSI2749C | 23-03-2026 | CHINGOLA | 05-03-2026 | 28-01-2026 | 30-01-2026 |  |  | BV INSPECTION COMPLETED | 25-01-2026 | 2026-04-01 | 2026-04-02 | 03-04-2026 | KOPFONTEIN BORDER 04-04-2026 | KOPFONTEIN BORDER 06-04-2026 | TLOKWENG BW 06-04-2026 | TLOKWENG BW 06-04-2026 | NATA 06-04-2026 | NATA 06-04-2026 | KAZ BW 06-04-2026 | KAZ BW 06-04-2026 | KAZ ZM 08-04-2026 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-01-2026 | VESSEL ARRIVED AND DISCHARGING CONTAINERS - AWAITING AVAILABILITY TO COLLECT FROM PORT | DISCHARGED CONTAINER - AT BONDED FACILITY AWAITING UNPACK - AWAITING BV INSPECTION | CONTAINER HAVE BEEN UNPACK - BV INSPECTION BOOKED FOR TOMORROW, AWAITING BV RSA TO CONFIRM INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY - PLANNED LOADING WEDNESDAY / THURSDAY WEEK 6 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY / THURSDAY | VEHICLE DELAYED - LOADING PLANNED FOR END OF THIS WEEK EARLY NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | VEHICLE DELAYED - LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | LOADING PLANNED FOR NEXT WEEK | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | UNIT AT BONDED FACILITY - LOADING PLAN TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION DATE TO FOLLOW | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLAN TO FOLLOW - BV RE-INSPECTION BOOKED FOR MONDAY 23-03-2026 | AT BONDED FACILITY - LOADING PLANNED FOR NEXT WEEK | AT BONDED FACILITY - LOADING PLANNED FOR THIS WEEK - DATE TO BE CONFIRM | LOADING TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JHB - WAITING TO DISPATCH | KAZUNGULA - ZAM SIDE - UNDER CLEARANCE | LUSAKA | CHINGOLA

## OFFLOADED - 2026
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | VESSEL DETAILS & ETA | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | BV RECEIVED | BV COMPLETE | DATE PRELIMINARY NOTIFICATE RECEIVED | CRF ISSUE DATE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | MUSINA ARR | MUSINA DISPATCH | BBR ARR | BBR DSP | HARARE ARR | HARARE DISP | CHIRUNDU ZIM ARR | CHIRUNDU ZIM DISP | CHIRUNDU ZAM ARR | CHIRUNDU ZAM DISP | LUSAKA ARR | LUSAKA DISP | KABWE | CHINGOLA ARR | CHINGOLA DISP | KASUMBALESA / MOKAMBO ARR | KASUMBALESA / MOKAMBO DSP | WHISKY ARR | WHISKY DISP | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 03-01-2025 | COMMENTS 06-01-2025 | COMMENTS 07-01-2025 | COMMENTS 08-01-2025 | COMMENTS 09-01-2025 | COMMENTS 10-01-2025 | COMMENTS 13-01-2025 | COMMENTS 14-01-2025 | COMMENTS 15-01-2025 | COMMENTS 16-01-2025 | COMMENTS 17-01-2025 | COMMENTS 20-01-2025 | COMMENTS 21-01-2025 | COMMENTS 22-01-2025 | COMMENTS 23-01-2025 | COMMENTS 24-01-2025 | COMMENTS 27-01-2025 | COMMENTS 28-01-2025 | COMMENTS 29-01-2025 | COMMENTS 30-01-2025 | COMMENTS 31-01-2025 | COMMENTS 03-02-2025 | COMMENTS 04-02-2025 | COMMENTS 05-02-2025 | COMMENTS 06-02-2025 | COMMENTS 07-02-2025 | COMMENTS 10-02-2025 | COMMENTS 11-02-2025 | COMMENTS 12-02-2025 | COMMENTS 13-02-2025 | COMMENTS 14-02-2025 | COMMENTS 17-02-2025 | COMMENTS 18-02-2025 | COMMENTS 19-02-2025 | COMMENTS 20-02-2025 | COMMENTS 21-02-2025 | COMMENTS 24-02-2025 | COMMENTS 25-02-2025 | COMMENTS 26-02-2025 | COMMENTS 27-02-2025 | COMMENTS 28-02-2025 | COMMENTS 03-03-2025 | COMMENTS 04-03-2025 | COMMENTS 05-03-2025 | COMMENTS 06-03-2025 | COMMENTS 07-03-2025 | COMMENTS 10-03-2025 | COMMENTS 11-03-2025 | COMMENTS 12-03-2025 | COMMENTS 13-03-2025 | COMMENTS 14-03-2025 | COMMENTS 17-03-2025 | COMMENTS 18-03-2025 | COMMENTS 19-03-2025 | COMMENTS 20-03-2025 | COMMENTS 24-03-2025 | COMMENTS 25-03-2025 | COMMENTS 26-03-2025 | COMMENTS 27-03-2025 | COMMENTS 28-03-2025 | COMMENTS 31-03-2025 | COMMENTS 01-04-2025 | COMMENTS 02-04-2025 | COMMENTS 03-04-2025 | COMMENTS 04-04-2025 | COMMENTS 07-04-2025 | COMMENTS 08-04-2025 | COMMENTS 09-04-2025 | COMMENTS 10-04-2025 | COMMENTS 11-04-2025 | COMMENTS 14-04-2025 | COMMENTS 15-04-2025 | COMMENTS 16-04-2025 | COMMENTS 17-04-2025 | COMMENTS 22-04-2025 | COMMENTS 23-04-2025 | COMMENTS 24-04-2025 | COMMENTS 25-04-2025 | COMMENTS 29-04-2025 | COMMENTS 30-04-2025 | COMMENTS 02-05-2025 | COMMENTS 05-05-2025 | COMMENTS 06-05-2025 | COMMENTS 07-05-2025 | COMMENTS 08-05-2025 | COMMENTS 09-05-2025 | COMMENTS 12-05-2025 | COMMENTS 13-05-2025 | COMMENTS 14-05-2025 | COMMENTS 15-05-2025 | COMMENTS 16-05-2025 | COMMENTS 19-05-2025 | COMMENTS 20-05-2025 | COMMENTS 21-05-2025 | COMMENTS 22-05-2025 | COMMENTS 23-05-2025 | COMMENTS 26-05-2025 | COMMENTS 27-05-2025 | COMMENTS 28-05-2025 | COMMENTS 29-05-2025 | COMMENTS 30-05-2025 | COMMENTS 02-06-2025 | COMMENTS 03-06-2025 | COMMENTS 04-06-2025 | COMMENTS 05-06-2025 | COMMENTS 06-06-2025 | COMMENTS 09-06-2025 | COMMENTS 10-06-2025 | COMMENTS 11-06-2025 | COMMENTS 12-06-2025 | COMMENTS 13-06-2025 | COMMENTS 17-06-2025 | COMMENTS 18-06-2025 | COMMENTS 19-06-2025 | COMMENTS 20-06-2025 | COMMENTS 23-06-2025 | COMMENTS 24-06-2025 | COMMENTS 25-06-2025 | COMMENTS 26-06-2025 | COMMENTS 27-06-2025 | COMMENTS 30-06-2025 | COMMENTS 01-07-2025 | COMMENTS 02-07-2025 | COMMENTS 03-07-2025 | COMMENTS 04-07-2025 | COMMENTS 07-07-2025 | COMMENTS 08-07-2025 | COMMENTS 09-07-2025 | COMMENTS 10-07-2025 | COMMENTS 11-07-2025 | COMMENTS 14-07-2025 | COMMENTS 15-07-2025 | COMMENTS 16-07-2025 | COMMENTS 17-07-2025 | COMMENTS 18-07-2025 | COMMENTS 21-07-2025 | COMMENTS 22-07-2025 | COMMENTS 23-07-2025 | COMMENTS 24-07-2025 | COMMENTS 25-07-2025 | COMMENTS 28-07-2025 | COMMENTS 29-07-2025 | COMMENTS 30-07-2025 | COMMENTS 31-07-2025 | COMMENTS 01-08-2025 | COMMENTS 04-08-2025 | COMMENTS 05-08-2025 | COMMENTS 06-08-2025 | COMMENTS 07-08-2025 | COMMENTS 08-08-2025 | COMMENTS 11-08-2025 | COMMENTS 12-08-2025 | COMMENTS 13-08-2025 | COMMENTS 14-08-2025 | COMMENTS 15-08-2025 | COMMENTS 18-08-2025 | COMMENTS 19-08-2025 | COMMENTS 20-08-2025 | COMMENTS 21-08-2025 | COMMENTS 22-08-2025 | COMMENTS 25-08-2025 | COMMENTS 26-08-2025 | COMMENTS 27-08-2025 | COMMENTS 28-08-2025 | COMMENTS 29-08-2025 | COMMENTS 01-09-2025 | COMMENTS 02-09-2025 | COMMENTS 03-09-2025 | COMMENTS 04-09-2025 | COMMENTS 05-09-2025 | COMMENTS 08-09-2025 | COMMENTS 09-09-2025 | COMMENTS 10-09-2025 | COMMENTS 11-09-2025 | COMMENTS 12-09-2025 | COMMENTS 15-09-2025 | COMMENTS 16-09-2025 | COMMENTS 17-09-2025 | COMMENTS 18-09-2025 | COMMENTS 19-09-2025 | COMMENTS 22-09-2025 | COMMENTS 23-09-2025 | COMMENTS 25-09-2025 | COMMENTS 26-09-2025 | COMMENTS 29-09-2025 | COMMENTS 30-09-2025 | COMMENTS 01-10-2025 | COMMENTS 02-10-2025 | COMMENTS 03-10-2025 | COMMENTS 06-10-2025 | COMMENTS 07-10-2025 | COMMENTS 08-10-2025 | COMMENTS 09-10-2025 | COMMENTS 10-10-2025 | COMMENTS 13-10-2025 | COMMENTS 14-10-2025 | COMMENTS 15-10-2025 | COMMENTS 16-10-2025 | COMMENTS 17-10-2025 | COMMENTS 20-10-2025 | COMMENTS 21-10-2025 | COMMENTS 22-10-2025 | COMMENTS 23-10-2025 | COMMENTS 24-10-2025 | COMMENTS 27-10-2025 | COMMENTS 28-10-2025 | COMMENTS 29-10-2025 | COMMENTS 30-10-2025 | COMMENTS 03-11-2025 | COMMENTS 04-11-2025 | COMMENTS 05-11-2025 | COMMENTS 06-11-2025 | COMMENTS 07-11-2025 | COMMENTS 10-11-2025 | COMMENTS 11-11-2025 | COMMENTS 12-11-2025 | COMMENTS 13-11-2025 | COMMENTS 18-11-2025 | COMMENTS 19-11-2025 | COMMENTS 20-11-2025 | COMMENTS 21-11-2025 | COMMENTS 24-11-2025 | COMMENTS 25-11-2025 | COMMENTS 26-11-2025 | COMMENTS 27-11-2025 | COMMENTS 28-11-2025 | COMMENTS 01-12-2025 | COMMENTS 02-12-2025 | COMMENTS 03-12-2025 | COMMENTS 04-12-2025 | COMMENTS 05-12-2025 | COMMENTS 08-12-2025 | COMMENTS 09-12-2025 | COMMENTS 10-12-2025 | COMMENTS 11-12-2025 | COMMENTS 12-12-2025 | COMMENTS 15-12-2025 | COMMENTS 17-12-2025 | COMMENTS 18-12-2025 | COMMENTS 19-12-2025 | COMMENTS 22-12-2025 | COMMENTS 23-12-2025 | COMMENTS 24-12-2025 | COMMENTS 29-12-2025 | COMMENTS 30-12-2025 | COMMENTS 31-12-2025 | COMMENTS 02-01-2026 | COMMENTS 05-01-2026 | COMMENTS 06-01-2026 | COMMENTS 07-01-2026 | COMMENTS 08-01-2026 | COMMENTS 09-01-2026 | COMMENTS 12-01-2026
BA3109 | CAT307,5-07A MINI HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GW703969 | CAT3075JGW703969 | TBA | 2511DRE2733 | N/A | COD 2025 325226 | tba | N/A | 2511DRE2733 | 26-11-2025 | OFFLOADED 08-01-2026 | 19-11-2025 | 24-11-2025 | 26-11-2025 | 29-11-2025 | CRF ISSUE DATE 29-11-2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18-12-2025 | 22-12-2025 | 26-12-2025 | 26-12-2025 | 26-12-2025 | 26-12-2025 | 27-12-2025 | 27-12-2025 | 27-12-2025 | 27-12-2025 | MOKAMBO 27-12-2025 | MOKAMBO 03-01-2026 | 03-01-2026 | 04-01-2026 | 04-01-2026 | 08-01-2026 | 08-01-2026 | [217 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION BOOKED - AWAITING CONFIRMATION ON INSPECTION DATE | BV INSPECTION PLANNED FOR MONDAY 24-11-2025 - LOADING PLANNED FOR TUESDAY 25-11-2025 | BV INSPECTION TO BE DONE TODAY 24-11-2025 - LOADING PLANNED FOR TUESDAY 25-11-2025 | LOADING TODAY | VEHICLE DELAYED - LOADING TODAY | VEHICLE ENROUTE SITE TO LOAD | VEHICLE ON SITE TO LOAD | INCORRECT VEHICLE SIZE - NEW VEHICLE TO LOAD THE UNIT TOMORROW AS THE DOCUMENTS IS STILL IN PROCESS | INCORRECT VEHICLE SIZE - NEW VEHICLE TO LOAD THE UNIT TODAY IF ALL THE DOCUMENTS IS COMPLETED | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | WAITING CONFIRMATION FROM BWE ZIM ON DOCUMENTATION - AWAITING EXPORT LICENSE | EXPORT LICENSE AND DOCUMENTS RECEIVED - UNIT TO BE LOADED | UNIT LOADED 17-12-2025 - DISPATCHED HARARE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER CLEARING | 10KM BEFORE CHIRUNDU ON BREAKDOWN - ATTENDING TO THE PROBLEM | CHIRUNDU ZIM SIDE | CHIRUNDU BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER IN THE QUE TO CROSS | MOKAMBO BORDER STILL IN THE QUE TO CROSS | MOKAMBO BORDER STILL IN THE QUE TO CROSS AND WAITING DOCUMENTS | CONNEX LUBUMBASHI, AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI, AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI, AWAITING FINAL CLEARANCE AND RELEASE - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 08-01-2026 | OFFLOADED 08-01-2026
BA3010 TO BA3031 | 22 PALLETS OF LIGHTING TOWERS AND 1 PALLET ACCESSORIES | BARTRAC EQUIPMENT / CONGO EQUIPMNET |  |  |  | 2511DSI2731 | VESSEL: COSCO WELLINGTON Voy. 100W - ETA DURBAN: 24-12-2025 | COD 2025 346013 | BCF1181ZM | BCF6178ZM | 2511DSI2731 | 02-01-2026 | OFFLOADED 30-01-2026 | 16-12-2025 | 02-01-2026 | 02-01-2026 | 05-01-2026 | CRF ISSUE DATE 05-01-2026 | 24-12-2025 | 08-01-2026 | 08-01-2026 | 09-01-2026 | GRB 10-01-2026 | GRB 12-01-2026 | MARTINS DRIFT 12-01-2026 | MARTINS DRIFT 12-01-2026 | FRANCISTOWN 12-01-2026 | FRANCISTOWN 12-01-2026 | KASUNGULA BW 12-01-2026 | KASUNGULA BW 13-01-2026 | KASUNGULA ZM 13-01-2026 | KASUNGULA ZM 14-01-2026 | 2026-01-16 | 16-01-2026 | 16-01-2026 | 19-01-2026 | 19-01-2026 | 2025-01-20 | 22-01-2026 | 2026-01-23 | 29-01-2026 | 2026-01-30 | 2026-01-30 | 2026-01-30 | [234 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 23-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | VESSEL ARRIVED - CONTAINER TO BE COLLECTED FROM PORT | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK | CONTAINER UNPACKED - BV INSPECTION PLANNED FOR FRIDAY 02-01-2026 - AWAITING CONFIRMATION FROM BV RSA | BV INSPECTION BOOKED FOR TODAY 02-01-2026 | BV INSPECTION COMPLETED - LOADING TODAY | LOADING TODAY | VEHICLE DELAYED - ENROUTE TO WAREHOUSE - LOADING TODAY | LOADED TO DISPATCH DURBAN TODAY | MOKOPANE ENROUTE GROBERSBRIDGE BORDER | GROBERSBRIDGE BORDER CLEARING AND WAITING RELEASE | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | ZIMBA EN-ROUTE LUSAKA | LUSAKA ENROUTE KASUMBALESA BORDER | NDOLA - DOING ROUTINE CHECK ON VEHICLE BEFORE DISPATCHING FOR KASUMBALESA BORDER | LEAVING NDOLA EN ROUTE KASUMBALESA BORDER | KASUMBALESA BORDER WAITING CLEARING | KASUMBALESA BORDER WAITING CLEARING | KASUMBALESA BORDER WAITING CLEARING | KASUMBALESA BORDER DRC SIDE CLEARING AND WAITING RELEASE | KASUMBALESA BORDER DRC SIDE CLEARING AND WAITING RELEASE | WHISKEY UNDER CLEARANCE | WHISKEY UNDER CLEARANCE - DAY 6 PLEASE ASSIST | WHISKEY UNDER CLEARANCE - DAY 7 PLEASE ASSIST | KANYAKA EN ROUTE TO LUMBASHASHI | OFFLOADED 30-01-2026 | OFFLOADED 30-01-2026
BA2861 | CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | DXZ04163 | CAT0226BCDXZ04163 | CZ213502 | FML2502DSI2674 | VESSEL: MSC LUCY Voy. ZF507A - ETA DURBAN PORT: 24-03-2025 | COD 2025 346181 | BCH 8449 ZM | BCG 2604 ZM / BCG 2605 ZM | 2502DSI2674 | 03-01-2026 | OFFLOADED 12-02-2026 | 12-02-2026 | 16-12-2025 | 22-12-2025 | 22-12-2025 | 24-12-2025 | CRF ISSUE DATE 24-12-2025 | 24-03-2025 | 12-01-2026 | 12-01-2026 | 13-01-2026 | GRB 13-01-2026 | GRB 14-01-2026 | MARTINS DRIFT 15-01-2026 | MARTINS DRIFT 15-01-2026 | FRANCISTOWN 16-01-2026 | FRANCISTOWN 16-01-2026 | KAZUNGULA BW 16-01-2026 | KAZUNGULA BW 17-01-2026 | KAZUNGULA ZM 17-01-2026 | KAZUNGULA ZM 23-01-2026 | 25-01-2026 | 25-01-2026 | 26-01-2026 | 2026-02-01 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-03 | 12-02-2026 | 12-02-2026 | 12-02-2026 | 12-02-2026 | [233 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | VEHICLE DELAYED - LOADING NEXT WEEK | LOADING TOMORROW AFTERNOON | VEHICLE ENROUTE TO LOAD | VEHICLE DELAYED - LOADING FRIDAY | VEHICLE DELAYED - LOADING NEXT WEEK | LOADING MONDAY 12-01-2026 | LOADING TODAY | LOADED ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER CLEARING | DUKWI EN ROUTE KAZUNGULA | DUKWI EN ROUTE KAZUNGULA | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | NDOLA DOING ROUTINE CHECKS | DSP NDOLA - CHAMBISHI EN ROUTE KASUMBALESA | CHAMBISHI EN CHINGOLA | CHAMBISHI IN QUEUE DRC | CHAMBISHI STILL IN QUEUE TO KASUMBALESA BORDER | CHINGOLA IN QUEUE TO KASUMBALESA BORDER | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE - DAY 6 - DOCUMENTS TO BE COLLECTED FROM CONNEX OFFICE | WHISKEY - DOCUMENTS COLLECTED FROM CONNEX OFFICE - TO DISPATCH FROM WHISKEY | IN THE QUEUE TO DISPATCH FROM WHISKEY | OFFLOADED 12-02-2026 | OFFLOADED 12-02-2026
BA2862 | CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | DXZ04165 | CAT0226BPDXZ04165 | CZ213507 | FML2502DSI2674 | VESSEL: MSC LUCY Voy. ZF507A - ETA DURBAN PORT: 24-03-2025 | COD 2025 346181 | BCH 8449 ZM | BCG 2604 ZM / BCG 2605 ZM | 2502DSI2674 | 03-01-2026 | OFFLOADED 12-02-2026 | 12-02-2026 | 16-12-2025 | 22-12-2025 | 22-12-2025 | 24-12-2025 | CRF ISSUE DATE 24-12-2025 | 24-03-2025 | 12-01-2026 | 12-01-2026 | 13-01-2026 | GRB 13-01-2026 | GRB 14-01-2026 | MARTINS DRIFT 15-01-2026 | MARTINS DRIFT 15-01-2026 | FRANCISTOWN 16-01-2026 | FRANCISTOWN 16-01-2026 | KAZUNGULA BW 16-01-2026 | KAZUNGULA BW 17-01-2026 | KAZUNGULA ZM 17-01-2026 | KAZUNGULA ZM 23-01-2026 | 25-01-2026 | 25-01-2026 | 26-01-2026 | 2026-02-01 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-03 | 12-02-2026 | 12-02-2026 | 12-02-2026 | 12-02-2026 | [233 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | VEHICLE DELAYED - LOADING NEXT WEEK | LOADING TOMORROW AFTERNOON | VEHICLE ENROUTE TO LOAD | VEHICLE DELAYED - LOADING FRIDAY | VEHICLE DELAYED - LOADING NEXT WEEK | LOADING MONDAY 12-01-2026 | LOADING TODAY | LOADED ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER CLEARING | DUKWI EN ROUTE KAZUNGULA | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | NDOLA DOING ROUTINE CHECKS | DSP NDOLA - CHAMBISHI EN ROUTE KASUMBALESA | CHAMBISHI EN CHINGOLA | CHAMBISHI IN QUEUE DRC | CHAMBISHI STILL IN QUEUE TO KASUMBALESA BORDER | CHINGOLA IN QUEUE TO KASUMBALESA BORDER | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE - DAY 6 - DOCUMENTS TO BE COLLECTED FROM CONNEX OFFICE | WHISKEY - DOCUMENTS COLLECTED FROM CONNEX OFFICE - TO DISPATCH FROM WHISKEY | IN THE QUEUE TO DISPATCH FROM WHISKEY | OFFLOADED 12-02-2026 | OFFLOADED 12-02-2026
BA2863 | CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | DXZ04164 | CAT0266BTDXZ04164 | CZ213480 | FML2502DSI2674 | VESSEL: MSC LUCY Voy. ZF507A - ETA DURBAN PORT: 24-03-2025 | COD 2025 346181 | BCH 8449 ZM | BCG 2604 ZM / BCG 2605 ZM | 2502DSI2674 | 06-01-2026 | OFFLOADED 12-02-2026 | 12-02-2026 | 16-12-2025 | 22-12-2025 | 05-01-2026 | 24-12-2025 | CRF ISSUE DATE 24-12-2025 | 24-03-2025 | 12-01-2026 | 12-01-2026 | 13-01-2026 | GRB 13-01-2026 | GRB 14-01-2026 | MARTINS DRIFT 15-01-2026 | MARTINS DRIFT 15-01-2026 | FRANCISTOWN 16-01-2026 | FRANCISTOWN 16-01-2026 | KAZUNGULA BW 16-01-2026 | KAZUNGULA BW 17-01-2026 | KAZUNGULA ZM 17-01-2026 | KAZUNGULA ZM 23-01-2026 | 25-01-2026 | 25-01-2026 | 26-01-2026 | 2026-02-01 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-03 | 12-02-2026 | 12-02-2026 | 12-02-2026 | 12-02-2026 | [233 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR MONDAY | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - LOADING THIS WEEK - VEHICLE DETAILS TO FOLLOW | VEHICLE DELAYED - LOADING NEXT WEEK | LOADING TOMORROW AFTERNOON | VEHICLE ENROUTE TO LOAD | VEHICLE DELAYED - LOADING FRIDAY | VEHICLE DELAYED - LOADING NEXT WEEK | LOADING MONDAY 12-01-2026 | LOADING TODAY | LOADED ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER CLEARING | DUKWI EN ROUTE KAZUNGULA | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | NDOLA DOING ROUTINE CHECKS | DSP NDOLA - CHAMBISHI EN ROUTE KASUMBALESA | CHAMBISHI EN CHINGOLA | CHAMBISHI IN QUEUE DRC | CHAMBISHI STILL IN QUEUE TO KASUMBALESA BORDER | CHINGOLA IN QUEUE TO KASUMBALESA BORDER | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE - DAY 6 - DOCUMENTS TO BE COLLECTED FROM CONNEX OFFICE | WHISKEY - DOCUMENTS COLLECTED FROM CONNEX OFFICE - TO DISPATCH FROM WHISKEY | IN THE QUEUE TO DISPATCH FROM WHISKEY | OFFLOADED 12-02-2026 | OFFLOADED 12-02-2026
BA2959 | CATERPILLAR C4,4 ENGINE | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 44628310 |  |  | 2511DSI2739 | VESSEL: ONE RESOLUTION Voy. 254S - ETA DURBAN: 25-12-2025 | COD 2025 346494 | BCH 8449 ZM | BCG 2604 ZM / BCG 2605 ZM | 2502DSI2674 | 06-01-2026 | OFFLOADED 12-02-2026 | 12-06-2026 | 16-12-2025 | 06-01-2026 | 06-01-2026 | 08-01-2026 | CRF IDDUE DATE 08-01-2026 | 25-12-2025 | 12-01-2026 | 12-01-2026 | 13-01-2026 | GRB 13-01-2026 | GRB 14-01-2026 | MARTINS DRIFT 15-01-2026 | MARTINS DRIFT 15-01-2026 | FRANCISTOWN 16-01-2026 | FRANCISTOWN 16-01-2026 | KAZUNGULA BW 16-01-2026 | KAZUNGULA BW 17-01-2026 | KAZUNGULA ZM 17-01-2026 | KAZUNGULA ZM 23-01-2026 | 25-01-2026 | 25-01-2026 | 26-01-2026 | 2026-02-01 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-03 | 12-02-2026 | 12-02-2026 | 12-02-2026 | 12-02-2026 | [234 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-12-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-12-2025 | VESSEL ARRIVED - AWAITING CONTAINER UNPACK AT UNPACK DEPOT | AWAITING CONTAINER UNPACK AT UNPACK DEPOT | CONTAINER UNPACKED - TO COLLECT FROM UNPACK DEPOT TODAY | BV INSPECTION BOOKED FOR MONDAY 05-01-2026 | BV INSPECTION BOOKED FOR TODAY 05-01-2026 | BV INSPECTION COMPLETED - LOADING PLANNED FOR WEDNESDAY | BV INSPECTION COMPLETED - LOADING PLANNED FOR FRIDAY | VEHICLE DELAYED - LOADING NEXT WEEK | LOADING MONDAY 12-01-2026 | LOADING TODAY | LOADED ENROUTE GROBLERS BRIDGE BORDER | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER CLEARING | DUKWI EN ROUTE KAZUNGULA | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | KAZUNGULA BORDER ZAM SIDE CLEARING | NDOLA DOING ROUTINE CHECKS | DSP NDOLA - CHAMBISHI EN ROUTE KASUMBALESA | CHAMBISHI EN CHINGOLA | CHAMBISHI IN QUEUE DRC | CHAMBISHI STILL IN QUEUE TO KASUMBALESA BORDER | CHINGOLA IN QUEUE TO KASUMBALESA BORDER | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE - DAY 6 - DOCUMENTS TO BE COLLECTED FROM CONNEX OFFICE | WHISKEY - DOCUMENTS COLLECTED FROM CONNEX OFFICE - TO DISPATCH FROM WHISKEY | IN THE QUEUE TO DISPATCH FROM WHISKEY | OFFLOADED 12-02-2026 | OFFLOADED 12-02-2026
BA2970 | CAT D9GC-03B TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT / CONGO EQUIPMNET | AK401088 | CAT000D9TAK401088 | TNR00986 | 2510DSI2724 | VESSEL: AMALIA Voy. 253210 - ETA DURBAN 14-01-2026 | COD 2025 341172 | BT14FTGP | XXZ257GP / XVL628GP | 2510DSI2724A | 23-01-2026 | OFFLOADED 20-02-2026 | 12-02-2026 | 29-12-2025 | 23-01-2026 | 23-01-2026 |  | PN RECEIVED | 16-01-2026 | 2025-01-20 | 22-01-2026 | 26-01-2026 | 26-01-2026 | 26-01-2026 | 2025-01-27 | 27-01-2026 | 2026-01-28 | 28-01-2026 | 29-01-2026 | 29-01-2026 | 30-01-2026 | 2026-01-31 | 31-01-2026 | 01-02-2026 | 01-02-2026 | 01-02-2026 | 01-02-2026 | 2026-02-02 | 2026-02-04 | 2026-02-05 | 2026-02-12 | 2026-02-16 | 2026-02-20 | 2026-02-20 | [231 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-01-2026 | VESSEL DUE TO ARRIVE TODAY | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - VEHICLES IN PORT TO LOAD ONCE CARGO IS AVAILABEL | LOADED FROM PORT - BV INSPECTION BOoKED FOR WEDNESDAY - AWAITING CONFIRMATION FROM BV RSA | DURBAN EN ROUTE PRETORIA | VOLKSRUST EN ROUTE BB BORDER | VOLKSRUST EN ROUTE BB BORDER | PRETORIA - BV INSPECTION BOOKED FOR TOMORROW | PRETORIA - BV INSPECTION BOOKED FOR TODAY | PRETORIA -EN ROUTE BEIT BRIDGE BORDER | BBR-ZIM SIDE AWAITING RELEASE | SHURUGWI EN ROUTE HARARE | MAKUTI EN ROUTE CHIRUNDU | CHIRUNDU-ZAM SIDE - AWAITING RELEASE | QUEUE TO KASUMBALESA BORDER | QUEUE TO KASUMBALESA BORDER - DAY 2 | QUEUE TO KASUMBALESA BORDER - DAY 3 | WHISKEY | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE - DAY 6 - DOCUMENTS TO BE COLLECTED FROM CONNEX OFFICE | WHISKEY - DOCUMENTS COLLECTED FROM CONNEX OFFICE - TO DISPATCH FROM WHISKEY | WHISKEY - DOCUMENTS COLLECTED FROM CONNEX OFFICE - DISPATCHING TODAY | LUMTATA ENROUTE LUBUMBASHI | LUBUMBASHI - CONNEX | LUBUMBASHI - CONNEX - DAY 2 | LUBUMBASHI - CONNEX - DAY 3 | LUBUMBASHI - CONNEX - DAY 4 | LUBUMBASHI - CONNEX - DAY 5 | OFFLOADED 20-02-2026
BA2970 | CAT D9GC-03B TRACTOR - PARTS/ACCESSORIES | BARTRAC EQUIPMENT / CONGO EQUIPMNET | AK401088 | CAT000D9TAK401088 | TNR00986 | 2510DSI2724 | VESSEL: AMALIA Voy. 253210 - ETA DURBAN 14-01-2026 | COD 2025 341172 | BB75HZGP | BL56SFGP | 2510DSI2724B | 23-01-2026 | OFFLOADED 20-02-2026 | 17-02-2026 | 29-12-2025 | 23-01-2026 | 23-01-2026 |  | PN RECEIVED | 16-01-2026 | 2025-01-20 | 20-01-2026 | 24-01-2026 | 24-01-2026 | 25-01-2026 | 2026-01-25 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 30-01-2026 | 01-02-2026 | 2026-02-02 | 2026-02-04 | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-06 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-13 | 2026-02-16 | 2026-02-20 | 2026-02-20 | [231 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-01-2026 | VESSEL DUE TO ARRIVE TODAY | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - VEHICLES IN PORT TO LOAD ONCE CARGO IS AVAILABEL | LOADED FROM PORT - BV INSPECTION BOoKED FOR WEDNESDAY - AWAITING CONFIRMATION FROM BV RSA | DURBAN EN ROUTE PRETORIA | MEYERTON EN ROUTE BB BORDER | MEYERTON EN ROUTE BB BORDER | PRETORIA - BV INSPECTION BOOKED FOR TOMORROW | PRETORIA - BV INSPECTION BOOKED FOR TODAY | BBR-ZIM SIDE AWAITING RELEASE | BBR-ZIM SIDE AWAITING RELEASE | BBR RELEASED EN ROUTE HARARE | HARARE EN ROUTE CHIRUNDU | HARARE EN ROUTE CHIRUNDU | CHIRUNDU-ZAM SIDE - AWAITING RELEASE | CHIRUNDU-ZAM SIDE - AWAITING RELEASE - DAY 2 | CHIRUNDU ZAM SIDE - AWAITING RELEASE - DAY 3 | KAFUE - EN ROUTE TO LUSAKA | KAFUE - EN ROUTE TO LUSAKA | CHILIABOMBWE IN QUEUE TO KASUMBALESA ZAM SIDE - DAY 2 | CHILIABOMBWE IN QUEUE TO KASUMBALESA ZAM SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI - CONNEX | LUBUMBASHI - CONNEX - DAY 2 | LUBUMBASHI - CONNEX - DAY 3 | LUBUMBASHI - CONNEX - DAY 4 | LUBUMBASHI - CONNEX - DAY 5 | OFFLOADED 20-02-2026
BA3087 | CAT AD63-03A UNDERGROUND MINING TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TNW00228 | CAT0AD63ATNW00228 | WH300225 | 2512DSI2745 | VESSEL: IRIS ACE Voy. 0101A - Transhipment Vessel: GLORIOUS ACE Voy. 0106A - ETA DURBAN: 22-01-2025 | COD 2026 101891 | LH64CCGP | LL76KNGP / FTN679GP | ND60956 | 28-01-2025 | OFFLOADED 06-03-2026 | 25-02-2026 | 07-01-2026 | 26-01-2026 | 27-01-2026 | 29-01-2026 | CRF ISSUE DATE 29-01-2026 | 2026-01-26 | 27-01-2026 | 2026-02-02 | 03-02-2026 | 03-02-2026 | 03-02-2026 | 03-02-2026 | 2026-02-05 | 2026-02-06 | 2026-02-06 | 2026-02-09 | 10-02-2026 | 10-02-2026 | 13-02-2026 | 13-02-2026 | 13-02-2026 | 13-02-2026 | 13-02-2026 | 13-02-2026 | 13-02-2026 | 14-02-2026 | 2026-02-15 | 2026-03-01 | 2026-03-04 | 2026-03-06 | 2026-03-06 | [245 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 20-01-2026 | VESSEL DUE TO ARRIVE TODAY | VESSEL DELAYED - NEW ETA 22-01-2026 | VESSEL DELAYED - NEW ETA 22-01-2026 | VESSEL DUE TO BIRTH TODAY | COLLECTING FROM PORT TODAY | COLLECTING FROM PORT TODAY | BV INSPECITON DONE - DISPATCHING TODAY | HARRISMITH - VEHICLE ON BREAKDOWN, AWAITING REPLACEMENT VEHICLE | HARRISMITH - VEHICLE ON BREAKDOWN, AWAITING REPLACEMENT VEHICLE - VEHICLE ENROUTE TO RELOAD | HARRISMITH - VEHICLE ON BREAKDOWN, AWAITING REPLACEMENT VEHICLE - VEHICLE ENROUTE TO RELOAD | HARRISMITH - VEHICLE ON BREAKDOWN, AWAITING REPLACEMENT VEHICLE - VEHICLE ENROUTE TO RELOAD | DISPATCHING PTA | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | RUTENGA - EN ROUTE HARARE | CHIRUNDU ZAM SIDE - WAITING CUSTOMS INSPECTION | CHIRUNDU ZAM SIDE - WAITING CUSTOMS INSPECTION | CHIRUNDU ZAM SIDE - WAITING RELEASE | CHIRUNDU ZAM SIDE - WAITING RELEASE. RUNNER CHECKING | DISPATCHING CHIRUNDU BORDER | WHISKEY - DAY 2 | WHISKEY - DAY 3 | WHISKEY - DAY 4 | WHISKEY - DAY 5 - PLEASE ASSIST | WHISKEY - DAY 6 - WAITING FOR INSURANCE - PLEASE ASSIST | WHISKEY WAITING DECLARATION - DAY 9 IN DRC. PLEASE ATTEND TO URGENTLY | WHISKEY WAITING DECLARATION - DAY 10 AT WHISKEY AND DRC - PLEASE ATTEND TO URGENTLY | WHISKEY WAITING DECLARATION - DAY 11 AT WHISKEY AND DRC - PLEASE ATTEND TO URGENTLY | WHISKEY WAITING DECLARATION - DAY 12 AT WHISKEY AND DRC - PLEASE ATTEND TO URGENTLY | WHISKEY WAITING DECLARATION - DAY 13 AT WHISKEY AND DRC - WAITING RELEASE | KANYAKA CHECKPOINT | KANYAKA CUSTOMS STOP - AWAITING RELEASE TO PROCEED | LUBUMBASHI | LIKASI - EN ROUTE KOLWEZI | KOLWEZI - WAITING TO OFFLOAD | OFFLOADED 06-03-2026 | OFFLOADED 06-03-2026
BA3086 | CAT AD63-03A UNDERGROUND MINING TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TNW00227 | CAT0AD63VTNW00227 | WH300222 | 2512DSI2744 | VESSEL: IRIS ACE Voy. 0101A - Transhipment Vessel: GLORIOUS ACE Voy. 0106A - ETA DURBAN: 22-01-2025 | COD 2026 101891 | CT37XKZN | DF10CXZN / DF10DGZN | ND60955 | 28-01-2025 | OFFLOADED - 10/03/2026 | 25-02-2026 | 07-01-2026 | 26-01-2026 | 27-01-2026 | 29-01-2026 | CRF ISSUE DATE 29-01-2026 | 2026-01-27 | 27-01-2026 | 29--01-2026 | 2026-01-30 | 2026-01-30 | 2026-01-31 | 2026-01-31 | 2026-02-02 | 2026-02-02 | 04-02-2026 | 2026-02-05 | 2026-02-05 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 13-02-2026 | 2026-02-13 | 2026-02-20 | 2026-02-23 | 2026-03-05 | 2026-03-10 | [245 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 18-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 22-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 20-01-2026 | VESSEL DUE TO ARRIVE TODAY | VESSEL DELAYED - NEW ETA 22-01-2026 | VESSEL DELAYED - NEW ETA 22-01-2026 | VESSEL DUE TO BIRTH TODAY | COLLECTING FROM PORT TODAY | COLLECTING FROM PORT TODAY | BV INSPECITON DONE - DISPATCHING TODAY | PMB EN ROUTE BBR | WARDEN EN ROUTE BBR | MONTSOLE EN ROUTE BBR | BB-SA SIDE | HARARE | DISPATCHING HARARE TODAY FOR CHIRUNDU BORDER | MAKUTI EN ROUTE CHIRUNDU | CHIRUNDU ZAM SIDE | LUSAKA | LUSAKA | KASUMBALESA - ZAM SIDE | KASUMBALESA - DRC SIDE - IN QUEUE TO WHISKEY | KASUMBALESA - DRC SIDE - STILL IN QUEUE TO WHISKEY | WHISKEY - DAY 3 | WHISKEY - DAY 4 | WHISKEY - DAY 5 | WHISKEY - DAY 6 - PAPERS ARE OUT - JOINING QUEUE TO DISPATCH | KANYAKA CHECKPOINT - EN ROUTE LUBUMBASHI | LUBUMBASHI - EN ROUTE TO OFFLOAD POINT | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE - DAY 4 ( 13 DAYS IN THE DRC) - PLEASE ASSIST | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE - DAY 5 ( 14 DAYS IN THE DRC) - PLEASE ASSIST | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE - DAY 5 ( 15 DAYS IN THE DRC) - PLEASE ASSIST | DISPATCHING LUBUMBASHI | TRAILER BREAKDOWN AT MUTAKA | TRAILER BREAKDOWN AT MUTAKA - REPLACEMENT VEHICLE AT LUBUMBASHI WAITING TO OFFLOAD | TRAILER BREAKDOWN AT MUTAKA - REPLACEMENT VEHICLE AT LUBUMBASHI WAITING TO OFFLOAD | REPLACEMENT VEHICLE EN ROUTE TO TAKE OVER LOAD | RELAODED 05-03-2026 MUTAKA - CONNEX KOLWEZI | KOLWEZI - WAITING TO OFFLOAD | KOLWEZI - WAITING TO OFFLOAD - DAY 3 | OFFLOADED - 10/03/2026 | OFFLOADED - 10/03/2026
BA3090 | CAT R2900XE-09A LOAD HAUL DUMP | BARTRAC EQUIPMENT / CONGO EQUIPMNET | PLK00336 | CATR2900EPLK00336 | E4T01095 | 2601DSI2757 | VESSEL: CHANG AN KOU Voy. 159 - ETA DURBAN: 31-01-2026 | COD 2026 114780 | DN85SJGP | KN32ZCGP | ND61052 | 12-02-2026 | OFFLOADED 11-03-2026 | 04-03-2026 | 28-01-2026 | 2026-02-05 | 04-02-2026 | 07-02-2026 | CRF ISSUE DATE 07-02-2026 | 31-01-2026 | 2026-02-09 | PRETORIA 13-02-2026 | 2026-02-13 | 2026-02-19 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-26 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-28 | 2026-02-28 | 2026-03-01 | 2026-03-03 | 2026-03-04 | 2026-03-11 | 2026-03-11 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 31-01-2026 | COLLECTING FROM PORT - 03-02-2026 | COLLECTING FROM PORT TODAY - BV INSPECTION PLANNED FOR TOMORROW ON CONFIRMATION FROM BV RSA | BV INSPECTION BOOKED FOR TODAY 04-02-2026 | BV INSPECTION COMPLETE, AWAITING ABNORMAL PERMIT BEFORE DISPACHING | BV INSPECTION COMPLETE, AWAITING ABNORMAL PERMIT BEFORE DISPACHING - PERMIT SHOULD BE RECEIVED LATER TODAY - TO DISPATCH MONDAY | CAMPERDOWN EN ROUTE TO PMB | CAMPERDOWN EN ROUTE TO PMB | MOOIRIVER EN ROUTE TO BBR | MOOIRIVER EN ROUTE TO BBR - AWAITING TOWN ESCOURTS | VILLIERS ENROUTE BEIT BRIDGE BORDER | PRETORIA ENROUTE BEIT BRIDGE BORDER | PRETORIA - WAITING FOR LP PERMIT - ENROUTE BEIT BRIDGE BORDER | PIENAARSRIVIER - ENROUTE BEIT BRIDGE BORDER | BELA BELA - ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT - ENROUTE BEIT BRIDGE BORDER | HARARE - EN ROUTE CHIRUNDU | CHIRUNDU - ZIM SIDE | CHIRUNDU - ZAM SIDE | CHIRUNDU - ZAM SIDE | CHIRUNDU - ZAM SIDE - WAITIMNG FOR ABNORMAL PERMIT - 27-02-2026 | WHISKEY - DAY 2 | WHISKEY - DAY 3 | LUBUMBASHI | LUBUMBASHI - DAY 2 | CONNEX LUBUMBASHI - DAY 3 | CONNEX LUBUMBASHI - DAY 5 | LIKASI EN ROUTE KOLWEZI | KOLWEZI CONNEX - PLANNED OFFLOAD 11-03-2026 | OFFLOADED 11-03-2026 | OFFLOADED 11-03-2026
BA3048 | CAT14-15A MOTOR GRADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | F5800355 | CAT00014TF5800355 | TXX06298 | 2511DSI2738 | VESSEL: TING JIANG KOU Voy. 005 - ETA DURBAN: 16-12-2026 | COD 2026 215433 | HC17DTGP | CC59CYGP | 2511DSI2738 | 19-02-2026 | OFFLOADED 19-03-2026 | 17-03-2026 | 12-02-2026 | 16-02-2026 | 16-02-2026 | 19-02-2026 | CRF ISSUED 19-02-2026 |  | CATO RIDGE - 23 02 2026 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-02 | 2026-03-02 | 2026-02-03 | 2026-03-04 | 2026-03-05 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-16 | 2026-03-17 | 2026-03-19 | 2026-03-19 | [270 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION PLANNED FOR MONDAY 16-02-2026 | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY 16-02-2026 | BV INSPECTION COMPLETED - LOADING PLAN TO FOLLOW 3 | BV INSPECTION COMPLETED - LOADING FRIDAY 20-02-2026 | BV INSPECTION COMPLETED - LOADING FRIDAY 20-02-2026 | LOADING TODAY | DEPARTED CATO RIDGE | JHB - FINAL CHECKS BEFORE DEPARTING 25/02/2025 | JHB - FINAL CHECKS BEFORE DEPARTING 25/02/2025 | POLOKWANE - EN ROUTE TO BBR | BBR - SA SIDE | HARARE - EN ROUTE CHIRUNDU | CHIRUNDU - ZIM SIDE | CHIRUNDU - ZIM SIDE - DAY 2 | CHIRUNDU - ZAM SIDE | CHIRUNDU - ZAM SIDE - DAY 2 | CHIRUNDU BORDER ZAM SIDE- ZAM SYSTEMS OFFLINE - DAY 5 | PASSING LUSAKA ON ROUTE KASUMBULESA BORDER POST | CHINGOLA - EN ROUTE KASUMBULESA BORDER | KASUMBULESA BORDER - ZAM SIDE | WHISKEY - ARRIVED 12-03-2026 | WHISKEY - DISPATCHING | LUBUMBASHI - CONNEX | LUBUMBASHI - CONNEX - AWAITING RELEASE DAY 2 | LUBUMBASHI - DISPATCHING | OFFLOADED 19-03-2026 | OFFLOADED 19-03-2026
BA2867 | CAT 777 DIESEL LUBE TANK | BARTRAC EQUIPMENT / CONGO EQUIPMNET |  |  |  | 2208DSI1697 / 2602DRE2775 | XE RICHARDS BAY | COD 2025 215433 | BT33NKZN | KW72PLGP | 2601DRE2775 | 20-02-2026 | OFFLOADED 25-03-2026 | 2026-03-27 | 10-02-2026 | 13-02-2026 | 20-02-2026 | 24-02-2026 | CRF ISSUE DATE 24-02-2026 | 2026-02-16 | PIET RETIEF - 23-02-2026 | MIDDELBURG - 25-02-2026 | ROEDTAN - 27-02-2026 | 2026-03-03 | 2026-03-03 | 2026-03-04 | 2026-03-06 | 2026-03-06 | 06 03 2026 - MAPINGA | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 20-03-2026 - CHISAMBA | 23-03-2026 - NDOLA | 24-03-2026 - NDOLA | [5 empty] | 2026-03-25 | 2026-03-25 | [231 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 08-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 10-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 13-01-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 14-01-2026 | VESSEL DUE TO ARRIVE TODAY | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING - VEHICLES IN PORT TO LOAD ONCE CARGO IS AVAILABEL | LOADED FROM PORT - BV INSPECTION BOoKED FOR WEDNESDAY - AWAITING CONFIRMATION FROM BV RSA | DURBAN EN ROUTE PRETORIA | VOLKSRUST EN ROUTE BB BORDER | VOLKSRUST EN ROUTE BB BORDER | PRETORIA - BV INSPECTION BOOKED FOR TOMORROW | PRETORIA - BV INSPECTION BOOKED FOR TODAY | PRETORIA -EN ROUTE BEIT BRIDGE BORDER | BBR-ZIM SIDE AWAITING RELEASE | SHURUGWI EN ROUTE HARARE | MAKUTI EN ROUTE CHIRUNDU | CHIRUNDU-ZAM SIDE - AWAITING RELEASE | QUEUE TO KASUMBALESA BORDER | QUEUE TO KASUMBALESA BORDER - DAY 2 | QUEUE TO KASUMBALESA BORDER - DAY 3 | WHISKEY | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 6 | WHISKEY AWAITING RELEASE - DAY 6 - DOCUMENTS TO BE COLLECTED FROM CONNEX OFFICE | WHISKEY - DOCUMENTS COLLECTED FROM CONNEX OFFICE - TO DISPATCH FROM WHISKEY | WHISKEY - DOCUMENTS COLLECTED FROM CONNEX OFFICE - DISPATCHING TODAY | LUMTATA ENROUTE LUBUMBASHI | LUBUMBASHI - CONNEX | RCB - WAITING TO LOAD | LOADED - RCB WAITING FOR POLICE ESCORT - BOOKED FRI 20/02/2026 (FIRST AVAILABLE SLOT) | LOADED - RCB WAITING FOR POLICE ESCORT - BOOKED FRI 20/02/2026 (FIRST AVAILABLE SLOT) | LOADED - RCB WAITING FOR POLICE ESCORT - BOOKED FRI 20/02/2026 (FIRST AVAILABLE SLOT) | PHONGOLA - WAITING FOR POLICE ESCORTS | PIET RETIEF - WAITING FOR POLICE ESCORTS | CAROLINA - WAITING FOR POLICE ESCORTS | MIDDELBURG - WAITING FOR POLICE ESCORTS | ROEDTAN - WAITING FOR POLICE ESCORTS - EN ROUTE MUSINA | POLOKWANE - WAITING FOR POLICE ESCORTS - EN ROUTE MUSINA | VENETIA MINE - WAITING FOR POLICE ESCORTS - EN ROUTE MUSINA | BBR - AWAITING ZIM NOTIFICATION TO CROSS | BBR - IN QUEUE TO CROSS | BBR - ZIM SIDE | MAPINGA - ENROUTE CHIRUNDU | LIONS DEN TOLLGATE - BYPASS BLOCKED - CAN NOT PROCEED TO USE THE BYPASS - BYPASS SHOULD BE CLEAR TO PROCEED BY FRIDAY | LIONS DEN TOLLGATE - BYPASS BLOCKED - DAY 2 CAN NOT PROCEED TO USE THE BYPASS - BYPASS SHOULD BE CLEAR TO PROCEED BY FRIDAY | LIONS DEN TOLLGATE - BYPASS BLOCKED - DAY 3 CAN NOT PROCEED TO USE THE BYPASS - BYPASS SHOULD BE CLEAR TO PROCEED BY FRIDAY | LIONS DEN TOLLGATE - BYPASS BLOCKED - DAY 4 CAN NOT PROCEED TO USE THE BYPASS - PLANNED OPENING OF BYPASS FRIDAY 13-02-2026 | CHIRUNDU ZIM SIDE - IN QUEUE TO CROSS | CHIRUNDU ZAM SIDE - AWAITING RELEASE | CHIRUNDU ZAM SIDE - RELEASED - AWAITING ZESCO TO LIFT POWERLINES | LUSAKA - AWAITING ZESCO TO LIFT POWERLINES | CHISAMBA - AWAITING ZESCO TO LIFT POWERLINES | NDOLA - AWAITING ZESCO TO LIFT POWERLINES | ON SITE - WAITING TO OFFLOAD | ON SITE - WAITING TO OFFLOAD - CUSTOMS DELAY | OFFLOADED 25-03-2026 | OFFLOADED 25-03-2026
BA3088 | CAT AD63-03A UNDERGROUND MINING TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TNW00229 | CAT0AD63LTNW00229 |  | 2601DSI2753 | VESSEL: VENUS LEADER Voy. 076 - Transhipment Vessel: DELPHINUS LEADER Voy. 063 - ETA DURBAN: 19-02-2026 | COD 2026 111222 | CM09LLZN | MF84MJGP / MF85JFGP | ND61053 | 05-03-2026 | OFFLOADED - 02-04-2026 |  | 21-01-2026 | 26-02-2026 | 26-02-2026 | 28-02-206 | CRF ISSUED 28-02-2026 | 2026-02-27 | 2026-04-03 | 2026-03-05 | 2026-06-05 | 09-03-2026 DENDRON | 2026-03-10 | 2026-03-10 | 11-03-2026 EN ROUTE CHIBI | 2026-02-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-22 | 23-03-2026 - KITWE | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-04-01 | 2026-04-02 | [262 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 23-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-02-2026 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-02-2026 | COLLECTING - 23-02-2026 | LOADED FROM PORT - AWATING PERMIT TO PROCEED TO BV INSPECITON LOACTION. - BV INSPECTION BOOKED FOR WEDNESDAY 25-02-2026 | BV INSPECITON BOOKED FOR TOMORROW 26-02-2026 | BV INSPECITON BOOKED FOR TOMORROW 26-02-2026 | DISPATCHING - 01-03-2026 | AWAITING PERMIT - DISPATCHING TOMORROW | DISPATCHING TODAY - 03-03-2026 | TUGELA | VAAL TRUCK STOP VILLIERS - WAITING FOR PERMIT | DESPATCHING VILLIERS | DENDRON ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER - SA SIDE | BBR SA SIDE - IN QUEUE TO CUSTOMS | CHIBI | HARARE | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE - AWAITING RELEASE | CHIRUNDU ZAM SIDE - AWAITING RELEASE DAY 2 | CHIRUNDU - AWAITING ABNORMAL PERMIT - DISPATCHING | CHIRUNDU - ZAM SIDE - DISPATCHING | KITWE - EN ROUTE TO LUBUMBASHI | KASUMBALESA - DRC SIDE - WAITING CLEARANCE AND RELEASE | WHISKEY | WHISKEY - DAY 2 | EN ROUTE LUBUMBASHI | LUBUMBASHI - UNDER CLEARING (CONNEX DAY2) | LUBUMBASHI - DISPATCHING - WAITING FOR ESCORT | KOLWEZI | OFFLOADED - 02-04-2026 | OFFLOADED - 02-04-2026
BA2971 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JZ404216 | CAT00426VJZ404216 | CC210787 | 2511DSI2734 | VESSEL: APL CAIRO Voy. 549S - ETA DURBAN: 28-12-2026 | COD 2026 141043 PT01 | CAG2766ZM | BBD9785ZM | 2511DSI2734 | 23-03-2026 | OFFLOADED |  | 09-03-2026 | 11-03-2026 | 11-03-2026 | 20-03-2026 | CRF ISSUE DATE 20-03-2026 | 28-12-2025 | 19-03-2026 | 20-03-2026 | 21-03-2026 |  | GRB 21-03-2026 | GRB 23-03-2026 | MARTINS 24-03-2026 | MARTINS 25-03-2026 |  |  |  | KAZUNGULA 25-03-2026 | KAZUNGULA 28-03-2026 | KABWE - 31-03-2026 | KABWE - 31-03-2026 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-02 | 2026-04-04 | 2026-04-05 | 2026-04-07 | 2026-04-07 | [290 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING CONFIRMATION FROM BV RSA ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING DATE TO FOLLOW | BV INSPECTION DONE - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | BV INSPECTION DONE - LOADING WEDNESDAY | BV INSPECTION DONE - LOADING TODAY | BV INSPECTION DONE - VEHICLE ON SITE - LOADING TODAY | LOADING - TO DISPATCHED ONCE DONE | ENROUTE JOHANNESBURG | GROBLERS BRIDGE BORDER - WAITING TO CROSS | GROBLERS BRIDGE BORDER - WAITING TO CROSS | PANDAMATENGA | KAZUNGULA - UNDER CLEARANCE | KAZUNGULA - UNDER CLEARANCE - DAY 2 | LUSAKA | KABWE | KASUMBALESA - ZAM SIDE | ONSITE - WAIITNG TO OFFLOAD | ONSITE - WAIITNG TO OFFLOAD - DAY 2 | OFFLOADED | OFFLOADED
BA2976 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JZ404214 | CAT00426JJZ404214 | CC210784 | 2511DSI2734 | VESSEL: APL CAIRO Voy. 549S - ETA DURBAN: 28-12-2026 | COD 2026 141043 PT01 | CAG2766ZM | BBD9785ZM | 2511DSI2734 | 23-03-2026 | OFFLOADED |  | 09-03-2026 | 11-03-2026 | 11-03-2026 | 20-03-2026 | CRF ISSUE DATE 20-03-2026 | 28-12-2025 | 19-03-2026 | 20-03-2026 | 21-03-2026 |  | GRB 21-03-2026 | GRB 23-03-2026 | MARTINS 24-03-2026 | MARTINS 25-03-2026 |  |  |  | KAZUNGULA 25-03-2026 | KAZUNGULA 28-03-2026 | KABWE - 31-03-2026 | KABWE - 31-03-2026 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-02 | 2026-04-04 | 2026-04-05 | 2026-04-07 | 2026-04-07 | [290 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING CONFIRMATION FROM BV RSA ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING DATE TO FOLLOW | BV INSPECTION DONE - LOADING DATE TO FOLLOW - AWAITING VEHICLE AVAILABILITY | BV INSPECTION DONE - LOADING WEDNESDAY | BV INSPECTION DONE - LOADING TODAY | BV INSPECTION DONE - VEHICLE ON SITE - LOADING TODAY | LOADING - TO DISPATCHED ONCE DONE | ENROUTE JOHANNESBURG | GROBLERS BRIDGE BORDER - WAITING TO CROSS | GROBLERS BRIDGE BORDER - WAITING TO CROSS | PANDAMATENGA | KAZUNGULA - UNDER CLEARANCE | KAZUNGULA - UNDER CLEARANCE - DAY 2 | LUSAKA | KABWE | KASUMBALESA - ZAM SIDE | ONSITE - WAIITNG TO OFFLOAD | ONSITE - WAIITNG TO OFFLOAD - DAY 2 | OFFLOADED | OFFLOADED

## OFFLOADED - 2025
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | VESSEL DETAILS & ETA | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | BV RECEIVED | BV COMPLETE | CRF ISSUE DATE | BV COMMENTS | DBN ARR | DBN DISP | JHB ARR | JHB DISP | MUSINA ARR | MUSINA DISPATCH | BBR ARR | BBR DSP | HARARE ARR | HARARE DISP | CHIRUNDU ZIM ARR | CHIRUNDU ZIM DISP | CHIRUNDU ZAM ARR | CHIRUNDU ZAM DISP | LUSAKA ARR | LUSAKA DISP | KABWE | CHINGOLA ARR | CHINGOLA DISP | KASUMBALESA / MOKAMBO ARR | KASUMBALESA / MOKAMBO DSP | WHISKY ARR | WHISKY DISP | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 03-01-2025 | COMMENTS 06-01-2025 | COMMENTS 07-01-2025 | COMMENTS 08-01-2025 | COMMENTS 09-01-2025 | COMMENTS 10-01-2025 | COMMENTS 13-01-2025 | COMMENTS 14-01-2025 | COMMENTS 15-01-2025 | COMMENTS 16-01-2025 | COMMENTS 17-01-2025 | COMMENTS 20-01-2025 | COMMENTS 21-01-2025 | COMMENTS 22-01-2025 | COMMENTS 23-01-2025 | COMMENTS 24-01-2025 | COMMENTS 27-01-2025 | COMMENTS 28-01-2025 | COMMENTS 29-01-2025 | COMMENTS 30-01-2025 | COMMENTS 31-01-2025 | COMMENTS 03-02-2025 | COMMENTS 04-02-2025 | COMMENTS 05-02-2025 | COMMENTS 06-02-2025 | COMMENTS 07-02-2025 | COMMENTS 10-02-2025 | COMMENTS 11-02-2025
BA2856 | CAT D6R2 TRACK TYPE TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | SSS01771 | CAT00D6RTSSS01771 | TXD26505 | 2412DSI2644 | VESSEL: HOEGH OSAKA Voy. 120 - ETA DURBAN: 16-01-2025 | COD 2025 109440 | ND142761 | ND542263 | ND59405 | 27-01-2025 | OFFLOADED 08-02-2025 | 20-01-2025 | 21-01-2025 |  | BV COMPLETE | 16-01-2025 | 22-01-2025 | MIDDELBURG 22-01-2025 | MIDDELBURG 22-01-2025 | 23-01-2025 | 23-01-2025 | 23-01-2025 | 26-01-2025 | 27-01-2025 | 28-01-2025 | 28-01-2025 | 29-01-2025 | 29-01-2025 | 29-01-2025 | 29-01-2025 | 30-01-2025 | 30-01-2025 | 31-01-2025 | 31-01-2025 | 31-01-2025 | 02-02-2025 | 02-02-2025 | 04-02-2025 | 04-02-2025 | 07-02-2025 | 08-02-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | VESSEL IN AND WORKING | UNIT COLLECTED FROM PORT - AT OUR FACILITY AWAITING BV INSPECTION - BV NUMBER RECEIVED TODAY | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - AWAITING PERMITS | MARBLE HALL ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA BORDER CLEARING | BEATRICE ENROUTE HARARE | BANKET ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAMBIAN SIDE CLEARING | KABWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI CLEARING | CONNEX LUBUMBASHI CLEARING AND WAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI CLEARING AND WAITING RELEASE - DAY 3 | OFFLOADED 08-02-2025 | OFFLOADED 08-02-2025
BA2857 | CAT D6R2 TRACK TYPE TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | SSS01777 | CAT00D6RASSS01777 | TBA | 2412DSI2644 | VESSEL: HOEGH OSAKA Voy. 120 - ETA DURBAN: 16-01-2025 | COD 2025 109440 | ND61605 | ND868372 | ND59406 | 27-01-2025 | OFFLOADED 17-02-2025 | 20-01-2025 | 21-01-2025 |  | BV COMPLETE | 16-01-2025 | 28-01-2025 | 28-01-2025 | 29-01-2025 | 29-01-2025 | 30-01-2025 | 30-01-2025 | 30-01-2025 | 31-01-2025 | 02-02-2025 | 03-02-2025 | 03-02-2025 | 03-02-2025 | 05-02-2025 | 07-02-2025 | 07-02-2025 | 07-02-2025 | 07-02-2025 | 07-02-2025 | 07-02-2025 | 10-02-2025 | 10-02-2025 | 12-02-2025 | 12-02-2025 | 15-02-2025 | 17-02-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | AWAITING VESSEL ARRIVAL - VESSEL ETA 16-01-2025 | VESSEL IN AND WORKING | UNIT COLLECTED FROM PORT - AT OUR FACILITY AWAITING BV INSPECTION - BV NUMBER RECEIVED TODAY | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - AWAITING PERMITS | AWAITING PERMIT BEFORE DISPATCHING | AWAITING PERMIT BEFORE DISPATCHING - TO DISPATCH MONDAY MORNING | DISPATCHING DURBAN TODAY | MOOI RIVER ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE WAITING RELEASE | MAKUTI ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE CLEARING | SIAVHONGA ENROUTE KASUMBALESA BORDER | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | DISPATCHING WHISKEY FOR LUBUMBASHI | CONNEX LUBUMBASHI, AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI, AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-02-2025 | OFFLOADED 17-02-2025
BA2826 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | KGX00615 | CAT000D8CKGX00615 | TXJ02801 | 2501DSI2655 | VESSEL: AQUARIUS LEADER Voy. 062 - ETA DURBAN: 20-01-2025 | COD 2025 122672 PT01 | BJ59YVZN | BN39DZZN | MFST002874 | 10-02-2025 | OFFLOADED 11-03-2025 | 06-02-2025 | 07-02-2025 |  | BV COMPLETED | 20-01-2025 | 11-02-2025 | MIDDELBURG 12-02-2025 | MIDDELBURG 13-02-2025 | 14-02-2025 | 15-02-2025 | 15-02-2025 | 17-02-2025 | 19-02-2025 | 20-02-2025 | 20-02-2025 | 23-02-2025 | 23-02-2025 | 25-02-2025 | 25-02-2025 | 26-02-2025 | 26-02-2025 | 27-02-2025 | 27-02-2025 | MOKAMBO 27-02-2025 | MOKAMBO 03-03-2025 | 04-03-2025 | 05-03-2025 | 06-03-2025 | 10-03-2025 | 11-03-2025 | [20 empty] | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - BV NUMBER RECEIVED - AWAITING CONFIRMATION OF INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | DEPARTING TODAY ONCE WEATHER CLEARS | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE | POLOKWANE WAITING FOR RAIN TO STOP TO PROCEED TO BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | RUTANGA ENROUTE HARARE | CHIKOMBA ENROUTE HARARE | MAKONDE ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATCHED CHIRUNDU BORDER ENROUTE LUSAKA | DISPATCHED LUSAKA ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE IN THE QUE | WHISKEY - AWAITING RELEASE - DAY 1 | WHISKEY - AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 5 | CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 11-03-2025
BA2431 | CAT336-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET / MMG | GDY21772 | CAT00336AGDY21772 |  | 2302DSI1950 | VESSEL: SHANGHAI HIGHWAY Voy. 163 - ETA DURBAN: 29-03-2023 | COD 2025 127986 | ND570587 | BH61YRZN | ND59442 | 21-02-2025 | OFFLOADED 12-03-2025 | 13-02-2025 | 17-02-2025 |  | BV COMPLETED | 29-03-2023 | 18-02-2025 | 20-02-2025 | 20-02-2025 | 21-02-2025 | 22-02-2025 | 22-02-2025 | 24-02-2025 | 25-02-2025 | 25-02-2025 | 25-02-2025 | 27-02-2025 | 27-02-2025 | 27-02-2025 | 27-02-2025 | 28-02-2025 | 28-02-2025 | 28-02-2025 | 28-02-2025 | 28-02-2025 | 03-03-2025 | 04-03-2025 | 06-03-2025 | 07-03-2025 | 11-03-2025 | 12-03-2025 | [24 empty] | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY - LOADING MONDAY | LOADING TODAY | DISPATCHING DURBAN FOR BEIT BRIDGE BORDER | TUGELA ENROUTE BEIT BRIDGE BORDER | VAN REENEN ENROUTE BEIT BRIDGE BORDER | KRANSKOP ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | GWERU ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KABWE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER DRC SIDE - AWAITING RELEASE | WHISKEY - AWAITING RELEASE - DAY 1 | WHISKEY - AWAITING RELEASE - DAY 2 | WHISKEY - TO DISPATCH FOR LUBUMBASHI | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 4 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 5 | CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 12-03-2025
BA2833 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | KGX00622 | CAT000D8HKGX00622 | TXJ02812 | 2501DSI2658 | VESSEL: SIERRA NEVADA HIGHWAY Voy. 173A - ETA DURBAN: 03-02-2025 | COD 2025 122672 PT02 | BJ59ZYZN | BN39FRZN | MFST002876 | 10-02-2025 | OFFLOADED 12-03-2025 | 06-02-2025 | 07-02-2025 |  | BV COMPLETED | 02-02-2025 | 11-02-2025 | MIDDELBURG 12-02-2025 | MIDDELBURG 13-02-2025 | 14-02-2025 | 15-02-2025 | 15-02-2025 | 17-02-2025 | 19-02-2025 | 20-02-2025 | 20-02-2025 | 23-02-2025 | 23-02-2025 | 25-02-2025 | 25-02-2025 | 26-02-2025 | 26-02-2025 | 27-02-2025 | 27-02-2025 | MOKAMBO 27-02-2025 | MOKAMBO 03-03-2025 | 04-03-2025 | 05-03-2025 | 06-03-2025 | 11-03-2025 | 12-03-2025 | [20 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 03-02-2025 | VESSEL IN AND WORKING - AWAITING BV NUMBER | UNIT TO BE COLLECTED FROM PORT - AWAITING BV NUMBER | UNIT TO BE COLLECTED FROM PORT - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - BV NUMBER RECEIVED - AWAITING CONFIRMATION OF INSPECTION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | DEPARTING TODAY ONCE WEATHER CLEARS | VOLKSRUST ENROUTE BEIT BRIDGE BORDER | MIDDELBURG | POLOKWANE WAITING FOR RAIN TO STOP TO PROCEED TO BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | RUTANGA ENROUTE HARARE | CHIKOMBA ENROUTE HARARE | MAKONDE ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATCHED CHIRUNDU BORDER ENROUTE LUSAKA | DISPATCHED LUSAKA ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE IN THE QUE | WHISKEY - AWAITING RELEASE - DAY 1 | WHISKEY - AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 5 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 6 | CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 12-03-2025
BA2423 | CAT140K MOTOR GRADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | SZL21010 | CAT0140KKSZL21010 | TX713200 | 2302DSI1944 | VESSEL: SHANGHAI HIGHWAY Voy. 163 - ETA DURBAN: 29-03-2023 | COD 2025 124555 | ND760431 | ND627367 | ND59440 | 14-02-2025 | OFFLOADED 13-03-2025 | 11-02-2025 | 13-02-2025 |  | BV COMPLETED | 29-03-2023 | 14-02-2025 | MIDDELBURG 15-02-2025 | MIDDELBURG 17-02-2025 | 17-02-2025 | 18-02-2025 | 18-02-2025 | 22-02-2025 | 22-02-2025 | 23-02-2025 | 24-02-2025 | 24-02-2025 | 24-02-2025 | 24-02-2025 | 24-02-2025 | 25-02-2025 | 25-02-2025 | 25-02-2025 | 25-02-2025 | 27-02-2025 | 02-03-2025 | 02-03-2025 | 07-03-2025 | 08-03-2025 | 13-03-2025 | 13-03-2025 | [21 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | UNIT AT BONDED FACILITY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 13-02-2025 | BV INSPECTION TO BE DONE TODAY | LOADING TODAY | GROBLERSDAL ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE TO CROSS TO ZIM SIDE | DISPATCHING BEIT BRIDGE FOR HARARE | CHIRUNDU ZIM SIDE CLEARING | KABWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE IN THE QUEUE TO KASUMBALESA BORDER | KASUMBALESA ZAM SIDE | KASUMBALESA DRC SIDE - AWAITING RELEASE | WHISKEY - AWAITING RELEASE | WHISKEY - AWAITING RELEASE - DAY 2 | WHISKEY - AWAITING RELEASE - DAY 3 | WHISKEY - AWAITING RELEASE - DAY 4 - AWAITING DOCUMENTS - PLEASE ASSIST | WHISKEY - AWAITING RELEASE - DAY 5 - AWAITING DOCUMENTS - PLEASE ASSIST | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 3 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 4 | OFFLOADED 13-03-2025
BA2832 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | KGX00626 | CAT000D8PKGX00626 | TXJ02807 | 2501DSI2664 | VESSEL: DIVINE ACE Voy. 100A TRANSHIPMENT VESSEL: MIRACULOUS ACE V. 0134A- ETA DURBAN 01-03-2025 | COD 2025 122672 PT03 | BJ30DXZN | ND650731 | MFST002998 | 10-03-2025 | OFFLOADED 28-03-2025 | 06-02-2025 | 07-03-2025 |  | BV COMPLETED | 01-03-2025 | 06-03-2025 | MIDDELBURG 07-03-2025 | MIDDELBURG 07-03-2025 | 07-03-2025 | 08-03-2025 | 08-03-2025 | 10-03-2025 | 11-03-2025 | 13-03-2025 | 14-03-2025 | 15-03-2025 | 15-03-2025 | 16-03-2025 | 16-03-2025 | 16-03-2025 | 16-03-2025 | 18-06-2025 | 18-03-2025 | MOKAMBO 18-03-2025 | MOKAMBO 20-03-2025 | 21-03-2025 | 22-03-2025 | 22-03-2025 | 28-03-2025 | 28-03-2025 | [20 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | LOADING TODAY FROM PORT | LOADED - BV INSPECTION BOOKED FOR TOMORROW | LOADED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER ZIM SIDE | CHIVI ENROUTE HARARE | HARARE ENROUTE CHIRUNDU BORDER | HURUNGWE ENROUTE CHIRUNDU BORDER | HURUNGWE ENROUTE CHIRUNDU BORDER | CHISAMBA ENROUTE MOKAMBO BORDER | APPROCHING KITWE | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE | CONNEX LUBUMBASHI AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 PLEASE ASSIST | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 3 PLEASE ASSIST | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 4 PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 28-03-2025
BA2846 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | KGX00636 | CAT000D8HKGX00636 | TXJ02815 | 2501DSI2665 | VESSEL: DIVINE ACE Voy. 100A TRANSHIPMENT VESSEL: MIRACULOUS ACE V. 0134A- ETA DURBAN 01-03-2025 | COD 2025 122672 PT04 | BC01XZZN | BJ29YRZN | MFST002997 | 10-03-2025 | OFFLOADED 28-03-2025 | 06-02-2025 | 07-03-2025 |  | BV COMPLETED | 01-03-2025 | 06-03-2025 | MIDDELBURG 07-03-2025 | MIDDELBURG 07-03-2025 | 07-03-2025 | 08-03-2025 | 08-03-2025 | 10-03-2025 | 11-03-2025 | 13-03-2025 | 14-03-2025 | 15-03-2025 | 15-03-2025 | 16-03-2025 | 16-03-2025 | 16-03-2025 | 16-03-2025 | 18-06-2025 | 18-03-2025 | MOKAMBO 18-03-2025 | MOKAMBO 20-03-2025 | 21-03-2025 | 22-03-2025 | 22-03-2025 | 28-03-2025 | 28-03-2025 | [20 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 27-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 26-02-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-03-2025 | LOADING TODAY FROM PORT | LOADING TODAY - BV INSPECTION BOOKED FOR TOMORROW | LOADED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE | CHIVI ENROUTE HARARE | HARARE ENROUTE CHIRUNDU BORDER | HURUNGWE ENROUTE CHIRUNDU BORDER | HURUNGWE ENROUTE CHIRUNDU BORDER | CHISAMBA ENROUTE MOKAMBO BORDER | APPROCHING KITWE | MOKAMBO BORDER ZAMBIAN SIDE | MOKAMBO BORDER ZAMBIAN SIDE | CONNEX LUBUMBASHI AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 PLEASE ASSIST | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 3 PLEASE ASSIST | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 4 PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 28-03-2025
BA2877 | CAT DE9,53E GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GB800536 | CAT00C11AGB800536 |  | 2503DSI2679 | VESSEL: SANTA TERESA Voy. 250S - ETA DURBAN: 11-04-2025 | COD 2025 163116 | BCF903ZM | BCF980ZM / BCF982ZM | 2501DSI2667 | 23-04-2025 | OFFLOADED 12-05-2025 | 04-04-2025 | 16-04-2025 |  | BV NUMBER RECEIVED | 11-04-2025 | 17-04-2025 | 18-04-2025 | 19-04-2025 | GRB - 19-04-2025 | GRB - 20-04-2025 | MARTINS DRIFT 20-04-2025 | MARTINS DRIFT 20-04-2025 | FRANCISTOWN 21-04-2025 | FRANCISTOWN 21-04-2025 | KAZUNGULA BW SIDE 22-04-2025 | KAZUNGULA BW SIDE 23-04-2025 | KAZUNGULA ZM SIDE 23-04-2025 | KAZUNGULA ZM SIDE 29-04-2025 | 30-04-2025 | 30-04-2025 | 30-04-2025 | 02-05-2025 | 02-05-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 09-05-2025 | 12-05-2025 | [60 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - CONTAINER TO BE COLLECTED TODAY / TOMORROW | COLLECTING CONTAINER FROM PORT TODAY | CONTAINER TO BE UNPACKED TODAY - BV INSPECTION BOOKED FOR TUESDAY 22-04-2025 | BV INSPECTION COMPLETED - LOADING TODAY | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE - AWAITING RELEASE | LUSAKA ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE (CROSSED TO DRC SIDE 03-05-2025) | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | ARRIVED ON SITE 09-05-2025 - AWAITING TO OFFLOAD | OFFLOADED 12-05-2025
BA2878 | CAT DE9,53E GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GB800542 | CAT00C11EGB800542 |  | 2503DSI2679 | VESSEL: SANTA TERESA Voy. 250S - ETA DURBAN: 11-04-2025 | COD 2025 163116 | BCF903ZM | BCF980ZM / BCF982ZM | 2501DSI2667 | 23-04-2025 | OFFLOADED 12-05-2025 | 04-04-2025 | 16-04-2025 |  | BV NUMBER RECEIVED | 11-04-2025 | 17-04-2025 | 18-04-2025 | 19-04-2025 | GRB - 19-04-2025 | GRB - 20-04-2025 | MARTINS DRIFT 20-04-2025 | MARTINS DRIFT 20-04-2025 | FRANCISTOWN 21-04-2025 | FRANCISTOWN 21-04-2025 | KAZUNGULA BW SIDE 22-04-2025 | KAZUNGULA BW SIDE 23-04-2025 | KAZUNGULA ZM SIDE 23-04-2025 | KAZUNGULA ZM SIDE 29-04-2025 | 30-04-2025 | 30-04-2025 | 30-04-2025 | 02-05-2025 | 02-05-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 09-05-2025 | 12-05-2025 | [60 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - CONTAINER TO BE COLLECTED TODAY / TOMORROW | COLLECTING CONTAINER FROM PORT TODAY | CONTAINER TO BE UNPACKED TODAY - BV INSPECTION BOOKED FOR TUESDAY 22-04-2025 | BV INSPECTION COMPLETED - LOADING TODAY | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE - AWAITING RELEASE | LUSAKA ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE (CROSSED TO DRC SIDE 03-05-2025) | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | ARRIVED ON SITE 09-05-2025 - AWAITING TO OFFLOAD | OFFLOADED 12-05-2025
BA2879 | CAT DE9,53E GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GB800533 | CAT00C11JGB800533 |  | 2503DSI2679 | VESSEL: SANTA TERESA Voy. 250S - ETA DURBAN: 11-04-2025 | COD 2025 163116 | BCF903ZM | BCF980ZM / BCF982ZM | 2501DSI2667 | 23-04-2025 | OFFLOADED 12-05-2025 | 04-04-2025 | 16-04-2025 |  | BV NUMBER RECEIVED | 11-04-2025 | 17-04-2025 | 18-04-2025 | 19-04-2025 | GRB - 19-04-2025 | GRB - 20-04-2025 | MARTINS DRIFT 20-04-2025 | MARTINS DRIFT 20-04-2025 | FRANCISTOWN 21-04-2025 | FRANCISTOWN 21-04-2025 | KAZUNGULA BW SIDE 22-04-2025 | KAZUNGULA BW SIDE 23-04-2025 | KAZUNGULA ZM SIDE 23-04-2025 | KAZUNGULA ZM SIDE 29-04-2025 | 30-04-2025 | 30-04-2025 | 30-04-2025 | 02-05-2025 | 02-05-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 09-05-2025 | 12-05-2025 | [60 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - CONTAINER TO BE COLLECTED TODAY / TOMORROW | COLLECTING CONTAINER FROM PORT TODAY | CONTAINER TO BE UNPACKED TODAY - BV INSPECTION BOOKED FOR TUESDAY 22-04-2025 | BV INSPECTION COMPLETED - LOADING TODAY | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE - AWAITING RELEASE | LUSAKA ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE (CROSSED TO DRC SIDE 03-05-2025) | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | ARRIVED ON SITE 09-05-2025 - AWAITING TO OFFLOAD | OFFLOADED 12-05-2025
BA2880 | CAT DE9,53E GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GB800541 | CAT00C1HGB800541 |  | 2503DSI2679 | VESSEL: SANTA TERESA Voy. 250S - ETA DURBAN: 11-04-2025 | COD 2025 163116 | BCF903ZM | BCF980ZM / BCF982ZM | 2501DSI2667 | 23-04-2025 | OFFLOADED 12-05-2025 | 04-04-2025 | 16-04-2025 |  | BV NUMBER RECEIVED | 11-04-2025 | 17-04-2025 | 18-04-2025 | 19-04-2025 | GRB - 19-04-2025 | GRB - 20-04-2025 | MARTINS DRIFT 20-04-2025 | MARTINS DRIFT 20-04-2025 | FRANCISTOWN 21-04-2025 | FRANCISTOWN 21-04-2025 | KAZUNGULA BW SIDE 22-04-2025 | KAZUNGULA BW SIDE 23-04-2025 | KAZUNGULA ZM SIDE 23-04-2025 | KAZUNGULA ZM SIDE 29-04-2025 | 30-04-2025 | 30-04-2025 | 30-04-2025 | 02-05-2025 | 02-05-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 09-05-2025 | 12-05-2025 | [60 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - CONTAINER TO BE COLLECTED TODAY / TOMORROW | COLLECTING CONTAINER FROM PORT TODAY | CONTAINER TO BE UNPACKED TODAY - BV INSPECTION BOOKED FOR TUESDAY 22-04-2025 | BV INSPECTION COMPLETED - LOADING TODAY | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE - AWAITING RELEASE | LUSAKA ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE (CROSSED TO DRC SIDE 03-05-2025) | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | ARRIVED ON SITE 09-05-2025 - AWAITING TO OFFLOAD | OFFLOADED 12-05-2025
BA2881 | CAT DE9,53E GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GB800537 | CAT00C11LGB800537 |  | 2503DSI2679 | VESSEL: SANTA TERESA Voy. 250S - ETA DURBAN: 11-04-2025 | COD 2025 163116 | BCF903ZM | BCF980ZM / BCF982ZM | 2501DSI2667 | 23-04-2025 | OFFLOADED 12-05-2025 | 04-04-2025 | 16-04-2025 |  | BV NUMBER RECEIVED | 11-04-2025 | 17-04-2025 | 18-04-2025 | 19-04-2025 | GRB - 19-04-2025 | GRB - 20-04-2025 | MARTINS DRIFT 20-04-2025 | MARTINS DRIFT 20-04-2025 | FRANCISTOWN 21-04-2025 | FRANCISTOWN 21-04-2025 | KAZUNGULA BW SIDE 22-04-2025 | KAZUNGULA BW SIDE 23-04-2025 | KAZUNGULA ZM SIDE 23-04-2025 | KAZUNGULA ZM SIDE 29-04-2025 | 30-04-2025 | 30-04-2025 | 30-04-2025 | 02-05-2025 | 02-05-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 09-05-2025 | 12-05-2025 | [60 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - CONTAINER TO BE COLLECTED TODAY / TOMORROW | COLLECTING CONTAINER FROM PORT TODAY | CONTAINER TO BE UNPACKED TODAY - BV INSPECTION BOOKED FOR TUESDAY 22-04-2025 | BV INSPECTION COMPLETED - LOADING TODAY | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE - AWAITING RELEASE | LUSAKA ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE (CROSSED TO DRC SIDE 03-05-2025) | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | ARRIVED ON SITE 09-05-2025 - AWAITING TO OFFLOAD | OFFLOADED 12-05-2025
BA2882 | CAT DE9,53E GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GB800534 | CAT00C11CGB800534 |  | 2503DSI2679 | VESSEL: SANTA TERESA Voy. 250S - ETA DURBAN: 11-04-2025 | COD 2025 163116 | BCF903ZM | BCF980ZM / BCF982ZM | 2501DSI2667 | 23-04-2025 | OFFLOADED 12-05-2025 | 04-04-2025 | 16-04-2025 |  | BV NUMBER RECEIVED | 11-04-2025 | 17-04-2025 | 18-04-2025 | 19-04-2025 | GRB - 19-04-2025 | GRB - 20-04-2025 | MARTINS DRIFT 20-04-2025 | MARTINS DRIFT 20-04-2025 | FRANCISTOWN 21-04-2025 | FRANCISTOWN 21-04-2025 | KAZUNGULA BW SIDE 22-04-2025 | KAZUNGULA BW SIDE 23-04-2025 | KAZUNGULA ZM SIDE 23-04-2025 | KAZUNGULA ZM SIDE 29-04-2025 | 30-04-2025 | 30-04-2025 | 30-04-2025 | 02-05-2025 | 02-05-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 09-05-2025 | 12-05-2025 | [60 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - CONTAINER TO BE COLLECTED TODAY / TOMORROW | COLLECTING CONTAINER FROM PORT TODAY | CONTAINER TO BE UNPACKED TODAY - BV INSPECTION BOOKED FOR TUESDAY 22-04-2025 | BV INSPECTION COMPLETED - LOADING TODAY | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE - AWAITING RELEASE | LUSAKA ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE (CROSSED TO DRC SIDE 03-05-2025) | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | ARRIVED ON SITE 09-05-2025 - AWAITING TO OFFLOAD | OFFLOADED 12-05-2025
BA2883 | CAT DE55E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | EC508730 | CAT00C33CEC508730 |  | 2503DSI2679 | VESSEL: SANTA TERESA Voy. 250S - ETA DURBAN: 11-04-2025 | COD 2025 165784 | BCF903ZM | BCF980ZM / BCF982ZM | 2501DSI2667 | 23-04-2025 | OFFLOADED 12-05-2025 | 09-04-2025 | 16-04-2025 |  | BV NUMBER RECEIVED | 11-04-2025 | 17-04-2025 | 18-04-2025 | 19-04-2025 | GRB - 19-04-2025 | GRB - 20-04-2025 | MARTINS DRIFT 20-04-2025 | MARTINS DRIFT 20-04-2025 | FRANCISTOWN 21-04-2025 | FRANCISTOWN 21-04-2025 | KAZUNGULA BW SIDE 22-04-2025 | KAZUNGULA BW SIDE 23-04-2025 | KAZUNGULA ZM SIDE 23-04-2025 | KAZUNGULA ZM SIDE 29-04-2025 | 30-04-2025 | 30-04-2025 | 30-04-2025 | 02-05-2025 | 02-05-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 09-05-2025 | 12-05-2025 | [60 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - CONTAINER TO BE COLLECTED TODAY | CONTAINER TO BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TUESDAY 22-04-2025 | BV INSPECTION COMPLETED - LOADING TODAY | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE - AWAITING RELEASE | LUSAKA ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE (CROSSED TO DRC SIDE 03-05-2025) | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | ARRIVED ON SITE 09-05-2025 - AWAITING TO OFFLOAD | OFFLOADED 12-05-2025
BA2884 | CAT C32 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GJ900109 | GJ900109 |  | 2503DSI2679 | VESSEL: SANTA TERESA Voy. 250S - ETA DURBAN: 11-04-2025 | COD 2025165937 | BCF903ZM | BCF980ZM / BCF982ZM | 2501DSI2667 | 23-04-2025 | OFFLOADED 12-05-2025 | 09-04-2025 | 16-04-2025 |  | BV NUMBER RECEIVED | 11-04-2025 | 17-04-2025 | 18-04-2025 | 19-04-2025 | GRB - 19-04-2025 | GRB - 20-04-2025 | MARTINS DRIFT 20-04-2025 | MARTINS DRIFT 20-04-2025 | FRANCISTOWN 21-04-2025 | FRANCISTOWN 21-04-2025 | KAZUNGULA BW SIDE 22-04-2025 | KAZUNGULA BW SIDE 23-04-2025 | KAZUNGULA ZM SIDE 23-04-2025 | KAZUNGULA ZM SIDE 29-04-2025 | 30-04-2025 | 30-04-2025 | 30-04-2025 | 02-05-2025 | 02-05-2025 | 02-05-2025 | 05-05-2025 | 05-05-2025 | 06-05-2025 | 06-05-2025 | 09-05-2025 | 12-05-2025 | [60 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 06-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 07-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 09-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 10-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 11-04-2025 | VESSEL DUE TO ARRIVE PM TODAY | VESSEL IN AND WORKING - CONTAINER TO BE COLLECTED TODAY | CONTAINER TO BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TUESDAY 22-04-2025 | BV INSPECTION COMPLETED - LOADING TODAY | KAZUNGULA BORDER BOTSWANA SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE - AWAITING RELEASE | LUSAKA ENROUTE NDOLA | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE AWAITING RELEASE (CROSSED TO DRC SIDE 03-05-2025) | WHISKEY AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | ARRIVED ON SITE 09-05-2025 - AWAITING TO OFFLOAD | OFFLOADED 12-05-2025
BA2921 | CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | EC903995 | CAT00C44KEC903995 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 188964 | AJB9891 | N/A | 2504DSI2687C | 23-05-2025 | OFFLOADED 14-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 26-05-2025 | 27-05-2025 | 28-05-2025 | GRB 28-05-2025 | GRB 28-05-2025 | MARTINS DRIFT 28-05-2025 | MARTINS DRIFT 28-05-2025 | FRANCISTOWN 28-05-2025 | FRANCISTOWN 28-05-2025 | KAZUNGULA BW 28-05-2025 | KAZUNGULA BW 29-05-2025 | KAZUNGULA BW 29-05-2025 | KAZUNGULA BW 31-05-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | MOKAMBO 01-06-2025 | MOKAMBO 03-06-2025 | 03-06-2025 | 06-06-2025 | 06-06-2025 | 13-06-2025 | 14-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADED YESTERDAY - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER BOTSWANA SIDE WAITING TO CROSS TO ZAMBIAN SIDE | KAZUNGULA BORDER ZAMBIAN SIDE | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CROSSING TO DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 PLEASE ASSIST | ENROUTE LUBUMBASHI TO DO FINAL CLEARANCE AT CONNEX | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 4 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 5 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | OFFLOADED 14-06-2025 | OFFLOADED 14-06-2025
BA2922 | CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | EC903994 | CAT00C44PEC903994 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 188964 | AJB9891 | N/A | 2504DSI2687C | 23-05-2025 | OFFLOADED 14-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 26-05-2025 | 27-05-2025 | 28-05-2025 | GRB 28-05-2025 | GRB 28-05-2025 | MARTINS DRIFT 28-05-2025 | MARTINS DRIFT 28-05-2025 | FRANCISTOWN 28-05-2025 | FRANCISTOWN 28-05-2025 | KAZUNGULA BW 28-05-2025 | KAZUNGULA BW 29-05-2025 | KAZUNGULA BW 29-05-2025 | KAZUNGULA BW 31-05-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | MOKAMBO 01-06-2025 | MOKAMBO 03-06-2025 | 03-06-2025 | 06-06-2025 | 06-06-2025 | 13-06-2025 | 14-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADED YESTERDAY - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER BOTSWANA SIDE WAITING TO CROSS TO ZAMBIAN SIDE | KAZUNGULA BORDER ZAMBIAN SIDE | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CROSSING TO DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 PLEASE ASSIST | ENROUTE LUBUMBASHI TO DO FINAL CLEARANCE AT CONNEX | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 4 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 5 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | OFFLOADED 14-06-2025 | OFFLOADED 14-06-2025
BA2923 | CAT DE88GC0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7C00747 | CAT0DE88CN7C00747 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 197307 | AJB9891 | N/A | 2504DSI2687C | 28-05-2025 | OFFLOADED 14-06-2025 | 22-05-2025 | 26-05-2025 |  | BV COMPLETED | 13-05-2025 | 26-05-2025 | 27-05-2025 | 28-05-2025 | GRB 28-05-2025 | GRB 28-05-2025 | MARTINS DRIFT 28-05-2025 | MARTINS DRIFT 28-05-2025 | FRANCISTOWN 28-05-2025 | FRANCISTOWN 28-05-2025 | KAZUNGULA BW 28-05-2025 | KAZUNGULA BW 29-05-2025 | KAZUNGULA BW 29-05-2025 | KAZUNGULA BW 31-05-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | 01-06-2025 | MOKAMBO 01-06-2025 | MOKAMBO 03-06-2025 | 03-06-2025 | 06-06-2025 | 06-06-2025 | 13-06-2025 | 14-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLAN TO BE ADVISED ONCE BV NUMBER HAS BEEN RECEIVED | BV INSPECTION BOOKED FOR MONDAY 26-05-2025 - LOADING ONCE INSPECTION IS DONE | BV INSPECTION BOOKED FOR TODAY 26-05-2025 - LOADING ONCE INSPECTION IS DONE | LOADED YESTERDAY - DISPATCHED DURBAN ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER BOTSWANA SIDE WAITING TO CROSS TO ZAMBIAN SIDE | KAZUNGULA BORDER ZAMBIAN SIDE | MOKAMBO BORDER CLEARING | MOKAMBO BORDER CROSSING TO DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 PLEASE ASSIST | ENROUTE LUBUMBASHI TO DO FINAL CLEARANCE AT CONNEX | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 4 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 5 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | OFFLOADED 14-06-2025 | OFFLOADED 14-06-2025
BA2904 | CAT DE150E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GTY01934 | CAT00C71HGTY01934 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 191969 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 23-05-2025 | OFFLOADED 17-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2905 | CAT DE200E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | ECW8065 | CAT00C71HECW08065 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 191998 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 23-05-2025 | OFFLOADED 17-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2906 | CAT DE220E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | ECW08075 | CAT00C71CECW08075 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 197260 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 28-05-2025 | OFFLOADED 17-06-2025 | 22-05-2025 | 26-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLAN TO BE ADVISED ONCE BV NUMBER HAS BEEN RECEIVED | BV INSPECTION BOOKED FOR MONDAY 26-05-2025 - LOADING ONCE INSPECTION IS DONE | BV INSPECTION BOOKED FOR TODAY 26-05-2025 - LOADING ONCE INSPECTION IS DONE | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2914 | CAT DE500E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 2S300393 | CAT0C15C2S300393 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 191995 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 23-05-2025 | OFFLOADED 17-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2915 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7B00815 | CAT0DE50HN7B00815 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 188943 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 23-05-2025 | OFFLOADED 17-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2916 | CAT DE50GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7B00814 | CAT0DE50LN7B00814 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 188943 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 23-05-2025 | OFFLOADED 17-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2917 | CAT DE65E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | EC509947 | CAT00C33HEC509947 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 188946 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 23-05-2025 | OFFLOADED 17-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2918 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7300876 | CAT0DE65EN7300876 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 188947 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 23-05-2025 | OFFLOADED 17-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2919 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7300858 | CAT0DE65HN7300858 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 188947 | KT12NKGP | YSN353GP / YSN837GP | 2504DSI2687B | 23-05-2025 | OFFLOADED 17-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 27-05-2025 | 28-05-2025 | 30-05-2025 | KOPFONTEIN RSA - 31-05-2025 | KOPFONTEIN RSA - 31-05-2025 | TLOKWENG BW 31-05-2025 | TLOKWENG BW 01-06-2025 | FRANCISTOWN 01-06-2025 | FRANCISTOWN 01-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 02-06-2025 | KAZUNGULA BW 03-06-2025 | 03-06-2025 | 03-06-2025 | 04-06-2025 | 05-06-2025 | 05-06-2025 | 06-06-2025 | 07-06-2025 | 07-06-2025 | 10-06-2025 | 11-06-2025 | 16-06-2025 | 17-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISED ONCE THE OUTSTANDING BV NUMBER HAS BEEN RECEIVED | LOADING MONDAY 26-05-2025 | LOADING TODAY | LOADING TODAY - DISPATCHING ONCE LOADED | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER | JOHANNESBURG - TO DISPATCH FOR KOPFONTEIN BORDER LATER TODAY | PANDAMATENGA ENROUTE KAZUNGULA BORDER | KALOMO ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA UNDER CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2025 | OFFLOADED 17-06-2025
BA2903 | CAT DE1500 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TZJ00728 | CAT00C32JTZJ00728 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 192047 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2907 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7500456 | CATDE220TN7500456 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 1862222 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 12-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL 13-05-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER OF ALL GENSETS | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2908 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7500450 | CATDE220VN7500450 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 1862222 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 12-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL 13-05-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER OF ALL GENSETS | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2909 | CAT DE220GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7500459 | CATDE220JN7500459 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 1862222 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 12-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL 13-05-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER OF ALL GENSETS | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2910 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7A00853 | CAT0DE33VN7A00853 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 186209 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 12-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL 13-05-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER OF ALL GENSETS | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2911 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7A00852 | CAT0DE33CN7A00852 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 186209 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 12-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL 13-05-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER OF ALL GENSETS | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2912 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7A00854 | CAT0DE33AN7A00854 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 186209 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 12-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL 13-05-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER OF ALL GENSETS | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2913 | CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7A00866 | CAT0DE33CN7A00866 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 186209 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 12-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL 13-05-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND WORKING | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY | AT BONDED FACILITY - BV INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER OF ALL GENSETS | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2920 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7300859 | CAT0DE65EN7300859 | N/A | 2504DSI2687 | VESSEL: SANTA CLARA Voy. 251S - ETA DURBAN: 13-05-2025 | COD 2025 188947 | LH12MYGP | YSN849GP / YSN855GP | 2504DSI2687A | 23-05-2025 | OFFLOADED 19-06-2025 | 19-05-2025 | 21-05-2025 |  | BV COMPLETED | 13-05-2025 | 22-05-2025 | 23-05-2025 | 24-05-2025 | KOPFONTEIN RSA - 24-05-2025 | KOPFONTEIN RSA - 25-05-2025 | TLOKWENG BW 25-05-2025 | TLOKWENG BW 25-05-2025 | FRANCISTOWN 25-05-2025 | FRANCISTOWN 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA BW 26-05-2025 | KAZUNGULA ZM 27-05-2025 | KAZUNGULA ZM 27-05-2025 | 28-05-2025 | 28-05-2025 | 29-05-2025 | 30-05-2025 | 30-05-2025 | 30-05-2025 | 07-06-2025 | 07-06-2025 | 11-06-2025 | 11-06-2025 | 18-06-2025 | 19-06-2025 | [81 empty] | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER | AWAITING VESSEL ARRIVAL AND BV NUMBER - ETA 13-05-2025 | VESSEL DUE TO ARRIVE TODAY - AWAITING BV NUMBER | VESSEL IN AND WORKING - AWAITING BV NUMBER | CONTAINER COLLECTED FROM PORT & WILL BE UNPACKED TODAY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER AND INSPECTION - LOADING PLANNED FOR WEDNESDAY PENDING RECEIPT OF BV NUMBER | AT BONDED FACILITY - BV NUMBER RECEIVED & INSPECTION TO BE BOOKED FOR WEDNESDAY - LOADING PLANNED FOR THURSDAY | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TOMORROW - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | AT BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR THURSDAY PENDING RECEIPT OF OUTSTANDING BV NUMBERS | BV INSPECTION COMPLETED - LOADING FROM BONDED FACILITY TODAY | LOADED - DISPATCHED DURBAN ENROUTE JOHANNESBURG | FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAMBIAN SIDE CLEARING | LIVINGSTONE ENROUTE NDOLA | KABWE ENROUTE NDOLA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING - DAY 2 | KASUMBALESA DRC SIDE CLEARING - DAY 3 | KASUMBALESA DRC SIDE CLEARING - DAY 4 | KASUMBALESA DRC SIDE CLEARING - DAY 5 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | WHISKEY ENROUTE KANYAKA | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE - DAY 7 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-06-2025 | OFFLOADED 19-06-2025
BA2804 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TJT20275 | CAT00333TTJT20275 | E7A63609 | 2409DSI2596A | VESSEL: GANIANGKOU Voy. 01 - ETA DURBAN 15-10-2024 | COD 2025 208596 | BJ30GWZN | BK71HCZN | MFST003911 | 18-06-2025 | OFFLOADED 05-07-2025 | 09-06-2025 | 11-06-2025 | 13-06-2025 | AV (CONFORM CERTIFICATE) ISSUED 13-06-2025 | 15-10-2024 | 18-06-2025 | 19-06-2025 | 20-06-2025 | 20-06-2025 | 23-06-2025 | 23-06-2025 | 25-06-2025 | 26-06-2025 | 27-06-2025 | 27-06-2025 | 28-06-2025 | 28-06-2025 | 30-06-2025 | 30-06-2025 | 30-06-2025 | 30-06-2025 | 01-07-2025 | 01-07-2025 | MOKAMBO 01-07-2025 | MOKAMBO 02-07-2025 | 03-07-2025 | 03-07-2025 | 04-07-2025 | 05-07-2025 | 05-07-2025 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW - CONFIRMATION TO BE RECEIVED FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | LOADING MONDAY 16-06-2025 | LOADING TUESDAY 17-06-2025 | LOADING TOMORROW | LAODING TODAY | WARDEN ENROUTE JOHANNESBURG | MOOKGOPONG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE TO CROSS TO ZIM SIDE | BEIT BRIDGE BORDER ZIM SIDE AWAITING RELEASE | MASVINGO ENROUTE HARARE | HURUNGWE ENROUTE CHIRUNDU BORDER | CHIKANKANTA ENROUTE LUSAKA | MPONGWE ENROUTE MOKAMBO BORDER | MOKAMOBO BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | OFFLOADED 05-07-2025 | OFFLOADED 05-07-2025
BA2790 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TJT20219 | CAT0333ATJT20219 | E7A63295 | 2409DSI2581 | VESSEL: MORNING CHANT Voy. 101 - ETA DURBAN 18-10-2024 | COD 2025 208596 | BJ60GTZN | BN54MHZN | MFST003910 | 18-06-2025 | OFFLOADED 09-07-2025 | 09-06-2025 | 11-06-2025 | 12-06-2025 | AV (CONFORM CERTIFICATE) ISSUED 12-06-2025 | 18-10-2024 | 17-06-2025 | 17-06-2025 | 18-06-2025 | 19-06-2025 | 19-06-2025 | 19-06-2025 | 21-06-2025 | 23-06-2025 | 23-06-2025 | 24-06-2025 | 25-06-2025 | 25-06-2025 | 27-06-2025 | 27-06-2025 | 27-06-2025 | 28-06-2025 | 30-06-2025 | 30-06-2025 | MOKAMBO 01-07-2025 | MOKAMBO 02-07-2025 | 03-07-2025 | 03-07-2025 | 04-07-2025 | 09-07-2025 | 09-07-2025 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW - CONFIRMATION TO BE RECEIVED FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED - AWAITING PERMITS - DUE TO LONG WEEKEND AND EMBARGO FROM TODAY. VEHICLE WILL DISPATCH TUESDAY 17-06-2025 | DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | HARARE ENROUTE CHIRUNDU | HURUNGWE ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE TO DISPATCH FOR MOKAMBO BORDER | KITWE REFUELING | MOKAMOBO BORDER ZAMBIAN SIDE CLEARING | MOKAMOBO BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE - DAY 4 | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE - DAY 5 | OFFLOADED 09-07-2025
BA2791 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TJT20220 | CAT0333CTJT20220 | E7A63356 | 2409DSI2581 | VESSEL: MORNING CHANT Voy. 101 - ETA DURBAN 18-10-2024 | COD 2025 208596 | BC02BWZN | CJ99PTZN | MFST003909 | 18-06-2025 | OFFLOADED 09-07-2025 | 09-06-2025 | 11-06-2025 | 13-06-2025 | AV (CONFORM CERTIFICATE) ISSUED 13-06-2025 | 18-10-2024 | 17-06-2025 | 18-06-2025 | 19-06-2025 | 19-06-2025 | 19-06-2025 | 19-06-2025 | 24-06-2025 | 25-06-2025 | 25-06-2025 | 26-06-2025 | 27-06-2025 | 27-06-2025 | 27-06-2025 | 27-06-2025 | 27-06-2025 | 28-06-2025 | 30-06-2025 | 30-06-2025 | MOKAMBO 01-07-2025 | MOKAMBO 02-07-2025 | 03-07-2025 | 03-07-2025 | 04-07-2025 | 09-07-2025 | 09-07-2025 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW - CONFIRMATION TO BE RECEIVED FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED - AWAITING PERMITS - DUE TO LONG WEEKEND AND EMBARGO FROM TODAY. VEHICLE WILL DISPATCH TUESDAY 17-06-2025 | DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | VAN REENEN ENROUTE JOHANNESBURG | BELA BELA ENROUTE BETI BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE AWAITING RELEASE | DISPATCH BEIT BRIDGE BORDER ENROUTE HARARE | CHIKOMBA ENROUTE HARARE | HURUNGWE ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | KITWE REFUELING | MOKAMOBO BORDER ZAMBIAN SIDE CLEARING | MOKAMOBO BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE - DAY 4 | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE - DAY 5 | OFFLOADED 09-07-2025
BA2799 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TJT20270 | CAT00333ATJT20270 | E7A63615 | 2409DSI2589 | VESSEL: VIKING QUEEN Voy. 0424 - ETA DURBAN: 25-10-2024 | COD 2025 208596 | BF94MDZN | BJ30BBZN | MFST003912 | 18-06-2025 | OFFLOADED 09-07-2025 | 09-06-2025 | 11-06-2025 | 12-06-2025 | AV (CONFORM CERTIFICATE) ISSUED 12-06-2025 | 25-10-2024 | 17-06-2025 | 18-06-2025 | 19-06-2025 | 19-06-2025 | 20-06-2025 | 20-06-2025 | 21-06-2025 | 23-06-2025 | 23-06-2025 | 24-06-2025 | 25-06-2025 | 25-06-2025 | 27-06-2025 | 28-06-2025 | 28-06-2025 | 28-06-2025 | 30-06-2025 | 30-06-2025 | MOKAMBO 01-07-2025 | MOKAMBO 02-07-2025 | 03-07-2025 | 03-07-2025 | 04-07-2025 | 09-07-2025 | 09-07-2025 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW - CONFIRMATION TO BE RECEIVED FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | LOADING TOMORROW 13-06-2025 | LOADING TODAY - DUE TO LONG WEEKEND AND EMBARGO FROM TODAY. VEHICLE WILL DISPATCH TUESDAY 17-06-2025 | DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | VAN REENEN ENROUTE JOHANNESBURG | BELA BELA ENROUTE BETI BRIDGE BORDER | MUSINA ENROUTE BEIT BRIDGE BORDER | HARARE ENROUTE CHIRUNDU | HURUNGWE ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE TO DISPATCH FOR MOKAMBO BORDER | KITWE REFUELING | MOKAMOBO BORDER ZAMBIAN SIDE CLEARING | MOKAMOBO BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE - DAY 4 | CONNEX LUBUMBASHI CLEARANCE COMPLETE AWAITING RELEASE - DAY 5 | OFFLOADED 09-07-2025
BA2795 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | JZ402381 | CAT00426KJZ402381 | CC208747 | 2408DSI2572 | VESSEL: MSC DARDANELLES Voy. ZF437R - ETA DURBAN: 23-09-2024 | COD 2025 222762 | BAX5111ZM | ADE2534ZM | 2408DSI2572 | 03-07-2025 | OFFLOADED 31-07-2025 | 01-07-2025 | 02-07-2025 | 05-07-2025 | AV (CONFORM CERTIFICATE) ISSUED 05-07-2025 | 23-09-2024 | 14-07-2025 | 14-07-2025 | 14-07-2025 | GRB - 15-07-2025 | GRB 17-07-2025 | MARTINS DRIFT 17-07-2025 | MARTINS DRIFT 17-07-2025 | FRANCISTOWN 17-07-2025 | FRANCISTOWN 17-07-2025 | KAZUNGULA BW 17-07-2025 | KAZUNGULA BW 18-07-2025 | KAZUNGULA ZM 19-07-2025 | KAZUNGULA ZM 19-07-2025 | 19-07-2025 | 20-07-2025 | 21-07-2025 | 22-07-2025 | 22-07-2025 | 22-07-2025 | 23-07-2025 | 24-07-2025 | 25-07-2025 | 25-07-2025 | 30-07-2025 | 31-07-2025 | [116 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED - AWAITING CONFIRMATION FROM BV RSA O NINSPECTION DATE | BV INSPECTION BOOKED FOR TODAY 02-07-2025 - LOADING PLANNED FOR NEXT WEEK TUESDAY | LOADING PLANNED FOR MONDAY 07-07-2025 | LOADING PLANNED FOR MONDAY 07-07-2025 | LOADING TODAY | VEHICLE DELAYED - LOADING THURSDAY | VEHICLE DELAYED - LOADING THURSDAY | LOADING TODAY | COMPLETING LOADING | DISPATCHING DURBAN FOR GROBLERSBRIDGE BORDER | GROBLERSBRIDGE BORDER CLEARING | GROBLERSBRIDGE BORDER CLEARING | THOBE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | KABWE ENROUTE KASUMBALESA BORDER | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE - DAY 3 | ON SITE, WAITING TO OFFLOAD | OFFLOADED 31-07-2025
BA2796 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | JZ402391 | CAT00426EJZ402391 | CC208924 | 2408DSI2572 | VESSEL: MSC DARDANELLES Voy. ZF437R - ETA DURBAN: 23-09-2024 | COD 2025 222762 | BAX5111ZM | ADE2534ZM | 2408DSI2572 | 03-07-2025 | OFFLOADED 31-07-2025 | 01-07-2025 | 02-07-2025 | 05-07-2025 | AV (CONFORM CERTIFICATE) ISSUED 05-07-2025 | 23-09-2024 | 14-07-2025 | 14-07-2025 | 14-07-2025 | GRB - 15-07-2025 | GRB 17-07-2025 | MARTINS DRIFT 17-07-2025 | MARTINS DRIFT 17-07-2025 | FRANCISTOWN 17-07-2025 | FRANCISTOWN 17-07-2025 | KAZUNGULA BW 17-07-2025 | KAZUNGULA BW 18-07-2025 | KAZUNGULA ZM 19-07-2025 | KAZUNGULA ZM 19-07-2025 | 19-07-2025 | 20-07-2025 | 21-07-2025 | 22-07-2025 | 22-07-2025 | 22-07-2025 | 23-07-2025 | 24-07-2025 | 25-07-2025 | 25-07-2025 | 30-07-2025 | 31-07-2025 | [116 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED - AWAITING CONFIRMATION FROM BV RSA O NINSPECTION DATE | BV INSPECTION BOOKED FOR TODAY 02-07-2025 - LOADING PLANNED FOR NEXT WEEK TUESDAY | LOADING PLANNED FOR MONDAY 07-07-2025 | LOADING PLANNED FOR MONDAY 07-07-2025 | LOADING TODAY | VEHICLE DELAYED - LOADING THURSDAY | VEHICLE DELAYED - LOADING THURSDAY | LOADING TODAY | COMPLETING LOADING | DISPATCHING DURBAN FOR GROBLERSBRIDGE BORDER | GROBLERSBRIDGE BORDER CLEARING | GROBLERSBRIDGE BORDER CLEARING | THOBE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | KABWE ENROUTE KASUMBALESA BORDER | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE - DAY 3 | ON SITE, WAITING TO OFFLOAD | OFFLOADED 31-07-2025
BA2798 | CAT350-06C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | WDP20175 | CAT00350HWDP20175 | NTB14841 | 2409DSI2588 | VESSEL: VIKING QUEEN Voy. 0424 - ETA DURBAN: 25-10-2024 | COD 2025 249514 | DM28SJGP | JM62HNGP / KG03VLGP | ND60656 | 12-08-2025 | OFFLOADED 02-09-2025 | 07-08-2025 | 08-08-2025 | 12-08-2025 | 13-08-2025 | BV COMPLETE | 25-10-2025 | 14-08-2025 | 16-08-2025 | 18-08-2025 | 18-08-2025 | 18-08-2028 | 18-08-2025 | 20-08-2025 | 20-08-2025 | 21-08-2025 | 22-08-2025 | 23-08-2025 | 23-08-2025 | 24-08-2025 | 24-08-2025 | 24-08-2025 | 24-08-2025 | 25-08-2025 | 25-08-2025 | 25-08-2025 | 27-08-2025 | 27-08-2025 | 28-08-2025 | 28-08-2025 | 01-09-2025 | 02-09-2025 | [137 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING PRELIMINARY NOTIFICATION FROM BV BEFORE LOADING - LOADING PLANNED FOR WEDNESDAY 13-08-2025 | LOADING TOMORROW | LOADING TODAY | HOWICK ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | PIENAARSREVIER ENORUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | MAKUTI ENROUTE CHIRUNDU | KASUMBALESA ZAMBIAN SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE - AWAITING DUTIES | DISPATCHING WHISKEY | CONNEX LUBUMBASHI - AWATING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI - AWATING FINAL CLEARANCE AND RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | OFFLOADED 02-09-2025
BA2792 | CAT350-06C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | WDP20141 | CAT00350VWDP20141 | NTB14602 | 2409DSI2582 | VESSEL: MORNING CHANT Voy. 101 - ETA DURBAN: 18-10-2024 | COD 2025 249514 | CR83TPGP | KR05VLGP / KS98MPGP | ND60655 | 11-08-2025 | OFFLOADED 02-09-2025 | 07-08-2025 | 08-08-2025 | 08-08-2025 | 13-08-2025 | BV COMPLETE | 18-10-2024 | 14-08-2025 | 16-08-2025 | 18-08-2025 | 18-08-2025 | 18-08-2028 | 18-08-2025 | 20-08-2025 | 20-08-2025 | 21-08-2025 | 22-08-2025 | 23-08-2025 | 23-08-2025 | 24-08-2025 | 24-08-2025 | 24-08-2025 | 24-08-2025 | 25-08-2025 | 25-08-2025 | 25-08-2025 | 27-08-2025 | 27-08-2025 | 28-08-2025 | 28-08-2025 | 01-09-2025 | 02-09-2025 | [137 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING TODAY | LOADING TODAY | CATO RIDGE TO DISPATCH FOR JOHANNESBURG | PIETERMARITZBURG ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | PIENAARSREVIER ENORUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | MAKUTI ENROUTE CHIRUNDU | KASUMBALESA ZAMBIAN SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE - AWAITING DUTIES | DISPATCHING WHISKEY | CONNEX LUBUMBASHI - AWATING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI - AWATING FINAL CLEARANCE AND RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | OFFLOADED 02-09-2025
BA2805 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TJT20277 | CAT00333KTJT20277 | E7A63804 | 2409DSI2596B | VESSEL: GAIN JIANG KOU Voy. 01 - ETA DURBAN: 15-10-2024 | COD 2025 247487 | JT84DPGP | KW61VSGP | 2409DSI2596B | 07-08-2025 | OFFLOADED 03-09-2025 | 05-08-2025 | 06-08-2025 | 07-08-2025 | 08-08-2025 | BV COMPLETE | 15-10-2024 | 13-08-2025 | 14-05-2025 | 19-08-2025 | 19-08-2025 | 20-08-2025 | 20-08-2025 | 21-08-2025 | 22-08-2025 | 22-08-2025 | 22-08-2025 | 23-08-2025 | 23-08-2025 | 25-08-2025 | 26-08-2025 | 26-08-2025 | 26-08-2025 | 26-08-2025 | 27-08-2025 | 27-08-2025 | 28-08-2025 | 28-08-2025 | 31-08-2025 | 01-09-2025 | 03-09-2025 | 03-09-2025 | [137 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION REQUEST SENT TO BV RSA - AWAITING CONFIRMATION ON INSPECTION DATE | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING TUESDAY 12-08-2025 | BV INSPECTION COMPLETED - LOADING TUESDAY 12-08-2025 | LOADING TODAY | DISPATCHING DURBAN ENROUTE JOHANNESBURG | HARRISMITH ENROUTE JOHANNESBURG | JOHANNESBURG - AWAITING LIMPOPO PERMIT | JOHANNESBURG - AWAITING LIMPOPO PERMIT - PERMIT TO BE FINALIZED TODAY | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE CLEARING | KAFUE ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE - IN THE QUE TO CROSS | WHISKEY AWAITING RELEASE | KANYAKA PARKING | CONNEX LUBUMBASHI - AWATING FINAL CLEARANCE AND RELEASE - DAY 1 | ON SITE WAITING TO OFFLOAD | OFFLOADED 03-09-2025
BA2848 | CAT966GC-01B WHEEL LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | SGW02720 | CAT00966CSGW02720 | NTB14720 | 2412DSI2641 | VESSEL: TOREADOR Voy. 034 - ETA DURBAN: 14-01-2025 | COD 2025 253534 | KW41BTGP | BZ72BJGP | 2412DSI2641 | 14-08-2025 | OFFLOADED 03-09-2025 | 12-08-2025 | 13-08-2025 | 14-08-2025 | 16-08-2025 | BV COMPLETE | 14-01-2025 | 19-08-2025 | 19-08-2025 | 20-08-2025 | 20-08-2025 | 20-08-2025 | 20-08-2025 | 22-08-2025 | 22-08-2025 | 22-08-2025 | 22-08-2025 | 23-08-2025 | 23-08-2025 | 25-08-2025 | 26-08-2025 | 26-08-2025 | 26-08-2025 | 26-08-2025 | 27-08-2025 | 27-08-2025 | 28-08-2025 | 28-08-2025 | 31-08-2025 | 01-09-2025 | 03-09-2025 | 03-09-2025 | [146 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING PRELIMINARY NOTIFICATION FROM BV - LOADING PLANNED FOR MONDAY 18-08-2025 | LOADING PLANNED FOR TUESDAY 19-08-2025 | LOADING TODAY | ESCOURT ENROUTE JOHANNESBURG | MANTSOLE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | MVUMA ENROUTE HARARE | CHIRUNDU ZAMBIAN SIDE CLEARING | KAFUE ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE - IN THE QUE TO CROSS | WHISKEY AWAITING RELEASE | KANYAKA PARKING | CONNEX LUBUMBASHI - AWATING FINAL CLEARANCE AND RELEASE - DAY 1 | ON SITE WAITING TO OFFLOAD | OFFLOADED 03-09-2025
BA2849 | CAT M317-04E WHEEL EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | D7Y00264 | CAT0M317JD7X00264 | 2W239391 | 2501DSI2656 | VESSEL: SIERRA NEVADA HIGHWAY Voy. 173 - ETA DURBAN: 01-02-2025 | COD 2025 249219 | CJ84RCZN | ND542263 | ND60657 | 07-08-2025 | OFFLOADED 03-09-2025 | 05-08-2025 | 06-08-2025 | 07-08-2025 | 12-08-2025 | BV COMPLETE | 01-02-2025 | 14-08-2025 | 16-08-2025 | 18-08-2025 | 18-08-2025 | 18-08-2028 | 18-08-2025 | 21-08-2025 | 21-08-2025 | 22-08-2025 | 22-08-2025 | 23-08-2025 | 23-08-2025 | 25-08-2025 | 26-08-2025 | 26-08-2025 | 27-08-2025 | 27-08-2025 | 27-08-2025 | 28-08-2025 | 29-08-2025 | 29-08-2025 | 30-08-2025 | 30-08-2025 | 03-09-2025 | 03-09-2025 | [137 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION REQUEST SENT TO BV RSA - AWAITING CONFIRMATION ON INSPECTION DATE | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING TUESDAY 12-08-2025 | BV INSPECTION COMPLETED - LOADING TUESDAY 12-08-2025 | LOADING TODAY | LOADED - AWAITING PERMIT | DISPATCHING DURBAN TODAY | HOWICK ENROUTE JOHANNESBURG | CAROUSEL ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | CHIVHU ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE CLEARING | SIAVONGA ENROUTE KASUMBALESA BORDER | KAPIRI MPOSHE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI - AWATING FINAL CLEARANCE AND RELEASE - DAY 1 | CONNEX LUBUMBASHI - AWATING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 03-09-2025
BA2794 | CAT D6GC TRACK TYPE TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | XPC01063 | CAT000D6CXPC01063 | R6J05125 | 2409DSI2597 | VESSEL: ORIEN LEADER Voy. 050 - ETA DURBAN: 19-10-2024 | COD 2025 261888 | LF 89 JJ GP | LH 44 FZ GP | ND60701 | 28-08-2025 | OFFLOADED 15-09-2025 | 23-08-2025 | 26-08-2025 | 27-08-2025 | 28-08-2025 | BV COMPLETE | 19-10-2024 | 29-08-2025 | 30-08-2025 | 02-09-2025 | 02-09-2025 | 03-09-2025 | 03-09-2025 | 04-09-2025 | 05-09-2025 | 05-09-2025 | 06-09-2025 | 07-09-2025 | 07-09-2025 | 09-09-2025 | 09-09-2025 | 09-09-2025 | 10-09-2025 | 10-09-2025 | 10-09-2025 | 10-09-2025 | 11-09-2025 | 12-09-2025 | 13-09-2025 | 14-09-2025 | 15-09-2025 | 15-09-2025 | [137 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED | BV INSPECTION BOOKED FOR TODAY - LOADING DATE TO BE CONFIRMED | BV INSPECITON COMPLETED - LOADING TOMORROW 28-08-2025 | LOADING TODAY | CAMPERDOWN AWAITING PERMIT - TO DISPTACH ONCE PERMIT IS RECEIVED | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | DISPATCHING JOHANNESBURG ONCE PERMIT IS RECEIVED | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER ZIM SIDE CLEARING | MVUMA ENROUTE HARARE | CHIRUNDU ZAMBAIN SIDE CLEARING | CHIRUNDU ZAMBAIN SIDE CLEARING | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | OFFLOADED 15-09-2025
BA2459 | CAT140K MOTOR GRADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | SZL21042 | CAT0140KJSZL21042 | TX713308 | 2303DSI2007 | VESSEL: FREMENTEL HIGHWAY Voy. 74 - ETA DURBAN: 28-04-2023 | COD 2025 277184 | LP 37 ZM GP | LL 54 VX GP | ND60770 | 17-09-2025 | OFFLOADED 04-10-2025 | 15-09-2025 | 16-09-2025 | 17-09-2025 | 20-09-2025 | CRF ISSUE DATE 20-09-2025 | 28-04-2023 | 19-09-2025 | 20-09-2025 | 21-09-2025 | 21-09-2025 | 22-09-2025 | 22-09-2025 | 23-09-2025 | 24-09-2025 | 25-09-2025 | 25-09-2025 | 27-09-2025 | 27-09-2025 | 28-09-2025 | 28-09-2025 | 28-09-2025 | 28-09-2025 | 28-09-2025 | 28-09-2025 | 29-08-2025 | 29-09-2025 | 30-09-2025 | 30-09-2025 | 03-10-2025 | 03-10-2025 | 04-10-2025 | [167 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED | BV INSPECTION BOOKED FOR TODAY 16-09-2025 | BV INSPECTION COMPLETED - AWAITING BV RELEASE | LOADING FROM BONDED FACILITY TOMORROW 19-09-2025 | LOADING TODAY | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | KAROI ENROUTE CHIRUDNU BORDER | CHIRUDNU ZIM SIDE CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE - DAY 1 | LUMATA ENROUTE LUBUMBASHI | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE - DAY 3 | OFFLOADED 04-10-2025
BA2854 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TJT30048 | CAT00333JTJT30048 | E7A64735 | 2501DSI2657 | VESSEL: SIERRA NEVADA HIGHWAY Voy. 173 - ETA DURBAN: 01-02-2025 | COD 2025 275396 | LF54LFGP | LF56YXGP | ND60754 | 12-09-2025 | OFFLOADED 04-10-2025 | 09-09-2025 | 12-09-2025 | 15-09-2025 | 13-09-2025 | CRF ISSUE DATE 13-09-2025 | 01-02-2025 | 15-09-2025 | BETHAL 16-09-2025 | BETHAL 16-09-2025 | 18-09-2025 | 18-09-2025 | 18-09-2025 | 19-09-2025 | 20-09-2025 | 21-09-2025 | 21-09-2025 | 22-09-2025 | 22-09-2025 | 23-09-2025 | 24-09-2025 | 24-09-2025 | 24-09-2025 | 24-09-2025 | 25-09-2025 | 25-09-2025 | 25-09-2025 | 26-09-2025 | 28-09-2025 | 30-09-2025 | 03-10-2025 | 04-10-2025 | [168 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED - AWAITING CONFIRMATION DATE FROM BV RSA | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWAITING BV RELEASE | LOADED FROM BONDED FACILITY - AWAITING BV RELEASE | BETHAL ENROUTE BEIT BRIDGE BORDER | POLOKWANE ENROUTE BEIT BRIDGE BORDER | DISPATCHING POLOKWANE TO PROCEED TO BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE | KANYAKA CHECK POINT AWAITING RELEASE | LUBUMBASHI | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 04-10-2025
BA2872 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TJT30095 | CAT00333KTJT30095 | E7A65373 | 2504DSI2685 | VESSEL: MORNING CAROL Voy. 153 - ETA DURBAN: 07-05-2025 | COD 2025 275544 | CV76JXZN | CD46KDZN | ND60755 | 20-09-2025 | OFFLOADED 18-10-2025 | 16-07-2025 | 18-07-2025 | 22-09-2025 | 23-09-2025 | CRF ISSUE DATE | 07-05-2025 | 30-09-2025 | 30-09-2025 | 01-10-2025 | 01-10-2025 | 02-10-2025 | 02-10-2025 | 04-10-2025 | 05-10-2025 | 06-10-2025 | 06-10-2025 | 06-10-2025 | 06-10-2025 | 08-10-2025 | 08-10-2025 | 08-10-2025 | 09-10-2025 | 10-10-2025 | 10-10-2025 | 10-10-2025 | 11-10-2025 | 12-10-2025 | 15-10-2025 | 15-10-2025 | 17-10-2025 | 18-10-2025 | [168 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - TO BOOK BV INSPECTION | BV INSPECTION BOOKED FOR TOMORROW 19-09-2025 | BV INSPECTION BOOKED FOR TODAY 19-09-2025 | BV INSPECTION COMPLETED - AWAITING BV RELEASE - LOADING PLANNED FOR THIS WEEK | BV INSPECTION COMPLETED - BV RELEASE RECEIVED - LOADING PLANNED FOR THURSDAY/FRIDAY | LOADING TODAY | LOADED - AWAITNG PERMITS | DISPATCHING DURBAN TODAY | HEAVY ROA ACROSS RSA - AWAITING WEATHER TO CLEAR TO DISPATCH FROM DURBAN | JOHANNESBURG ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | HARARE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAMBIAN SIDE CLEARING | DISPATCHING CHIRUNDU | KABWE ENTROUTE KASUMBALESA BORDER | CHINGOLA ENTROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY IN THE QUEUE TO PAY FOR PARKING TO DISPATCH | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE - DAY 2 | OFFLOADED 18-10-2025
BA3003 | CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 7W805383 | CAT00777T7W805383 | ZRK02250 | 2508DSI2713 | VESSEL: GLOVIS SOLOMON Voy. 75A - TRANSHIPMENT VESSEL: GRAND PIONEER Voy. 062 - ETA DURBAN: 16-09-2025 | COD 2025 271511 | MH73ZBGP | CV71JLGP / DD10RDGP | ND60730 | 22-09-2025 | OFFLOADED 21-10-2025 | 04-09-2025 | 22-09-2025 | 22-09-2025 | 23-09-2025 | CRF ISSUE 23-09-2025 | 16-09-2025 | 18-09-2025 | HEIDELBERG 02-10-2025 | HEIDELBERG 03-10-2025 | 08-10-2025 | 08-10-2025 | 08-10-2025 | 09-10-2025 | 10-10-2025 | 11-10-2025 | 12-10-2025 | 13-10-2025 | 13-10-2025 | 13-10-2025 | 14-10-2025 | 14-10-2025 | 14-10-2025 | 14-10-2025 | 15-10-2025 | 15-10-2025 | 15-10-2025 | 15-10-2025 | 17-10-2025 | 18-10-2025 | 21-10-2025 | 21-10-2025 | [164 empty] | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 21-10-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 21-10-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 21-10-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 21-10-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 15-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 15-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 15-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 15-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 16-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-09-2025 | VESSEL IN AND WORKING | LOADED FROM PORT AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT AWAITING POLICE ESCORT | CAMPERDOWN - BV INSPECTION TO BE BOOKED FOR MONDAY 22-09-2025 | PIETERMARITZBURG - BV INSPECTION BOOKED FOR TODAY 22-09-2025 | PIETERMARITZBURG - BV INSPECTION COMPLETED, AWAITING POLICE ESCORTS | DALTON AWAITING POLICE ESCORT | WEENEN AWAITING POLICE ESCORT | COLENSO AWAITING POLICE ESCORT | HEAVY ROA ACROSS RSA - LADYSMITH AWAITING POLICE ESCORT | WARDEN AWAITING POLICE ESCORT | VILLERS AWAITING POLICE ESCORT | HEIDELBERG AWAITING POLICE ESCORT | MARBLE HALL AWAITING POLICE ESCORT | POLOKWANE AWAITING POLICE ESCORTS | MUSINA AWAITING POLICE TO ESCORT TO BEIT BRIDGE BORDER | DISPATCHING BEIT BRIDGE BORDER | MASVINGO ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | LUSAKA ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE - DAY 1 | DISPATCHING WHISKEY FOR LUBUMBASHI | LUBUMBASHI WATING FOR INSPECTION | ON SITE WAITING TO OFFLOAD | OFFLOADED 21-10-2025
BA3006 | CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 7W805376 | CAT00777L7W805376 | ZRK02241 | 2508DSI2710 | VESSEL: GRAND VICTORY Voy. 33 - ETA DURBAN: 03-09-2025 | COD 2025 271511 | MN79GKGP | KR31WRGP / KR31WBGP | 2508DSI2710C-BA3006 | 26-09-2025 | OFFLOADED 28-10-2025 | 04-09-2025 | 25-09-2025 | 26-09-2025 | 28-09-2025 | CRF ISSUE DATE 28-09-2025 | 03-09-2025 | 10-09-2025 | MIDDELBURG 26-09-2025 | MIDDELBURG 30-09-2025 | 06-10-2025 | 08-10-2025 | 08-10-2025 | 11-10-2025 | 13-10-2025 | 13-10-2025 | 14-10-2025 | 14-10-2025 | 14-10-2025 | 16-10-2025 | 17-10-2025 | 18-10-2025 | 19-10-2025 | 20-10-2025 | 20-10-2025 | 20-10-2025 | 22-10-2025 | 22-10-2025 | 26-10-2025 | 27-10-2025 | 28-10-2025 | 28-10-2025 | [158 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 01-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 02-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 02-09-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL DELAYED - DUE TO BIRTH TODAY | COLLECTING FROM PORT TODAY | LOADED FROM PORT, AWAITING PERMIT AND ESCORTS - EMBARGO FROM 12PM TODAY | LOADED FROM PORT, AWAITING PERMIT AND ESCORTS (PERMITS TO BE RECEIVED TODAY AND EXCORTS IS BOOKED FOR TOMORROW) | AWAITING ESCORTS TO ARRIVE | ESCORTS ARRIVED, DISPATCHING DURBAN | PIETERMARITZBURG AWAITING POLICE ESCORTS | WARTBURG AWAITING POLICE ESCORTS | DALTON AWAITING POLICE ESCORTS | UMPHUMULO AWAITING POLICE ESCORTS | KWADUKZA AWAITING POLICE ESCORTS | KWADUKZA AWAITING POLICE ESCORTS | MATUBATUBA AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR TUESDAY / WEDNESDAY | MATUBATUBA AWAITING POLICE ESCORTS (RAIN DELAYED TRAVELLING) - BV INSPECTION BOOKED FOR THURSDAY / FRIDAY | PONGOLA AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR THURSDAY | PIET RETIEF AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR TODAY | ERMELO AWAITING POLICE ESCORTS - BV INSPECTION COMPLETED | MIDDELBURG AWAITING POLICE ESCORTS - BV INSPECTION COMPLETED | HEAVY RAIN ACROSS RSA - MIDDELBURG AWAITING POLICE ESCORTS - DUE TO HEAVY RAIN UNIT COULDN'T MOVE | GROBLERSDAL AWAITING POLICE ESCORTS | ROEDTAN AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS - TO BE ESCORTED TODAY | MUSINA AWAITING POLICE TO ESCORT TO BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | CROSSING TO BEIT BRIDGE ZIM SIDE | CHINHOYI ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE AWAITING RELEASE | DISPATCHED KAFUE ENROUTE KASUMBALESA BORDER | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE CROSSING TO DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | KANYAKA AWAITING INSPECTION | ON SITE WAITING TO OFFLOAD | OFFLOADED 28-10-2025 | OFFLOADED 28-10-2025
BA3007 | CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 7W805375 | CAT00777A7W805375 | ZRK02240 | 2508DSI2710 | VESSEL: GRAND VICTORY Voy. 33 - ETA DURBAN: 03-09-2025 | COD 2025 271511 | MM89TSGP | XDH022GP / LR30YVGP | 2508DSI2710D-BA3007 | 26-09-2025 | OFFLOADED 28-10-2025 | 04-09-2025 | 25-09-2025 | 26-09-2025 | 30-09-2025 | CRF ISSUE 30-09-2025 | 03-09-2025 | 10-09-2025 | MIDDELBURG 26-09-2025 | MIDDELBURG 30-09-2025 | 06-10-2025 | 08-10-2025 | 08-10-2025 | 11-10-2025 | 13-10-2025 | 13-10-2025 | 14-10-2025 | 14-10-2025 | 14-10-2025 | 16-10-2025 | 17-10-2025 | 18-10-2025 | 19-10-2025 | 20-10-2025 | 20-10-2025 | 20-10-2025 | 22-10-2025 | 22-10-2025 | 26-10-2025 | 27-10-2025 | 28-10-2025 | 28-10-2025 | [158 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 01-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 02-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 02-09-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL DELAYED - DUE TO BIRTH TODAY | COLLECTING FROM PORT TODAY | LOADED FROM PORT, AWAITING PERMIT AND ESCORTS - EMBARGO FROM 12PM TODAY | LOADED FROM PORT, AWAITING PERMIT AND ESCORTS (PERMITS TO BE RECEIVED TODAY AND EXCORTS IS BOOKED FOR TOMORROW) | AWAITING ESCORTS TO ARRIVE | ESCORTS ARRIVED, DISPATCHING DURBAN | PIETERMARITZBURG AWAITING POLICE ESCORTS | WARTBURG AWAITING POLICE ESCORTS | DALTON AWAITING POLICE ESCORTS | UMPHUMULO AWAITING POLICE ESCORTS | KWADUKZA AWAITING POLICE ESCORTS | KWADUKZA AWAITING POLICE ESCORTS | MATUBATUBA AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR TUESDAY / WEDNESDAY | MATUBATUBA AWAITING POLICE ESCORTS (RAIN DELAYED TRAVELLING) - BV INSPECTION BOOKED FOR THURSDAY / FRIDAY | PONGOLA AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR THURSDAY | PIET RETIEF AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR TODAY | ERMELO AWAITING POLICE ESCORTS - BV INSPECTION COMPLETED | MIDDELBURG AWAITING POLICE ESCORTS - BV INSPECTION COMPLETED | HEAVY RAIN ACROSS RSA - MIDDELBURG AWAITING POLICE ESCORTS - DUE TO HEAVY RAIN UNIT COULDN'T MOVE | GROBLERSDAL AWAITING POLICE ESCORTS | ROEDTAN AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS - TO BE ESCORTED TODAY | MUSINA AWAITING POLICE TO ESCORT TO BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | CROSSING TO BEIT BRIDGE ZIM SIDE | CHINHOYI ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE AWAITING RELEASE | DISPATCHED KAFUE ENROUTE KASUMBALESA BORDER | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE CROSSING TO DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 | KANYAKA AWAITING INSPECTION | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 28-10-2025
BA3004 | CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 7W805382 | CAT00777C7W805382 | ZRK02248 | 2508DSI2710 | VESSEL: GRAND VICTORY Voy. 33 - ETA DURBAN: 03-09-2025 | COD 2025 271511 | MM89TGGP | XTD933GP / LV90MZGP | 2508DSI2710A-BA3004 | 26-09-2025 | OFFLOADED 03-11-2025 | 04-09-2025 | 25-09-2025 | 26-09-2025 | 28-09-2025 | CRF ISSUE DATE 28-09-2025 | 03-09-2025 | 10-09-2025 | MIDDELBURG 26-09-2025 | MIDDELBURG 30-09-2025 | 06-10-2025 | 08-10-2025 | 08-10-2025 | 11-10-2025 | 13-10-2025 | 13-10-2025 | 14-10-2025 | 14-10-2025 | 14-10-2025 | 17-10-2025 | 17-10-2025 | 18-10-2025 | 20-10-2025 | 21-10-2025 | 21-10-2025 | 21-10-2025 | 26-10-2025 | 26-10-2025 | 30-10-2025 | 30-10-2025 | 01-11-2025 | 03-11-2025 | [158 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 01-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 02-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 02-09-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL DELAYED - DUE TO BIRTH TODAY | COLLECTING FROM PORT TODAY | LOADED FROM PORT, AWAITING PERMIT AND ESCORTS - EMBARGO FROM 12PM TODAY | LOADED FROM PORT, AWAITING PERMIT AND ESCORTS (PERMITS TO BE RECEIVED TODAY AND EXCORTS IS BOOKED FOR TOMORROW) | AWAITING ESCORTS TO ARRIVE | ESCORTS ARRIVED, DISPATCHING DURBAN | PIETERMARITZBURG AWAITING POLICE ESCORTS | WARTBURG AWAITING POLICE ESCORTS | DALTON AWAITING POLICE ESCORTS | UMPHUMULO AWAITING POLICE ESCORTS | KWADUKZA AWAITING POLICE ESCORTS | KWADUKZA AWAITING POLICE ESCORTS | MATUBATUBA AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR TUESDAY / WEDNESDAY | MATUBATUBA AWAITING POLICE ESCORTS (RAIN DELAYED TRAVELLING) - BV INSPECTION BOOKED FOR THURSDAY / FRIDAY | PONGOLA AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR THURSDAY | PIET RETIEF AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR TODAY | ERMELO AWAITING POLICE ESCORTS - BV INSPECTION COMPLETED | MIDDELBURG AWAITING POLICE ESCORTS - BV INSPECTION COMPLETED | HEAVY RAIN ACROSS RSA - MIDDELBURG AWAITING POLICE ESCORTS - DUE TO HEAVY RAIN UNIT COULDN'T MOVE | GROBLERSDAL AWAITING POLICE ESCORTS | ROEDTAN AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS - TO BE ESCORTED TODAY | MUSINA AWAITING POLICE TO ESCORT TO BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | CROSSING TO BEIT BRIDGE ZIM SIDE | CHINHOYI ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE AWAITING RELEASE | DISPATCHING CHIRUNDU | KABWE ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASBUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE IN THE QUE TO CROSS TO DRC SIDE | KASUMBALESA BORDER DRC SIDE WAITING TO MOVE TO WHISKEY | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA AWAITING CUSTOMS INSPECTION AND RELEASE | ON SITE WAITING SEAL REMOVAL AND OFFLOADING | OFFLOADED 03-11-2025
BA3005 | CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 7W805377 | CAT00777H7W805377 | ZRK02244 | 2508DSI2710 | VESSEL: GRAND VICTORY Voy. 33 - ETA DURBAN: 03-09-2025 | COD 2025 271511 | MN79GFGP | LV86BMGP / LV85ZXGP | 2508DSI2710B-BA3005 | 26-09-2025 | OFFLOADED 03-11-2025 | 04-09-2025 | 25-09-2025 | 27-09-2025 | 29-09-2025 | CRF ISSUE 29-09-2025 | 03-09-2025 | 10-09-2025 | MIDDELBURG 26-09-2025 | MIDDELBURG 30-09-2025 | 06-10-2025 | 08-10-2025 | 08-10-2025 | 10-10-2025 | 12-10-2025 | 13-10-2025 | 14-10-2025 | 14-10-2025 | 14-10-2025 | 17-10-2025 | 17-10-2025 | 18-10-2025 | 20-10-2025 | 21-10-2025 | 21-10-2025 | 21-10-2025 | 26-10-2025 | 26-10-2025 | 30-10-2025 | 30-10-2025 | 01-11-2025 | 03-11-2025 | [158 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 03-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 01-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 02-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 02-09-2025 | VESSEL DUE TO ARRIVE TODAY | VESSEL DELAYED - DUE TO BIRTH TODAY | COLLECTING FROM PORT TODAY | LOADED FROM PORT, AWAITING PERMIT AND ESCORTS - EMBARGO FROM 12PM TODAY | LOADED FROM PORT, AWAITING PERMIT AND ESCORTS (PERMITS TO BE RECEIVED TODAY AND EXCORTS IS BOOKED FOR TOMORROW) | AWAITING ESCORTS TO ARRIVE | ESCORTS ARRIVED, DISPATCHING DURBAN | PIETERMARITZBURG AWAITING POLICE ESCORTS | WARTBURG AWAITING POLICE ESCORTS | DALTON AWAITING POLICE ESCORTS | UMPHUMULO AWAITING POLICE ESCORTS | KWADUKZA AWAITING POLICE ESCORTS | KWADUKZA AWAITING POLICE ESCORTS | MATUBATUBA AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR TUESDAY / WEDNESDAY | MATUBATUBA AWAITING POLICE ESCORTS (RAIN DELAYED TRAVELLING) - BV INSPECTION BOOKED FOR THURSDAY / FRIDAY | PONGOLA AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR THURSDAY | PIET RETIEF AWAITING POLICE ESCORTS - BV INSPECTION BOOKED FOR TODAY | ERMELO AWAITING POLICE ESCORTS - BV INSPECTION COMPLETED | MIDDELBURG AWAITING POLICE ESCORTS - BV INSPECTION COMPLETED | HEAVY RAIN ACROSS RSA - MIDDELBURG AWAITING POLICE ESCORTS - DUE TO HEAVY RAIN UNIT COULDN'T MOVE | GROBLERSDAL AWAITING POLICE ESCORTS | ROEDTAN AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS - TO BE ESCORTED TODAY | MUSINA AWAITING POLICE TO ESCORT TO BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | CROSSING TO BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | KAROI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE AWAITING RELEASE | DISPATCHING CHIRUNDU | KABWE ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASBUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | KASUMBALESA BORDER ZAMBIAN SIDE IN THE QUE TO CROSS TO DRC SIDE | KASUMBALESA BORDER DRC SIDE WAITING TO MOVE TO WHISKEY | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | KANYAKA AWAITING CUSTOMS INSPECTION AND RELEASE | ON SITE WAITING SEAL REMOVAL AND OFFLOADING | OFFLOADED 03-11-2025
BA2901 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F606514 | CAT00745J3F606514 | TXW08477 | 2507DSI2704 | VESSEL: HOEGH BERLIN Voy. 134 - ETA DURBAN: 22-08-2025 | COD 2025 291726 | CL70WLZN | BH61YRZN | ND60783 | 06-10-2025 | OFFLOADED 03-11-2025 | 02-10-2025 | 03-10-2025 | 06-10-2025 | 07-10-2025 | CRF ISSUE 07-10-2025 | 22-08-2025 | 14-10-2025 | 14-10-2025 | 15-10-2025 | 16-10-2025 | 16-10-2025 | 16-10-2025 | 18-10-2025 | 18-10-2025 | 19-10-2025 | 20-10-2025 | 20-10-2025 | 20-10-2025 | 22-10-2025 | 24-10-2025 | 24-10-2025 | 24-10-2025 | 24-10-2025 | 25-10-2025 | 25-10-2025 | 26-10-2025 | 27-10-2025 | 29-10-2025 | 29-10-2025 | 03-11-2025 | 03-11-2025 | [182 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED - INSPECTION DATE TBA ONCE BV RSA CONFIRMS | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - AWATING BV RELEASE | BV RELEASE RECEIVED - LOADING TOMORROW | LOADING THIS AFTERNOON | LOADED, AWAITING PERMITS BEFORE DISPATCHING | LOADED, AWAITING PERMITS - DISPATCHING MONDAY ONCE PERMITS IS RECEIVED | LOADED, AWAITING PERMITS, SHOULD BE RECEIVED TODAY. TO DISPATCH TOMORROW MORNING | DISPATCHING DURBAN | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BANDELIERSKOP ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE - TO DISPATCH TODAY | KAFUE ENROUTE KASUMBALESA BORDER | SIYAVONGA ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 3 | CONNEX LUBUMBASHI AWAITING FINAL RELESAE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 03-11-2025
BA3002 | CAT777-05B OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 7W805384 | CAT00777P7W805384 | ZRK02249 | 2508DSI2713 | VESSEL: GLOVIS SOLOMON Voy. 75A - TRANSHIPMENT VESSEL: GRAND PIONEER Voy. 062 - ETA DURBAN: 16-09-2025 | COD 2025 271511 | ZKB404GP | KB37RRGP / KB35KCGP | ND60731 | 22-09-2025 | OFFLOADED 05-11-2025 | 04-09-2025 | 22-09-2025 | 22-09-2025 | 23-09-2025 | CRF ISSUE 23-09-2025 | 16-09-2025 | 07-10-2025 | HEIDELBERG 15-10-2025 | HEIDELBERG 15-10-2025 | 17-10-2025 | 20-10-2025 | 20-10-2025 | 21-10-2025 | 22-10-2025 | 22-10-2025 | 23-10-2025 | 23-10-2025 | 23-10-2025 | 27-10-2025 | 28-10-2025 | 28-10-2025 | 28-10-2025 | 30-10-2025 | 30-10-2025 | 30-10-2025 | 02-11-2025 | 03-11-2025 | 04-11-2025 | 05-11-2025 | 05-11-2025 | 05-11-2025 | [164 empty] | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 21-10-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 21-10-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 21-10-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 21-10-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 15-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 15-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 15-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 15-09-2025 | AWAITING INVOICE AND VESSEL ARRIVAL - ETA DURBAN PORT 16-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-09-2025 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 16-09-2025 | VESSEL IN AND WORKING | LOADED FROM PORT AWAITING PERMIT AND POLICE ESCORT | LOADED FROM PORT AWAITING POLICE ESCORT | CAMPERDOWN - BV INSPECTION TO BE BOOKED FOR MONDAY 22-09-2025 | CAMPERDOWN - BV INSPECTION BOOKED FOR TODAY 22-09-2025 | BV INSPECTION COMPLETED - AWAITING POLICE ESCORTS | AWAITING POLICE ESCORT TO ARRIVE | CAMPERDOWN AWAITING POLICE ESCORT TO ARRIVE | CAMPERDOWN AWAITING POLICE ESCORT TO ARRIVE - ESCORT TO ARRIVE TODAY | HEAVY ROA ACROSS RSA - DUE TO RAINING WEATHER THE ESCORTS DID NOT COLLECT THE UNIT - AWATING WEATHER TO CLEAR | AWAITING PERMITS & POLICE ESCORT TO COLLECT UNIT - DELAYS WITH ESCORTS AND PERMITS AS SYSTEM IS OFFLINE | AWAITING PERMITS & POLICE ESCORT TO COLLECT UNIT - DELAYS WITH ESCORTS AND PERMITS AS SYSTEM IS OFFLINE - PERMITS SHOULD BE RECEIVED LATER TODAY | AWAITING PERMITS & POLICE ESCORT TO COLLECT UNIT - DELAYS WITH ESCORTS AND PERMITS AS SYSTEM IS OFFLINE | CATO RIDGE AWAITING POLICE ESCORT | DISPATCHED CATO RIDGE ENROUTE PIETERMARITZBURG | PIETERMARITZBURG WAITING POLICE ESCORTS | GREYTOWN WAITING POLICE ESCORTS | COLENSO WAITING POLICE ESCORTS | VAN REENEN WAITING POLICE ESCORTS | VAN REENEN WAITING POLICE ESCORTS - ONLY CONFIRMED COLLECTION FOR TODAY | HEIDELBERG AWAITING POLICE ESCORTS | ROEDTAN AWAITING POLICE ESCORTS | POLOKWANE AWAITING POLICE ESCORTS | BEIT BRIDGE RSA SIDE CLEARING | DISPATCHING BEIT BRIDGE ZIM | HARARE ENROUTE CHIRUNDU | MAKUTI ENROUTE CHIRUNDU BORDER | CHIRUNDU ZAMBIAN SIDE | KAFUE ENROUTE KASUMBALESA | LUSAKA ENROUTE KASUMBALESA | KAPIRI MPOSHE ENROUTE KASUMBALESA | KASUMBALESA BORDER DRC SIDE | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 - AWAITING SEGEUCE | ON SITE WAITING FOR CUSTOMS INSPECTION | OFFLOADED 05-11-2025
BA2597 | CAT D6GC-01A TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | XPC00892 | CAT000D6CXPC00892 | R6J04851 | 2310DSI2236 | VESSEL: LEO LEADER Voy. 105 - ETA DURBAN 18-11-2023 | COD 2025 296228 | HL20JSGP | CC59CYGP | 2310DSI2236 | 15-10-2025 | OFFLOADED 10-11-2025 | 08-10-2025 | 10-10-2025 | 11-10-2025 | 18-10-2025 | CRF ISSUE 18-10-2025 | 18-11-2023 | 15-10-2025 | 16-10-2025 | 21-10-2025 | 21-10-2025 | 21-10-2025 | 21-10-2025 | 24-10-2025 | 27-10-2025 | 27-10-2025 | 27-10-2025 | 27-10-2025 | 27-10-2025 | 30-10-2025 | 30-10-2025 | 30-10-2025 | 30-10-2025 | 31-10-2025 | 31-10-2025 | 31-10-2025 | 02-11-2025 | 03-11-2025 | 05-11-2025 | 05-11-2025 | 10-11-2025 | 10-11-2025 | [187 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV BOOKED FOR FRIDAY 10-10-2025 | BV BOOKED FOR TODAY 10-10-2025 | BV INSPECTION COMPLETED - LOADING THIS WEEK | LOADING WEDNESDAY 15-10-2025 | LOADING TODAY 15-10-2025 | LOADED - HARRISMITH ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG - TO DISPATCH LATER TODAY | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE CLEARING & AWAIITNG ZIM NOTIFICATION | BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE CLEARING & WAITING RELEASE | NDOLA ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | DISPATCHING WHISKEY | CONNEX LUBUMBASHI - AWAITING FINAL RELEASE - DAY 1 | CONNEX LUBUMBASHI - AWAITING FINAL RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-11-2025
BA2968 | CAT14-15A MOTOR GRADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | F5800334 | CAT00014LF5800334 | TXX05484 | 2508DSI2709 | VESSEL: TING JIANG KOU Voy. 4 - ETA DURBAN: 11-09-2025 | COD 2025 296232 | LB37HSGP | BB38WPGP | 2508DSI2709 | 15-10-2025 | OFFLOADED 10-11-2025 | 08-10-2025 | 10-10-2025 | 11-10-2025 | 20-10-2025 | CRF ISSUDE 20-10-2025 | 11-09-2025 | 16-10-2025 | 18-10-2025 | 21-10-2025 | 21-10-2025 | 21-10-2025 | 21-10-2025 | 23-10-2025 | 27-10-2025 | 27-10-2025 | 27-10-2025 | 29-10-2025 | 29-10-2025 | 30-10-2025 | 30-10-2025 | 30-10-2025 | 31-10-2025 | 31-10-2025 | 31-10-2025 | 31-10-2025 | 02-11-2025 | 03-11-2025 | 05-11-2025 | 05-11-2025 | 10-11-2025 | 10-11-2025 | [187 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV BOOKED FOR FRIDAY 10-10-2025 | BV BOOKED FOR TODAY 10-10-2025 | BV INSPECTION COMPLETED - LOADING THIS WEEK | LOADING WEDNESDAY 15-10-2025 | LOADING TODAY 15-10-2025 | LOADED - AWAITING KZN PERMITS | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG - TO DISPATCH LATER TODAY | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | GWERU ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE CLEARING & WAITING RELEASE | KABWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | DISPATCHING WHISKEY | CONNEX LUBUMBASHI - AWAITING FINAL RELEASE - DAY 1 | CONNEX LUBUMBASHI - AWAITING FINAL RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-11-2025
BA2850 | CAT336-08C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | MZR30095 | CAT00336JMZR30095 | D7E01650 | 2412DSI2651 | VESSEL:l TARIFA Voy. 146 - ETA DURBAN 04-02-2025 | COD 2025 296230 | LB54YKGP | HZ12FCGP | 2412DSI2651 | 15-10-2025 | OFFLOADED 13-11-2025 | 08-10-2025 | 10-10-2025 | 11-10-2025 | 21-10-2025 | CRF ISSUE 21-10-2025 | 04-02-2025 | 21-10-2025 | 22-10-2025 | 24-10-2025 | 24-10-2025 | 25-10-2025 | 25-10-2025 | 28-10-2025 | 28-10-2025 | 29-10-2025 | 30-10-2025 | 30-10-2025 | 30-10-2025 | 02-11-2025 | 03-11-2025 | 03-11-2025 | 03-11-2025 | 04-11-2025 | 04-11-2025 | 04-11-2025 | 05-11-2025 | 05-11-2025 | 08-11-2025 | 08-11-2025 | 13-11-2025 | 13-11-2025 | [187 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV BOOKED FOR FRIDAY 10-10-2025 | BV BOOKED FOR TODAY 10-10-2025 | BV INSPECTION COMPLETED - LOADING THIS WEEK | LOADING THURSDAY 16-10-2025 | LOADING THURSDAY 16-10-2025 | VEHICLE DELAYED - LOADING TOMORROW | PERMITS DELAYED FOR KZN - LOADING MONDAY MORING | LOADING TODAY ONCE RAIN STOP | RAIN STOPPED - UNIT CURRENTLY LOADING | HARRISMITH ENROUTE JOHANNESBURG | JOHANNESBURG AWAITING LIMPOPO PERMITS | PERMITS RECEIVED - DISPATCHING AM TODAY FOR BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | DISPATCHING BEIT BRIDGE TODAY | HARARE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAMBIAN SIDE CLEARING | KAFUE ENROUTE LUSAKA | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI - AWAITING FINAL RELEASE - DAY 1 | CONNEX LUBUMBASHI - AWAITING FINAL RELEASE - DAY 2 | CONNEX LUBUMBASHI - AWAITING FINAL RELEASE - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 13-11-2025
BA2902 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F606515 | CAT00745C3F606515 | TXW08485 | 2508DSI2712 | VESSEL: SILVER SOUL Voy. 25SS08 - ETA DURBAN: 24-09-2025 | COD 2025 332825 | CL70WLZN | BH61YRZN | ND60902 | 02-12-2025 | OFFLOADED 22-12-2025 | 01-12-2025 | 02-12-2025 | 02-12-2025 | 10-12-2025 | CRF ISSUE DATE 10-12-2025 | 24-09-2025 | 04-12-2025 | 05-12-2025 | 05-12-2025 | 05-12-2025 | 06-12-2025 | 06-12-2025 | 08-12-2025 | 09-12-2025 | 09-12-2025 | 09-12-2025 | 10-12-2025 | 10-12-2025 | 12-12-2025 | 12-12-2025 | 13-12-2025 | 13-12-2025 | 14-12-2025 | 15-12-2025 | 15-12-2025 | 16-12-2025 | 16-12-2025 | 17-12-2025 | 18-12-2025 | 19-12-2025 | 22-12-2025 | [218 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY 02-12-2025 - LOADING WEDNESDAY 03-12-2025 | LOADING TODAY | MOOIREVER ENROUTE JOHANNESBURG | HEIDELBER ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE AWAITING RELEASE | HARARE ENROUTE CHIRUNDU BORDER | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU BORDER | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY AWAITING RELEASE - DAY 2 | KANYAKA ENROUTE LUBUMBASHSI | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - PLEASE ASSIST | OFFLOADED 22-12-2025 | OFFLOADED 22-12-2025
BA2869 | CAT966GC-01B WHEEL LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | SGW02759 | CAT00966PSGW02759 | NTB15349 | 2503DSI2680 | VESSEL: GRAND PAVO Voy. 126 - ETA DURBAN: 09-04-2025 | COD 2025 332121 | KW41BTGP | BZ 72 BJ GP | 2503DSI2680 | 01-12-2025 | OFFLOADED AT CONNEX LUBUMBASHI | 27-11-2025 | 28-11-2025 | 28-11-2025 | 30-11-2025 | CRF ISSUE DATE 30-11-2025 | 09-04-2025 | 03-12-2025 | 04-12-2025 | 08-12-2025 | 08-12-2025 | 08-12-2025 | 08-12-2025 | 10-12-2025 | 11-12-2025 | 12-12-2025 | 13-12-2025 | 14-12-2025 | 14-12-2025 | 16-12-2025 | 16-12-2025 | 16-12-2025 | 16-12-2025 | 17-12-2025 | 17-12-2025 | 17-12-2025 | 19-12-2025 | 19-12-2025 | 23-12-2025 | 24-12-2055 |  | 29-12-2025 | [218 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR MONDAY 01-12-2025 | BV INSPECTION COMPLETED - LOADING TOMORROW 02-12-2025 | LOADING TODAY | LOADING NOW, DISPATCHING ONCE LOADED | HARRISMITH ENROUTE JOHANNESBURG | JOHANNSBURG | BELA BELA ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE IN THE QUE TO CROSS TO ZIM SIDE | MASIVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU BORDER | CHIRUNDU BORDER ZAMBIAN SIDE CLEARING | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAMBIAN SIDE CLEARING | ENROUTE TO WHISKEY | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY IN THE QUE TO DISPATCH | KANYAKA ENROUTE LUBUMBASHI | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE AND RELEASE - PLEASE ASSIST | OFFLOADED AT CONNEX LUBUMBASHI | OFFLOADED AT CONNEX LUBUMBASHI

## OFFLOADED - 2024
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | LIKASI | OFFLOADED | COMMENTS 28.05.2021 | COMMENTS 31.05.2021 | COMMENTS 01.06.2021 | COMMENTS 02.06.2021 | COMMENTS 03.06.2021 | COMMENTS 04.06.2021 | COMMENTS 07.06.2021 | COMMENTS 08.06.2021 | COMMENTS 09.06.2021 | COMMENTS 10.06.2021 | COMMENTS 11.06.2021 | COMMENTS 14.06.2021 | COMMENTS 15.06.2021 | COMMENTS 16.06.2021 | COMMENTS 17.06.2021 | COMMENTS 18.06.2021 | COMMENTS 21.06.2021 | COMMENTS 22.06.2021 | COMMENTS 23.06.2021 | COMMENTS 24.06.2021 | COMMENTS 25.06.2021 | COMMENTS 28.06.2021 | COMMENTS 29.06.2021 | COMMENTS 30.06.2021 | COMMENTS 01.07.2021 | COMMENTS 02.07.2021
BA1578 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20339 | CAT00330TFEK20339 | E7A43768 | 2105DSI1123 | COD 2021 214801 | ND598162 | ND488806 | ND63525 | 07.06.2021 | OFFLOADED 30.06.2021 | 01.06.2021 | 07.06.2012 | 12.06.2021 | 14.06.2021 | 16.06.2021 | 17.06.2021 | 19.06.2021 | 21.06.2021 | 22.06.2021 | 23.06.2021 | 24.06.2021 | 25.06.2021 | 28.06.2021 | 29.06.2021 | 30.06.2021 | 30.06.2021 | * AWAITING THE GRAND VISION TO ARRIVE ON THE 29.05.2021 | * VESSEL CURRENTLY WORKING - AWAITING DISCHARGE AS OF 31.05.2021 | * UNITS IN BONDED FACILITY - AWAITING BV NUMBERS AS OF 01.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR 03.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY 03.06.2021 | * BV INSPECTION COMPLETED YESTERDAY - VEHILCES PLANNING TO DISPATCH MONDAY 07.04.2021 | * VEHICLE DISPATCHING TODAY - 07.06.2021 | * VEHICLE CURRENTLY AT MVOTI ENROUTE MOOIRIVIERE | * VEHICLE CURRENTLY AT MOOIRIVIER ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT HARRYSMITH ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE AT BEITBRIDGE SA SIDE - UNDER CLEARANCE | * VEHICLE DISPATCHED BEITBRIDGE ENROUTE HARARE | * VEHICLE AT MVUMA ENROUTE HARARE | * KAROI ENROUTE CHIRINDU | *CHIRINDU ZAM SIDE UNDER CLEARANCE | *DISPATCHING CHIRUNDU ENROUTE LUSAKA | * NDOLA ENROUTE TO KASUMBELESA ZAM | *KASUMBELESA ZAM SIDE UNDER CLEARANCE | *KASUMBELESA ZAM SIDE IN QUEUE TO CROSS TO DRC SIDE | TRUCK CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE
BA1576 | 1 X NEW CAT D6GC-01A | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XPC00303 | CAT00D6CXPC00303 | R6J03988 | 2105DSI1122 | COD 2021 214794 | JN38KXGP | XVD958GP | ND63527 | 07.06.2021 | OFFLOADED 01.07.2021 | 01.06.2021 | 07.06.2021 | 12.06.2021 | 14.06.2021 | 15.06.2021 | 17.06.2021 | 18.06.2021 | 19.06.2021 | 20.06.2021 | 21.06.2021 | 21.06.2021 | 24.06.2021 | 24.06.2021 | 01.07.2021 | 01.07.2021 | 01.07.2021 | * AWAITING THE GRAND VISION TO ARRIVE ON THE 29.05.2021 | * VESSEL CURRENTLY WORKING - AWAITING DISCHARGE AS OF 31.05.2021 | * UNITS IN BONDED FACILITY - AWAITING BV NUMBERS AS OF 01.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR 03.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY 03.06.2021 | * BV INSPECTION COMPLETED YESTERDAY - VEHILCES PLANNING TO DISPATCH MONDAY 07.06.2021 | * VEHILCE DISPATCHING THIS AFTERNOON AS OF 07.06.2021 | * VEHILCE CURRENTLY AT MARION HILL TOLL - ENROUTE HARRYSMITH | * VEHILCE CURRENTLY AT HARRYSMITH | * VEHILCE CURRENT AT WARDEN ENROUTE POLOKWANE | * VEHILCE CURRENT AT MIDRAND ENROUTE POLOKWANE | * VEHICLE AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE AT BUBI RIVER ENROUTE HARARE | * VEHICLE AT MASVINGO ENROUTE HARARE | * VEHICLE AT HARARE ENROUTE CHIRUNDU | *BANKET ENROUTE CHIRINDU ZIM | * KITWE ENROUTE TO KASUMBELSA | *KASUMBELESA ZAM SIDE UNDER CLEARANCE | *KASUMBELESA ZAM SIDE UNDER CLEARANCE | *KASUMBELESA DRC SIDE UNDER CLEARANCE | *WHISKY UNDER CLEARANCE | TRUCK CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK CURRENTLY AT WHISKEY AWAITING RELEASE DOCUMENTS | TRUCK CURRENTLY AT WHISKEY AWAITING RELEASE DOCUMENTS | OFFLOADED ON 01.07.2021
BA1584 | 1 X NEW CAT CS11G VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK800860 | MFX10891 | 2103DSI1083 | COD 2021 190913 | AAM7911 | ACE7458T | ND59091 | 11.06.2021 | * OFFLOADED 02.07.2021 | OFFLOADED 02.07.2021 | 14.06.2021 | 17.06.2021 | 18.06.2021 | 18.06.2021 | 19.06.2021 | 20.06.2021 | 22.06.2021 | 22.06.2021 | 22.06.2021 | 23.06.2021 | 25..6.2021 | 26.06.2021 | 28.06.2021 | 02.07.2021 | 02.07.2021 | 02.07.2021 | * AWAITING VESSEL ARRIVAL ON THE 02.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 29.05.2021 | * VESSEL CURRENTLY UNDER DISCHARGE AS OF 31.05.2021 | * LOADED OUT OF PORT- VEHICLE ENROUTE BONDED FACILITY AS OF 01.06.2021 | * UNIT WAITING IN BONDED FACILITY TO BE CO-LOADED WITH BA1696. VESSEL CURRENT ETA 04.06.2021 | * UNIT WAITING IN BONDED FACILITY TO BE CO-LOADED WITH BA1696. VESSEL CURRENT ETA 04.06.2021 | * UNIT WAITING IN BONDED FACILITY TO BE CO-LOADED WITH BA1696. VESSEL CURRENT ETA 04.06.2021 | * BV INSPECTION TO BE BOOKED FOR TOMORROW 08.06.2021 | * BV INSPETION TO BE COMPLETED TODAY | * BV INSPECTION COMPLETE - VEHILCE PLANNING TO DISPATCH TOMORROW 10.06.2021 | * VEHILCE LOADING TODAY - AWAITING DISPATCH | * VEHILCE TO DISPATCH THIS AFTERNOON | * VEHICLE TO DISPATCH DURBAN TODAY | * VEHICLE AT PIETERMARITZBURG ENROUTE POLOKWANE | * VEHICLE AT MOOI RIVIER ENROUTE POLOKWANE | * VEHICLE AT ESTCOURT ENROUTE POLOKWANE | * POLOKWANE ENROUTE BBR | * CHIRINDU ZIM SIDE UNDER CLEARANCE | * LUSAKA ENROUTE KASUMBELESA | * KASUMBELESA ZAM SIDE UNDER CLEARANCE | * KASUMBELESA ZAM SIDE UNDER CLEARANCE | * KASUMBELESA ZAM SIDE UNDER CLEARANCE | TRUCK CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | TRUCK CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | TRUCK CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | * OFFLOADED 02.07.2021
BA1696 | 1 X NEW CAT CS74B VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | B7M00209 | CATCS74BKB7M00209 | E7A27051 | 2105DSI1136 | COD 2021 202540 | AAM7911 | ACE7458T | ND59091 | 11.06.2021 | OFFLOADED 02.07.2021 | 04.06.2021 | 14.06.2021 | 17.06.2021 | 18.06.2021 | 18.06.2021 | 18.06.2021 | 20.06.2021 | 22.06.2021 | 22.06.2021 | 22.06.2021 | 23.06.2021 | 25.06.2021 | 26.06.2021 | 28.06.2021 | 02.07.2021 | 02.07.2021 | * AWAITING THE VESSEL HOEGH TRAVELLER V.28 TO ARRIVE IN DURBAN PORT ON THE 04.06.2021 | * BV INSPECTION TO BE BOOKED FOR TOMORROW 08.06.2021 | * BV INSPETION TO BE COMPLETED TODAY | * BV INSPECTION COMPLETE - VEHILCE PLANNING TO DISPATCH TOMORROW 10.06.2021 | * VEHILCE LOADING TODAY - AWAITING DISPATCH | * VEHILCE TO DISPATCH THIS AFTERNOON | * VEHICLE TO DISPATCH DURBAN TODAY | * VEHICLE AT PIETERMARITZBURG ENROUTE POLOKWANE | * VEHICLE AT MOOI RIVIER ENROUTE POLOKWANE | * VEHICLE AT ESTCOURT ENROUTE POLOKWANE | * POLOKWANE ENROUTE BBR | * CHIRINDU ZIM SIDE UNDER CLEARANCE | * LUSAKA ENROUTE KASUMBELESA | * KASUMBELESA ZAM SIDE UNDER CLEARANCE | * KASUMBELESA ZAM SIDE UNDER CLEARANCE | * KASUMBELESA ZAM SIDE UNDER CLEARANCE | TRUCK CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | TRUCK CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | TRUCK CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | ON SITE AWAITING OFFLOAD | * OFFLOADED 02.07.2021
BA1570 | 1 X NEW CAT 426F2 BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ403616 | CAT0426FTEJ403616 | CC203887 | 2105DSI1150 | COD 2021 222759 | JH88HCGP | DF96FDGP | JOB033393 | 14.06.2021 | OFFLOADED 12.07.2021 | 23.05.2021 | 14.06.2021 | 17.06.2021 | 19.06.2021 | 21.06.2021 | 23.06.2021 | 26.06.2021 | 27.06.2021 | 28.06.2021 | 29.06.2021 | 01.07.2021 | 02.07.201 | 04.07.2021 | 08.07.2021 | 12.07.2021 | 12.07.2021 | * UNITS TO BE LOADED OUT OF THE PORT TODAY | * UNITS IN BONDED FACILITY AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR MONDAY 14th JUNE 2021 | * BV INSPECTION TO BE COMPLETED TODAY | * VEHICLE DISPATCHED YESTERDAY 14.06.2021 - ENROUTE POLOKWANE | * VEHICLE AT MOOI RIVIER - ENROUTE POLOKWANE | *POLOKWANA ENROUTE BBR | * BEITBRIDGE ZIM SIDE UNDER CLEARANCE | *ENROUTE HARARE | * HARARE | *HARARE ENROUTE TO KITWE | *ENROUTE TO KITWE | TRUCK CURRENTLY AT SIGONGO EN-ROUTE TO LUSAKA | TRUCK CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | TRUCK CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | TRUCK CURRENTLY AT KASUMBALESA ZAMBIA SIDE | TRUCK CURRENTLY AT KASUMBALESA ZAMBIA SIDE DAY 2 | * WHISKEY AWAITING CLEARANCE | * WHISKEY AWAITING CLEARANCE | VEHICLE AT WHISKY - AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 12.07.2021
BA1571 | 1 X NEW CAT 426F2 BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ403617 | CAT0426FPEJ403617 | CC203864 | 2105DSI1150 | COD 2021 222759 | JH88HCGP | DF96FDGP | JOB033393 | 14.06.2021 | OFFLOADED 12.07.2021 | 23.05.2021 | 14.06.2021 | 17.06.2021 | 19.06.2021 | 21.06.2021 | 23.06.2021 | 26.06.2021 | 27.06.2021 | 28.06.2021 | 29.06.2021 | 01.07.2021 | 02.07.201 | 04.07.2021 | 08.07.2021 | 12.07.2021 | 12.07.2021 | * UNITS TO BE LOADED OUT OF THE PORT TODAY | * UNITS IN BONDED FACILITY AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR MONDAY 14th JUNE 2021 | * BV INSPECTION TO BE COMPLETED TODAY | * VEHICLE DISPATCHED YESTERDAY 14.06.2021 - ENROUTE POLOKWANE | * VEHICLE AT MOOI RIVIER - ENROUTE POLOKWANE | *POLOKWANA ENROUTE BBR | * BEITBRIDGE ZIM SIDE UNDER CLEARANCE | *ENROUTE HARARE | * HARARE | *HARARE ENROUTE TO KITWE | *ENROUTE TO KITWE | TRUCK CURRENTLY AT SIGONGO EN-ROUTE TO LUSAKA | TRUCK CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | TRUCK CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | TRUCK CURRENTLY AT KASUMBALESA ZAMBIA SIDE | TRUCK CURRENTLY AT KASUMBALESA ZAMBIA SIDE DAY 2 | * WHISKEY AWAITING CLEARANCE | * WHISKEY AWAITING CLEARANCE | VEHICLE AT WHISKY - AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 12.07.2021
BA1570 | 1 X NEW CAT 426F2 BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ403616 | CAT0426FTEJ403616 | CC203887 | 2105DSI1150 | COD 2021 222759 | JH88HCGP | DF96FDGP | JOB033393 | 14.06.2021 | OFFLOADED 12.07.2021 | 23.05.2021 | 14.06.2021 | 17.06.2021 | 19.06.2021 | 21.06.2021 | 23.06.2021 | 26.06.2021 | 27.06.2021 | 28.06.2021 | 29.06.2021 | 01.07.2021 | 02.07.201 | 04.07.2021 | 08.07.2021 | 12.07.2021 | * UNITS TO BE LOADED OUT OF THE PORT TODAY | * UNITS IN BONDED FACILITY AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR MONDAY 14th JUNE 2021 | * BV INSPECTION TO BE COMPLETED TODAY | * VEHICLE DISPATCHED YESTERDAY 14.06.2021 - ENROUTE POLOKWANE | * VEHICLE AT MOOI RIVIER - ENROUTE POLOKWANE | *POLOKWANA ENROUTE BBR | * BEITBRIDGE ZIM SIDE UNDER CLEARANCE | *ENROUTE HARARE | * HARARE | *HARARE ENROUTE TO KITWE | *ENROUTE TO KITWE | TRUCK CURRENTLY AT SIGONGO EN-ROUTE TO LUSAKA | TRUCK CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | TRUCK CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | TRUCK CURRENTLY AT KASUMBALESA ZAMBIA SIDE | TRUCK CURRENTLY AT KASUMBALESA ZAMBIA SIDE DAY 2 | * WHISKEY AWAITING CLEARANCE | * WHISKEY AWAITING CLEARANCE | VEHICLE AT WHISKY - AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 12.07.2021
BA1571 | 1 X NEW CAT 426F2 BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ403617 | CAT0426FPEJ403617 | CC203864 | 2105DSI1150 | COD 2021 222759 | JH88HCGP | DF96FDGP | JOB033393 | 14.06.2021 | OFFLOADED 12.07.2021 | 23.05.2021 | 14.06.2021 | 17.06.2021 | 19.06.2021 | 21.06.2021 | 23.06.2021 | 26.06.2021 | 27.06.2021 | 28.06.2021 | 29.06.2021 | 01.07.2021 | 02.07.201 | 04.07.2021 | 08.07.2021 | 12.07.2021 | * UNITS TO BE LOADED OUT OF THE PORT TODAY | * UNITS IN BONDED FACILITY AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR MONDAY 14th JUNE 2021 | * BV INSPECTION TO BE COMPLETED TODAY | * VEHICLE DISPATCHED YESTERDAY 14.06.2021 - ENROUTE POLOKWANE | * VEHICLE AT MOOI RIVIER - ENROUTE POLOKWANE | *POLOKWANA ENROUTE BBR | * BEITBRIDGE ZIM SIDE UNDER CLEARANCE | *ENROUTE HARARE | * HARARE | *HARARE ENROUTE TO KITWE | *ENROUTE TO KITWE | TRUCK CURRENTLY AT SIGONGO EN-ROUTE TO LUSAKA | TRUCK CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | TRUCK CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | TRUCK CURRENTLY AT KASUMBALESA ZAMBIA SIDE | TRUCK CURRENTLY AT KASUMBALESA ZAMBIA SIDE DAY 2 | * WHISKEY AWAITING CLEARANCE | * WHISKEY AWAITING CLEARANCE | VEHICLE AT WHISKY - AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 12.07.2021
BA1612 | 1 X NEW CAT C9.3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RZB00107 DWY00124 LWL04105 | 6057067 5891015 5972785 | N.A | 2105DSI1139 | COD 2021 227056 | ND142761 | ND542263 | ND53524 | TBA | OFFLOADED 22.07.2021 | 16.06.2021 | 24.06.2021 | 01.07.2021 | 03.07.2021 | 05.07.2021 | 06.07.2021 | 08.07.2021 | 09.07.2021 | 10.07.2021 | 11.07.2021 | 12.07.2021 | 15.07.2021 | 15.07.2021 | 18.07.2021 | 22.07.2021 | * AWAITING VESSEL ARRIVAL ON THE 15.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 15.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 15.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 12.06.2021 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 12.06.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE WAITING TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE WAITING TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE WAITING TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE WAITING TO LOAD | * VESSEL CURRENTLY DISCHARGING - AWAITING CONTAINER AVAILABILITY | * PORT DELAYS HENCE COLELCTION WILL BEDONE TODAY 21.06.2021 - BV INSPECTION TO BE COMPLETED 22.06.2021 - PLANNED FOR LOADING 22.06.2021 | * UNIT IN BONDED FACILITY TO CO-LOAD WITH 1 X CAT 14M - BA1663. PLANNED TO LOAD TUESDAY 22.06 | * LOADING 23.06.2021 - BV DELAYED ON C9 DUE TO UNREST ON THE ROADS ON ROUTE TO SITE | * DEPARTING 24.06.2021 | **PIETERMARTIZBURG EN-ROUTE JOHANNESBURG | TRUCK CURRENTLY AT MOOI RIVER EN ROUTE TO JOHANNESBURG | TRUCK CURRENTLY AT JOHANNESBURG DEPO UNDERGOING FINAL CHECKS | TRUCK CURRENTLY AT JOHANNESBURG DEPO UNDERGOING FINAL CHECKS.TRUCK TO DISPATCH TOMMROW | TRUCK CURRENTLY AT POLOKWANE EN-ROUTE TO BEIT BRIDGE | TRUCK CURRENTLY AT LOUIS TRICHARDT EN-ROUTE TO BEIT BRIDGE | BEITBRIDGE SA SIDE - UNDER CLEARANCE | VEHICLE PASSING THROUGH CHIVHU - ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE UNDER CLEARANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE WAITING CLEARANCE | KASUMBALESA ZAMBIAN SIDE WAITING CLEARANCE | KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | VEHICLE ON SITE AWAITING TO OFFLOAD | TRUCK OFFLOADED ON THE 22.07.2021
BA1663 | 1 X USED CAT 14M MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | R9J00649 | N.A | N.A | 2105DSI1124 | COD 2021 198379 | ND142761 | ND542263 | ND53524 | TBA | OFFLOADED 22.07.2021 | 11.06.2021 | 24.06.2021 | 01.07.2021 | 03.07.2021 | 05.07.2021 | 06.07.2021 | 08.07.2021 | 09.07.2021 | 10.07.2021 | 11.07.2021 | 12.07.2021 | 15.07.2021 | 15.07.2021 | 18.07.2021 | 22.07.2021 | * AWAITING THE VESSEL MV SANTA URSULA ARRIVAL ON THE 08.06.2021 | * AWAITING THE VESSEL MV SANTA URSULA ARRIVAL TODAY | * AWAITING VESSEL DISCHARGE - VEHICLES ALOGSIDE WAITING TO LOAD | * AWAITING VESSEL DISCHARGE - VEHICLES ALOGSIDE WAITING TO LOAD | * LOADING UNIT FROM PORT TODAY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER TO BOOK INSPECTION | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER TO BOOK INSPECTION | * UNIT IN BONDED FACILITY TO CO-LOAD WITH 1 X CAT C9.3 GENSET - BA1612. BV INSPECTION BOOKED FOR FRIDAY 18.06.2021 | * UNIT IN BONDED FACILITY TO CO-LOAD WITH 1 X CAT C9.3 GENSET - BA1612. BV INSPECTION BOOKED FOR FRIDAY 18.06.2021 | * UNIT IN BONDED FACILITY TO CO-LOAD WITH 1 X CAT C9.3 GENSET - BA1612. BV INSPECTION BOOKED FOR FRIDAY 18.06.2021 | * UNIT IN BONDED FACILITY TO CO-LOAD WITH 1 X CAT C9.3 GENSET - BA1612. PLANNED TO LOAD TUESDAY 22.06 | * UNIT IN BONDED FACILITY TO CO-LOAD WITH 1 X CAT C9.3 GENSET - BA1612. PLANNED TO LOAD TUESDAY 22.06 | * LOADING 23.06.2021 - BV DELAYED ON C9 DUE TO UNREST ON THE ROADS ON ROUTE TO SITE | * DEPARTING 24.06.2021 | **PIETERMARTIZBURG EN-ROUTE JOHANNESBURG | TRUCK CURRENTLY AT MOOI RIVER EN ROUTE TO JOHANNESBURG | TRUCK CURRENTLY AT JOHANNESBURG DEPO UNDERGOING FINAL CHECKS | TRUCK CURRENTLY AT JOHANNESBURG DEPO UNDERGOING FINAL CHECKS.TRUCK TO DISPATCH TOMMROW | TRUCK CURRENTLY AT POLOKWANE EN-ROUTE TO BEIT BRIDGE | TRUCK CURRENTLY AT LOUIS TRICHARDT EN-ROUTE TO BEIT BRIDGE | BEITBRIDGE SA SIDE - UNDER CLEARANCE | VEHICLE PASSING THROUGH CHIVHU - ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE AWAITING CLEARANCE | CHIRUNDU ZAM SIDE UNDER CLEARANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE WAITING CLEARANCE | KASUMBALESA ZAMBIAN SIDE WAITING CLEARANCE | KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | VEHICLE ON SITE AWAITING TO OFFLOAD | TRUCK OFFLOADED ON THE 22.07.2021
BA1614 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06022 LXL00810 LWL04147 | 5854458 5787141 5029783 | N.A | 2106DSI1152 | COD 2021 241327 | DL51NLGP | DK67LHGP.DK67HVGP | 2106DSI1152 | 20.07.2021 | OFFLOADED 30.07.2021 | 02.07.2021 | 12.07.2021 | 20.07.2021 | 21.07.2021 | 21.07.2021 | 22.07.2021 | 22.07.2021 | 26.07.2021 | 26.07.2021 | 26.07.2021 | 27.07.2021 | 27.07.2021 | 28.07.2021 | 29.07.2021 |  | * AWAITING VESSEL ARRIVAL ON THE 21.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 21.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 21.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 23.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 23.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 23.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 23.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 27.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 27.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 27.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL TODAY - VESSEL MOVED OUT DUE TO PORT CONGESTION | AWAITING VESSEL DISCHARGE IN ORDER TO LOAD THE CONTAINER FROM PORT | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TOMORROW 07.07.2021 | BV NUMBER TO BE VALIDATED IN ORDER FOR US TO BOOK INSPECTION | BV NUMBER TO BE VALIDATED IN ORDER FOR US TO BOOK INSPECTION | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD & DISPATCH THIS WEEK | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK CURRENTLY AT MAKHADO EN-ROUTE TO BEITBRIDGE BORDER | TRUCK CURRENTLY AT LIVINGSTONE UNDERGOING CLEARANCE | TRUCK CURRENTLY AT LIVINGSTONE UNDERGOING CLEARANCE | TRUCK CURRENTLY AT KAPIRI ENROUTE LUSAKA | * VEHICLE AT KASUMBALESA ZAMBIAN SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY PARKING - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY PARKING - AWAITING CLEARANCE | * VEHICLE AT LUBUMBASHI ENROUTE SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED
BA1615 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06021 LXL00797 LWL04151 | 5854458 5787141 5029783 | N.A | 2106DSI1152 | COD 2021 241325 | DL51NLGP | DK67LHGP.DK67HVGP | 2106DSI1152 | 20.07.2021 | OFFLOADED 30.07.2021 | 02.07.2021 | 12.07.2021 | 20.07.2021 | 21.07.2021 | 21.07.2021 | 22.07.2021 | 22.07.2021 | 26.07.2021 | 26.07.2021 | 26.07.2021 | 27.07.2021 | 27.07.2021 | 28.07.2021 | 29.07.2021 |  | * AWAITING VESSEL ARRIVAL ON THE 21.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 21.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 21.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 20.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 23.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 23.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 23.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 23.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 27.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 27.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL ON THE 27.06.2021 - VESSEL MOVED OUT DUE TO PORT CONGESTION | * AWAITING VESSEL ARRIVAL TODAY - VESSEL MOVED OUT DUE TO PORT CONGESTION | AWAITING VESSEL DISCHARGE IN ORDER TO LOAD THE CONTAINER FROM PORT | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TOMORROW 07.07.2021 | BV NUMBER TO BE VALIDATED IN ORDER FOR US TO BOOK INSPECTION | BV NUMBER TO BE VALIDATED IN ORDER FOR US TO BOOK INSPECTION | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD & DISPATCH THIS WEEK | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK CURRENTLY AT MAKHADO EN-ROUTE TO BEITBRIDGE BORDER | TRUCK CURRENTLY AT LIVINGSTONE UNDERGOING CLEARANCE | TRUCK CURRENTLY AT LIVINGSTONE UNDERGOING CLEARANCE | TRUCK CURRENTLY AT KAPIRI ENROUTE LUSAKA | * VEHICLE AT KASUMBALESA ZAMBIAN SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY PARKING - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY PARKING - AWAITING CLEARANCE | * VEHICLE AT LUBUMBASHI ENROUTE SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED
BA1616 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06004 LXL00812 LWL04129 | 584458 5787141 5029783 | N.A | 2106DSI1168 | COD 2021 206553 | DL51NLGP | DK67LHGP.DK67HVGP | 2106DSI1152 | 20.07.2021 | OFFLOADED 30.07.2021 | 02.07.2021 | 12.07.2021 | 20.07.2021 | 21.07.2021 | 21.07.2021 | 22.07.2021 | 22.07.2021 | 26.07.2021 | 26.07.2021 | 26.07.2021 | 27.07.2021 | 27.07.2021 | 28.07.2021 | 29.07.2021 |  | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 26.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 28.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 28.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 28.06.2021 | * AWAITING VESSEL ARRIVAL ON THE 29.06.2021 | AWAITING VESSEL DISCHARGE IN ORDER TO LOAD THE CONTAINER FROM PORT | VESSEL IN AND WORKING | VESSEL IN AND WORKING | COLLECTING CONTAINER TODAY FROM PORT | UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED TOMORROW 06.07.2021 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE. TO BE CO-LOADED WITH BA1614 & BA1615 | BV INSPECTION COMPLETE. TO BE CO-LOADED WITH BA1614 & BA1615 | BV INSPECTION COMPLETE. TO BE CO-LOADED WITH BA1614 & BA1615 | BV INSPECTION COMPLETE. TO BE CO-LOADED WITH BA1614 & BA1615 | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | BV INSPECTION COMPLETE - DETAILS REGARDING VEHICLE DISPATCH TO BE CONFIRMED | TRUCK DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK CURRENTLY AT MAKHADO EN-ROUTE TO BEITBRIDGE BORDER | TRUCK CURRENTLY AT LIVINGSTONE UNDERGOING CLEARANCE | TRUCK CURRENTLY AT LIVINGSTONE UNDERGOING CLEARANCE | TRUCK CURRENTLY AT KAPIRI ENROUTE LUSAKA | * VEHICLE AT KASUMBALESA ZAMBIAN SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY PARKING - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY PARKING - AWAITING CLEARANCE | * VEHICLE AT LUBUMBASHI ENROUTE SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED
BA1677 | 1 X USED CAT 14M MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | B9J01167 | CAT0014MKB9J01167 | RSX16290 | 2106DSI1191 | COD 2021 245472 | JN38KXGP | XVD958GP | ND59203 | 04.08.2021 | OFFLOADED 30.08.2021 | 01.08.2021 | 04.08.2021 | 11.08.2021 | 12.08.2021 | 15.08.2021 | 16.08.2021 | 18.08.2021 | 20.08.2021 | 21.08.2021 | 22.08.2021 | 23.08.2021 | 23.08.2021 | 24.08.2021 | 26.08.2021 | 30.08.2021 | * AWAITING THE GRAND VISION TO ARRIVE ON THE 29.05.2021 | * VESSEL CURRENTLY WORKING - AWAITING DISCHARGE AS OF 31.05.2021 | * UNITS IN BONDED FACILITY - AWAITING BV NUMBERS AS OF 01.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR 03.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY 03.06.2021 | * BV INSPECTION COMPLETED YESTERDAY - VEHILCES PLANNING TO DISPATCH MONDAY 07.04.2021 | * VEHICLE DISPATCHING TODAY - 07.06.2021 | * VEHICLE CURRENTLY AT MVOTI ENROUTE MOOIRIVIERE | * VEHICLE CURRENTLY AT MOOIRIVIER ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT HARRYSMITH ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE AT BEITBRIDGE SA SIDE - UNDER CLEARANCE | * VEHICLE DISPATCHED BEITBRIDGE ENROUTE HARARE | * VEHICLE AT MVUMA ENROUTE HARARE | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL FINAL DOCS + CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 28.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 30.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 30.07.2022 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 30.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 30.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 30.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 30.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 30.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 01.08.2021 | * TRUCK DISPATCHED EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE | * TRUCK AT LADYSMITH EN-ROUTE TO BEITBRIDGE | * TRUCK AT PRETORIA EN-ROUTE TO BEITBRIDGE | * TRUCK AT MOKOPANE EN-ROUTE TO BEITBRIDGE | * BEITBRIDGE SA SIDE AWAITING CLEARANCE | * BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | * TRUCK AT CHINOYI EN-ROUTE TO CHIRUNDU | * TRUCK AT CHIRUNDU AWAITING RELEASE | * TRUCK AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * TRUCK AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHICLE AT KASUMBALESA DRC SIDE UNDER CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY WAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY WAITING CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED
BA1617 | 1 X NEW CAT C18 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK03460 TWS00664 C7A03866 | 5579149 5365368 5618489 | N.A | 2106DSI1169 | COD 2021 206553 | AJB9958 | N.A | 300053 | 03.08.2021 | OFFLOADED 30.08.2021 | 02.07.2021 | 03.08.2021 | 04.08.2021 | 05.08.2021 | 07.08.2021 |  | 10.08.2021 | 16.08.2021 | 17.08.2021 | 17.08.2021 | 18.08.2021 | 20.08.2021 | 23.08.2021 | 30.08.2021 | 30.08.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2022 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2023 | * AWAITING FINAL BILL | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 10.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 10.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 12.07.2021 | * AWAITING VESSEL DISCHARGE | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * AWAITING CONTAINER TO BE RECEIVED AT UNPACKING FACILITY FROM THE SHIPPING LINE | DELAYED DUE TO PROTEST ACTION LAST WEEK | * CONTAINER RECEIVED AT UNPACKING FACILITY. AWAITING UNPACK | * CONTAINER CURRENTLY UNDER UNPACK. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR THURSDAY 29th JULY 2021 |  | * BV INSPECTION BOOKED FOR THURSDAY 29th JULY 2021 | * BV INSPECTION BOOKED FOR MONDAY 02nd AUGUST 2021 | * BV INSPECTION BOOKED FOR MONDAY 02nd AUGUST 2021 | * TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE | * TRUCK AT GROBLERSBRIDGE AWAITING CLEARANCE | * TRUCK AT GROBLERSBRIDGE BOTSWANA SIDE AWAITING COVID RESULT | * VEHILCE CURRENTLY AT LIVINGSTONE ENROUTE KASUMBALESA | * VEHILCE CURRENTLY AT MONZE ENROUTE KASUMBALESA | * PUBLIC HOLIDAY IN ZAMBIA DUE TO VOTING - VEHILCE CURRENTLY AT MONZE ENROUTE KASUMBALESA | * VEHILCE CURRENTLY AT MONZE TO DISPATCH FOR KASUMBALESA TODAY | * VEHILCE CURRENTLY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | * VEHILCE CURRENTLY AT KASUMBALESA UNDER GOING CUSTOM FORMALITIES | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING TO RELEASE TO WHISKEY | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL CLEARANCE | * VEHILCE CURRENTLY AT LIVINGSTONE ENROUTE KASUMBALESA | * VEHILCE CURRENTLY AT MONZE ENROUTE KASUMBALESA | * PUBLIC HOLIDAY IN ZAMBIA DUE TO VOTING - VEHILCE CURRENTLY AT MONZE ENROUTE KASUMBALESA | * VEHILCE CURRENTLY AT MONZE TO DISPATCH FOR KASUMBALESA TODAY | * VEHILCE CURRENTLY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | * VEHILCE CURRENTLY AT KASUMBALESA UNDER GOING CUSTOM FORMALITIES | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING TO RELEASE TO WHISKEY | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL CLEARANCE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE . COVID CLEARANCE CERTIFICATE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE . COVID CLEARANCE CERTIFICATE | * VEHILCE DISPATCHING WHISKEY TODAY | OFFLOADED
BA1739 | 1 X NEW 120GC HAMMER FOR 320GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KSP00570 | N.A | N.A | 2106DSI1172 | COD 2021 255979 | AJB9958 | N.A | 300053 | 03.08.2021 | OFFLOADED 30.08.2021 | 12.07.2021 | 03.08.2021 | 04.08.2021 | 05.08.2021 | 07.08.2021 | 07.08.2022 | 10.08.2021 | 16.08.2021 | 17.08.2021 | 17.08.2021 | 18.08.2021 | 20.08.2021 | 23.08.2021 | 30.08.2021 | 30.08.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2022 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2023 | * AWAITING FINAL BILL | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 10.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 10.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 12.07.2021 | * AWAITING VESSEL DISCHARGE | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * AWAITING CONTAINER TO BE RECEIVED AT UNPACKING FACILITY FROM THE SHIPPING LINE | DELAYED DUE TO PROTEST ACTION LAST WEEK | * CONTAINER RECEIVED AT UNPACKING FACILITY. AWAITING UNPACK | * CONTAINER CURRENTLY UNDER UNPACK. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR THURSDAY 29th JULY 2021 |  | * BV INSPECTION BOOKED FOR THURSDAY 29th JULY 2021 | * BV INSPECTION BOOKED FOR MONDAY 02nd AUGUST 2021 | * BV INSPECTION BOOKED FOR MONDAY 02nd AUGUST 2021 | * TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE | * TRUCK AT GROBLERSBRIDGE AWAITING CLEARANCE | * TRUCK AT GROBLERSBRIDGE BOTSWANA SIDE AWAITING COVID RESULT | * VEHILCE CURRENTLY AT LIVINGSTONE ENROUTE KASUMBALESA | * VEHILCE CURRENTLY AT MONZE ENROUTE KASUMBALESA | * PUBLIC HOLIDAY IN ZAMBIA DUE TO VOTING - VEHILCE CURRENTLY AT MONZE ENROUTE KASUMBALESA | * VEHILCE CURRENTLY AT MONZE TO DISPATCH FOR KASUMBALESA TODAY | * VEHILCE CURRENTLY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | * VEHILCE CURRENTLY AT KASUMBALESA UNDER GOING CUSTOM FORMALITIES | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING TO RELEASE TO WHISKEY | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL CLEARANCE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE . COVID CLEARANCE CERTIFICATE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE . COVID CLEARANCE CERTIFICATE | * VEHILCE DISPATCHING WHISKEY TODAY | OFFLOADED
BA1740 | 1 X NEW 120GC HAMMER FOR 320GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KSP00571 | N.A | N.A | 2106DSI1172 | COD 2021 255979 | AJB9958 | N.A | 300053 | 03.08.2021 | OFFLOADED 30.08.2021 | 12.07.2021 | 03.08.2021 | 04.08.2021 | 05.08.2021 | 07.08.2021 |  | 10.08.2021 | 16.08.2021 | 17.08.2021 | 17.08.2021 | 18.08.2021 | 20.08.2021 | 23.08.2021 | 30.08.2021 | 30.08.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2021 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2022 | * AWAITING BV NUMBER. COMMERCIAL INVOICE + CONFIRMATION OF ETD ORIGIN - ETA DBN 15.07.2023 | * AWAITING FINAL BILL | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 15.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 10.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 10.07.2021 | * AWAITING VESSEL ARRIVAL - BROTONNE BRIDGE CURRENT ETA 12.07.2021 | * AWAITING VESSEL DISCHARGE | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * CONTAINER TO BE LOADED FROM PORT AS SOON AS WE HAVE CONFIRMATION THAT ROADS ARE CLEAR | * AWAITING CONTAINER TO BE RECEIVED AT UNPACKING FACILITY FROM THE SHIPPING LINE | DELAYED DUE TO PROTEST ACTION LAST WEEK | * CONTAINER RECEIVED AT UNPACKING FACILITY. AWAITING UNPACK | * CONTAINER CURRENTLY UNDER UNPACK. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR THURSDAY 29th JULY 2021 |  | * BV INSPECTION BOOKED FOR THURSDAY 29th JULY 2021 | * BV INSPECTION BOOKED FOR MONDAY 02nd AUGUST 2021 | * BV INSPECTION BOOKED FOR MONDAY 02nd AUGUST 2021 | * TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE | * TRUCK AT GROBLERSBRIDGE AWAITING CLEARANCE | * TRUCK AT GROBLERSBRIDGE BOTSWANA SIDE AWAITING COVID RESULT | * VEHILCE CURRENTLY AT LIVINGSTONE ENROUTE KASUMBALESA | * VEHILCE CURRENTLY AT MONZE ENROUTE KASUMBALESA | * PUBLIC HOLIDAY IN ZAMBIA DUE TO VOTING - VEHILCE CURRENTLY AT MONZE ENROUTE KASUMBALESA | * VEHILCE CURRENTLY AT MONZE TO DISPATCH FOR KASUMBALESA TODAY | * VEHILCE CURRENTLY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | * VEHILCE CURRENTLY AT KASUMBALESA UNDER GOING CUSTOM FORMALITIES | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING TO RELEASE TO WHISKEY | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL CLEARANCE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE . COVID CLEARANCE CERTIFICATE | * VEHILCE CURRENTLY AT WHISKEY WAITING FINAL RELEASE . COVID CLEARANCE CERTIFICATE | * VEHILCE DISPATCHING WHISKEY TODAY | OFFLOADED
BA1662 | 1 X CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9E00302 | CAT00140LW9E00302 | D7A17677 | 2107DSI1195 | COD 2021 255977 | ND400011 | ND700343 | ND59397 | 11.08.2021 | OFFLOADED 02.09.2021 | 05.08.2021 | 11.08.2021 | 15.08.2021 | 17.08.2021 | 20.08.2021 | 21.08.2021 | 23.08.2021 | 24.08.2021 | 25.08.2021 | 25.08.2021 | 26.08.2021 | 28.08.2021 | 30.08.2021 | 31.08.2021 |  | * AWAITING THE GRAND VISION TO ARRIVE ON THE 29.05.2021 | * VESSEL CURRENTLY WORKING - AWAITING DISCHARGE AS OF 31.05.2021 | * UNITS IN BONDED FACILITY - AWAITING BV NUMBERS AS OF 01.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR 03.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY 03.06.2021 | * BV INSPECTION COMPLETED YESTERDAY - VEHILCES PLANNING TO DISPATCH MONDAY 07.04.2021 | * VEHICLE DISPATCHING TODAY - 07.06.2021 | * VEHICLE CURRENTLY AT MVOTI ENROUTE MOOIRIVIERE | * VEHICLE CURRENTLY AT MOOIRIVIER ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT HARRYSMITH ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE AT BEITBRIDGE SA SIDE - UNDER CLEARANCE | * VEHICLE DISPATCHED BEITBRIDGE ENROUTE HARARE | * VEHICLE AT MVUMA ENROUTE HARARE | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL FINAL DOCS + CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 28.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 04.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 05.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 05.08.2021 | VESSEL TO BERTH TODAY.TRUCKS ALONG SIDE SHIP AWAITING TO LOAD | LOADING MACHINE IN PORT TODAY. BV BOOKED FOR THE 10.08.2021 | BV INSPECTION BOOKED FOR TODAY | * AWAITING PERMITS - VEHICLE PLANNING TO DISPATCH TOMORROW MORNING | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE DISPATCHING JHB ENROUTE BEITBRIDGE | * VEHICLE AT PIETERSBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE AT BEIT BRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE AT BEIT BRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE AT BEIT BRIDGE ZIM SIDE AWAITING FINAL RELEASE | * VEHICLE AT MASVINGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY CROSSING OVER TO KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | AWAITING TO OFFLOAD
BA1670 | 1 X NEW CAT 345GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF20127 | CAT00345 | NTB04849 | 2107DSI1193 | COD 2021 255975 | CR84FXGP | WGR358GP . WGR365GP | ND59389 | 11.08.2021 | OFFLOADED 02.09.2021 | 05.08.2021 | 13.08.2021 | 15.08.2021 | 16.08.2021 | 19.08.2021 | 21.08.2021 | 23.08.2021 | 25.08.2021 | 26.08.2021 | 27.08.2021 | 28.08.2021 | 29.08.2021 | 30.08.2021 | 31.08.2021 | 02.09.2021 | * AWAITING THE GRAND VISION TO ARRIVE ON THE 29.05.2021 | * VESSEL CURRENTLY WORKING - AWAITING DISCHARGE AS OF 31.05.2021 | * UNITS IN BONDED FACILITY - AWAITING BV NUMBERS AS OF 01.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR 03.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY 03.06.2021 | * BV INSPECTION COMPLETED YESTERDAY - VEHILCES PLANNING TO DISPATCH MONDAY 07.04.2021 | * VEHICLE DISPATCHING TODAY - 07.06.2021 | * VEHICLE CURRENTLY AT MVOTI ENROUTE MOOIRIVIERE | * VEHICLE CURRENTLY AT MOOIRIVIER ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT HARRYSMITH ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE AT BEITBRIDGE SA SIDE - UNDER CLEARANCE | * VEHICLE DISPATCHED BEITBRIDGE ENROUTE HARARE | * VEHICLE AT MVUMA ENROUTE HARARE | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL FINAL DOCS + CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING FINAL BILL | AWAITING VESSEL ARRIVAL - CURRENT ETA 25.07.2021 | AWAITING VESSEL ARRIVAL - CURRENT ETA 25.07.2021 | AWAITING VESSEL ARRIVAL - CURRENT ETA 25.07.2021 | AWAITING VESSEL ARRIVAL - CURRENT ETA 25.07.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2022 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 04.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 05.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 05.08.2021 | VESSEL TO BERTH TODAY.TRUCKS ALONG SIDE SHIP AWAITING TO LOAD | LOADING MACHINE IN PORT TODAY. BV BOOKED FOR THE 10.08.2021 | BV INSPECTION BOOKED FOR TODAY | * AWAITING PERMITS - VEHICLE PLANNING TO DISPATCH TOMORROW MORNING | * AWAITING PERMITS - VEHICLE PLANNING TO DISPATCH TOMORROW MORNING 13.08.2021 | * VEHICLE CURRENTLY AT MOOIRIVIER ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA AWAITING TO CROSS | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KABWE ENROUTE KITWE | * VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT WHISKEY AWAITING DUTIES PAYMENT | AWAITING TO OFFLOAD | PLEASE ASSIST WITH OFFLOADING | AWAITING TO OFFLOAD | * OFFLOADED 02.09.2021
BA1662 | 1 X CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9E00302 | CAT00140LW9E00302 | D7A17677 | 2107DSI1195 | COD 2021 255977 | ND400011 | ND700343 | ND59397 | 11.08.2021 | OFFLOADED 02.09.2021 | 05.08.2021 | 11.08.2021 | 15.08.2021 | 17.08.2021 | 20.08.2021 | 21.08.2021 | 23.08.2021 | 24.08.2021 | 25.08.2021 | 25.08.2021 | 26.08.2021 | 28.08.2021 | 30.08.2021 | 31.08.2021 | 02.09.2021 | * AWAITING THE GRAND VISION TO ARRIVE ON THE 29.05.2021 | * VESSEL CURRENTLY WORKING - AWAITING DISCHARGE AS OF 31.05.2021 | * UNITS IN BONDED FACILITY - AWAITING BV NUMBERS AS OF 01.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR 03.06.2021 | * UNITS IN BONDED FACILITY - BV INSPECTION BOOKED FOR TODAY 03.06.2021 | * BV INSPECTION COMPLETED YESTERDAY - VEHILCES PLANNING TO DISPATCH MONDAY 07.04.2021 | * VEHICLE DISPATCHING TODAY - 07.06.2021 | * VEHICLE CURRENTLY AT MVOTI ENROUTE MOOIRIVIERE | * VEHICLE CURRENTLY AT MOOIRIVIER ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT HARRYSMITH ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE AT BEITBRIDGE SA SIDE - UNDER CLEARANCE | * VEHICLE DISPATCHED BEITBRIDGE ENROUTE HARARE | * VEHICLE AT MVUMA ENROUTE HARARE | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL FINAL DOCS + CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 28.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - ETA 25.07.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 04.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 05.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 05.08.2021 | VESSEL TO BERTH TODAY.TRUCKS ALONG SIDE SHIP AWAITING TO LOAD | LOADING MACHINE IN PORT TODAY. BV BOOKED FOR THE 10.08.2021 | BV INSPECTION BOOKED FOR TODAY | * AWAITING PERMITS - VEHICLE PLANNING TO DISPATCH TOMORROW MORNING | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE DISPATCHING JHB ENROUTE BEITBRIDGE | * VEHICLE AT PIETERSBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE AT BEIT BRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE AT BEIT BRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE AT BEIT BRIDGE ZIM SIDE AWAITING FINAL RELEASE | * VEHICLE AT MASVINGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY CROSSING OVER TO KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | PLEASE URGENTLY ASSIST WITH OFFLOADING | AWAITING TO OFFLOAD | * OFFLOADED 02.09.2021
BA1628 | 1 X NEW CAT 345GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF20118 | CAT00345 | NTB04853 | FML2107DSI1193 | COD 2021 245473 | ND754967 | ND654346 . ND526880 | ND59388 | 11.08.2021 | OFFLOADED 11.09.2021 | 05.08.2021 | 11.08.2021 | 13.08.2021 | 23.08.2021 | 26.08.2021 | 28.08.2021 | 30.08.2021 | 03.09.2021 | 04.09.2021 | 05.09.2021 | 06.09.2021 | 08.09.2021 | 08.09.2021 | 10.09.2021 | 11.09.2021 | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL FINAL DOCS + CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING FINAL BILL | AWAITING VESSEL ARRIVAL - CURRENT ETA 25.07.2021 | AWAITING VESSEL ARRIVAL - CURRENT ETA 25.07.2021 | AWAITING VESSEL ARRIVAL - CURRENT ETA 25.07.2021 | AWAITING VESSEL ARRIVAL - CURRENT ETA 25.07.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2022 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 01.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 04.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 05.08.2021 | WAITING VESSEL ARRIVAL - AMERICAN HIGHWAY VOY. 186 - ETA 05.08.2021 | VESSEL TO BERTH TODAY.TRUCKS ALONG SIDE SHIP AWAITING TO LOAD | LOADING MACHINE IN PORT TODAY. BV BOOKED FOR THE 10.08.2021 | BV INSPECTION BOOKED FOR TODAY | * AWAITING PERMITS - VEHICLE PLANNING TO DISPATCH TOMORROW MORNING | * VEHICLE CURRENTLY AT MOOIRIVIER ENROUTE POLOKWANE | * VEHICLE CURRENTLY POLOKWANE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT CATO RIDGE EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT MOOI RIVER EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT HARRISMITH EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT JOHANNESBURG AND WILL DISPATCH TO BEITBRIDGE | * VEHICLE CURRENTLY AT LOUIS TRICHARDT ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT MVUMA ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | DISPCATCHING CHIRUNDU EN-ROUTE TO LUSAKA | * VEHICLE CURRENTLY AT CHIRUNDU ZAM AWAITING ESCORT | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWATING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWATING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI WAITING FINAL CLEARANCE TO PROCEED TO SITE & OFFLOAD | TRUCK OFFLOADED 11.09.2021
BA1654 | 1 X CAT 374-07A HYDRAULIC EXCAVATOR MAIN BODY | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00217 | CAT00374PRGM00217 | N.A | FML2107DSI1194 | COD 2021 255981 | ND760431 | ND760424 . ND760428 | ND59396 | 06.09.2021 | * OFFLOADED 23.09.2021 | 28.08.2021 | 04.09.2021 | 08.09.2021 | 08.09.2021 | 11.09.2021 | 13.09.2021 | 14.09.2021 | 17.09.2021 | 17.09.2021 | 18.09.2021 | 19.09.2021 | 19.09.2021 | 20.09.2021 | 22.09.2021 | 23.09.2021 | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL FINAL DOCS + CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 28.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THE 03.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE TODAY 03.09.2021 | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MOKOPANE ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * VEHICLE CURRENTLY AT CHINHOYI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT KAFUE EN-ROUTE TO LUSAKA | * VEHICLE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI UNDERGOING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 23.09.2021
BA1705 | 1 X CAT 336-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JFW21161 | CAT00336CJFW21161 | E7A45093 | FML2107DSI1196 | COD 2021 255984 | ND142761 | ND542263 | ND59398 | 02.09.2021 | * OFFLOADED 23.09.2021 | 28.08.2021 | 02.09.2021 | 06.09.2021 | 08.09.2021 | 11.09.2021 | 13.09.2021 | 14.09.2021 | 17.09.2021 | 17.09.2021 | 17.09.2021 | 18.09.2021 | 19.09.2021 | 20.09.2021 | 22.09.2021 | 23.09.2021 | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL FINAL DOCS + CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 28.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | WAITING VESSEL ARRIVAL - ETA 18.08.2021 | WAITING VESSEL ARRIVAL - ETA 18.08.2021 | WAITING VESSEL ARRIVAL - ETA 18.08.2021 | WAITING VESSEL ARRIVAL - ETA 18.08.2021 | WAITING VESSEL ARRIVAL - ETA 18.08.2021 | WAITING VESSEL ARRIVAL - ETA 18.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 01.09.2021 | VEHICLE TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT MARIANNHILL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT PRETORIA ENROUTE POLOKWANE | * VEHICLE CURRENTLY ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE AT KAFUE EN-ROUTE TO LUSAKA | * VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI UNDERGOING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 23.09.2021
BA1668 | 1 X CAT374-07A HYDRAULIC EXCAVATOR MAIN BODY | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00222 | CAT00374JRGM00222 | E4T00285 | FML2108DSI1221 | COD 2021 280825 | WMN927GP | BG55CXGP.BG37PLGP | ND59243 | 06.09.2021 | * OFFLOADED 21.09.2021 | 28.08.2021 | 04.08.2021 | 08.09.2021 | 08.09.2021 | 11.09.2021 | 12.09.2021 | 13.09.2021 | 14.09.2021 | 14.09.2021 | 14.09.2021 | 15.09.2021 | 16.09.2021 | 17.09.2021 | 20.09.2021 | 21.09.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2022 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE AT BONDED FACILITY. BV INSPECTION TO BE DONE TODAY & VEHICLE TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * VEHICLE CURRENLTY AT KABWE ENROUTE KITWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 21.09.2021 | * OFFLOADED 21.09.2021 | * OFFLOADED 21.09.2021
BA1676 | 1 X CAT 966GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW00553 | VAT00966HSGW00553 | NTB08620 | FML2108DSI1225 | COD 2021 275305 | NJ100398 | ND702133 | ND59244 | 02.09.2021 | * OFFLOADED 23.09.2021 | 28.08.2021 | 04.09.2021 | 07.09.2021 | 08.09.2021 | 12.09.2021 | 13.09.2021 | 14.09.2021 | 16.09.2021 | 17.09.2021 | 17.09.2021 | 18.09.2021 | 19.09.2021 | 20.09.2021 | 22.09.2021 | 23.09.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | * BV INSPECTION COMPLETE. VEHICLE TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * TRUCK AT RUTENGA EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE AT KAFUE EN-ROUTE TO LUSAKA | * VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI UNDERGOING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 23.09.2021
BA1703 | 1 X CAT 966GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW00561 | CAT00966KSGW00561 | NTB08739 | FML2108DSI1229 | COD 2021 275305 | ND834401 | ND854241 | ND59248 | 02.09.2021 | * OFFLOADED 23.09.2021 | 28.08.2021 | 04.09.2021 | 07.09.2021 | 08.09.2021 | 12.09.2021 | 13.09.2021 | 14.09.2021 | 16.09.2021 | 17.09.2021 | 17.09.2021 | 18.09.2021 | 19.09.2021 | 20.09.2021 | 22.09.2021 | 23.09.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | * BV INSPECTION COMPLETE. VEHICLE TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT ERMELO ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE AT KAFUE EN-ROUTE TO LUSAKA | * VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI UNDERGOING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 23.09.2021
BA1701 | 1 X CAT 950GC WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M5K05395 | CAT00950HM5K05395 | E7A45935 | FML2108DSI1228 | COD 2021 276198 | ND72819 | ND274710 | ND59247 | 03.09.2021 | * OFFLOADED 27.09.2021 | 28.08.2021 | 04.09.2021 | 07.09.2021 | 08.09.2021 | 14.09.2021 | 15.09.2021 | 16.09.2021 | 20.09.2021 | 20.09.2021 | 20.09.2021 | 21.09.2021 | 21.09.2021 | 22.09.2021 | 27.09.2021 | 27.09.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | BV INSPECTION COMPLETED YESTERDAY. VEHICLE TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MOKOPANE ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * HEAVY CONGESTION AT BEITBRIDGE BORDER | * VEHICLE AT BEITBRIDGE ZIM SIDE AWAITING FINAL CLEARANCE | * VEHICLE AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE AT KAFUE EN-ROUTE TO LUSAKA | * VEHICLE DISPATCHING LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALES - UNDER CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - UNDER CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - WAITING CLEARANCE | * OFFLOADED 27.09.2021
BA1692 | 1 X CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9200850 | CAT00140PW9200850 | E7A45823 | FML2108DSI1226 | COD 2021 275592 | ND66858 | ND226486 | ND59245 | 03.09.2021 | * OFFLOADED 27.09.2021 | 28.08.2021 | 04.09.2021 | 07.09.2021 | 07.09.2021 | 12.09.2021 | 13.09.2021 | 14.09.2021 | 15.09.2021 | 16.09.2021 | 16.09.2021 | 17.09.2021 | 20.09.2021 | 22.09.2021 | 24.09.2021 | 27.09.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | * BV INSPECTION COMPLETE. VEHICLE TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT VILLIERS ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZAMBIAN SIDE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE AT KASUMBALESA AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE - DISPATCHING TODAY | * VEHICLE AT KASUMBALESA DRC SIDE - UNDER CLEARANCE | * VEHICLE AT WHISKY - AWAIITNG CLEARANCE | * VEHICLE AT WHISKY - UNDER CLEARANCE | * VEHICLE AT COMEXAS YARD UNDER FINAL CLEARANCE | * OFFLOADED 27.09.2021
BA1693 | 1 X CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9200852 | CAT00140JW9200852 | E7A45810 | FML2108DSI1227 | COD 2021 275592 | ND706468 | ND256330 | ND59246 | 03.09.2021 | * OFFLOADED 27.09.2021 | 28.08.2021 | 04.09.2021 | 08.09.2021 | 10.09.2021 | 16.09.2021 | 17.09.2021 | 21.09.2021 | 22.09.2021 | 22.09.2021 | 23.09.2021 | 24.09.2021 | 26.09.2021 | 26.09.2021 | 27.09.2021 | 27.09.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | * BV INSPECTION COMPLETE. VEHICLE TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT VILLIERS ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MATSEKE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT MOPANE ENROUTE BEITBRIDGE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * HEAVY CONGESTION AT BEITBRIDGE BORDER | * TRUCK AT BEITBRIDGE RSA SIDE UNDER CLEARANCE - WEIGHBRIDGE | * TRUCK AT BEITBRIDGE RSA SIDE AWAITING TO CROSS | * TRUCK AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | * TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE ENROUTE CHIRUNDU | * VEHICLE CURRENLTLY AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE AT COMEXAS YARD UNDER FINAL CLEARANCE | * OFFLOADED 27.09.2021
BA1654 | * CYLINDER * PALLET * COUNTER WEIGHT * STICK * BOOM * BOX * GUARD * BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00217 | CAT00374PRGM00217 | N.A | FML2107DSI1194 | COD 2021 255981 | ACK1474 | ACG4891T.ACG4892T | ND59396-2 | 06.09.2021 | * OFFLOADED 28.09.2021 | 28.08.2021 | 04.09.2021 | 06.09.2021 | 07.09.2021 | 13.09.2021 | 14.09.2021 | 14.09.2021 | 17.09.2021 | 17.09.2021 | 20.09.2021 | 21.09.2021 | 22.09.2021 | 23.09.2021 | 28.09.2021 | 28.09.2021 | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL DRAFT DOCS + CONFIRMATION OF ETD ORIGIN + VESSEL DETAILS | * AWAITING ALL FINAL DOCS + CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 28.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.06.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | * AWAITING VESSEL ARRIVAL - ALLIANCE ST. LOUIS - VOY. 133 - CURRENT ETA 29.07.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 17.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | WAITING VESSEL ARRIVAL - ETA 29.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THE 03.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE TODAY 03.09.2021 | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT KABWE EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENLY AT NDOLA ENROUTE KASUMBALESA | * VEHILCE CURRENLY AT KASUMBALESA - UNDER CLEARANCE | * VEHILCE CURRENLY AT KASUMBALESA DRC SIDE - TO DISPATCH FOR WHISKY TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE AT COMEXAS YARD AWAITING SEAL REMOVAL & FINAL CLEARANCE | * OFFLOADED 28.09.2021
BA1668 | * CYLINDER * PALLET * COUNTER WEIGHT * STICK * BOOM * BOX * GUARD * BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00222 | CAT00374JRGM00222 | E4T00285 | FML2108DSI1221 | COD 2021 280825 | ACK1474 | ACE5851T.ACE5873T | ND59243 | 06.09.2021 | * OFFLOADED 28.09.2021 | 28.08.2021 | 04.08.2021 | 07.09.2021 | 07.09.2021 | 13.09.2021 | 14.09.2021 | 14.09.2021 | 16.09.2021 | 17.09.2021 | 19.09.2021 | 21.09.2021 | 22.09.2021 | 23.09.2021 | 28.09.2021 | 29.09.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL ARRIVAL - GRAVITY HIGHWAY. CURRENT ETA 28.08.2021 | AWAITING VESSEL DISCHARGE TO LOAD THE MACHINE FROM PORT | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2022 | VEHICLE IS AT OUR BONDED FACILITY AWAITING BV INSPECTION TO BE DONE ON THURSDAY THE 02.09.2021 | VEHICLE AT BONDED FACILITY. BV INSPECTION TO BE DONE TODAY & VEHICLE TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * CLEARANCE COMPLETE - VEHICLE WAITING TO CROSS TO ZIM SIDE | * VEHILCE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHILCE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHILCE AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHILCE AT KABWE EN-ROUTE TO KASUMBALESA | * VEHICLE DISPATCHING NDOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALES - UNDER CLEARANCE | * VEHILCE CURRENLY AT KASUMBALESA DRC SIDE - TO DISPATCH FOR WHISKY TODAY | * VEHICLE CURRENTLY AT WHISKEY - UNDER CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY - AWAITING CLEARANCE | * VEHICLE AT COMEXAS YARD AWAITING SEAL REMOVAL & FINAL CLEARANCE | * OFFLOADED 28.09.2021
BA1782 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEL20792 | CAT00330PKEL20792 | E7A46215 | FML2108DSI1217.1 | COD 2021 256846 | CW60VVGP | JD83RDGP | ND59272 | 13.10.2021 | OFFLOADED 31.10.2021 | 08.10.2021 | 12.10.2021 | 13.10.2021 | 14.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 24.10.2021 | 24.10.2021 | 25.10.2021 | 26.10.2021 | 26.10.2021 | 27.10.2021 | 31.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 12.10.2021 | * TRUCK AT JNB EN-ROUTE TO BEIT BRIDGE | * TRUCK AT BEIT BRIDGE RSA SIDE | * TRUCK AT BEIT BRIDGE RSA SIDE | * VEHICLE CURRENLTY AT BEITBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT CHINHOYI ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA DRC | * VEHICLE CURRENTLY AT WHSIKEY AWAITING DUTIES TO BE PAID | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | OFFLOADED 31.10.2021 | OFFLOADED 31.10.2021
BA1783 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEL20788 | CAT00330TKEL20788 | E7A46101 | FML2108DSI1217.2 | COD 2021 256846 | KB15KRGP | JM62HNGP.JD77VMGP | ND59273 | 13.10.2021 | OFFLOADED 31.10.2021 | 08.10.2021 | 12.10.2021 | 13.10.2021 | 14.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 24.10.2021 | 24.10.2021 | 25.10.2021 | 26.10.2021 | 26.10.2021 | 27.10.2021 | 31.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 12.10.2021 | * TRUCK AT JNB EN-ROUTE TO BEIT BRIDGE | * TRUCK AT BEIT BRIDGE RSA SIDE | * TRUCK AT BEIT BRIDGE RSA SIDE | * VEHICLE CURRENLTY AT BEITBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT CHINHOYI ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA DRC | * VEHICLE CURRENTLY AT WHSIKEY AWAITING DUTIES TO BE PAID | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL RELEASE | OFFLOADED 31.10.2021 | OFFLOADED 31.10.2021
BA1738 | 1 X CAT 320-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DKJ31020 | CAT00320KDKJH31020 | 2109DSI1261 | COD 2021 303883 | ND834401 | ND854241 | ND59287 | 12.10.2021 | OFFLOADED 31.10.2021 | 08.10.2021 | 12.10.2021 | 13.10.2021 | 15.10.2021 | 17.10.2021 | 18.10.2021 | 20.10.2021 | 22.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 26.10.2021 | 26.10.2021 | 27.10.2021 | 31.10.2021 | 31.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCK AT HOWICK EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT GROBLERSDAL EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT MUSINA EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT BEIT BRIDGE RSA SIDE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HURUNGWE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHILCE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KASUMBALESA DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 31.10.2021 | OFFLOADED 31.10.2021 | OFFLOADED 31.10.2021
BA1675 | 1 X CAT 320-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ZBN30934 | CAT00320CZBN30934 | 2109DSI1260 | COD 2021 301566 | ND142761 | ND542263 | ND59288 | 12.10.2021 | OFFLOADED 31.10.2021 | 08.10.2021 | 12.10.2021 | 14.10.2021 | 15.10.2021 | 16.10.2021 | 18.10.2021 | 21.10.2021 | 22.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 26.10.2021 | 26.10.2021 | 27.10.2021 | 31.10.2021 | 31.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCKS WILL DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE | TRUCKS AT PIETERMARITZBURG EN-ROUTE TO BEIT BRIDGE | TRUCKS AT MARBE HALL EN-ROUTE TO BEIT BRIDGE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HURUNGWE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MAKHUTI ENROUTE CHIRUNDU | * VEHILCE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KASUMBALESA DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 31.10.2021 | OFFLOADED 31.10.2021 | OFFLOADED 31.10.2021
BA1784 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEL20795 | CAT00330CKEL20795 | E7A46219 | FML2108DSI1217.3 | COD 2021 256846 | JML417MP | JML416MP.JMM291MP | ND59274 | 13.10.2021 | * OFFLOADED 02.11.2021 | 08.10.2021 | 14.10.2021 | 19.10.2021 | 21.10.2021 | 22.10.2021 | 23.10.2021 | 26.10.2021 | 28.10.2021 | 28.10.2021 | 28.10.2021 | 29.10.2021 | 01.11.2021 | 01.11.2021 | 02.11.2021 | 02.11.2021 | 02.11.2021 | [16 empty] | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 12.10.2021 | * TRUCK TO DISPATCH TOMORROW EN-ROUTE TO BEIT BRIDGE BORDER | * TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE | * TRUCK AT CATO RIDGE EN-ROUTE TO BEIT BRIDGE | * VEHICLE CURRENTLY AT HARRISMITH ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT POLOKWANE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT LOUIS TRICHARDT ENROUTE BEITBRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT KAROI | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHINGOLA EN-ROUTE TO KASUMBALESA BORDER | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 02.11.2021 | * OFFLOADED 02.11.2021
BA1737 | 1 X CAT 320-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DKJ30992 | CAT00320HDKJ30992 |  | 2109DSI1261 | COD 2021 303883 | ND706468 | ND256330 | ND59286 | 12.10.2021 | * OFFLOADED 03.11.2021 | 12.10.2021 | 13.10.2021 | 15.10.2021 | 19.10.2021 | 19.10.2021 | 20.10.2021 | 25.10.2021 | 26.10.2021 | 26.10.2021 | 27.10.2021 | 31.10.2021 | 01.11.2021 | 02.11.2021 | 03.11.2021 | 03.11.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCK AT HOWICK EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT GROBLERSDAL EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT MUSINA EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT BEIT BRIDGE RSA SIDE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE UNDER CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHILCE CURRENTLY AT LUSAKA | * VEHILCE CURRENTLY AT KITWE EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING FINAL CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021
BA1673 | 1 X NEW CAT CS11 VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801040 | CAT0CS11KRK801040 | FML2109DSI1259 | COD 2021 291462 | ND72819 | ND274710 | ND59289 | 13.10.2021 | * OFFLOADED 03.11.2021 | 08.10.2021 | 13.10.2021 | 16.10.2021 | 18.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 29.10.2021 | 30.10.2021 | 31.10.2021 | 03.11.2021 | 03.11.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCKS TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT WARDEN EN-ROUTE TO BEIT BRIDGE | TRUCKS AT JNB EN-ROUTE TO BEIT BRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHICLE DISPATCHED HARARE - CURRENTLY AT CHINHOYI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 03.11.2021
BA1674 | 1 X NEW CAT CS11 VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801041 | CAT0CS11JRK801041 | FML2109DSI1259 | COD 2021 291462 | ND72819 | ND274710 | ND59289 | 13.10.2021 | * OFFLOADED 03.11.2021 | 08.10.2021 | 13.10.2021 | 16.10.2021 | 18.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 29.10.2021 | 30.10.2021 | 31.10.2021 | 03.11.2021 | 03.11.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCKS TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT WARDEN EN-ROUTE TO BEIT BRIDGE | TRUCKS AT JNB EN-ROUTE TO BEIT BRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHICLE DISPATCHED HARARE - CURRENTLY AT CHINHOYI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 03.11.2021
BA1709 | 1 X NEW CAT CS11 VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801071 | CAT0CS11KRK801071 | FML2109DSI1259 | COD 2021 300224 | ND66858 | ND226486 | ND59290 | 13.10.2021 | * OFFLOADED 03.11.2021 | 08.10.2021 | 13.10.2021 | 16.10.2021 | 18.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 28.10.2021 | 28.10.2021 | 31.10.2021 | 03.11.2021 | 03.11.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCKS TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT WARDEN EN-ROUTE TO BEIT BRIDGE | TRUCKS AT JNB EN-ROUTE TO BEIT BRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHICLE DISPATCHED HARARE - CURRENTLY AT CHINHOYI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 03.11.2021
BA1710 | 1 X NEW CAT CS11 VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801073 | CAT0CS11CRK801073 | FML2109DSI1259 | COD 2021 300224 | ND66858 | ND226486 | ND59290 | 13.10.2021 | * OFFLOADED 03.11.2021 | 08.10.2021 | 13.10.2021 | 16.10.2021 | 18.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 28.10.2021 | 28.10.2021 | 31.10.2021 | 03.11.2021 | 03.11.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCKS TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT WARDEN EN-ROUTE TO BEIT BRIDGE | TRUCKS AT JNB EN-ROUTE TO BEIT BRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHICLE DISPATCHED HARARE - CURRENTLY AT CHINHOYI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 03.11.2021
BA1754 | 1 X NEW CAT CS11 VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801089 | CAT0CS11ARK801089 | FML2109DSI1259 | COD 2021 303858 | ND73011 | ND702865 | ND59291 | 13.10.2021 | * OFFLOADED 03.11.2021 | 08.10.2021 | 13.10.2021 | 16.10.2021 | 18.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 29.10.2021 | 30.10.2021 | 31.10.2021 | 03.11.2021 | 03.11.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCKS TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT WARDEN EN-ROUTE TO BEIT BRIDGE | TRUCKS AT JNB EN-ROUTE TO BEIT BRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHICLE DISPATCHED HARARE - CURRENTLY AT CHINHOYI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 03.11.2021
BA1755 | 1 X NEW CAT CS11 VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801090 | CAT0CS11CRK801090 | FML2109DSI1259 | COD 2021 303858 | ND73011 | ND702865 | ND59291 | 13.10.2021 | * OFFLOADED 03.11.2021 | 08.10.2021 | 13.10.2021 | 16.10.2021 | 18.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 29.10.2021 | 30.10.2021 | 31.10.2021 | 03.11.2021 | 03.11.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 08.10.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | TRUCKS TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE BORDER | TRUCKS AT WARDEN EN-ROUTE TO BEIT BRIDGE | TRUCKS AT JNB EN-ROUTE TO BEIT BRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHICLE DISPATCHED HARARE - CURRENTLY AT CHINHOYI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 03.11.2021
BA1708 | 1 X NEW CAT 140K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZL20574 | CAT0140KASZL20574 | TX711354 | 2108DSI1247 | COD 2021 310824 | ND791864 | ND533183 | ND60106 | 13.10.2021 | * OFFLOADED 04.11.2021 | 08.10.2021 | 13.10.2021 | 15.10.2021 | 18.10.2021 | 19.10.2021 | 20.10.2021 | 21.10.2021 | 22.10.2021 | 23.10.2021 | 24.10.2021 | 25.10.2021 | 29.10.2021 | 30.10.2021 | 31.10.2021 | 03.11.2021 | 04.11.2021 | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 12.10.2021 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | * TRUCK AT WARDEN EN-ROUTE TO BEIT BRIDGE BORDER | * TRUCK AT JNB EN-ROUTE TO BEIT BRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE - AWAITING CLEARANCE | * VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY CHIRUNDU ZIM SIDE - AWAITING CLEARANCE | * VEHILCE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHILCE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHILCE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHILCE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHILCE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING TO CROSS TO DRC SIDE | * VEHILCE CURRENTLY AT KASUMBALESA DRC AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 04.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 29.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 08.10.2021 | COMMENTS 11.10.2021 | COMMENTS 12.10.2021 | COMMENTS 13.10.2021 | COMMENTS 14.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 22.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021
BA1781 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEL20793 | CAT00330HFEK20793 | E7A45759 | FML 2108DSI1217 | COD 2021 256846 | ND705348 | ND476150 | ND59271 | 13.10.2021 | * OFFLOADED 04.11.2021 | 08.10.2021 | 14.10.2021 | 18.10.2021 | 19.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 27.10.2021 | 28.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 02.11.2021 | 03.11.2021 | 04.11.2021 | 04.11.2021 | [16 empty] | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 12.10.2021 | * TRUCK TO DISPATCH TOMORROW EN-ROUTE TO BEIT BRIDGE BORDER | * TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEIT BRIDGE | * TRUCK AT PIETERMARITZBURG EN-ROUTE TO BEIT BRIDGE | * VEHICLE CURRENLTY AT POLOKWANE ENROUTE BEITBRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BUBI ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT SIYAVONGA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI WAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 04.11.2021 | * OFFLOADED 04.11.2021 | * OFFLOADED 04.11.2022
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 29.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 08.10.2021 | COMMENTS 11.10.2021 | COMMENTS 12.10.2021 | COMMENTS 13.10.2021 | COMMENTS 14.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 22.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021
BA1785 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEL20794 | CAT00330JKEL20794 | E7A46220 | FML 2108DSI1217.4 | COD 2021 256846 | ZRK025GP | VZJ027GP | ND59275 | 13.10.2021 | OFFLOADED AS OF 10.11.2021 | 08.10.2021 | 13.10.2021 | 14.10.2021 | 20.10.2021 | 22.10.2021 | 23.10.2021 | 25.10.2021 | 28.10.2021 | 28.10.2021 | 28.10.2021 | 29.10.2021 | 01.11.2021 | 02.11.2021 | 04.11.2021 | 08.11.2021 | 09.11.2021 | [16 empty] | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL DUE TO ARRIVE IN DURBAN PORT TODAY - VEHICLES PLACED ALONGSIDE TO LOAD | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 11.10.2021 | * UNITS ARE AT OUR FACILITY AND BV INSPECTION IS BOOKED FOR TODAY THE 12.10.2021 | * TRUCK TO DISPATCH TOMORROW EN-ROUTE TO BEIT BRIDGE BORDER | * TRUCK AT JNB EN-ROUTE TO BEIT BRIDGE BORDER | * TRUCK AT JNB EN-ROUTE TO BEIT BRIDGE BORDER | * VEHICLE CURRENTLY MATSEKE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT LOUIS TRICHARDT ENROUTE BEITBRIDGE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE AWAITING CLEARANCE | * VEHILCE CURRENLTY AT BEITHBRIDGE ZIM SIDE UNDER FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | * VEHICLE TO DISPATCH CHIRUNDU EN-ROUTE TO KASUMBALESA BORDER | * VEHICLE CURRENTLY AT CHINGOLA EN-ROUTE TO KASUMBALESA BORDER | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI - AWAITING CLEARANCE | OFFLOADED | OFFLOADED
BA1718 | 1 X NEW CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9200902 | CAT00140JW9200902 | E7A44379 | 2108DSI1249 | COD 2021 301560 | CF93WWGP | HG09ZFGP | ND60137 | 26.10.2021 | * OFFLOADED 17.11.2021 | 19.10.2021 | 26.10.2021 | 27.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 01.11.2021 | 02.11.2021 | 02.11.2021 | 03.11.2021 | 03.11.2021 | 05.11.2021 | 06.11.2021 | 12.11.2021 | 17.11.2021 | 17.11.2021 | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 14.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 14.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 14.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 14.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 18.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 18.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 18.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 18.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 18.10.2021 | * AWAITING VESSEL ARRIVAL . CONTI COURAGE - CURRENT ETA 18.10.2021 | * AWAITING VESSEL ARRIVAL . MSC ALESSIA ZF136A - CURRENT ETA 19.10.2021 | * AWAITING VESSEL ARRIVAL . MSC ALESSIA ZF136A - CURRENT ETA 19.10.2021 | * VESSEL DUE TO ARRIVE AT 16H00 TODAY - VEHICLES TO BE PLACED ALONGSIDE THIS AFTERNOON. | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNIT | * UNIT TO BE LOADED OUT OF PORT TODAY. BV INSPECTION PLANNED FOT FRIDAY 22 OCTOBER 2021 | * BV INSPECTION BOOKED FOR TODAY 22.10.2021 | * BV COMPLETE. TRUCK TO DISPATCH TOMMROW MORNING | * TRUCK HAS DISPATCH OUR DURBAN FACILITY EN-ROUTE TO BEIT BRIDGE BORDER | * TRUCK IS AT MARIANHILL TOLL EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK IS AT JOHANNESBURG UNDER GOING TRIP CHECK | * TRUCK IS AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE DAY 4 | * VEHICLE DISPATCHING WHISKEY EN-ROUTE TO SITE | * VEHICLE AT LUBUMBASHI AWAITING FINAL CLEARANCE TO PROCEED TO SITE | * VEHICLE AT LUBUMBASHI AWAITING FINAL CLEARANCE TO PROCEED TO SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 17.11.2021
BA1664 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15ELXJ06224 |  |  | FML 2109DSI1254 | COD 2021 279130 | AAZ5353 | ABB2019.ABB2020 | 2109DSI1254 | 29.10.2021 | * OFFLOADED 17.11.2021 | 24.10.2021 | 27.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 03.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 12.11.2021 | 12.11.2021 | 17.11.2021 | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 15.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2022 | * CARGO IS AT OUR DURBAN FACILITY AND BV INSPECTION IS BOOKED FOR TODAY. TRUCK PLANNED TO LOAD AND DISPACTH ON THE 27.10.2021 | * TRUCKS WILL DISPATCH TODAY EN-ROUTE TO JOHANNESBURG FACILITY FOR TRIP CHECK | * TRUCKS AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | * TRUCKS AT HARRISMITH EN-ROUTE TO JOHANNESBURG | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHILCE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIBOMBO ENROUTE KABWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE DISPATCH WHISKEY EN-ROUTE TO SITE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 17.11.2021 | * OFFLOADED 17.11.2021
BA1667 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15CLXJ06225 |  |  | FML 2109DSI1254 | COD 2021 279130 | AAZ5353 | ABB2019.ABB2020 | 2109DSI1254 | 29.10.2021 | * OFFLOADED 17.11.2021 | 24.10.2021 | 27.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 03.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 12.11.2021 | 12.11.2021 | 17.11.2021 | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 15.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2022 | * CARGO IS AT OUR DURBAN FACILITY AND BV INSPECTION IS BOOKED FOR TODAY. TRUCK PLANNED TO LOAD AND DISPACTH ON THE 27.10.2021 | * TRUCKS WILL DISPATCH TODAY EN-ROUTE TO JOHANNESBURG FACILITY FOR TRIP CHECK | * TRUCKS AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | * TRUCKS AT HARRISMITH EN-ROUTE TO JOHANNESBURG | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHILCE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIBOMBO ENROUTE KABWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE DISPATCH WHISKEY EN-ROUTE TO SITE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 17.11.2021 | * OFFLOADED 17.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | TENKE | OFFLOADED | COMMENTS 02.09.2021 | COMMENTS 03.09.2021 | COMMENTS 06.09.2021 | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 08.10.2021 | COMMENTS 13.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 22.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021
BA1665 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15ALXJ06171 | FML 2109DSI1253 | COD 2021 279130 | AAZ6925 | AAS7099.AAS7112 | 2108DSI1251 | 29.10.2021 | * OFFLOADED 21.11.2021 | 24.10.2021 | 27.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 03.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 15.11.2021 | 19.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 15.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * VESSEL IN & WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL IN & WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * CARGO IS AT OUR DURBAN FACILITY AND BV INSPECTION IS BOOKED FOR TODAY. TRUCK PLANNED TO LOAD AND DISPACTH ON THE 27.10.2021 | * TRUCKS WILL DISPATCH TODAY EN-ROUTE TO JOHANNESBURG FACILITY FOR TRIP CHECK | * TRUCKS AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | * TRUCKS AT HARRISMITH EN-ROUTE TO JOHANNESBURG | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHILCE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIBOMBO ENROUTE KABWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT KANYAKHA ENROUTE SITE | * VEHICLE CURRENLTY AT KANYAKHA CUSTOMS - AWAITING CLEARANCE | * VEHICLE UNDERGOING FINAL CUSTOMS CLEARANCE BEFORE PROCEEDING TO SITE | * VEHICLE TO DISPATCH LUBUMBASHI THIS MORNING ENROUTE TFM SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 21.11.2021
BA1666 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15LLXJ06172 | FML 2109DSI1253 | COD 2021 279130 | AAZ6925 | AAS7099.AAS7112 | 2108DSI1251 | 29.10.2021 | * OFFLOADED 21.11.2021 | 24.10.2021 | 27.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 03.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 15.11.2021 | 19.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 15.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2022 | * CARGO IS AT OUR DURBAN FACILITY AND BV INSPECTION IS BOOKED FOR TODAY. TRUCK PLANNED TO LOAD AND DISPACTH ON THE 27.10.2021 | * TRUCKS WILL DISPATCH TODAY EN-ROUTE TO JOHANNESBURG FACILITY FOR TRIP CHECK | * TRUCKS AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | * TRUCKS AT HARRISMITH EN-ROUTE TO JOHANNESBURG | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHILCE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIBOMBO ENROUTE KABWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT KANYAKHA ENROUTE SITE | * VEHICLE CURRENLTY AT KANYAKHA CUSTOMS - AWAITING CLEARANCE | * VEHICLE UNDERGOING FINAL CUSTOMS CLEARANCE BEFORE PROCEEDING TO SITE | * VEHICLE TO DISPATCH LUBUMBASHI THIS MORNING ENROUTE TFM SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 21.11.2021
BA1685 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15CLXJ06197 | FML 2109DSI1252 | COD 2021 279130 | AAZ6925 | AAS7099.AAS7112 | 2108DSI1251 | 29.10.2021 | * OFFLOADED 21.11.2021 | 24.10.2021 | 27.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 03.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 15.11.2021 | 19.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 15.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2022 | * CARGO IS AT OUR DURBAN FACILITY AND BV INSPECTION IS BOOKED FOR TODAY. TRUCK PLANNED TO LOAD AND DISPACTH ON THE 27.10.2021 | * TRUCKS WILL DISPATCH TODAY EN-ROUTE TO JOHANNESBURG FACILITY FOR TRIP CHECK | * TRUCKS AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | * TRUCKS AT HARRISMITH EN-ROUTE TO JOHANNESBURG | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHILCE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIBOMBO ENROUTE KABWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT KANYAKHA ENROUTE SITE | * VEHICLE CURRENLTY AT KANYAKHA CUSTOMS - AWAITING CLEARANCE | * VEHICLE UNDERGOING FINAL CUSTOMS CLEARANCE BEFORE PROCEEDING TO SITE | * VEHICLE TO DISPATCH LUBUMBASHI THIS MORNING ENROUTE TFM SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 21.11.2021
BA1684 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15JLXJ06196 | FML 2109DSI1252 | COD 2021 279130 | AAZ8877 | AAF6848.ACZ9415 | 2108DSI1251 | 29.10.2021 | * OFFLOADED 21.11.2021 | 24.10.2021 | 27.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 03.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 15.11.2021 | 19.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 15.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2022 | * CARGO IS AT OUR DURBAN FACILITY AND BV INSPECTION IS BOOKED FOR TODAY. TRUCK PLANNED TO LOAD AND DISPACTH ON THE 27.10.2021 | * TRUCKS WILL DISPATCH TODAY EN-ROUTE TO JOHANNESBURG FACILITY FOR TRIP CHECK | * TRUCKS AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | * TRUCKS AT HARRISMITH EN-ROUTE TO JOHANNESBURG | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHILCE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIBOMBO ENROUTE KABWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT KANYAKHA ENROUTE SITE | * VEHICLE CURRENLTY AT KANYAKHA CUSTOMS - AWAITING CLEARANCE | * VEHICLE UNDERGOING FINAL CUSTOMS CLEARANCE BEFORE PROCEEDING TO SITE | * VEHICLE TO DISPATCH LUBUMBASHI THIS MORNING ENROUTE TFM SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 21.11.2021
BA1686 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15CLXJ06202 | FML 2108DSI1251 | COD 2021 279130 | AAZ8877 | AAF6848.ACZ9415 | 2108DSI1251 | 29.10.2021 | * OFFLOADED 21.11.2021 | 24.10.2021 | 27.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 03.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 15.11.2021 | 19.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 15.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2022 | * CARGO IS AT OUR DURBAN FACILITY AND BV INSPECTION IS BOOKED FOR TODAY. TRUCK PLANNED TO LOAD AND DISPACTH ON THE 27.10.2021 | * TRUCKS WILL DISPATCH TODAY EN-ROUTE TO JOHANNESBURG FACILITY FOR TRIP CHECK | * TRUCKS AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | * TRUCKS AT HARRISMITH EN-ROUTE TO JOHANNESBURG | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHILCE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIBOMBO ENROUTE KABWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT KANYAKHA ENROUTE SITE | * VEHICLE CURRENLTY AT KANYAKHA CUSTOMS - AWAITING CLEARANCE | * VEHICLE UNDERGOING FINAL CUSTOMS CLEARANCE BEFORE PROCEEDING TO SITE | * VEHICLE TO DISPATCH LUBUMBASHI THIS MORNING ENROUTE TFM SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 21.11.2021
BA1687 | 1 X NEW CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15JLXJ06201 | FML 2108DSI1251 | COD 2021 279130 | AAZ8877 | AAF6848.ACZ9415 | 2108DSI1251 | 29.10.2021 | * OFFLOADED 21.11.2021 | 24.10.2021 | 27.10.2021 | 28.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 03.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 15.11.2021 | 19.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 05.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 15.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL MILAN MAERSK TO ARRIVE DURBAN PORT ON THE 20.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2021 | * AWAITING VESSEL SANTA CATARINA TO ARRIVE DURBAN PORT ON THE 21.10.2022 | * CARGO IS AT OUR DURBAN FACILITY AND BV INSPECTION IS BOOKED FOR TODAY. TRUCK PLANNED TO LOAD AND DISPACTH ON THE 27.10.2021 | * TRUCKS WILL DISPATCH TODAY EN-ROUTE TO JOHANNESBURG FACILITY FOR TRIP CHECK | * TRUCKS AT MARIANHILL TOLL EN-ROUTE TO JOHANNESBURG | * TRUCKS AT HARRISMITH EN-ROUTE TO JOHANNESBURG | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHILCE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CHIBOMBO ENROUTE KABWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT KANYAKHA ENROUTE SITE | * VEHICLE CURRENLTY AT KANYAKHA CUSTOMS - AWAITING CLEARANCE | * VEHICLE UNDERGOING FINAL CUSTOMS CLEARANCE BEFORE PROCEEDING TO SITE | * VEHICLE TO DISPATCH LUBUMBASHI THIS MORNING ENROUTE TFM SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 21.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021
BA1809 | 1 X CAT M317D2 WHEEL EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CA600772 | CATM317DACA600772 | 2W229537 | FML 2110DS1290 | COD 2021 319611 | JR76FMGP | CF23JHGP | ND601026 | 03.11.2021 | OFFLOADED | 29.10.2021 | 04.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 11.11.2021 | 12.11.2021 | 13.11.2021 | 14.11.2021 | 15.11.2021 | 17.11.2021 | 18.11.2021 | 19.11.2021 | 25.11.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 28.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 28.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 28.10.2021 | * VESSEL IS DUE TO BERTH TODAY-TRUCKS PLACED ALONG SIDE THE VESSEL TO LOAD | * VESSEL IS IN AND WORKING AWAITING TO LOAD MACHINES FROM PORT ONCE AVAILABLE | * UNITS LOADED - BV INSPECTION BOOKED FOR 03.11.2021 | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE. VEHICLE TO DISPATCH DURBAN TODAY ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROPUTE POLOKWANE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE TO DISPATCH HARARE TODAY EN-ROUTE TO CHIRUNDU | * VEHICLE AT MAKUTI EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUDNU ZIM CUSTOMS | * VEHICLE AT CHIRUDNU ZAM SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE - AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE - AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI - AWAITING FINAL RELEASE AND CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI - AWAITING FINAL RELEASE AND CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI - AWAITING FINAL RELEASE AND CLEARANCE | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | OFFLOADED
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKEY | LUBUMBASHI | OFFLOADED | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021
BA1695 | 1 X CAT D8R TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | MEJ00559 | CAT00D8RLMEJ00559 | TXJ02023 | FML 2109DSI1281 | COD 2021 322588 | HJT791MP | JPC983MP | ND60148 | 03.11.2021 | OFFLOADED | 28.10.2021 | 02.11.2021 | 04.11.2021 | 08.11.2021 | 09.11.2021 | 10.11.2021 | 12.11.2021 | 13.11.2021 | 13.11.2021 | 14.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 19.11.2021 | 25.11.2021 | * VEHICLE AT MVUMA EN-ROUTE TO HARARE | * VEHICLE AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE AT KAROI EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE UNDER GOING CUSTOMS FORMALITIES | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY ENROUTE LUBUMBASI | * VEHICLE CURRENTLY AT WHISKEY - AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI - AWAITING FINAL RELEASE AND CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI - AWAITING FINAL RELEASE AND CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI - AWAITING FINAL RELEASE AND CLEARANCE | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | OFFLOADED
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 29.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 08.10.2021 | COMMENTS 11.10.2021 | COMMENTS 12.10.2021 | COMMENTS 13.10.2021 | COMMENTS 14.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 22.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021
BA1722 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20764 | CAT00330KFEK20764 | E7A46695 | FML 2109DSI1272 | COD 2021 301579 | HR34JHGP | DS93YTGP | ND60116 | 10.11.2021 | * OFFLOADED 25.11.2021 | 05.11.2021 | 10.11.2021 | 11.11.2021 | 12.11.2021 | 14.11.2021 | 15.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 19.11.2021 | 22.11.2021 | 25.11.2021 | 25.11.2021 | [7 empty] | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * MACHINE ARE AT OUR DURBAN FACILITY AWAITNG BV INSPECTION | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | * TRUCK CURRENTLY AT NEW VAN REENEN EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CONNEXAFRICA LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CONNEXAFRICA LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT CONNEXAFRICA LUBUMBASHI AWAITING FINAL CLEARANCE DAY 5 | * VEHICLE CURRENTLY AT CONGO EQUIPMENT LUBUMBASHI AWAITING TO OFFLOAD | * OFFLOADED 25.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021
BA1652 | 1 X CAT 426F2 BACKHOE LOADERS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ404062 | CAT0426FVEJ404062 | CC204324 | FML 210DSI1263 | COD 2021 314872 | HP84TSGP | FT74XWGP | ND60141 | 05.11.2021 | * OFFLOADED 25.11.2021 | 29.10.2021 | 05.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 09.11.2021 | 10.11.2021 | 12.11.2021 | 12.11.2021 | 13.11.2021 | 14.11.2021 | 17.11.2021 | 18.11.2021 | 22.11.2021 | 25.11.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | VESSEL IS IN AND WORKING AWAITING TO LOAD CONTAINER ONCE AVAILABLE | MACHINES ARE AT OUR DURBAN FACILITY AND BV IS BOOKED FOR THE 02.11.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE. VEHICLE TO DISPATCH DURBAN TODAY ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE TO DISPATCH BEITBRIDGE ZIM SIDE | * VEHICLE AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAIITNG FINAL CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITNG FINAL RELEASE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITNG CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITNG CLEARANCE | * VEHICLE CROSSED TO KASUMBALESA DRC SIDE - AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY - AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY - AWAITING FINAL CLEARANCE | * LUBUMBASHI AWAITNG FINAL CLEARANCE | * LUBUMBASHI AWAITNG FINAL CLEARANCE | * ON SITE AWAITING TO OFFLOAD | * ON SITE AWAITING TO OFFLOAD | * OFFLOADED 25.11.2021
BA1653 | 1 X CAT 426F2 BACKHOE LOADERS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ404064 | CAT0426FLEJ404064 | CC204324 | FML 210DSI1263 | COD 2021 314872 | HP84TSGP | FT74XWGP | ND60141 | 05.11.2021 | * OFFLOADED 25.11.2021 | 29.10.2021 | 05.11.2021 | 06.11.2021 | 07.11.2021 | 08.11.2021 | 09.11.2021 | 10.11.2021 | 12.11.2021 | 12.11.2021 | 13.11.2021 | 14.11.2021 | 17.11.2021 | 18.11.2021 | 22.11.2021 | 25.11.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . MS MANALI 006 - CURRENT ETA 27.10.2021 | VESSEL IS IN AND WORKING AWAITING TO LOAD CONTAINER ONCE AVAILABLE | MACHINES ARE AT OUR DURBAN FACILITY AND BV IS BOOKED FOR THE 02.11.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE. VEHICLE TO DISPATCH DURBAN TODAY ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE TO DISPATCH BEITBRIDGE ZIM SIDE | * VEHICLE AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAIITNG FINAL CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITNG FINAL RELEASE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITNG CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITNG CLEARANCE | * VEHICLE CROSSED TO KASUMBALESA DRC SIDE - AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY - AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY - AWAITING FINAL CLEARANCE | * LUBUMBASHI AWAITNG FINAL CLEARANCE | * LUBUMBASHI AWAITNG FINAL CLEARANCE | * ON SITE AWAITING TO OFFLOAD | * ON SITE AWAITING TO OFFLOAD | * OFFLOADED 25.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | ENGINE NO | PIN NO: | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021
BA1689 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03089 | CZ207632 | CAT0226BEDXZ03089 | FML 2110DSI1303 | COD 2021 325626 | CB67PGGP | JZ68SNGP | ND60156 | 08.11.2021 | * OFFLOADED 25.11.2021 | 30.10.2021 | 09.11.2021 | 10.11.2021 | 11.11.2021 | 13.11.2021 | 15.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 21.11.2021 | 23.11.2021 | 25.11.2021 | 25.11.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * UNITS LOADED - BV INSPECTION BOOKED FOR 04.11.2021 | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE - WAITING INSPECTION ON BA1689 . BA1690 . BA1691 | * TRUCKS DISPATCHED TODAY EN-ROUTE TO BEITBRIDGE | * TRUCKS AT JOHANNESBURG AWAIITNG DISPATCH | * TRUCKS AT BEITBRIDGE RSA SIDE | * TRUCKS AT BEITBRIDGE RSA SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT CONNEXAFRICA LUBUMBASHI | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * OFFLOADED 25.11.2021
BA1690 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03090 | CZ207607 | CAT0226BLDXZ03090 | FML 2110DSI1303 | COD 2021 325626 | CB67PGGP | JZ68SNGP | ND60156 | 08.11.2021 | * OFFLOADED 25.11.2021 | 30.10.2021 | 09.11.2021 | 10.11.2021 | 11.11.2021 | 13.11.2021 | 15.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 21.11.2021 | 23.11.2021 | 25.11.2021 | 25.11.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * UNITS LOADED - BV INSPECTION BOOKED FOR 04.11.2021 | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE - WAITING INSPECTION ON BA1689 . BA1690 . BA1691 | * TRUCKS DISPATCHED TODAY EN-ROUTE TO BEITBRIDGE | * TRUCKS AT JOHANNESBURG AWAIITNG DISPATCH | * TRUCKS AT BEITBRIDGE RSA SIDE | * TRUCKS AT BEITBRIDGE RSA SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT CONNEXAFRICA LUBUMBASHI | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * OFFLOADED 25.11.2021
BA1691 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03091 | CZ207613 | CAT0226BHDXZ03091 | FML 2110DSI1303 | COD 2021 325626 | CB67PGGP | JZ68SNGP | ND60156 | 08.11.2021 | * OFFLOADED 25.11.2021 | 30.10.2021 | 09.11.2021 | 10.11.2021 | 11.11.2021 | 13.11.2021 | 15.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 21.11.2021 | 23.11.2021 | 25.11.2021 | 25.11.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * UNITS LOADED - BV INSPECTION BOOKED FOR 04.11.2021 | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE - WAITING INSPECTION ON BA1689 . BA1690 . BA1691 | * TRUCKS DISPATCHED TODAY EN-ROUTE TO BEITBRIDGE | * TRUCKS AT JOHANNESBURG AWAIITNG DISPATCH | * TRUCKS AT BEITBRIDGE RSA SIDE | * TRUCKS AT BEITBRIDGE RSA SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT CONNEXAFRICA LUBUMBASHI | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * OFFLOADED 25.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 29.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 08.10.2021 | COMMENTS 11.10.2021 | COMMENTS 12.10.2021 | COMMENTS 13.10.2021 | COMMENTS 14.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 22.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021
BA1720 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20933 | CAT00330AFEK20933 | E7A48660 | FML 2109DSI1289 | COD 2021 319610 | HTJ794MP | JMT934MP | ND60125 | 28.10.2021 | * OFFLOADED 26.11.2021 | 02.11.2021 | 04.11.2021 | 10.11.2021 | 12.11.2021 | 13.11.2021 | 14.11.2021 | 15.11.2021 | 17.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 25.11.2021 | 26.11.2021 | 26.11.2021 | [7 empty] | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 24.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 24.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 24.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 24.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 24.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 24.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 24.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 01.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 01.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 01.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 01.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 02.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . MORNING CHAMPION - CURRENT ETA 02.11.2021 | * BV INSPECTION BOOKED FOR TODAY 04.11.2021 | * VEHICLE CURRENTLY AT LADYSMITH ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEIT BRIDGE | * VEHICLE CURRENTLY AT POLOKWANE AWAITING PERMIT | * VEHICLE CURRENTLY AT POLOKWANE AWAITING PERMIT | * VEHICLE CURRENTLY AT LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT BEITBRIDGE BORDER UNDERGOING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KABWE ENROUTE KITWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT COMEXAS LUBUMBASHI | * OFFLOADED 26.11.2021
BA1723 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20765 | CAT00330JFEK20765 | E7A46943 | FML 2109DSI1272 | COD 2021 301579 | JRT725MP | JLR013MP | ND60117 | 10.11.2021 | * OFFLOADED 26.11.2021 | 05.11.2021 | 10.11.2021 | 15.11.2021 | 16.11.2021 | 17.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 23.11.2021 | 24.11.2021 | 25.11.2021 | 26.11.2021 | 26.11.2021 | [7 empty] | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * MACHINE ARE AT OUR DURBAN FACILITY AWAITNG BV INSPECTION | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | * TRUCK CURRENTLY AT NEW CASTLE EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * TRUCK CURRENTLY AT JOHANNESBURG AWAITING PERMIT BEFORE DISPATCH | * VEHICLE CURRENLTY AT PRETORIA ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUNDI ENROUTE HARARE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITNG FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITNG FINAL RELEASE | * VEHICLE CURRENTLY AT COMEXAS LUBUMBASHI | * OFFLOADED 26.11.2021
BA1724 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20766 | CAT00330CFEK20766 | E7A46946 | FML 2109DSI1272 | COD 2021 301579 | JLK618MP | JLR011MP | ND60118 | 10.11.2021 | * OFFLOADED 26.11.2021 | 05.11.2021 | 10.11.2021 | 11.11.2021 | 12.11.2021 | 14.11.2021 | 15.11.2021 | 16.11.2021 | 17.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 25.11.2021 | 26.11.2021 | 26.11.2021 | [7 empty] | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * MACHINE ARE AT OUR DURBAN FACILITY AWAITNG BV INSPECTION | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | * TRUCK CURRENTLY AT NEW CASTLE EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT KAROI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KABWE ENROUTE KITWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT COMEXAS LUBUMBASHI | * OFFLOADED 26.11.2021
BA1694 | 1 X NEW CAT 330GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20793 | CAT00330HFEK20739 | E7A46678 | FML 2109DSI1272 | COD 2021 301579 | KB15LCGP | JM62HNGP.JD77VMGP | ND60115 | 10.11.2021 | * OFFLOADED 26.11.2021 | 05.11.2021 | 10.11.2021 | 11.11.2021 | 12.11.2021 | 14.11.2021 | 15.11.2021 | 16.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 21.11.2021 | 23.11.2021 | 24.11.2021 | 25.11.2021 | 26.11.2021 | 26.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * MACHINE ARE AT OUR DURBAN FACILITY AWAITNG BV INSPECTION | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | * TRUCK CURRENTLY AT NEW VAN REENEN EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK CURRENTLY AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENLTY AT KABWE ENROUTE KITWE | * VEHICLE CURRENLTY KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT COMEXAS LUBUMBASHI | * OFFLOADED 26.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NO: | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 08.10.2021 | COMMENTS 11.10.2021 | COMMENTS 12.10.2021 | COMMENTS 13.10.2021 | COMMENTS 14.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021
BA1700 | 1 X CAT 320-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DKJ30889 | CAT00320ADKJ30889 | FML 2109DSI1271 | COD 2021 302261 | ND706468 | ND256330 | ND60113 | 04.11.2021 | 29.11.2021 | * OFFLOADED 29.11.2021 | 10.11.2021 | 15.11.2021 | 16.11.2021 | 17.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 21.11.2021 | 21.11.2021 | 22.11.2021 | 25.11.2021 | 25.11.2021 | 26.11.2021 | 29.11.2021 | 29.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 10.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 10.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 10.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 10.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 10.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 10.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 10.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 11.11.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 11.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 11.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 11.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 11.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 28.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 29.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 29.10.2021 | * AWAITING VESSEL BAHRI JAZAN TO ARRIVE DURBAN PORT ON THE 29.10.2021 | * BV INSPECTION BOOKED FOR 03.11.2021 | * BV INSPECTION BOOKED FOR 03.11.2021 | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH TOMORROW 05.11.2021 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 08.11.2021 | * VEHICLE TO DISPATCH WEDNESDAY 10.11.2021 | * VEHICLE TO DISPATCH WEDNESDAY 10.11.2021 | * VEHICLE DISPATCHED EN-ROUTE TO BEITBRIDGE | * VEHICLE AT MOOI RIVER EN-ROUTE TO BEITBRIDGE | * VEHICLE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 29.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021
BA1702 | 1 X CAT 980-14A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | MK90021 | CAT00980HMK900215 | P4E03931 | FML 2109DSI1282 | COD 2021 320619 | ND142761 | ND542263 | ND60147 | 03.11.2021 | * OFFLOADED 29.11.2021 | 29.10.2021 | 09.11.2021 | 11.11.2021 | 12.11.2021 | 15.11.2021 | 16.11.2021 | 19.11.2021 | 20.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 24.11.2021 | 25.11.2021 | 26.11.2021 | 29.11.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 27.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 28.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 28.10.2021 | * AWAITING VESSEL ARRIVAL . ATHENS HIGHWAY - CURRENT ETA 28.10.2021 | * VESSEL IS DUE TO BERTH TODAY-TRUCKS PLACED ALONG SIDE THE VESSEL TO LOAD | * VESSEL IS IN AND WORKING AWAITING TO LOAD MACHINES FROM PORT ONCE AVAILABLE | * UNITS LOADED - BV INSPECTION BOOKED FOR 03.11.2021 | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 08.11.2021 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 08.11.2021 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE | * VEHICLE MARIAN HILL TOLL EN ROUTE TO BEITBRIDGE | * VEHICLE PIETERMARITZBURG TOLL EN ROUTE TO BEITBRIDGE | * VEHICLE MIDDLEBURG EN ROUTE TO BEITBRIDGE | * VEHICLE AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MPINGA ENRPUTE CHIRUNDU | * VEHICLE CURRENTLY AT MPINGA ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE - AWITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 29.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | ENGINE NO | PIN NO: | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021
BA1688 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03088 | CZ207359 | CAT022BHDXZ03088 | FML 2110DSI1303 | COD 2021 322584 | CB67PGGP | JZ68SNGP | ND60156 | 08.11.2021 | * OFFLOADED 29.11.2021 | 30.10.2021 | 09.11.2021 | 10.11.2021 | 11.11.2021 | 13.11.2021 | 15.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 21.11.2021 | 23.11.2021 | 25.11.2021 | 29.11.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 28.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * AWAITING ALL FINAL DOCUMENTS - VESSEL ARRIVAL . BAHRI JAZAN - CURRENT ETA 29.10.2021 | * UNITS LOADED - BV INSPECTION BOOKED FOR 04.11.2021 | * BV INSPECTION BOOKED FOR TODAY 03.11.2021 | * BV INSPECTION COMPLETE - WAITING INSPECTION ON BA1689 . BA1690 . BA1691 | * TRUCKS DISPATCHED TODAY EN-ROUTE TO BEITBRIDGE | * TRUCKS AT JOHANNESBURG AWAIITNG DISPATCH | * TRUCKS AT BEITBRIDGE RSA SIDE | * TRUCKS AT BEITBRIDGE RSA SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT CONNEXAFRICA LUBUMBASHI | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE ENROUTE KOLWEZI TO OFFLOAD BA1688 | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 29.11.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 02.09.2021 | COMMENTS 03.09.2021 | COMMENTS 06.09.2021 | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 13.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 08.12.2021
BA1669 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00242 | CAT00374ARGM00242 | E4T00373 | FML 2109DSI1275 | COD 2021 315458 | WMN927GP | BG55CXGP.BG37PLGP | ND60121-1 | 10.11.2021 | OFFLOADED ON THE 06.12.2021 | 05.11.2021 | 10.11.2021 | 12.11.2021 | 14.11.2021 | 16.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 22.11.2021 | 23.11.2021 | 24.11.2021 | 25.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * VECHILE PLACED ALONG SIDE THE VESSEL IN ORDER TO LOAD THE MACHINES FROM PORT TOMMROW | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | * TRUCK AT PIETERMARITZBURG EN-ROUTE TO JOHANNESBURG | * TRUCK AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * TRUCK AT BELA BELA EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KABWE ENROUTE KITWE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED ON THE 06.12.2021 | OFFLOADED ON THE 06.12.2021 | OFFLOADED ON THE 06.12.2021 | OFFLOADED ON THE 06.12.2022
BA1669 | 1 X CAT 374 HYDRAULIC EXCAVATOR SPARES | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00242 | CAT00374ARGM00242 | E4T00373 | FML 2109DSI1275 | COD 2021 315458 | AGB 5285 | ACG 4957T.ACG 4958T | ND60121-2 | 10.11.2021 | OFFLOADED ON THE 07.12.2021 | 05.11.2021 | 10.11.2021 | 11.11.2021 | 12.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 22.11.2021 | 23.11.2021 | 23.11.2021 | 24.11.2021 | 25.11.2021 | 26.11.2021 | 02.12.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * VECHILE PLACED ALONG SIDE THE VESSEL IN ORDER TO LOAD THE MACHINES FROM PORT TOMMROW | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | AWAITING VEHICLE DISPATCH | * TRUCK AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * TRUCK AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENLTY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | OFFLOADED ON THE 07.12.2021 | OFFLOADED ON THE 07.12.2022
BA1704 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00240 | CAT00374CRGM00240 | E4T00313 | FML 2109DSI1275 | COD 2021 315458 | CR84FXGP | WGR358GP.WGR365GP | ND60122-1 | 10.11.2021 | SOMIKA AWAITING TO OFFLOAD | 05.11.2021 | 10.11.2021 | 12.11.2021 | 14.11.2021 | 16.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 22.11.2021 | 23.11.2021 | 24.11.2021 | 25.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * VECHILE PLACED ALONG SIDE THE VESSEL IN ORDER TO LOAD THE MACHINES FROM PORT TOMMROW | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | * TRUCK AT PIETERMARITZBURG EN-ROUTE TO JOHANNESBURG | * TRUCK AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * TRUCK AT BELA BELA EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BULUWAYO ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KABWE ENROUTE KITWE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE DAY 11 | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE DAY 12 | SOMIKA AWAITING TO OFFLOAD | SOMIKA AWAITING TO OFFLOAD
BA1704 | 1 X CAT 374 HYDRAULIC EXCAVATOR SPARES | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00240 | CAT00374CRGM00240 | E4T00313 | FML 2109DSI1275 | COD 2021 315458 | AGB 6322 ZM | ACG 8868T.ACG 8869T | ND60122-2 | 10.11.2021 | OFFLOADED 07.12.2021 | 05.11.2021 | 10.11.2021 | 11.11.2021 | 12.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 22.11.2021 | 23.11.2021 | 23.11.2021 | 24.11.2021 | 25.11.2021 | 26.11.2021 | 29.11.2021 |  | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * VECHILE PLACED ALONG SIDE THE VESSEL IN ORDER TO LOAD THE MACHINES FROM PORT TOMMROW | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | AWAITING VEHICLE DISPATCH | * TRUCK AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * TRUCK AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BULUWAYO ENROUTE HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENLTY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE 8 | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE 9 | OFFLOADED 07.12.2021 | OFFLOADED 07.12.2022
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 18.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021
BA1807 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20882 | CAT00330VFEK20882 | E7A48448 | FML 2111DSI1322 | COD 2021 340192 | ND834401 | ND854241 | ND60172 | 29.11.2021 | * OFFLOADED 15.12.2021 | 25.11.2021 | 29.11.2021 | 02.12.2021 | 03.11.2021 | 06.12.2021 | 06.12.2021 | 07.12.2021 | 08.12.2021 | 09.12.2021 | 09.12.2021 | 10.12.2021 | 12.12.2021 | 13.12.2021 | 15.12.2021 | 15.12.2021 | 15.12.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 21.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 21.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 21.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 24.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 24.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 23.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 23.11.2021 | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * BV INSPECTION BOOKED FOR TODAY 26.11.2021 PM | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH TODAY 29.11.2021 | * VEHICLE CURRENTLY AT CAMPERDOWN ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT MAKUTI EN-ROUTE TO HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * OFFLOADED 15.12.2021
BA1808 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20881 | CAT00330CFEK20881 | E7A48442 | FML 2111DSI1322 | COD 2021 340192 | ND730794 | ND443606 | ND60173 | 29.11.2021 | * OFFLOADED 15.12.2021 | 25.11.2021 | 30.11.2021 | 01.12.2021 | 03.11.2021 | 06.12.2021 | 06.12.2021 | 07.12.2021 | 09.12.2021 | 09.12.2021 | 09.12.2021 | 10.12.2021 | 12.12.2021 | 13.12.2021 | 15.12.2021 | 15.12.2021 | 15.12.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 21.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 21.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 21.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 24.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 24.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 23.11.2021 | * AWAITING FINAL INVOICES-VESSEL JASPER ARROW DUE TO ARRIVE ON THE 23.11.2021 | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * SLEW BOOM MALFUNCTION - BV INSPECTION BOOKED FOR THIS AFTERNOON . ONCE UNIT IS LOADED OUT OF THE PORT | * BV INSPECTION BOOKED FOR TODAY 29.11.2021 PM | * VEHICLE CURRENTLY AT NEW CASTLE ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT MAKUTI EN-ROUTE TO HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * OFFLOADED 15.12.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 02.09.2021 | COMMENTS 03.09.2021 | COMMENTS 06.09.2021 | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 29.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 10.11.2021 | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 19.11.2021 | COMMENTS 22.11.2021 | COMMENTS 23.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 20.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 23.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021
BA1699 | 1 X CAT 395-07A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGD00286 | CAT00395HSGD00286 | H4E00323 | FML 2109DSI1274 | COD 2021 310357 | ND760431 | ND760424 . ND760428 | ND60119-1 | 24.11.2021 | * TENKE WAITING TO OFFLOAD | 05.11.2021 | 25.11.2021 | 01.12.2021 | 10.12.2021 | 12.12.2021 | 13.12.2021 | 16.12.2021 | 17.12.2021 | 18.12.2021 | 19.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 24.12.2021 | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * VECHILE PLACED ALONG SIDE THE VESSEL IN ORDER TO LOAD THE MACHINES FROM PORT TOMMROW | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | BV COMPLETE AWAITNG DISPATCH | TRUCK UNDER GOING TRIP CHECK AND WILL DISPATCH ONCE DONE ON MONDAY THE 15.11.2021 | TRUCK UNDER GOING TRIP CHECK AND WILL DISPATCH ONCE DONE ON MONDAY THE 15.11.2021 | * VEHICLE CURRENTLY AT MIDRAND ENROUTE POLOKWANE | * UNIT LOADED - VEHICLE TO DISPATCH THIS WEEK | * UNIT LOADED - VEHICLE TO DISPATCH THIS WEEK | * UNIT LOADED - VEHICLE TO DISPATCH THIS WEEK | * UNIT LOADED - VEHICLE TO DISPATCH THIS WEEK | * UNIT LOADED - VEHICLE TO DISPATCH THIS WEEK ON THE 24.11.2021 | * UNIT LOADED - VEHICLE TO DISPATCH THIS WEEK ON THE 24.11.2021 | * VEHCILE IN OUR WORKSHOP UNDER GOING TRIP CHECK-TO DISPATCH MONDAY | * VEHCILE IN OUR WORKSHOP UNDER GOING TRIP CHECK-TO DISPATCH MONDAY | * VEHICLE CURRENTLY AT CATO RIDGE ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT PRETORIA ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLE HALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT VIVO ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT VIVO ATTENDING TO MINOR BREAKDOWN - VEHICLE TO DISPATCH FOR BEITBRIDGE TODAY | * VEHICLE CURRENTLY AT VIVO ATTENDING TO MINOR BREAKDOWN - VEHICLE TO DISPATCH FOR BEITBRIDGE TODAY | * VEHICLE CURRENTLY AT VIVO ATTENDING TO MINOR BREAKDOWN - VEHICLE TO DISPATCH TOMMOROW | * VEHICLE CURRENTLY AT VIVO ATTENDING TO MINOR BREAKDOWN - VEHICLE TO DISPATCH TOMMOROW | * VEHICLE CURRENTLY AT VIVO ATTENDING TO MINOR BREAKDOWN - AWAITING DISPATCH DATE | * VEHICLE CURRENTLY AT POLOKWANE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT BEITBRIDGE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHINOY ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE TO DISPATCH WHISKEY | * VEHICLE AT CONNEX YARD LUBUMBASHI | * TENKE WAITING TO OFFLOAD | OFFLOADED
BA1699 | BOOM STICK CYLINDER BOX PLATEN | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGD00286 | CAT00395HSGD00286 | H4E00323 | FML 2109DSI1274 | COD 2021 310357 | ACG3101 | AAG 8009T | ND60119-2 | 13.11.2021 | * VEHICLE AT TENKE AWAITING TO OFFLOAD DAY 2 | 05.11.2021 | 12.11.2021 | 15.11.2021 | 16.11.2021 | 20.11.2021 | 22.11.2021 | 23.11.2021 | 29.11.2021 | 29.11.2021 | 30.11.2021 | 30.11.2021 | 05.10.2021 | 08.12.2021 | 22.12.2021 | 24.12.2021 | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * VECHILE PLACED ALONG SIDE THE VESSEL IN ORDER TO LOAD THE MACHINES FROM PORT TOMMROW | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | BV COMPLETE AWAITNG DISPATCH | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT PRETORIA ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING RELEASE. TO DISPATCH FOR HARARE TODAY | * VEHICLE CURRENTLY AT KAROI EN-ROUTE TO HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE DISPATCHING CHIRUNDU THIS MORNING ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE DAY 4 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE DAY 5 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE AT CONNEX YARD LUBUMBASHI AWAITING RELEASE | * VEHICLE AT CONNEX YARD LUBUMBASHI AWAITING RELEASE DAY 3 | * VEHICLE AT CONNEX YARD LUBUMBASHI AWAITING RELEASE DAY 4 | * VEHICLE AT TENKE AWAITING TO OFFLOAD DAY 1 | * VEHICLE AT TENKE AWAITING TO OFFLOAD DAY 2 | OFFLOADED
BA1699 | COUNTERWIEGHT BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGD00286 | CAT00395HSGD00286 | H4E00323 | FML 2109DSI1274 | COD 2021 310357 | AAR 7026 | AAM 7902 | ND60119-3 | 13.11.2021 | OFFLOADED | 05.11.2021 | 12.11.2021 | 15.11.2021 | 16.11.2021 | 20.11.2021 | 22.11.2021 | 23.11.2021 | 29.11.2021 | 29.11.2021 | 30.11.2021 | 30.11.2021 | 02.12.2021 | 03.12.2021 | 22.12.2021 | 24.12.2021 | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING ALL FINAL DOCS & CONFIRMATION OF ETD ORIGIN | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 28.09.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING VESSEL ARRIVAL . MORNING LUCY - CURRENT ETA 07.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING ALL FINAL DOCS - AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 30.10.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 06.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * AWAITING VESSEL ARRIVAL . GLOVIS STAR - CURRENT ETA 08.11.2021 | * VECHILE PLACED ALONG SIDE THE VESSEL IN ORDER TO LOAD THE MACHINES FROM PORT TOMMROW | * BV INSPECTION BOOKED FOR TODAY THE 09.11.2021 | BV COMPLETE AWAITNG DISPATCH | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT PRETORIA ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING RELEASE. TO DISPATCH FOR HARARE TODAY | * VEHICLE CURRENTLY AT MAKUTI EN-ROUTE TO HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE DISPATCHING CHIRUNDU THIS MORNING ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE DAY 4 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE- AWAITING FINAL CLEARANCE DAY 5 | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING RELEASE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING RELEASE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING RELEASE DAY 3 | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING RELEASE DAY 6 | * OFFLOADED 13.12.2021 | * OFFLOADED 13.12.2021 | * OFFLOADED 13.12.2021 | * VEHICLE AT TENKE AWAITING TO OFFLOAD | * VEHICLE AT TENKE AWAITING TO OFFLOAD DAY 2 | * VEHICLE AT TENKE AWAITING TO OFFLOAD DAY 3 | * VEHICLE AT TENKE AWAITING TO OFFLOAD DAY 4 | OFFLOADED | OFFLOADED
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 02.09.2021 | COMMENTS 03.09.2021 | COMMENTS 06.09.2021 | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 29.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 20.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 23.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021
BA1762 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06309 LXL01124 LWL04627 | CAT00C15KLXJ06309 |  | FML 2110DSI1299 | COD 2021 341054 | FZ01KZGP | HB35MDGP.HB35MJGP | 2110DSI1299 | 14.12.2021 | * OFLOADED 28.12.2021 | 28.11.2021 | 07.12.2021 | 08.12.2021 | 09.11.2021 | 11.12.2021 | 13.12.2021 | 14.12.2021 | 15.12.2021 | 16.12.2021 | 16.12.2021 | 18.12.2021 | 19.12.2021 | 22.12.2021 | 23.12.2021 | 28.12.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * WAITING FOR PORT BOOKING IN ORDER TO COLLECT CONTAINER FROM PORT | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | * TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | * TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | * TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | * VEHILCE CURRENLTY AT MPINGA ENROUTE CHIRUNDU | * VEHICLE CURRENLY AT CHIRUNDU AWAITING CLEARANCE | * VEHICLE CURRENLY AT NDOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE DAY 4 | * VEHICLE CURRENLY AT LUBUMBASHI AWAITING RELEASE | * VEHICLE CURRENLY AT TENKE AWAITING TO OFFLOAD | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021
BA1764 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06304 LXL01131 LWL04609 | CAT00C15HLXJ06304 |  | FML 2110DSI1299 | COD 2021 341054 | FZ01KZGP | HB35MDGP.HB35MJGP | 2110DSI1299 | 14.12.2021 | * OFLOADED 28.12.2021 | 28.11.2021 | 07.12.2021 | 08.12.2021 | 09.11.2021 | 11.12.2021 | 13.12.2021 | 14.12.2021 | 15.12.2021 | 16.12.2021 | 16.12.2021 | 18.12.2021 | 19.12.2021 | 22.12.2021 | 23.12.2021 | 28.12.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * WAITING FOR PORT BOOKING IN ORDER TO COLLECT CONTAINER FROM PORT | * CONTAINER CURRENTLY UNDER UNPACK - BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | * TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | * TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | * TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | * VEHILCE CURRENLTY AT MPINGA ENROUTE CHIRUNDU | * VEHICLE CURRENLY AT CHIRUNDU AWAITING CLEARANCE | * VEHICLE CURRENLY AT NDOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE DAY 4 | * VEHICLE CURRENLY AT LUBUMBASHI AWAITING RELEASE | * VEHICLE CURRENLY AT TENKE AWAITING TO OFFLOAD | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021
BA1767 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06302 LXL01104 LWL04611 | CAT00C15ALXJ06302 |  | FML 2110DSI1299 | COD 2021 341054 | FZ01KZGP | HB35MDGP.HB35MJGP | 2110DSI1299 | 14.12.2021 | * OFLOADED 28.12.2021 | 28.11.2021 | 07.12.2021 | 08.12.2021 | 09.11.2021 | 11.12.2021 | 13.12.2021 | 14.12.2021 | 15.12.2021 | 16.12.2021 | 16.12.2021 | 18.12.2021 | 19.12.2021 | 22.12.2021 | 23.12.2021 | 28.12.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * WAITING FOR PORT BOOKING IN ORDER TO COLLECT CONTAINER FROM PORT | * CONTAINER CURRENTLY UNDER UNPACK - BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | * TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | * TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | * TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | * TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | * VEHILCE CURRENLTY AT MPINGA ENROUTE CHIRUNDU | * VEHICLE CURRENLY AT CHIRUNDU AWAITING CLEARANCE | * VEHICLE CURRENLY AT NDOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLY AT WHISKEY AWAITING FINAL RELEASE DAY 4 | * VEHICLE CURRENLY AT LUBUMBASHI AWAITING RELEASE | * VEHICLE CURRENLY AT TENKE AWAITING TO OFFLOAD | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 20.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 23.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 03.01.2022 | COMMENTS 04.01.2022 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022
BA1741 | 1 X NEW CAT 980-14A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | MK900245 | CAT00980LMK900245 | P4E03957 | FML2111DSI1339 | COD 2021 340191 | ND706468 | ND256330 | ND60701 | 08.12.2021 | * OFFLOADED 07.01.2022 | 07.12.2021 | 13.12.2021 | 14.12.2021 | 16.12.2021 | 17.12.2021 | 18.12.2021 | 21.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 30.12.2021 | 03.01.2022 | 04.01.2022 | 07.01.2022 | 07.01.2022 | 07.01.2022 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 07.12.2021 | * VESSEL TREASURE 036 DUE TO BERTH TODAY AND OUR VEHICLE IS ALONG SIDE VESSEL AWAITING TO LOAD | LOADING MACHINE FROM PORT TODAY BV BOOKED FOR THE 09.12.2021 | BV BOOKED FOR THE 10.12.2021. AWAITING TRUCK DISPATCH DAY | BV TO BE DONE TODAY. TRUCK TO DISPATCH ON MONDAY | * VEHICLE CURRENTLY AT GREYTOWN ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT ERMELO ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY CROSSING TO BEITBRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT CHINOYI EN-ROUTE TO HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG RELEASE | * VEHICLE CURERNLTY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY ATWHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY ATWHISKEY AWAITING FINAL RELEASE DAY 2 | * VEHICLE CURRENTLY ATWHISKEY AWAITING FINAL RELEASE DAY 3 | * VEHICLE CURRENTLY ATWHISKEY AWAITING FINAL RELEASE DAY 4 | * OFFLOADED 07.01.2022
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED CONGO | ON SITE . TFM | OFFLOADED TFM | COMMENTS 02.09.2021 | COMMENTS 03.09.2021 | COMMENTS 06.09.2021 | COMMENTS 07.09.2021 | COMMENTS 08.09.2021 | COMMENTS 09.09.2021 | COMMENTS 13.09.2021 | COMMENTS 17.09.2021 | COMMENTS 20.09.2021 | COMMENTS 21.09.2021 | COMMENTS 22.09.2021 | COMMENTS 23.09.2021 | COMMENTS 27.09.2021 | COMMENTS 28.09.2021 | COMMENTS 29.09.2021 | COMMENTS 01.10.2021 | COMMENTS 04.10.2021 | COMMENTS 05.10.2021 | COMMENTS 06.10.2021 | COMMENTS 07.10.2021 | COMMENTS 15.10.2021 | COMMENTS 18.10.2021 | COMMENTS 19.10.2021 | COMMENTS 20.10.2021 | COMMENTS 21.10.2021 | COMMENTS 25.10.2021 | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 28.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 09.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 20.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 23.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 03.01.2022 | COMMENTS 04.01.2022 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022
BA1763 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06295 LXL01135 LWL04612 | CAT00C15LLXJ06298 |  | FML 2110DSI1299 | COD 2021 341054 | AAZ6908 | AAF6831 . AAF6832 | 2110DSI1299 | 14.12.2021 | OFFLOADED ON THE 12.01.2022 | 28.11.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 08.01.2022 | 08.01.2022 | 08.01.2022 | 08.01.2022 | 12.01.2022 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * CONTAINER CURRENTLY UNDER UNPACK | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE IS AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE IS AT LUBUMBASHI AWAITING OCC DOCUMENTS | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON THE 12.01.2022 | OFFLOADED ON THE 12.01.2022 | OFFLOADED ON THE 12.01.2022
BA1765 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06303 LXL01112 LWL04610 | CAT00C15LLXJ06303 |  | FML 2110DSI1299 | COD 2021 341054 | AAZ6908 | AAF6831 . AAF6832 | 2110DSI1299 | 14.12.2021 | OFFLOADED ON THE 12.01.2022 | 28.11.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 08.01.2022 | 08.01.2022 | 08.01.2022 | 08.01.2022 | 12.01.2022 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * CONTAINER CURRENTLY UNDER UNPACK | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE IS AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE IS AT LUBUMBASHI AWAITING OCC DOCUMENTS | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON THE 12.01.2022 | OFFLOADED ON THE 12.01.2022 | OFFLOADED ON THE 12.01.2022
BA1770 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06308 LXL01123 LWL04624 | CAT00C15PLXJ06308 |  | FML 2110DSI1299 | COD 2021 341054 | AAZ6840 | AAS7146 . AAF6759 | 2110DSI1299 | 14.12.2021 | OFFLOADED ON THE 16.01.2022 | 28.11.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 10.01.2022 | 11.01.2022 | 11.01.2022 | 12.01.2022 |  | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 30.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * WAITING FOR PORT BOOKING IN ORDER TO COLLECT CONTAINER FROM PORT | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE DAY 5 | * VEHICLE CURRENTLY AT KANYAKA AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA AWAITING FINAL CLEARANCE | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE (CONGO) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON THE 16.01.2022
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER: | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 20.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 23.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 03.01.2022 | COMMENTS 04.01.2022 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022
BA1826 | 1 X CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC305481 E3S11219 M2502007 | CAT00C33JEC305481 | FML 2110DSI1311 | COD 2021 325082 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | * OFFLOADED 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022
BA1827 | 1 X CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC305482 E3S11218 M2502008 | CAT00C33CEC305482 | FML 2110DSI1311 | COD 2021 325082 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | * OFFLOADED 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022
BA1828 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC507210 E3S11314 M2502015 | CAT00C33VEC507210 | FML 2110DSI1311 | COD 2021 325079 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | * OFFLOADED 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022
BA1829 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC507209 E3S11318 M2502018 | CAT00C33LEC507209 | FML 2110DSI1311 | COD 2021 325079 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | * OFFLOADED 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022
BA1831 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01439 KRG10140 M2700187 | CAT00C71JGTY01439 | FML 2110DSI1311 | COD 2021 324956 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | * OFFLOADED 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022
BA1832 | 1 X CAT DE165E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW05520 KRG10311 M2802398 | CAT00C71VECW05520 | FML 2110DSI1311 | COD 2021 325685 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | * OFFLOADED 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022
BA1833 | 1 X CAT DE165E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M2802417 ECW05521 KRG10312 | CAT00C71AECW05521 | FML 2110DSI1311 | COD 2021 325685 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | * OFFLOADED 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022
BA1834 | 1 X CAT DE165E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW05522 KRG10306 M2802399 | CAT00C71LECW05522 | FML 2110DSI1311 | COD 2021 325685 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | * OFFLOADED 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 19.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022
CLIENT PO | CARGO DETAILS | CLIENT | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED CONGO | ON SITE . TFM | OFFLOADED TFM | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 20.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 23.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 03.01.2022 | COMMENTS 04.01.2022 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022
BA1769 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15TLXJ06310 | N.A | FML 2110DSI1312 | COD 2021 327230 | AAZ6840 | AAS7146 . AAF6759 | 2110DSI1312 | 14.12.2021 | OFFLOADED ON 16.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 10.01.2022 | 11.01.2022 | 11.01.2022 | 12.01.2022 |  | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | UNPACKING CONTAINER TODAY-BV INSPECTION BOOKED FOR FRIDAY THE 10.12.2021 | BV DONE. TRUCK TO DISPATCH ON MONDAY | * BV INSPECTION BOOKED FOR TODAY - 13.12.2021 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH TO JOHANNESBURG FACILITY THIS AFTERNOON FOR FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CLEARING AT KANYAKA | * VEHICLE CURRENTLY AT KANYAKA AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA AWAITING FINAL CLEARANCE | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE (CONGO) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON 16.01.2022
BA1771 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15PLXJ06311 | N.A | FML 2110DSI1312 | COD 2021 327230 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1312 | 14.12.2021 | OFFLOADED ON 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 12.01.2022 | 12.01.2022 |  |  |  | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | UNPACKING CONTAINER TODAY-BV INSPECTION BOOKED FOR FRIDAY THE 10.12.2021 | BV DONE. TRUCK TO DISPATCH ON MONDAY | * BV INSPECTION BOOKED FOR TODAY - 13.12.2021 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH TO JOHANNESBURG FACILITY THIS AFTERNOON FOR FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11 -WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12 -WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | OFFLOADED ON 12.01.2022 | OFFLOADED ON 12.01.2022 | OFFLOADED ON 12.01.2022
CLIENT PO | CARGO DETAILS | CLIENT | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | OFFLOADED CONGO | ON SITE . TFM | OFFLOADED TFM | COMMENTS 08.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 20.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 23.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 03.01.2022 | COMMENTS 04.01.2022 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022
BA1766 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15JLXJ06313 | N.A | FML2111DSI1321 | COD 2021 340196 | AAZ6840 | AAS7146 . AAF6759 | 2110DSI1299 | 14.12.2021 | OFFLOADED ON 16.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 10.01.2022 | 11.01.2022 | 11.01.2022 | 12.01.2022 |  | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | UNPACKING CONTAINER TODAY-BV INSPECTION BOOKED FOR FRIDAY THE 10.12.2021 | BV DONE. TRUCK TO DISPATCH ON MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CLEARING AT KANYAKA | * VEHICLE CURRENTLY AT KANYAKA AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA AWAITING FINAL CLEARANCE | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE (CONGO) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON 16.01.2022
BA1768 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CAT00C15KLXJ06312 | N.A | FML2111DSI1321 | COD 2021 340196 | AAZ6908 | AAF6831 . AAF6832 | 2110DSI1299 | 14.12.2021 | OFFLOADED ON 12.01.2022 | 07.12.2021 | 14.12.2021 | 17.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 08.01.2022 | 08.01.2022 | 08.01.2022 | 08.01.2022 | 12.01.2022 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | VESSEL MAERSK STRALSUND IS IN AND WORKING.AWAITING CONTAINER TO BE OFFLOADED FROM VESSEL | UNPACKING CONTAINER TODAY-BV INSPECTION BOOKED FOR FRIDAY THE 10.12.2021 | BV DONE. TRUCK TO DISPATCH ON MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE AT LUBUMBASHI AWAITING OCC DOCUMENTS | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON 12.01.2022 | OFFLOADED ON 12.01.2022 | OFFLOADED ON 12.01.2022
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE . CONGO EQUIPMENT | KAMOA SITE | OFFLOADED | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 07.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 03.01.2022 | COMMENTS 04.01.2022 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 20.01.2022 | COMMENTS 24.01.2022
BA1699 | CAT 395-07A HANDRAIL | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N.A | N.A | N.A | FML2111DSI1322 | TBA | JR76FMGP | KH82PCGP | ND60722 | 13.12.2021 | OFFLOADED 18.01.2022 | 28.11.2021 | 22.12.2021 | 23.12.2021 | 24.12.2021 | 27.12.2021 | 28.12.2021 | 30.12.2022 | 02.01.2022 | 03.01.2022 | 04.01.2022 | 05.01.2022 | 09.01.2022 | 10.01.2022 | 18.01.2022 | 18.01.2022 | 18.01.2022 | 18.01.2022 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 10.12.2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 12.12.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY - AWAIITNG BV NUMBER TO BOOK BV INSPECTION | * UNIT IN BONDED FACILITY - AWAIITNG BV NUMBER TO BOOK BV INSPECTION | * TRUCK TO DISPATCH TODAY-EN-ROUTE TO BEITBRIDGE | * TRUCK AT JOHANNEBSURG AWAITING DISPATCH | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | * VEHICLE AT KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE BY BOLLORE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE BY BOLLORE FOR THE HANDRAIL DAY 4 | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | OFFLOADED 18.01.2022 | OFFLOADED 18.01.2022 | OFFLOADED 18.01.2022 | OFFLOADED 18.01.2022
BA1698 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F6018 | CAT00745P3F601875 | NR80037 | FML2111DSI1359 | COD 2021 364 155 | ND705348 | ND476150 | ND60726 | 07.01.2022 | * OFFLOADED 29.01.2022 | 22.12.2021 | 04.01.2022 | UNIT COULD NOT MOVE OVER THE FESTIVE SEASON, BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 23.12.2021 | 10.01.2022 | 11.01.2022 | 11.01.2022 | 12.01.2022 | 13.01.2022 | 15.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2022 | 20.01.2022 | 21.01.2022 | 21.01.2022 | 22.01.2022 | 22.01.2022 | 23.01.2022 | 23.01.2022 | 23.01.2022 | 24.01.2022 | 26.01.2022 | 27.01.2022 | 28.01.2022 | 28.01.2021 | 29.01.2021 | 29.01.2022 | [43 empty] | * AWAITING VESSEL TITUS TO ARRIVE ON THE 22.12.2021 | * AWAITING VESSEL TITUS TO ARRIVE ON THE 22.12.2021 | * AWAITING VESSEL TITUS TO ARRIVE ON THE 22.12.2021 | * AWAITING VESSEL TITUS TO ARRIVE ON THE 22.12.2021 | * AWAITING VESSEL TITUS TO ARRIVE ON THE 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY - TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * UNIT IN BONDED FACILITY - TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * AWAITING BV TO BE DONE.PLANNING TO DISPATCH THE TRUCK UPON RECEIVAL OF ABNORMAL PERMIT ON THE 05.01.2022 | * TRUCK TO DISPATCH MONDAY THE 10.01.2022 | * VEHICLE CURRENLTY AT MOOI RIVER ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT HARRISMITH ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT WARDEN ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT MARBLE HALL EN ROUTE POLOKWANE | * VEHICLE CURRENLTY AT DENDRON EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING CUSTOM FORMALITIES | * VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | * VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE TO DISPATCH TODAY | * VEHICLE CURRENLTY AT CHEGUTU EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBLAESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBLAESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBLAESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022 | * OFFLOADED 29.01.2022
BA1699 | 1 X CAT 395-07A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGD00286 | CAT00395HSGD00286 | H4E00323 | FML 2109DSI1274 | COD 2021 310357 | ND760431 | ND760424 . ND760428 | ND60119-1 | 24.11.2021 | * OFFLOADED 10.12.2021 | 21.10.2021 | 09.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 05.11.2021 | 12.11.2021 | 13.11.2021 | 14.11.2021 | 15.11.2021 | 15.11.2021 | 16.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 23.11.2021 | 23.11.2021 | 23.11.2021 | 23.11.2021 | 25.11.2021 | 29.11.2021 | 29.11.2021 | 30.11.2021 | 30.11.2021 | 30.11.2021 | 05.12.2021 | 06.12.2021 | 08.12.2021 | 09.12.2021 | 10.12.2021 | 10.12.2021 | [69 empty] | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021
BA1699 | BOOM STICK CYLINDER BOX PLATEN | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGD00286 | CAT00395HSGD00286 | H4E00323 | FML 2109DSI1274 | COD 2021 310357 | ACG3101 | AAG 8009T | ND60119-2 | 13.11.2021 | * OFFLOADED 10.12.2021 | 21.10.2021 | 09.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 05.11.2021 | 12.11.2021 | 13.11.2021 | 14.11.2021 | 15.11.2021 | 15.11.2021 | 16.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 23.11.2021 | 23.11.2021 | 23.11.2021 | 23.11.2021 | 25.11.2021 | 29.11.2021 | 29.11.2021 | 30.11.2021 | 30.11.2021 | 30.11.2021 | 05.12.2021 | 06.12.2021 | 08.12.2021 | 09.12.2021 | 10.12.2021 | 10.12.2021 | [69 empty] | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021
BA1699 | COUNTERWIEGHT BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGD00286 | CAT00395HSGD00286 | H4E00323 | FML 2109DSI1274 | COD 2021 310357 | AAR 7026 | AAM 7902 | ND60119-3 | 13.11.2021 | * OFFLOADED 10.12.2021 | 21.10.2021 | 09.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 05.11.2021 | 12.11.2021 | 13.11.2021 | 14.11.2021 | 15.11.2021 | 15.11.2021 | 16.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 23.11.2021 | 23.11.2021 | 23.11.2021 | 23.11.2021 | 25.11.2021 | 29.11.2021 | 29.11.2021 | 30.11.2021 | 30.11.2021 | 30.11.2021 | 05.12.2021 | 06.12.2021 | 08.12.2021 | 07.12.2021 | 10.12.2021 | 10.12.2021 | [69 empty] | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021
BA1700 | 1 X CAT 320-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DKJ30889 | CAT00320ADKJ30889 | FML 2109DSI1271 | COD 2021 302261 | COD 2021 302261 | ND256330 | ND60113 | 04.11.2021 | 10.11.2021 | * OFFLOADED 10.12.2021 | 21.10.2021 | 11.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 10.11.2021 | 15.11.2021 | 15.11.2021 | 16.11.2021 | 16.11.2021 | 16.11.2021 | 17.11.2021 | 18.11.2021 | 19.11.2021 | 19.11.2021 | 19.11.2021 | 19.11.2021 | 19.11.2021 | 20.11.2021 | 21.11.2021 | 21.11.2021 | 21.11.2021 | 22.11.2021 | 24.11.2021 | 25.11.2021 | 25.11.2021 | 26.11.2021 | 26.11.2021 | 29.11.2021 | 29.11.2021 | 29.11.2021 | [22 empty] | * VEHICLE CURRENLTY AT WHISKEY | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 29.11.2021 | * OFFLOADED 29.11.2021 | * OFFLOADED 29.11.2021 | * OFFLOADED 29.11.2021 | [40 empty] | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021
BA1702 | 1 X CAT 980-14A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | MK90021 | CAT00980HMK900215 | P4E03931 | FML 2109DSI1282 | COD 2021 320619 | ND142761 | ND542263 | ND60147 | 03.11.2021 | * OFFLOADED 10.12.2021 | 21.10.2021 | 02.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 29.10.2021 | 09.11.2021 | 15.11.2021 | 16.11.2021 | 16.11.2021 | 16.11.2021 | 17.11.2021 | 18.11.2021 | 19.11.2021 | 19.11.2021 | 19.11.2021 | 19.11.2021 | 19.11.2021 | 20.11.2021 | 21.11.2021 | 21.11.2021 | 21.11.2021 | 22.11.2021 | 24.11.2021 | 25.11.2021 | 25.11.2021 | 26.11.2021 | 26.11.2021 | 29.11.2021 | 29.11.2021 | 29.11.2021 | [22 empty] | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 29.11.2021 | * OFFLOADED 29.11.2021 | * OFFLOADED 29.11.2021 | * OFFLOADED 29.11.2021 | [40 empty] | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021 | * OFFLOADED 10.12.2021
BA1704 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00240 | CAT00374CRGM00240 | E4T00313 | FML 2109DSI1275 | COD 2021 315458 | CR84FXGP | WGR358GP.WGR365GP | ND60122-1 | 10.11.2021 | OFFLOADED 08.12.2021 | 07.10.2021 | 09.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 05.11.2021 | 10.11.2021 | 11.11.2021 | 11.11.2021 | 12.11.2021 | 12.11.2021 | 14.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 18.11.2021 | 18.11.2021 | 18.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 23.11.2021 | 24.11.2021 | 24.11.2021 | 25.11.2021 | 08.12.2021 | 08.12.2021 | [22 empty] | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | 02.02.2022 | [40 empty] | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021
BA1704 | 1 X CAT 374 HYDRAULIC EXCAVATOR SPARES | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00240 | CAT00374CRGM00240 | E4T00313 | FML 2109DSI1275 | COD 2021 315458 | AGB 6322 ZM | ACG 8868T.ACG 8869T | ND60122-2 | 10.11.2021 | OFFLOADED 08.12.2021 | 07.10.2021 | 09.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 05.11.2021 | 10.11.2021 | 11.11.2021 | 11.11.2021 | 12.11.2021 | 12.11.2021 | 14.11.2021 | 16.11.2021 | 17.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 18.11.2021 | 18.11.2021 | 18.11.2021 | 18.11.2021 | 19.11.2021 | 20.11.2021 | 21.11.2021 | 22.11.2021 | 23.11.2021 | 24.11.2021 | 24.11.2021 | 25.11.2021 | 08.12.2021 | 08.12.2021 | [22 empty] | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI - AWAITING FINAL CLEARANCE | 02.02.2022 | [40 empty] | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021 | OFFLOADED 08.12.2021
BA1706 | 1 X NEW CAT 426F2 BACHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ404427 | CAT0426FPEJ404427 | CC204689 | FML 2201DSI1409 | COD 2022 122 765 | WTS414GP | FY11FLGP | ND62903 | 22.02.2022 | OFFLOADED 24.03.2022 | 04.02.2022 | 10.02.2022 | BV WAS NOT VALIDATED ON THE SYSTEM THUS CAUSING DELAYS TO BOOK INSPECTION | 04.02.2022 | 22.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 24.02.2022 | 27.02.2022 | 28.02.2022 | 03.03.2022 | 04.03.2022 | 04.03.2022 | 05.03.2022 | 05.03.2022 | 06.03.2022 | 06.03.2022 | 07.03.2022 | 07.03.2022 | 07.03.2022 | 08.03.2022 | 10.03.2022 | 11.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | * BV INSPECTION BOOKED FOR TODAY 07.02.2022 | * TRUCK AT JNB UNDERGOING TRIP CHECK | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE RSA SIDE | BV COMPLETE, TRUCK TO DISPATCH TEUSDAY NEXT WEEK | BV COMPLETE, TRUCK TO DISPATCH TUESDAY | BV COMPLETE, TRUCK TO DISPATCH TUESDAY | * VEHICLE TO DIPATCH DURBAN TODAY | * VEHICLE TO DISPATCH NEXT WEEK | * VEHICLE TO DISPATCH NEXT WEEK | * VEHICLE TO DISPATCH THIS WEEK | * VEHICLE TO DISPATCH THIS WEEK | * TRUCK TO DIPSTACH TODAY EN-ROUTE TO DURBAN | * TRUCK ARE AT BEITBRIDGE RSA SIDE | * TRUCK ARE AT BEITBRIDGE RSA SIDE | * TRUCK ARE AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE STILL AT HARARE UNDERGOING MAINTENANCE CHECKS | * VEHICLE DISPATCHED HARARE ENROUTE CHRITUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE | * VEHICLE AT CHIRUNDU ZAM SIDE | * VEHICLE AT KASUMBALESA ZAM SIDE | * VEHICLE AT KASUMBALESA ZAM SIDE DAY 3 | * VEHICLE AT KASUMBALESA DRC SIDE | * VEHICLE AT WHISKEY AWAIITNG RELEASE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 5 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 6 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 7 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 8 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE ON SITE AWAITNG TO OFFLOAD | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022
BA1707 | 1 X NEW CAT 426F2 BACHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ404428 | CAT0426FKEJ404428 | CC204695 | FML 2201DSI1409 | COD 2022 122 765 | WTS414GP | FY11FLGP | ND62904 | 22.02.2022 | OFFLOADED 24.03.2022 | 04.02.2022 | 10.02.2022 | BV WAS NOT VALIDATED ON THE SYSTEM THUS CAUSING DELAYS TO BOOK INSPECTION | 04.02.2022 | 22.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 24.02.2022 | 27.02.2022 | 28.02.2022 | 03.03.2022 | 04.03.2022 | 04.03.2022 | 05.03.2022 | 05.03.2022 | 06.03.2022 | 06.03.2022 | 07.03.2022 | 07.03.2022 | 07.03.2022 | 08.03.2022 | 10.03.2022 | 11.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | * BV INSPECTION BOOKED FOR TODAY 07.02.2022 | * TRUCK AT JNB UNDERGOING TRIP CHECK | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE RSA SIDE | BV COMPLETE, TRUCK TO DISPATCH TEUSDAY NEXT WEEK | BV COMPLETE, TRUCK TO DISPATCH TUESDAY | BV COMPLETE, TRUCK TO DISPATCH TUESDAY | * VEHICLE TO DIPATCH DURBAN TODAY | * VEHICLE TO DISPATCH NEXT WEEK | * VEHICLE TO DISPATCH NEXT WEEK | * VEHICLE TO DISPATCH THIS WEEK | * VEHICLE TO DISPATCH THIS WEEK | * TRUCK TO DIPSTACH TODAY EN-ROUTE TO DURBAN | * TRUCK ARE AT BEITBRIDGE RSA SIDE | * TRUCK ARE AT BEITBRIDGE RSA SIDE | * TRUCK ARE AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE STILL AT HARARE UNDERGOING MAINTENANCE CHECKS | * VEHICLE DISPATCHED HARARE ENROUTE CHRITUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE | * VEHICLE AT CHIRUNDU ZAM SIDE | * VEHICLE AT KASUMBALESA ZAM SIDE | * VEHICLE AT KASUMBALESA ZAM SIDE DAY 3 | * VEHICLE AT KASUMBALESA DRC SIDE | * VEHICLE AT WHISKEY AWAIITNG RELEASE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 5 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 6 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 7 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 8- PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE ON SITE AWAITNG TO OFFLOAD | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022
BA1730 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F601870 | CAT00745L3F601870 | TXW06293 | FML2111DSI1349 | COD 2021 360996 | ND754967 | ND654346.ND526680 | ND60719 | 04.01.2022 | * OFFLOADED 04.01.2022 | 20.12.2021 | 23.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 20.12.2021 | 06.01.2022 | 07.01.2022 | 07.01.2022 | 08.01.2022 | 09.01.2022 | 10.01.2022 | 13.01.2022 | 13.01.2022 | 14.01.2022 | 14.01.2022 | 14.01.2022 | 15.01.2022 | 15.01.2022 | 16.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2022 | 20.01.2022 | 20.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 24.01.2022 | [21 empty] | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * COLLECTING MACHINE FROM PORT TODAY THE 20.12.2021 | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * TRUCK TO DISPATCH TOMORROW THE 06.01.2022 | * TRUCK AT HOWICK EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT MASVINGO EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT SIAVONGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITNG RELEASE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 24.01.2022 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 24.01.2022 | OFFLOADED 24.01.2022 | OFFLOADED 24.01.2022 | 0 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 24.01.2022 | 0 | 0 | OFFLOADED 24.01.2022 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 24.01.2022 | OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022 | * OFFLOADED 04.01.2022
BA1731 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F601872 | CAT00745E3F601872 | TXW06279 | FML2111DSI1350 | COD 2021 360996 | ND730794 | ND443606 | ND60720 | 04.01.2022 | * OFFLOADED 24.01.2022 | 20.12.2021 | 23.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 20.12.2021 | 06.01.2022 | 07.01.2022 | 07.01.2022 | 08.01.2022 | 09.01.2022 | 10.01.2022 | 13.01.2022 | 13.01.2022 | 14.01.2022 | 14.01.2022 | 14.01.2022 | 15.01.2022 | 15.01.2022 | 16.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2022 | 20.01.2022 | 20.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 24.01.2022 | [21 empty] | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * COLLECTING MACHINE FROM PORT TODAY THE 20.12.2021 | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * TRUCK TO DISPATCH TOMORROW THE 06.01.2022 | * TRUCK AT HOWICK EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT MASVINGO EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT SIAVONGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITNG RELEASE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 24.01.2022 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 24.01.2022 | OFFLOADED 24.01.2022 | OFFLOADED 24.01.2022 | 0 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 24.01.2022 | 0 | 0 | OFFLOADED 24.01.2022 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 24.01.2022 | OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022
BA1732 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F601931 | CAT00745C3F601931 | TXW06302 | FML 2202DSI1422 | COD 2022 116850 | ND730794 | ND443606 | ND62939 | 09.03.2022 | * OFFLOADED 04.04.2022 | 21.02.2022 | 07.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 01.03.2022 | 09.03.2022 | 10.03.2022 | 11.03.2022 | 12.03.2022 | 12.03.2022 | 13.03.2022 | 14.03.2022 | 15.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 27.03.2022 | 28.03.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [66 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL ARRIVAL - CURRENT ETA 25.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 25.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 25.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 27.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 27.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 27.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 27.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 27.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 27.02.2022 | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR FRIDAY 04.03.2022 | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR FRIDAY 04.03.2022 | TRUCK TO DISPATCH TOMMROW EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT HARRISMITH EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT BEITHBRIDGE SA SIDE WAITING TO CROSS OVER | * VEHICLE CURRENTLY AT BEITHBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAFULUFUTA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4. | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 5. | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITNG TO OFFLOAD | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1737 | 1 X CAT 320-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DKJ30992 | CAT00320HDKJ30992 | E4T00390 | 2109DSI1261 | COD 2021 303883 | ND706468 | ND256330 | ND59286 | 12.10.2021 | * OFFLOADED 03.11.2021 | 29.09.2021 | 12.10.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 12.10.2021 | 13.10.2021 | 14.10.2021 | 14.10.2021 | 15.10.2021 | 16.10.2022 | 19.10.2021 | 19.10.2021 | 20.10.2021 | 20.10.2021 | 25.10.2021 | 25.10.2021 | 25.10.2021 | 25.10.2021 | 26.10.2021 | 26.10.2021 | 26.10.2021 | 27.10.2021 | 29.10.2021 | 31.10.2021 | 01.11.2021 | 02.11.2021 | 03.11.2021 | 03.11.2021 | 03.11.2021 | 03.11.2021 | [69 empty] | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021 | * OFFLOADED 03.11.2021
BA1741 | 1 X NEW CAT 980-14A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | MK900245 | CAT00980LMK900245 | P4E03957 | FML2111DSI1339 | COD 2021 340191 | ND706468 | ND256330 | ND60701 | 08.12.2021 | * OFFLOADED 07.01.2022 | 18.11.2021 | 10.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 13.12.2021 | 13.12.2021 | 14.12.2021 | 14.12.2021 | 15.12.2022 | 16.12.2021 | 17.12.2021 | 18.12.2021 | 19.12.2021 | 21.12.2022 | 25.12.2021 | 26.12.2021 | 28.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 30.12.2021 | 03.01.2022 | 04.01.2022 | 07.01.2022 | 07.01.2022 | 07.01.2022 | 07.01.2022 | [22 empty] | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | * VESSEL TREASURE 036 DUE TO ARRIVE ON THE 05.12.2021 | 08.02.2022 | [40 empty] | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | OFFLOADED 07.01.2022 | OFFLOADED 07.01.2022 | OFFLOADED 07.01.2022 | * VEHICLE CURRENLY AT KASUMBALES ZAM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLY AT KASUMBALES DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLY AT KASUMBALES DRC SIDE - AWAITING CLEARANCE | * TRUCK TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | * OFFLOADED 07.01.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 07.01.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 07.01.2022 | OFFLOADED 07.01.2022 | OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022 | * OFFLOADED 07.01.2022
BA1748 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00280 | CAT00374CRGM00280 | E4T00391 | FML2201DSI1394 | COD 2022 123780 | ACG7846 | AAR7011T . AAR7067T | ND60787 | 16.02.2022 | * OFFLOADED 07.03.2022 | 07.02.2022 | 08.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 20.02.2022 | 22.02.2022 | 23.02.2022 | 24.02.2022 | 25.02.2022 | 25.02.2022 | 25.02.2022 | 26.02.2022 | 26.02.2022 | 27.02.2022 | 28.02.2022 | 28.02.2022 | 28.02.2022 | 28.02.2022 | 01.03.2022 | 03.03.2022 | 03.03.2022 | 06.03.2022 | 07.03.2022 | 07.03.2022 | 07.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNITS TO BE LOADED OUT OF THE PORT TODAY. AWAITING BV NUMBER IN ORDER TO BOOK BV | * UNIT IN OUR BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT IN OUR BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT IN OUR BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT IN OUR BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV TO BE DONE TODAY, TRUCK TO DISPATCH LATER THIS WEEK | TRUCK TO DISPATCH MONDAY THE 14.02.2022 | TRUCK TO DISPATCH MONDAY THE 14.02.2022 | TRUCK TO DISPATCH MONDAY THE 14.02.2022 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT CATO RIDGE ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT CATO RIDGE ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT BEIRBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT CHIBI EN-ROUTE HARARE | * VEHICLE CURRENTLY AT BEATRICE EN-ROUTE HARARE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE CHIRUDNU | * VEHICLE CURRENTLY AT KAROI EN-ROUTE CHIRUDNU | * VEHICLE CURRENTLY AT KAROI EN-ROUTE CHIRUDNU | * VEHICLE CURRENTLY AT CHISAMBA EN-ROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY DAY 2 | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022
BA1748 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00280 | CAT00374CRGM00280 | E4T00391 | FML2201DSI1394 | COD 2022 123780 | ACG7846 | AAR7011T . AAR7067T | ND60787 | 08.02.2022 | * OFFLOADED 02.03.2022 | 07.02.2022 | 08.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 12.02.2022 | 12.02.2022 | 13.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 17.02.2022 | 18.02.2022 | 22.02.2022 | 23.02.2022 | 24.02.2022 | 25.02.2022 | 01.03.2022 | 02.03.2022 | 02.03.2022 | 02.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNITS TO BE LOADED OUT OF THE PORT TODAY. AWAITING BV NUMBER IN ORDER TO BOOK BV | * UNIT IN OUR BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT IN OUR BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT IN OUR BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT IN OUR BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV TO BE DONE TODAY, TRUCK TO DISPATCH LATER THIS WEEK | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK TO DISPATCH JNB TODAY EN-ROUTE TO BEITBRIDGE | TRUCK IS AT POLOKWANE EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT POLOKWANE ENROUTE MUSINA | * VEHICLE CURRENLTY AT KAROI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT CHINGOLA EN ROUTE KASUMBALESA | * VEHICLE CURRENTLY AT CHINGOLA AWAITING TO DISPATCH | * VEHICLE CURRENTLY AT KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 3 | * VEHICLE CURRENTLY AT WHISKEY DAY 2 | * VEHICLE CURRENTLY AT WHISKEY DAY 3 | * VEHICLE CURRENTLY AT KANYAKHA AWAITING FINAL RELEASE | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022
BA1749 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00282 | CAT00374PRGM00282 | E4T00390 | FML2201DSI1394 | COD 2022 116 834 | CR84FXGP | WGR358GP . WGR365GP | ND60788 | 02.02.2022 | * OFFLOADED 23.02.2022 | 28.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 03.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 11.02.2022 | 11.02.2022 | 12.02.2022 | 12.02.2022 | 12.02.2022 | 12.02.2022 | 13.02.2022 | 13.02.2022 | 13.02.2022 | 13.02.2022 | 13.02.2022 | 14.02.2022 | 18.02.2022 | 18.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNITS TO BE LOADED OUT OF THE PORT TODAY. BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * VEHICLE CURRENLTY AT MOOIRIVIER ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT VAN REENENS'S PASS WAITING PERMIT | * VEHICLE CURRENLTY AT PRETORIA ENROUTE MUSINA | TRUCK IS AT POLOKWANE EN ROUTE TO BEITBRIDGE | TRUCK IS AT BEITBRIDGE SA SIDE | TRUCK IS AT MASVINGO EN-ROUTE TO HARARE | TRUCK IS AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE TO DISPATCH WHISKEY TODAY | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022
BA1749 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00282 | CAT00374PRGM00282 | E4T00390 | FML2201DSI1394 | COD 2022 116 834 | AJB9 | ACG8207T . ACG8208T | ND60788 | 02.02.2022 | * OFFLOADED 25.02.2022 | 28.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 03.02.2022 | 04.02.2022 | 04.02.2022 | 05.02.2022 | 06.02.2022 | 07.02.2022 | 10.02.2022 | 11.02.2022 | 12.02.2022 | 13.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 18.02.2022 | 24.02.2022 | 25.02.2022 | 25.02.2022 | 25.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNITS TO BE LOADED OUT OF THE PORT TODAY. BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * VEHICLE CURRENTLY AT HOWICK ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | TRUCK IS AT BEITBRIDGE UNDER GOING CLEARANCE | TRUCK IS AT BEITBRIDGE ZIM SIDE | TRUCK TO DISPATCH BEITBRIDGE ZIM TODAY | TRUCK AT BUBI EN-ROUTE TO HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY CROSSING TO KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 5 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 5 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022
BA1752 | 1 X NEW CAT 426F2 BACHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ404553 | CAT0426FEEJ404553 | CC204800 | FML 2201DSI1402 | COD 2022 121 785 | KH78RYGP | DM68NLGP | ND62904 | 22.02.2022 | OFFLOADED 24.03.2022 | 04.02.2022 | 10.02.2022 | BV WAS NOT VALIDATED ON THE SYSTEM THUS CAUSING DELAYS TO BOOK INSPECTION | 04.02.2022 | 22.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 24.02.2022 | 27.02.2022 | 28.02.2022 | 03.03.2022 | 04.03.2022 | 04.03.2022 | 05.03.2022 | 05.03.2022 | 06.03.2022 | 06.03.2022 | 07.03.2022 | 07.03.2022 | 07.03.2022 | 08.03.2022 | 11.03.2022 | 14.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | * BV INSPECTION BOOKED FOR TODAY 07.02.2022 | * TRUCK AT JNB UNDERGOING TRIP CHECK | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE RSA SIDE | BV COMPLETE, AWAITING FEEDBACK WITH REGARDS TO THE MISSING PIECES | BV COMPLETE, AWAITING FEEDBACK WITH REGARDS TO THE MISSING PIECES | BV COMPLETE, AWAITING FEEDBACK WITH REGARDS TO THE MISSING PIECES | BV COMPLETE, AWAITING FEEDBACK WITH REGARDS TO THE MISSING PIECES | BV COMPLETE, AWAITING FEEDBACK WITH REGARDS TO THE MISSING PIECES | * VEHICLE TO DISPATCH NEXT WEEK | * VEHICLE TO THIS WEEK | * VEHICLE TO DISPTACH THIS WEEK | * VEHICLE TO DISPTACH TODAY EN-ROUET TO BEIRBRIDGE | * TRUCK ARE AT BEITBRIDGE RSA SIDE | * TRUCK ARE AT BEITBRIDGE ZIM SIDE | * TRUCK ARE AT BEITBRIDGE ZIM SIDE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE STILL AT HARARE UNDERGOING MAINTENANCE CHECKS | * DISPATCHED HARARE ENROUTE CHIRUNDU | * VEHCILE ARE CURRENTLY AT CHIRUNDU | * VEHCILE ARE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE AT KASUMBALESA ZAM SIDE | * VEHICLE AT KASUMBALESA ZAM SIDE DAY 3 | * VEHICLE AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 3 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 4 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 5 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 6 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE IS ON SITE AWAITING TO OFFLOAD | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022
BA1753 | 1 X NEW CAT 426F2 BACHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ404554 | CAT0426FCEJ404554 | CC204819 | FML 2201DSI1402 | COD 2022 121 782 | KH78RYGP | DM68NLGP | ND62904 | 22.02.2022 | OFFLOADED 24.03.2022 | 04.02.2022 | 10.02.2022 | BV WAS NOT VALIDATED ON THE SYSTEM THUS CAUSING DELAYS TO BOOK INSPECTION | 04.02.2022 | 22.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 24.02.2022 | 27.02.2022 | 28.02.2022 | 03.03.2022 | 04.03.2022 | 04.03.2022 | 05.03.2022 | 05.03.2022 | 06.03.2022 | 06.03.2022 | 07.03.2022 | 07.03.2022 | 07.03.2022 | 08.03.2022 | 11.03.2022 | 14.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | * BV INSPECTION BOOKED FOR TODAY 07.02.2022 | * TRUCK AT JNB UNDERGOING TRIP CHECK | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE RSA SIDE | BV COMPLETE, TRUCK TO DISPATCH TEUSDAY NEXT WEEK | * BV COMPLETE - AWAITING FEEDBACK ON BA1752 BEFORE VEHICLE CAN DISPATCH | * BV COMPLETE - AWAITING FEEDBACK ON BA1752 BEFORE VEHICLE CAN DISPATCH | * BV COMPLETE - AWAITING FEEDBACK ON BA1752 BEFORE VEHICLE CAN DISPATCH | * BV COMPLETE - AWAITING FEEDBACK ON BA1752 BEFORE VEHICLE CAN DISPATCH | * VEHICLE TO DISPATCH NEXT WEEK | * VEHICLE TO THIS WEEK | * VEHICLE TO DISPTACH THIS WEEK | * VEHICLE TO DISPTACH TODAY EN-ROUET TO BEIRBRIDGE | * TRUCK ARE AT BEITBRIDGE RSA SIDE | * TRUCK ARE AT BEITBRIDGE ZIM SIDE | * TRUCK ARE AT BEITBRIDGE ZIM SIDE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE STILL AT HARARE UNDERGOING MAINTENANCE CHECKS | * DISPATCHED HARARE ENROUTE CHIRUNDU | * VEHCILE ARE CURRENTLY AT CHIRUNDU | * VEHCILE ARE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE AT KASUMBALESA ZAM SIDE | * VEHICLE AT KASUMBALESA ZAM SIDE DAY 3 | * VEHICLE AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 3 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 4 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 5 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE AT WHISKEY AWAIITNG RELEASE - DAY 5 - PLEASE URGNELTY ASSIST WITH CLEARANCE | * VEHICLE IS ON SITE AWAITING TO OFFLOAD | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022 | OFFLOADED 24.03.2022
BA1759 | 1 X 40FT CONTAINER STC 1 X H150 PUMP SET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N.A | XH150-PR-0013 | N.A | FML2112DSI1357 | COD 2021 340 190 | AJB9959 | N.A | ZP071091 | 20.01.2022 | * OFFLOADED 31.01.2022 | 07.01.2022 | 10.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.01.2022 | 11.01.2022 | 11.01.2022 | 11.01.2022 | 12.01.2022 | 12.01.2022 | 13.01.2022 | 14.01.2022 | 15.01.2022 | 15.01.2022 | 15.01.2022 | 15.01.2022 | 16.01.2022 | 16.01.2022 | 17.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 22.01.2022 | 25.01.2022 | 28.01.2022 | 28.01.2022 | 28.01.2022 | 29.01.2022 | 29.01.2022 | 31.01.2022 | [21 empty] | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30.11.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | * PUMPSET TO BE LOADED 05.12.2021 - VESSEL ETD 12.12.2021 | * PUMPSET TO BE LOADED 05.12.2021 - VESSEL ETD 12.12.2021 | * PUMPSET TO BE LOADED 05.12.2021 - VESSEL ETD 12.12.2021 | * PUMPSET TO BE LOADED 08.12.2021 - VESSEL ETD 12.12.2021 | * PUMPSET TO BE LOADED 08.12.2021 - VESSEL ETD 12.12.2021 | * CONTAINER IS LOADED - VESSEL ETD 12.12.2021 | * CONTAINER IS LOADED - VESSEL ETD 12.12.2021 | * CONTAINER IS LOADED - VESSEL ETD 12.12.2021 | * CONTAINER LOADED - AWAITING VESSEL DISPATCH | * VESSEL SAILED 11.12.2021 - CURRENT ETA 29.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 29.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 29.12.2021 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 07.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 07.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 07.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 07.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 06.01.2022-AWAITING VESSEL TO BERTH | * AWAITING VESSEL DISCHARGE IN ORDER TO COLLECT THE CONTAINER | * UNIT IN BONDED FACILITY. BV INSPECTION TO BE BOOKED FOR TOMORROW 11.01.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH FOR POLOKWANE THIS MORNING | * VEHICLE CURRENLTY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT MOKOPANE EN-ROUTE TO GROBLERS BRIDGE | * VEHICLE CURRENLTY AT GROBLERS BRIDGE AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KITWE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE DISPATCHED KASUMBALESA THIS MORNING ENROUTE WHISKEY | * VEHICLE DISPATCHED KASUMBALESA THIS MORNING ENROUTE WHISKEY | * VEHICLE ARRIVED ON SITE 29.01.2022 - AWAITING TO OFFLOAD | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022
BA1762 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06309 LXL01124 LWL04627 | CAT00C15KLXJ06309 | N.A | FML 2110DSI1299 | COD 2021 3041054 | FZ01KZGP | HB35MDGP . HB35MJGP | 2110DSI1299 | 14.12.2021 | * OFFLOADED 28.12.2021 | 18.11.2021 | 06.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 15.12.2021 | 17.12.2021 | 18.12.2022 | 20.12.2021 | 20.12.2021 | 21.12.2022 | 21.12.2022 | 23.12.2022 | 24.12.2022 | 24.12.2022 | 25.12.2022 | 26.12.2022 | 26.12.2022 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 08.01.2022 | 08.01.2021 | 12.01.2022 | [21 empty] | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * CONTAINER CURRENTLY UNDER UNPACK | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE IS AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE IS AT LUBUMBASHI AWAITING OCC DOCUMENTS | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON THE 12.01.2022 | [13 empty] | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021 | * OFFLOADED 28.12.2021
BA1763 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06295 LXL01135 LWL04612 | CAT00C15LLXJ06298 | N.A | FML2110DSI1299 | COD 2021 341054 | FZ01KZGP | HB35MDGP.HB35MJGP | 2110DSI1299 | 14.12.2021 | * OFFLOADED 12.01.2022 | 18.11.2021 | 06.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 15.12.2021 | 17.12.2021 | 18.12.2022 | 20.12.2021 | 20.12.2021 | 21.12.2022 | 21.12.2022 | 23.12.2022 | 24.12.2022 | 24.12.2022 | 25.12.2022 | 26.12.2022 | 26.12.2022 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 08.01.2022 | 08.01.2021 | 12.01.2022 | [21 empty] | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * CONTAINER CURRENTLY UNDER UNPACK | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE IS AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE IS AT LUBUMBASHI AWAITING OCC DOCUMENTS | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON THE 12.01.2022 | [13 empty] | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022
BA1764 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06304 LXL01131 LWL04609 | CAT00C15HLXJ06304 | N.A | FML2110DSI1299 | COD 2021 341054 | FZ01KZGP | HB35MDGP.HB35MJGP | 2110DSI1299 | 14.12.2021 | * OFLOADED 12.01.2022 | 18.11.2021 | 06.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 15.12.2021 | 17.12.2021 | 18.12.2022 | 20.12.2021 | 20.12.2021 | 21.12.2022 | 21.12.2022 | 23.12.2022 | 24.12.2022 | 24.12.2022 | 25.12.2022 | 26.12.2022 | 26.12.2022 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 08.01.2022 | 08.01.2021 | 12.01.2022 | [21 empty] | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * CONTAINER CURRENTLY UNDER UNPACK | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE IS AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE IS AT LUBUMBASHI AWAITING OCC DOCUMENTS | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON THE 12.01.2022 | [13 empty] | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022 | * OFLOADED 12.01.2022
BA1765 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06303 LXL01112 LWL04610 | CAT00C15LLXJ06303 | N.A | FML2110DSI1299 | COD 2021 341054 | AAZ6908 | AAF6831 . AAF6832 | 2110DSI1299 | 14.12.2021 | * OFFLOADED 12.01.2022 | 18.11.2021 | 06.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 15.12.2021 | 17.12.2021 | 18.12.2022 | 20.12.2021 | 20.12.2021 | 21.12.2022 | 21.12.2022 | 23.12.2022 | 24.12.2022 | 24.12.2022 | 25.12.2022 | 26.12.2022 | 26.12.2022 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 08.01.2022 | 08.01.2021 | 12.01.2022 | [21 empty] | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * CONTAINER CURRENTLY UNDER UNPACK | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE IS AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE IS AT LUBUMBASHI AWAITING OCC DOCUMENTS | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON THE 12.01.2022 | [13 empty] | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022
BA1766 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06313 LXL01087 LWL04625 | CAT00C15JLXJ06313 | N.A | FML2110DSI1299 | COD 2021 340196 | AAZ6840 | AAS7146 . AAF6759 | 2110DSI1299 | 14.12.2021 | * OFFLOADED 12.01.2022 | 18.11.2021 | 10.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 16.12.2021 | 20.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 10.01.2022 | 10.01.2022 | 11.01.2022 | 12.01.2022 | 12.01.2022 | [22 empty] | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL ARRIVED 28.11.2021 - VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL ARRIVED 28.11.2021 - VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | 2201DSE1391 | [40 empty] | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022
BA1767 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06302 LXL01104 LWL04611 | CAT00C15ALXJ06302 | N.A | FML2110DSI1299 | COD 2021 3041054 | FZ01KZGP | HB35MDGP.HB35MJGP | 2110DSI1299 | 14.12.2021 | * OFLOADED 28.12.2021 | 18.11.2021 | 06.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 15.12.2021 | 17.12.2021 | 18.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2022 | 21.12.2022 | 23.12.2022 | 24.12.2022 | 24.12.2022 | 25.12.2022 | 26.12.2022 | 26.12.2022 | 26.12.2021 | 26.12.2021 | 29.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 08.01.2022 | 08.01.2021 | 12.01.2022 | [22 empty] | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * CONTAINER CURRENTLY UNDER UNPACK | * BV INSPECTION BOOKED FOR MONDAY 06.12.2021 | * BV INSPECTION BOOKED FOR TODAY THE 06.12.2021 | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH BY THE END OF THE WEEK | BV INSPECTION DONE. TRUCK TO DISPATCH MONDAY | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE EN-ROUTE TO TENKE | * VEHICLE IS AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE IS AT LUBUMBASHI AWAITING OCC DOCUMENTS | * VEHICLE IS AT SABOT FACILITY LUBUMBASHI AWAITING OCC DOCUMENTS IN ORDER TO DISPATCH TO CONGO EQUIPMENT | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | * VEHICLE ON SITE (TFM) WAITING TO OFFLOAD | OFFLOADED ON THE 12.01.2022 | [13 empty] | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021 | * OFLOADED 28.12.2021
BA1768 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06312 LXL01133 LWL04623 | CAT00C15KLXJ06312 | N.A | FML2110DSI1299 | COD 2021 340196 | AAZ6908 | AAF6831 . AAF6832 | 2110DSI1299 | 14.12.2021 | * OFFLOADED 12.01.2022 | 18.11.2021 | 10.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 16.12.2021 | 20.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 10.01.2022 | 10.01.2022 | 11.01.2022 | 12.01.2022 | 12.01.2022 | [22 empty] | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX MAERSK HANGZHOU TO ARRIVE DURBAN PORT-ETA 04.12.2021 | ND62958 | [40 empty] | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * OFFLOADED 12.01.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | OFFLOADED 12.01.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022
BA1769 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06310 LXL01129 LWL04626 | CAT00C15TLXJ06310 | N.A | FML 2110DSI1312 | COD 2021 327230 | AAZ6840 | AAS7146 . AAF6759 | 2110DSI1312 | 14.12.2021 | * OFFLOADED 12.01.2022 | 18.11.2021 | 10.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 16.12.2021 | 20.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 10.01.2022 | 10.01.2022 | 11.01.2022 | 12.01.2022 | 12.01.2022 | [22 empty] | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | 2201DSE1391 | [40 empty] | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022
BA1770 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06308 LXL01123 LWL04624 | CAT00C15PLXJ06308 | N.A | FML2110DSI1299 | COD 2021 341054 | AAZ6840 | AAS7146 . AAF6759 | 2110DSI1299 | 14.12.2021 | * OFFLOADED 12.01.2022 | 18.11.2021 | 10.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE. BV OFFICE WAS EXTREMELY BUSY | 28.11.2021 | 14.12.2021 | 15.12.2021 | 16.12.2021 | 20.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 10.01.2022 | 10.01.2022 | 11.01.2022 | 12.01.2022 | 12.01.2022 | [22 empty] | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * AWAITING VESSEL ARRIVAL . MAERSK HOUSTON - CURRENT ETA 27.11.2021 | * VESSEL ARRIVED 28.11.2021 - VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * WAITING FOR PORT BOOKING IN ORDER TO COLLECT CONTAINER FROM PORT | #REF! | [40 empty] | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022
BA1771 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ06311 LXL01111 LWL04613 | CAT00C15PLXJ06311 | N.A | FML 2110DSI1312 | COD 2021 327230 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1312 | 14.12.2021 | * OFFLOADED 12.01.2022 | 03.11.2021 | 13.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 15.12.2021 | 16.12.2021 | 20.12.2021 | 20.12.2021 | 20.12.2021 | 21.12.2021 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 29.12.2021 | 29.12.2021 | 29.12.2021 | 10.01.2022 | 10.01.2022 | 11.01.2022 | 12.01.2022 | 12.01.2022 | [22 empty] | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04.12.2021 | 2201DSE1391 | [40 empty] | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | OFFLOADE 12.01.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | OFFLOADED 12.01.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | OFFLOADED 12.01.2022 | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022 | * OFFLOADED 12.01.2022
BA1792 | 1 X CAT 307 EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ZGC03002 | CAT00307HZGC03002 | N.A | FML2112DSI1362 | COD 2021 351 497 | AJB9958 | N.A | 2112DSI1362 | 13.01.2022 | * OFFLOADED 31.01.2022 | 06.01.2022 | 12.01.2022 | BV WAS NOT VALIDATED ON THE SYSTEM THUS CAUSING DELAYS TO BOOK INSPECTION | 04.01.2022 | 13.01.2022 | 13.01.2022 | 13.01.2022 | 14.01.2022 | 14.01.2022 | 14.01.2022 | 15.01.2022 | 16.01.2022 | 16.01.2022 | 16.01.2022 | 16.01.2022 | 16.01.2022 | 16.01.2022 | 17.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2021 | 19.01.2022 | 28.01.2022 | 28.01.2022 | 28.01.2022 | 29.01.2021 | 29.01.2022 | 31.01.2022 | [36 empty] | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL GENUINE ACE TO ARRIVE ON THE 29.12.2021 | * AWAITING VESSEL GENUINE ACE TO ARRIVE ON THE 29.12.2021 | * AWAITING VESSEL GENUINE ACE TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL GENUINE ACE TO ARRIVE ON THE 04.01.2022 | *MACHINE AT OUR FACILITY AWAITING BV LICENCE TO BE VALIDATED | *MACHINE AT OUR FACILITY AWAITING BV LICENCE TO BE VALIDATED IN ORDER TO BOOK BV INSPECTION | *MACHINE AT OUR FACILITY AWAITING BV LICENCE TO BE VALIDATED IN ORDER TO BOOK BV INSPECTION | *MACHINE AT OUR FACILITY AWAITING BV LICENSE TO BE VALIDATED IN ORDER TO BOOK BV INSPECTION | *MACHINE AT OUR FACILITY AWAITING BV LICENSE TO BE VALIDATED IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION BOOKED FOR TODAY | * TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | * TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE | * VEHICLE CURRENLTY AT LIVINGSTONE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KABWE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE DISPATCHED KASUMBALES THIS MORNING ENROUTE WHISKEY | * VEHICLE DISPATCHED KASUMBALES THIS MORNING ENROUTE WHISKEY | * VEHICLE ARRIVED ON SITE 29.01.2022 - AWAITING TO OFFLOAD | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022 | * OFFLOADED 31.01.2022
BA1803 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00284 | CAT00374JRGM00284 | N.A | FML2201DSI1387 | COD 2022 119813 | ND754967 | ND476150 . ND654346 | ND60776 | 03.02.2022 | * OFFLOADED 23.02.2022 | 31.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 28.01.2022 | 03.02.2022 | 06.02.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 11.02.2022 | 11.02.2022 | 11.02.2022 | 12.02.2022 | 12.02.2022 | 13.02.2022 | 13.02.2022 | 13.02.2022 | 14.02.2022 | 18.02.2022 | 18.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETD-26.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETD-26.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | * LOADING UNIT FROM PORT TODAY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNITS TO BE LOADED OUT OF THE PORT TODAY. BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * VEHICLE DISPATCHING DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT VAN REENENS'S PASS WAITING PERMIT | * VEHICLE CURRENTLY AT BELA BELA ENROUTE MUSINA | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | TRUCK AT BEITBRIDGE ZIM SIDE | TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE - DAY 4 | * VEHICLE AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE TO DISPATCH WHISKEY TODAY | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022
BA1803 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00284 | CAT00374JRGM00284 | N.A | FML2201DSI1387 | COD 2022 119813 | AEG5410 | AEZ3935 . AEZ3924 | ND60776-2 | 03.02.2022 | * OFFLOADED 28.02.2022 | 31.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 28.01.2022 | 03.02.2022 | 05.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 12.02.2022 | 13.02.2022 | 14.02.2022 | 18.02.2022 | 18.02.2022 | 25.02.2022 | 26.02.2022 | 26.02.2022 | 28.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETD-26.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETD-26.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | * LOADING UNIT FROM PORT TODAY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNITS TO BE LOADED OUT OF THE PORT TODAY. BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * VEHICLE DISPATCHING DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MOOI RIVIER ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT VAN REENENS PASS ENROUTE JOHANNESBURG | TRUCK AT CHIRUNDU ZIM SIDE | TRUCK AT CHIRUNDU ZAM SIDE | TRUCK AT KAFUE EN-ROUTE KASUMBALESA | TRUCK AT KITWE EN-ROUTE KASUMBALESA | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE - DAY 4 | * VEHICLE AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE AT WHISKEY AWAITING FINAL RELEASE DAY 5 | * VEHICLE AT WHISKEY AWAITING FINAL RELEASE DAY 6 | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1807 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20882 | CAT00330VFEK20882 | E7A48448 | FML 2111DSI1322 | COD 2021 340192 | ND834401 | ND854241 | ND60172 | 29.11.2021 | * OFFLOADED 15.12.2021 | 18.11.2021 | 25.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 25.11.2021 | 29.11.2021 | 30.11.2021 | 01.12.2021 | 02.12.2021 | 02.12.2021 | 03.11.2021 | 06.12.2021 | 06.12.2021 | 06.12.2021 | 07.12.2021 | 07.12.2021 | 07.12.2021 | 08.12.2021 | 08.12.2021 | 08.12.2021 | 09.12.2021 | 09.12.2021 | 10.12.2021 | 10.12.2021 | 12.12.2021 | 13.12.2021 | 13.12.2021 | 15.12.2021 | 15.12.2021 | 15.12.2021 | [22 empty] | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | #REF! | [40 empty] | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021
BA1808 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20881 | CAT00330CFEK20881 | E7A48442 | FML 2111DSI1322 | COD 2021 340192 | ND730794 | ND443606 | ND60173 | 29.11.2021 | * OFFLOADED 15.12.2021 | 18.11.2021 | 25.11.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 25.11.2021 | 30.11.2021 | 01.12.2021 | 01.12.2021 | 01.12.2021 | 02.12.2021 | 03.11.2021 | 06.12.2021 | 06.12.2021 | 06.12.2021 | 07.12.2021 | 07.12.2021 | 07.12.2021 | 07.12.2021 | 08.12.2021 | 09.12.2021 | 09.12.2021 | 09.12.2021 | 10.12.2021 | 10.12.2021 | 12.12.2021 | 12.12.2021 | 13.12.2021 | 15.12.2021 | 15.12.2021 | 15.12.2021 | [22 empty] | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VESSEL JASPER ARROW DUE TO ARRIVE TODAY. TRUCKS PLACED ALONG SIDE VESSEL. VESSEL IS IN AND WORKING | * VEHICLE CURRENTLY AT POLOKWANE ENROUTE BEITBRIDGE | * VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | #REF! | [40 empty] | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021 | * OFFLOADED 15.12.2021
BA1809 | 1 X CAT M317D2 WHEEL EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CA600772 | CATM317DACA600772 | 2W229537 | FML 2110DS1290 | COD 2021 319611 | JR76FMGP | CF23JHGP | ND601026 | 03.11.2021 | OFFLOADED 25.11.2021 | 18.11.2021 | 29.10.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 29.10.2021 | 04.11.2021 | 05.11.2021 | 05.11.2021 | 06.11.2021 | 06.11.2021 | 06.11.2021 | 07.11.2021 | 07.11.2021 | 08.11.2021 | 11.11.2021 | 11.11.2021 | 11.11.2021 | 11.11.2021 | 12.11.2021 | 12.11.2021 | 13.11.2021 | 14.11.2021 | 15.11.2021 | 15.11.2021 | 17.11.2021 | 18.11.2021 | 18.11.2021 | 19.11.2021 | 25.11.2021 | 25.11.2021 | [22 empty] | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | [40 empty] | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021 | OFFLOADED 25.11.2021
BA1820 | 1 X CAT D13.5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB903931 W2203899 TT904820 | 4512481 4488966 5849904 | N.A | FML2111DSI1351 | COD 2021 365 065 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 23.12.2021 | 11.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.01.2022 | 21.01.2022 | 21.01.202 | 21.01.2022 | 22.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2021 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [30 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING. AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18.01.2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHILCE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENLTY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1821 | 1 X CAT D13.5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB903930 W2203900 TT904819 | 4512481 4488966 5849904 | N.A | FML2111DSI1351 | COD 2021 365 065 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 23.12.2021 | 11.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.01.2022 | 21.01.2022 | 21.01.202 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2021 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [30 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING. AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18.01.2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHILCE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENLTY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1822 | 1 X CAT D13.5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB903929 W2203901 TT904821 | 4512481 4488966 5849904 | N.A | FML2111DSI1351 | COD 2021 365 065 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 23.12.2021 | 11.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.01.2022 | 21.01.2022 | 21.01.202 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2021 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [30 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING. AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18.01.2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHILCE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENLTY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1823 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY12582 SM812755 TT800314 | 4512485 4489035 5849908 | N.A | FML2111DSI1351 | COD 2021 366 245 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 23.12.2021 | 11.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.01.2022 | 21.01.2022 | 21.01.202 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2021 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [30 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING. AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18.01.2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHILCE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENLTY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1824 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY12581 SM812756 TT800315 | 4512485 4489035 5849908 | N.A | FML2111DSI1351 | COD 2021 366 245 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 23.12.2021 | 11.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.01.2022 | 21.01.2022 | 21.01.202 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2021 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [30 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING. AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18.01.2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHILCE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENLTY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1825 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY12580 SM812754 TT800299 | 4512485 4489035 5849908 | N.A | FML2111DSI1351 | COD 2021 366 245 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 23.12.2021 | 11.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.01.2022 | 21.01.2022 | 21.01.202 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2021 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [30 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING. AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18.01.2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KITWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHILCE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENLTY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1826 | 1 X CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC305481 E3S11219 M2502007 | CAT00C33JEC305481 | N.A | FML 2110DSI1311 | COD 2021 325082 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | OFFLOADED 12.01.2022 | 03.11.2021 | 07.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 16.12.2021 | 16.12.2021 | 17.12.2021 | 19.12.2021 | 20.12.2021 | 21.12.2022 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | [21 empty] | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022 | [13 empty] | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022
BA1827 | 1 X CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC305482 E3S11218 M2502008 | CAT00C33CEC305482 | N.A | FML 2110DSI1311 | COD 2021 325082 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | OFFLOADED 12.01.2022 | 03.11.2021 | 07.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 16.12.2021 | 16.12.2021 | 17.12.2021 | 19.12.2021 | 20.12.2021 | 21.12.2022 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | [21 empty] | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022 | [13 empty] | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022
BA1828 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC507210 E3S11314 M2502015 | CAT00C33VEC507210 | N.A | FML 2110DSI1311 | COD 2021 325079 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | OFFLOADED 12.01.2022 | 03.11.2021 | 07.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 16.12.2021 | 16.12.2021 | 17.12.2021 | 19.12.2021 | 20.12.2021 | 21.12.2022 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | [21 empty] | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022 | [13 empty] | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022
BA1829 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC507209 E3S11318 M2502018 | CAT00C33LEC507209 | N.A | FML 2110DSI1311 | COD 2021 325079 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | OFFLOADED 12.01.2022 | 03.11.2021 | 07.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 16.12.2021 | 16.12.2021 | 17.12.2021 | 19.12.2021 | 20.12.2021 | 21.12.2022 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | [21 empty] | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022 | [13 empty] | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022
BA1830 | 1 X CAT C13 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403696 PWE05873 LWL04851 | 4215066 3932805 5029779 | N.A | FML2111DSI1351 | COD 2021 351 494 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 23.12.2021 | 11.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.01.2022 | 21.01.2022 | 21.01.202 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2022 | 29.01.2022 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [30 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING. AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18.01.2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19.01.2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHILCE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENLTY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1831 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01439 KRG10140 M2700187 | CAT00C71JGTY01439 | N.A | FML 2110DSI1311 | COD 2021 324956 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | OFFLOADED 12.01.2022 | 03.11.2021 | 07.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 16.12.2021 | 16.12.2021 | 17.12.2021 | 19.12.2021 | 20.12.2021 | 21.12.2022 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | [21 empty] | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022 | [13 empty] | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022
BA1832 | 1 X CAT DE165E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW05520 KRG10311 M2802398 | CAT00C71VECW05520 | N.A | FML 2110DSI1311 | COD 2021 325685 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | OFFLOADED 12.01.2022 | 03.11.2021 | 07.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 16.12.2021 | 16.12.2021 | 17.12.2021 | 19.12.2021 | 20.12.2021 | 21.12.2022 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | [21 empty] | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022 | [13 empty] | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022
BA1833 | 1 X CAT DE165E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M2802417 ECW05521 KRG10312 | CAT00C71AECW05521 | N.A | FML 2110DSI1311 | COD 2021 325685 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | OFFLOADED 12.01.2022 | 03.11.2021 | 07.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 16.12.2021 | 16.12.2021 | 17.12.2021 | 19.12.2021 | 20.12.2021 | 21.12.2022 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | [21 empty] | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022 | [13 empty] | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022
BA1834 | 1 X CAT DE165E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW05522 KRG10306 M2802399 | CAT00C71LECW05522 | N.A | FML 2110DSI1311 | COD 2021 325685 | AAZ6810 | AAS7178 . AAS7179 | 2110DSI1311 | 14.12.2021 | OFFLOADED 12.01.2022 | 03.11.2021 | 07.12.2021 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.12.2021 | 14.12.2021 | 16.12.2021 | 16.12.2021 | 17.12.2021 | 19.12.2021 | 20.12.2021 | 21.12.2022 | 23.12.2021 | 24.12.2021 | 26.12.2021 | 26.12.2021 | 26.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 27.12.2021 | 30.12.2021 | 30.12.2021 | 30.12.2021 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | 12.01.2022 | [21 empty] | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 30.11.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL SHIMIN - VOY. 21007W ARRIVAL . CURRENT ETA 02.12.2021 | * WAITING VESSEL COSCO AQABA - VOY. 062W ARRIVAL . CURRENT ETA 04.12.2021 | *VESSEL COSCO AQABA - VOY. 062W IS IN AND WORKING-AWAITING CONTAINER TO BE LOADED FROM PORT | *THE CONTAINER IS AT OUR FACILITY AWAITING UNPACK. BV INSPECTION BOOK FOR TOMMROW | *BV INSPECTION WILL BE DONE TODAY AND TRUCK WILL DISPATCH LATER THIS WEEK | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | *BV INSPECTION DONE.TRUCK TO DISPATCH MONDAY THE 13.12.2021 | * VEHICLE PLANNING TO DISPATCH THIS AFTERNOON - ENROUTE JOHANNESBURG FACILITY FOR FINAL TRIP CHECK | * VEHICLE AT JOHANNESBURG FACILITY UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MARBLEHALL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY DISPATCHING HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - TO DISPATCH TO LUBUMBASHI TODAY | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 8-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 11-WAITING OCC STAMP | * VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE - DAY 12-WAITING OCC STAMP | * VEHICLE ON SITE (LUB) WAITING TO OFFLOAD | * OFFLOADED 12.01.2022 | [13 empty] | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022 | OFFLOADED 12.01.2022
BA1839 | 1 X CAT 140GC 01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201005 | CAT00140LW9201005 | E7A48161 | FML2112DSI1365 | COD 2021 367 761 | ND66858 | ND700343 | ND60735 | 06.01.2022 | * OFFLOADED 26.01.2022 | 18.12.2021 | 03.01.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.12.2021 | 06.01.2022 | 07.01.2022 | 07.01.2022 | 08.01.2022 | 09.01.2022 | 10.01.2022 | 11.01.2022 | 12.01.2022 | 12.01.2022 | 13.01.2022 | 13.01.2022 | 13.01.2022 | 13.01.2022 | 14.01.2022 | 14.01.2022 | 15.01.2022 | 16.01.2022 | 17.01.2022 | 18.01.2022 | 20.01.2022 | 20.01.2022 | 21.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | [44 empty] | * AWAITING VESSEL MORNING COURIER 155 TO ARRIVE ON THE 29.12.2021 | * AWAITING VESSEL MORNING COURIER 155 TO ARRIVE ON THE 29.12.2021 | * AWAITING VESSEL MORNING COURIER 155 TO ARRIVE ON THE 30.12.2021 | * AWAITING VESSEL MORNING COURIER 155 TO ARRIVE ON THE 30.12.2021 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD | BV BOOKED FOR TODAY. AWAITING DISPATCH | TRUCK TO DISPATCH TOMMROW THE 06.01.2022 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEANCE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE UNDERGOING CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE UNDERGOING CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT KITWE EN-ROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITNG CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITNG CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITNG RELEASE DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022 | * OFFLOADED 26.01.2022
BA1850 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00281 | CAT00374TRGM00281 | E4T00427 | FML2201DSI1394 | COD 2022 106 071 | WMN927GP | BG55CXGP . BG37PLGP | ND60789 | 16.02.2022 | * OFFLOADED 07.03.2022 | 20.01.2022 | 04.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 15.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 19.02.2022 | 20.02.2022 | 22.02.2022 | 24.02.2022 | 24.02.2022 | 25.02.2022 | 25.02.2022 | 26.02.2022 | 26.02.2022 | 27.02.2022 | 28.02.2022 | 28.02.2022 | 28.02.2022 | 28.02.2022 | 01.03.2022 | 03.03.2022 | 04.03.2022 | 06.03.2022 | 07.03.2022 | 07.03.2022 | 07.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNITS TO BE LOADED OUT OF THE PORT TODAY. BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 03.02.2022 | * BV INSPECTION BOOKED FOR TODAY 04.02.2022 | * VEHICLE UNDERGOING FINAL TRIP CHECK TO DISPATCH TUESDAY 08.02.2022 | * VEHICLE UNDERGOING FINAL TRIP CHECK TO DISPATCH WEDNESDAY 09.02.2022 | * VEHICLE ON BREAKDOWN, TRUCK TO DISPATCH END OF NEXT WEEK ONCE REPAIRS HAS BEEN RECEIVED | * VEHICLE ON BREAKDOWN, TRUCK TO DISPATCH END OF NEXT WEEK ONCE REPAIRS HAS BEEN RECEIVED | * VEHICLE ON BREAKDOWN, TRUCK TO DISPATCH END OF NEXT WEEK ONCE REPAIRS HAS BEEN RECEIVED | * VEHICLE ON BREAKDOWN, TRUCK TO DISPATCH AS SOON AS REPAIRS ARE COMPLETE | * VEHICLE TO DIPATCH DURBAN TODAY | * VEHICLE CURRENLTY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT CATO RIDGE ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT HENDRINA ENROUTE MUSINA | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT CHIBI EN-ROUTE HARARE | * VEHICLE CURRENTLY AT BEATRICE EN-ROUTE HARARE | * VEHICLE CURRENTLY AT KAROI EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM | * VEHICLE CURRENTLY AT CHIRUNDU ZAM | * VEHICLE CURRENTLY AT CHISAMBA EN-ROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY DAY 2 | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022 | * OFFLOADED 07.03.2022
BA1850 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00281 | CAT00374TRGM00281 | E4T00427 | FML2201DSI1394 | COD 2022 106 071 | ABJ6132 | ACE5852T . ACE5874T | ND60789-2 | 04.02.2022 | * OFFLOADED 02.03.2022 | 20.01.2022 | 04.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 04.02.2022 | 05.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 25.02.2022 | 25.02.2022 | 01.03.2022 | 02.03.2022 | 02.03.2022 | 02.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNITS TO BE LOADED OUT OF THE PORT TODAY. BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 03.02.2022 | * BV INSPECTION BOOKED FOR TODAY 04.02.2022 | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE | * VEHICLE TO DISPATCH BEIRBRIDGE ZIM TODAY | * VEHICLE AT BUBI EN-ROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHINGOLA AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENLTY AT WHISKEY - DAY 3 | * VEHICLE CURRENLTY AT WHISKEY - DAY 4 | * VEHICLE CURRENLTY AT KANYAKA AWAITING RELEASE | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022 | * OFFLOADED 02.03.2022
BA1851 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00283 | CAT00374KRGM00283 | E4T00382 | FML2201DSI1394 | COD 2022 106 071 | JP79VKGP | CS71TPGP . CS88PXGP | ND60790 | 06.02.2022 | OFFLOADED 23.02.2022 | 20.01.2022 | 04.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 06.02.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 11.02.2022 | 11.02.2022 | 11.02.2022 | 12.02.2022 | 12.02.2022 | 12.02.2022 | 12.02.2022 | 13.02.2022 | 13.02.2022 | 13.02.2022 | 13.02.2022 | 14.02.2022 | 18.02.2022 | 18.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNITS TO BE LOADED OUT OF THE PORT TODAY. BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 03.02.2022 | * BV INSPECTION BOOKED FOR TODAY 04.02.2022 | * VEHILCE CURRENTLY AT VILLIERS ENROUTE JOHANNESBURG | * VEHILCE CURRENTLY AT POLOKWANE EN ROUTE BEIT BRIDGE | * VEHILCE CURRENTLY AT BEIT BRIDGE RSA SIDE | * VEHILCE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHILCE CURRENTLY AT HARARE EN-ROUTE CHIRUNDU | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE TO DISPATCH WHISKEY TODAY | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1851 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00283 | CAT00374KRGM00283 | E4T00382 | FML2201DSI1394 | COD 2022 106 071 | ACE5887 | ACE7427T . ACE7453T | ND60790-2 | 04.02.2022 | * OFFLOADED 28.02.2022 | 20.01.2022 | 04.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 04.02.2022 | 05.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 11.02.2022 | 12.02.2022 | 12.02.2022 | 13.02.2022 | 13.02.2022 | 14.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 18.02.2022 | 18.02.2022 | 18.02.2022 | 21.02.2022 | 21.02.2022 | 28.02.2022 | 28.02.2022 | 28.02.2022 | 28.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNITS TO BE LOADED OUT OF THE PORT TODAY. BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 03.02.2022 | * BV INSPECTION BOOKED FOR TODAY 04.02.2022 | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHILCE CURRENTLY AT BEIT BRIDGE RSA SIDE | * VEHILCE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHILCE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | TRUCK AT WHISKEY DAY 4 | TRUCK AT WHISKEY DAY 5 | TRUCK AT WHISKEY DAY 5 | TRUCK AT WHISKEY DAY 5 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1859 | 1 X CAT M317D2 WHEEL EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CA600785 | CATM317DVCA600785 | 2W230458 | FML2022106071 | COD 2022 116828 | ND142761 | ND542263 | ND60780 | 14.02.2022 | * OFFLOADED 04.03.2022 | 04.02.2022 | 09.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 14.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 18.02.2022 | 19.02.2022 | 19.02.2022 | 19.02.2022 | 20.02.2022 | 20.02.2022 | 21.02.2022 | 21.02.2022 | 22.02.2022 | 22.02.2022 | 01.02.2022 | 02.03.2022 | 03.03.2022 | 04.03.2022 | 04.03.2022 | 04.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER TIN ORDER TO BOOK INSPECTION | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER TIN ORDER TO BOOK INSPECTION | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV INSPECTION BOOKED FOR TUESDAY 08.02.2022 | * BV INSPECTION BOOKED FOR TUESDAY 09.02.2022 | * BV INSPECTION BOOKED FOR TOMMOROW THE 10.02.2022 | * BV INSPECTION BOOKED FOR TODAY, TRUCK TO DISPATCH MONDAY | * BV DONE, TRUCK TO DISPATCH MONDAY | * VEHICLE DISPATCHING DURBAN TODAY | * VEHICLE DISPATCHING DURBAN TODAY | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAROI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT KAROI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT KASUMBALESA ZAM | * VEHICLE CURRENTLY AT KASUMBALESA ZAM DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | * VEHICLE AT WHISKEY AWAITING DUTIES TO BE PAID | * VEHICLE AT WHISKEY AWAITING DUTIES TO BE PAID | * VEHICLE AT LUBUMBASHI EN-ROUTE TO SITE | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022 | * OFFLOADED 04.03.2022
BA1862 | 1 X NEW CAT CS74B VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | B7M00373 | CATCS74BJB7M00373 | E7A47739 | FML2111DSI1324 | COD 2021 351497 | JR76FMGP | KH82PCGP | ND60722 | 11.01.2022 | * OFFLOADED 24.01.2022 | 11.01.2022 | 11.01.2022 | BV WAS NOT VALIDATED ON THE SYSTEM THUS CAUSING DELAYS TO BOOK INSPECTION | 12.12.2021 | 22.12.2021 | 22.12.2021 | 22.12.2021 | 23.12.2021 | 23.12.2021 | 24.12.2021 | 27.12.2021 | 28.12.2021 | 28.12.2021 | 29.12.2021 | 29.12.2021 | 30.12.2021 | 01.01.2022 | 02.01.2022 | 02.01.2022 | 03.01.2022 | 04.01.2022 | 05.01.2022 | 05.01.2022 | 09.01.2022 | 09.01.2022 | 10.01.2022 | 18.01.2022 | 18.01.2022 | 21.01.2022 | 24.01.2022 | [20 empty] | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 10.12.2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 12.12.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY - AWAIITNG BV NUMBER TO BOOK BV INSPECTION | * UNIT IN BONDED FACILITY - AWAIITNG BV NUMBER TO BOOK BV INSPECTION | * TRUCK TO DISPATCH TODAY-EN-ROUTE TO BEITBRIDGE | * TRUCK AT JOHANNEBSURG AWAITING DISPATCH | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | * VEHICLE AT KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE BY BOLLORE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE BY BOLLORE FOR THE HANDRAIL DAY 4 | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY AT LIKASI EN-ROUTE TO SITE | * VEHICLE CURRENTLY AT KOLWEZI EN-ROUTE TO SITE | OFFLOADED 21.01.2022 | * ON SITE WAITING TO OFFLOAD | * OFFLOADED 24.01.2022 | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | 0 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 21.01.2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 21.01.2022 | OFFLOADED 21.01.2022 | OFFLOADED 21.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022
BA1891 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JFW20940 | CAT00336HJFW20940 | E7A43844 | FML2201DSI1386 | COD 2022 116828 | HW42JWGP | KB50CHGP | ND60773 | 03.02.2022 | * OFFLOADED 28.02.2022 | 31.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 03.02.2022 | 06.02.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 18.02.2022 | 18.02.2022 | 25.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * VEHICLE CURRENLTY AT MOOIRIVIER ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT VAN REENEN'S PASS AWAITING PERMIT | * VEHICLE CURRENTLY AT BELA BELA ENROUTE MUSINA | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT MASVINGO EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING CHIRUNDU ZAM | * VEHICLE AT CHIRUNDU ZAM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE DAY 12 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE DAY 14 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE DAY 14 IN DRC | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1892 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JFW20941 | CAT00336EJFW20941 | E7A43821 | FML2201DSI1400 | COD 2022 116828 | KB15KRGP | JD77VMGP | ND62916 | 07.02.2022 | * OFFLOADED 23.02.2022 | 31.01.2022 | 04.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 01.02.2022 | 07.02.2022 | 10.02.2022 | 11.02.2022 | 12.02.2022 | 13.02.2022 | 14.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 18.02.2022 | 18.02.2022 | 18.02.2022 | 18.02.2022 | 19.02.2022 | 19.02.2022 | 19.02.2022 | 19.02.2022 | 20.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL DUE TO ARRIVE ON THE 31.01.2022 | VESSEL DUE TO ARRIVE ON THE 31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONSIDE TO LOAD | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONSIDE TO LOAD | * BV INSPECTION BOOKED FOR TODAY 04.02.2022 | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE AT MOOIRIVER EN ROUTE JOHANNESBURG | * VEHICLE AT HARRISMITH EN ROUTE JOHANNESBURG | * VEHICLE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAROI ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE TO DISPATCH WHISKEY TODAY EN-ROUTE TO SITE | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022 | * OFFLOADED 23.02.2022
BA1896 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JFW20946 | CAT00336JJFW20946 | E7A43868 | FML2201DSI1386 | COD 2022 116828 | JT84DPGP | BB38WPGP | ND60774 | 03.02.2022 | * OFFLOADED 25.02.2022 | 31.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 03.02.2022 | 06.02.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 18.02.2022 | 18.02.2022 | 19.02.2022 | 19.02.2022 | 19.02.2022 | 20.02.2022 | 21.02.2022 | 23.02.2022 | 24.02.2022 | 25.02.2022 | 25.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | COMMENTS 01.02.2022+DI1 | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * VEHICLE CURRENLTY AT VAN REENEN'S PASS ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT VAN REENEN'S PASS AWAITING PERMIT | * VEHICLE CURRENTLY AT BELA BELA ENROUTE MUSINA | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT MASVINGO EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING CHIRUNDU ZAM SIDE | * VEHICLE AT CHIRUNDU ZAM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE DAY 5 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE DAY 6 IN DRC | * ON SITE AWAITING TO OFFLOAD | * ON SITE AWAITING TO OFFLOAD | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022
BA1897 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JFW20945 | CAT00336KJFW20945 | E7A43876 | FML2201DSI1386 | COD 2022 116828 | KB15KRGP | JD77VMGP | ND60775 | 03.02.2022 | * OFFLOADED 25.02.2022 | 31.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 03.02.2022 | 06.02.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 11.02.2022 | 11.02.2022 | 11.02.2022 | 11.02.2022 | 11.02.2022 | 12.02.2022 | 12.02.2022 | 12.02.2022 | 13.02.2022 | 13.02.2022 | 14.02.2022 | 18.02.2022 | 18.02.2022 | 23.02.2022 | 24.02.2022 | 25.02.2022 | 25.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * VEHICLE CURRENLTY AT VAN REENEN'S PASS ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT VAN REENEN'S PASS AWAITING PERMIT | * VEHICLE CURRENTLY AT BELA BELA ENROUTE MUSINA | * VEHICLE CURRENTLY AT MUSINA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT HARARE EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT KAFUE EN-ROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE DAY 5 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE DAY 6 IN DRC | * ON SITE AWAITING TO OFFLOAD | * ON SITE AWAITING TO OFFLOAD | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022 | * OFFLOADED 25.02.2022
BA1898 | 1 X NEW CAT 336 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GDY12108 | CAT00336TGDY12108 | NTB05475 | FML2111DSI1325 | COD 2021 340189 | ND834401 | ND854241 | ND60200 | 17.01.2022 | * OFFLOADED 24.01.2022 | 18.12.2021 | 17.12.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 12.12.2021 | 06.01.2022 | 07.01.2022 | 07.01.2022 | 08.01.2022 | 09.01.2022 | 10.01.2022 | 13.01.2022 | 14.01.2022 | 14.01.2022 | 15.01.2022 | 15.01.2022 | 15.01.2022 | 15.01.2022 | 16.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2022 | 19.01.2022 | 20.01.2022 | 20.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 24.01.2022 | [22 empty] | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06.12.2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 12.12.2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * BV INSPECTION BOOKED FOR FRIDAY 17.12.2021 | * BV INSPECTION BOOKED FOR TODAY 17.12.2021 | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * TRUCK TO DISPATCH THE 06.01.2022 | * TRUCK TO DISPATCH THE 06.01.2022 | * TRUCK TO DISPATCH TOMORROW THE 06.01.2022 | * TRUCK AT HOWICK EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT MASVINGO EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT SIAVONGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITNG RELEASE | * VEHILCE ON SITE WAITING TO OFFLIOAD | * OFFLOADED 24.01.2022 |  |  |  |  | 0 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 24.01.2022 | 0 | 0 | 0 | 0 | 0 | 0 | * OFFLOADED 24.02.2022 | 0 | 0 | OFFLOADED 24.01.2022 | 0 | 0 | 0 | 0 | 0 | OFFLOADED 24.01.2022 | OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022 | * OFFLOADED 24.01.2022
BA1899 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GDY12127 | CAT00336KGDY12127 | NTB05819 | FML2201DSI1385 | COD 2022 116815 | ND834401 | ND852441 | ND60769 | 07.02.2022 | OFFLOADED 23.02.2022 | 28.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 18.02.2022 | 19.02.2022 | 20.02.2022 | 20.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THIS WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THIS WEEK | * VEHICLE CURRENTLY AT PIETERMARITSBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MIDDLEBURG EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1900 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GDY12128 | CAT00336JGDY12128 | NTB05825 | FML2201DSI1385 | COD 2022 116815 | ND730794 | ND443606 | ND60770 | 06.02.2022 | OFFLOADED 23.02.2022 | 28.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 06.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 18.02.2022 | 19.02.2022 | 20.02.2022 | 20.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THIS WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THIS WEEK | * VEHICLE CURRENTLY AT VAN REENENS PASS ENROUTE JOHANNESBURG | * VEHICLE AT MOOIRIVER EN ROUTE JOHANNESBURG | * VEHICLE AT MIDDELBURG EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1901 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GDY12126 | CAT00336PGDY12126 | NTB05800 | FML2201DSI1385 | COD 2022 116815 | ND705348 | ND476150 | ND60771 | 09.02.2022 | * OFFLOADED 28.02.2022 | 28.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 09.02.2022 | 10.02.2022 | 11.02.2022 | 12.02.2022 | 13.02.2022 | 14.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 18.02.2022 | 18.02.2022 | 18.02.2022 | 18.02.2022 | 19.02.2022 | 20.02.2022 | 20.02.2022 | 21.02.2022 | 24.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THIS WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THIS WEEK | * VEHICLE CURRENTLY UNDERGOING FINAL TRIP CHECK - TO DISPATCH TUESDAY 08.02.2022 | * VEHICLE CURRENTLY UNDERGOING FINAL TRIP CHECK - TO DISPATCH WEDNESDAY 09.02.2022 | * VEHICLE TO DISPATCH DURBAN TODAY | * VEHICLE AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE AT MIDDELBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BUBI ENROUTE HARARE | * VEHICLE CURRENTLY AT BEATRICE ENROUTE HARARE | * VEHICLE CURRENTLY AT MAKUTI ENROUTE LUSAKA | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM DAY 3 | * VEHICLE CURRENTLY AT WHISKEY DAY 1 | * VEHICLE CURRENTLY AT WHISKEY DAY 2 | * VEHICLE CURRENTLY AT WHISKEY DAY 2 | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1902 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GDY12124 | CAT00336CGDY12124 | NTB05839 | FML2201DSI1385 | COD 2022 116815 | ND142761 | NA542263 | ND60772 | 07.02.2022 | OFFLOADED 23.02.2022 | 28.01.2022 | 02.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.01.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 13.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 17.02.2022 | 17.02.2022 | 18.02.2022 | 19.02.2022 | 19.02.2022 | 20.02.2022 | 21.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAIITNG VESSEL ARRIVAL . ADRIATIC HIGHWAY ETA- 28.01.2022 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 02.02.2022 | * BV INSPECTION BOOKED FOR TODAY 02.02.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THIS WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THIS WEEK | * VEHICLE CURRENTLY AT PIETERMARITSBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MIDDLEBURG EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MAKUTI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1909 | 1 X CAT DE550 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CE500290 H5G01381 LWL03769 | 4895092 4662629 5029783 | CAT00C15PCE500290 | FML2112DSI1354 | COD 2022 116 778 | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 28.01.2022 | 01.02.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | [9 empty] | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR 01.02.2022 | * BV INSPECTION TO BE DONE TODAY | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1910 | 1 X CAT DE33GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7A00106 E3S09672 N7H00196 | 6052967 5010890 5992354 | CAT0DE33JN7A00106 | FML2112DSI1354 | COD 2021 901 728 | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.01.2022 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1911 | 1 X CAT DE33GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7A00111 E3S09728 N7H00192 | 6052967 5010890 5992354 | CAT0DE33VN7A00111 | FML2112DSI1354 | COD 2021 901 728 | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.01.2022 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1912 | 1 X CAT DE33GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7A00109 E3S09719 N7H00199 | 6052967 5010890 5992354 | CAT0DE33AN7A00109 | FML2112DSI1354 | COD 2021 901 728 | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.12.2021 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1913 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7200105 E3S09747 N7H00216 | 6052972 5011555 5992356 | CAT0DE55PN7200105 | FML2112DSI1354 | TBA | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.12.2021 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1914 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7200100 E3S09576 N7H00215 | 6052972 5011555 5992356 | CAT0DE55LN7200100 | FML2112DSI1354 | TBA | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.12.2021 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1915 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7200114 E3S10353 N7H00826 | 6052972 5011555 5992356 | CAT0DE55LN7200114 | FML2112DSI1354 | TBA | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.12.2021 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1916 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7200101 E3S09626 N7H00214 | 6052972 5011555 5992356 | CAT0DE55HN7200101 | FML2112DSI1354 | TBA | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.12.2021 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1917 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7200104 E3S09749 N7H00217 | 6052972 5011555 5992356 | CAT0DE55TN7200104 | FML2112DSI1354 | TBA | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.12.2021 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1918 | 1 X CAT DE22E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY11771 SM811725 TT902479 | 4512485 4489035 5849908 | CAT00C22AGBY11771 | FML2112DSI1354 | TBA | AEU9507 | AEG7043 | AEG7036 | 02.02.2022 | * OFFLOADED 28.02.2022 | 17.12.2021 | 19.01.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 02.02.2022 | 03.02.2022 | 03.02.2022 | 05.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 06.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 10.02.2022 | 13.02.2022 | 14.02.2022 | 25.02.2022 | 26.02.2022 | 28.02.2022 | 28.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) |  |  | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT VIVO ENROUTE MUSINA | * VEHICLE CURRENTLY AT KADOMA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KAFUE ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT NDOLA EN ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 13 IN DRC | * DISPATCHING WHISKEY | * DISPATCHING WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022 | * OFFLOADED 28.02.2022
BA1919 | 1 X CAT DE22E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY11772 SM811721 TT902486 | 4512485 4489035 5849908 | CAT00C22LGBY11772 | FML2112DSI1354 | COD 2021 901 729 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 17.01.2022 | 17.01.2022 | BV NUMBER RECEIVED ON 17 JAN 2022 - BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 21.01.2022 | 21.01.2022 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2022 | 29.01.2022 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1920 | 1 X CAT DE22EO GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY11830 SM811809 TT902531 | 4512485 4489035 5849908 | CAT00C22PGBY11830 | FML2112DSI1354 | COD 2021 901 729 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 17.01.2022 | 17.01.2022 | BV NUMBER RECEIVED ON 17 JAN 2022 - BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 21.01.2022 | 21.01.2022 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2022 | 29.01.2022 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1921 | 1 X CAT DE22EO GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY11828 SM811817 TT902518 | 4512485 4489035 5849908 | CAT00C22KGBY11828 | FML2112DSI1354 | COD 2021 901 729 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 17.01.2022 | 17.01.2022 | BV NUMBER RECEIVED ON 17 JAN 2022 - BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 21.01.2022 | 21.01.2022 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2022 | 29.01.2022 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1922 | 1 X CAT DE22EO GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2112DSI1354 | COD 2021 901 729 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | OFFLOADED 20.02.2022 | 17.01.2022 | 17.01.2022 | BV NUMBER RECEIVED ON 17 JAN 2022 - BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.12.2021 | 21.01.2022 | 21.01.2022 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2022 | 29.01.2022 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 17.02.2022 | 20.02.2022 | 20.02.2022 | 20.02.2022 | [26 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY. BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY. AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 4 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 5 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 7 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 8 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 9 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE DAY 10 AWAITING ASSESMENT | * VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022 | OFFLOADED 20.02.2022
BA1931 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15964 LXJ06502 P6B11005 | CAT00C15CLXJ06502 | N/A | FML2112DSI1361 | COD 2021 361369 | AFJ2620 | AEG2860 . AEG2852 | ND60754 | 25.01.2022 | * OFFLOADED 09.02.2022 | 18.01.2022 | 25.01.2022 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 11.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2022 | 27.01.2022 | 28.01.2022 | 28.01.2022 | 29.01.2021 | 29.01.2021 | 30.01.2021 | 30.01.2022 | 31.01.2022 | 31.01.2022 | 31.01.2022 | 01.02.2022 |  | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | [45 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | COLLECTING CONTAINER FROM PORT TODAY. AWAITING BV NUMBER | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV INSPECTION COMPLETE. WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE. WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT BEIBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA CUSTOMS | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022
BA1932 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15894 LXJ06503 F6B11002 | CAT00C15TLXJ06503 | N/A | FML2112DSI1360 | COD 2021 361369 | AEU7881 | AEG7120 | AEG7080 | 22.01.2022 | * OFFLOADED 09.02.2022 | 18.01.2022 | 25.01.2022 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 11.01.2022 | 21.01.2022 | 21.01.2022 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2022 | 27.01.2022 | 28.01.2022 | 29.01.2022 | 29.01.2022 |  | 30.01.2022 | 30.01.2022 | 30.01.2022 | 02.02.2022 | 03.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | [45 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | COLLECTING CONTAINER FROM PORT TODAY. AWAITING BV NUMBER | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV INSPECTION COMPLETE. WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE. WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA CUSTOMS | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022
BA1933 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15873 LXJ06501 F6B11001 | CAT00C15ELXJ06501 | N/A | FML2112DSI1361 | COD 2021 361369 | AEU7881 | AEG7120 | AEG7080 | 22.01.2022 | * OFFLOADED 09.02.2022 | 18.01.2022 | 25.01.2022 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 11.01.2022 | 21.01.2022 | 21.01.2022 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2022 | 27.01.2022 | 28.01.2022 | 29.01.2022 | 29.01.2022 |  | 30.01.2022 | 30.01.2022 | 30.01.2022 | 02.02.2022 | 03.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | [45 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | COLLECTING CONTAINER FROM PORT TODAY. AWAITING BV NUMBER | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV INSPECTION COMPLETE. WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE. WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA CUSTOMS | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022
BA1934 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15963 LXJ06530 F6B11008 | CAT00C15LLXJ06530 | N.A | FML2201DSI1391 | COD 2021 361369 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 18.02.2022 | 21.02.2022 | BV WAS BOOKED AS SOON AS BV NUMBER HAS BEEN RECEIVED | 14.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 20.03.2022 | 20.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [27 empty] | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * BV INSPECTION TO BE COMPLETED TODAY THE 21.02.2022 | * BV INSPECTION DONE AWAITING BV LICENCE FOR BA1973,BA1971 IN ORDER TO DISPATCH TO SITE | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1935 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15978 LXJ06507 F6B11004 | CAT00C15CLXJ06507 | N.A | FML2112DSI1379 | COD 2021 361369 | AAR7056 | AAR7028T/AAR7082T | 2112DSI1370 | 07.03.2022 | * OFFLOADED 01.04.2022 | 18.02.2022 | 25.02.2022 | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | 14.02.2022 | 07.03.2022 | 10.03.2022 | 10.03.2022 | 11.03.2022 | 11.03.2022 | 12.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 16.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 22.03.2022 | 24.03.2022 | 25.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | [44 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER FROM THE PORT AS WELL AS BV LICENCE NUMBER | LOADING THE CONTAINER FROM THE PORT.AWAITING BV LICENCE NUMBER TO BOOK INSPECTION | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR TUESDAY 25 JAN 2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KABWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY AT KANYAKHA AWAIITNG CLEARANCE | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022
BA1936 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15978 LXJ06507 F6B11004 | CAT00C15LLXJ06534 | N.A | FML2112DSI1379 | COD 2021 361369 | ACK2985 | ACJ5924T ACJ5923T | 2112DSI1367 | 07.03.2022 | * OFFLOADED 04.04.2022 | 18.02.2022 | 25.02.2022 | BV WAS BOOKED AS SOON AS BV NUMBER HAS BEEN RECEIVED | 14.02.2022 | 07.03.2022 | 10.03.2022 | 10.03.2022 | 11.03.2022 | 11.03.2022 | 12.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 16.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 22.03.2022 | 24.03.2022 | 25.03.2022 | 29.03.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [27 empty] | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * BV INSPECTION TO BE COMPLETED TODAY THE 21.02.2022 | * BV INSPECTION DONE, TRUCK TO DISPATCH LATER THIS WEEK | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENLTY AT KAZANGULA ENROUTE HARARE | * VEHICLE CURRENLTY AT CHOMA ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KABWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 10. WAITING NEW DECLARATIONS TO BE ISSUED | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1937 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15897 LXJ06505 F6B10998 | CAT00C15KLXJ06505 | N/A | FML2112DSI1369 | COD 2021 361369 | AFJ2620 | AEG2860 . AEG2852 | ND60754 | 25.01.2022 | * OFFLOADED 09.02.2022 | 18.01.2022 | 25.01.2022 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2022 | 27.01.2022 | 28.01.2022 | 28.01.2022 | 29.01.2021 | 29.01.2021 | 30.01.2021 | 30.01.2022 | 31.01.2022 | 31.01.2022 | 31.01.2022 | 01.02.2022 | 01.02.2022 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | [44 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER FROM THE PORT AS WELL AS BV LICENCE NUMBER | LOADING THE CONTAINER FROM THE PORT.AWAITING BV LICENCE NUMBER TO BOOK INSPECTION | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR TUESDAY 25 JAN 2022 | * BV INSPECTION BOOKED FOR TODAY | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT BEIBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA CUSTOMS | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022
BA1938 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15979 LXJ06504 F6B10999 | CAT00C15PLXJ06504 | N/A | FML2112DSI1360 | COD 2021 361369 | AEU7881 | AEG7120 | AEG7080 | 22.01.2022 | * OFFLOADED 09.02.2022 | 18.01.2022 | 25.01.2022 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 11.01.2022 | 21.01.2022 | 21.01.2022 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2022 | 27.01.2022 | 28.01.2022 | 29.01.2022 | 29.01.2022 | 29.01.2022 | 30.01.2022 | 30.01.2022 | 30.01.2022 | 02.02.2022 | 03.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | [27 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | [16 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | COLLECTING CONTAINER FROM PORT TODAY. AWAITING BV NUMBER | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY. AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV INSPECTION COMPLETE. WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE. WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA CUSTOMS | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022
BA1939 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15995 LXJ06529 F6B11009 | CAT00C15LLXJ06529 | N.A | FML 2112DSI1367 | COD 2021 361369 | ACK2985 | ACJ5924T ACJ5923T | 2112DSI1367 | 07.03.2022 | * OFFLOADED 04.04.2022 | 18.02.2022 | 21.02.2022 | BV WAS BOOKED AS SOON AS BV NUMBER HAS BEEN RECEIVED | 14.02.2022 | 07.03.2022 | 10.03.2022 | 10.03.2022 | 11.03.2022 | 11.03.2022 | 12.03.2022 | 12.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 16.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 22.03.2022 | 24.03.2022 | 25.03.2022 | 29.03.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [27 empty] | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * BV INSPECTION TO BE COMPLETED TODAY THE 21.02.2022 | * BV INSPECTION DONE, TRUCK TO DISPATCH LATER THIS WEEK | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENLTY AT KAZANGULA ENROUTE HARARE | * VEHICLE CURRENLTY AT CHOMA ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KABWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 10. WAITING NEW DECLARATIONS TO BE ISSUED | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1940 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15891 LXJ06508 F6B11006 | CAT00C15VLXJ06508 | N/A | FML2112DSI1379 | COD 2021 361369 | AGB6599ZM | ACG8203T . ACG8204T | ND60762 | 08.02.2022 | OFFLOADED 23.02.2022 | 18.01.2022 | 25.01.2022 | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | 14.01.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 11.02.2022 | 12.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 21.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [27 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | [15 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER FROM THE PORT AS WELL AS BV LICENCE NUMBER | LOADING THE CONTAINER FROM THE PORT.AWAITING BV LICENCE NUMBER TO BOOK INSPECTION | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR TUESDAY 25 JAN 2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948. BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLY AT KASUMBALES ZAM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLY AT KASUMBALES ZAM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLY AT KASUMBALES DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLY AT KASUMBALES DRC SIDE - AWAITING CLEARANCE | * TRUCK TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1941 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15782 LXJ06535 F6B11003 | CAT00C15LLXJ06535 | N.A | FML 2112DSI1367 | COD 2021 361369 | ACK2985 | ACJ5924T ACJ5923T | 2112DSI1367 | 07.03.2022 | * OFFLOADED 04.04.2022 | 18.02.2022 | 21.02.2022 | BV WAS BOOKED AS SOON AS BV NUMBER HAS BEEN RECEIVED | 14.02.2022 | 07.03.2022 | 10.03.2022 | 10.03.2022 | 11.03.2022 | 11.03.2022 | 12.03.2022 | 12.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 16.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 22.03.2022 | 24.03.2022 | 25.03.2022 | 29.03.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [27 empty] | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * BV INSPECTION TO BE COMPLETED TODAY THE 21.02.2022 | * BV INSPECTION DONE, TRUCK TO DISPATCH LATER THIS WEEK | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENLTY AT KAZANGULA ENROUTE HARARE | * VEHICLE CURRENLTY AT CHOMA ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KABWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 10. WAITING NEW DECLARATIONS TO BE ISSUED | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1942 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FTH15940 LXJ06506 F6B11000 | CAT00C15JLXJ06506 | N/A | FML2112DSI1369 | COD 2021 361369 | AFJ2620 | AEG2860 . AEG2852 | ND60754 | 25.01.2022 | * OFFLOADED 09.02.2022 | 14.01.2022 | 25.01.2022 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.01.2022 | 26.01.2022 | 26.01.2022 | 27.01.2021 | 27.01.2021 | 27.01.2021 | 28.01.2021 | 28.01.2022 | 29.01.2021 | 29.01.2021 | 30.01.2021 | 30.01.2022 | 31.01.2022 | 31.01.2022 | 31.01.2022 | 01.02.2022 | 01.02.2022 | 01.02.2022 | 01.02.2022 | 02.02.2022 | 04.02.2022 | 07.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | 09.02.2022 | [27 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | [15 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER FROM THE PORT AS WELL AS BV LICENCE NUMBER | LOADING THE CONTAINER FROM THE PORT.AWAITING BV LICENCE NUMBER TO BOOK INSPECTION | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING. AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR TUESDAY 25 JAN 2022 | * BV INSPECTION BOOKED FOR TODAY | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT BEIBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHILCE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA CUSTOMS | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022 | * OFFLOADED 09.02.2022
BA1948 | 1 X CAT DE220E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | F5D03974 ECW05649 KRG10551 | CAT00C71HECW05649 | N/A | FML 2112DSI1370 | COD 2022 139688 | AAR7056 | AAR7028T/AAR7082T | 2112DSI1370 | 07.03.2022 | * OFFLOADED 01.04.2022 | 24.02.2022 | 25.02.2022 | BV INSPECTION WAS BOOKED AS SOON AS WE RECEIVED THE BV NUMBER. | 17.01.2022 | 07.03.2022 | 10.03.2022 | 10.03.2022 | 11.03.2022 | 11.03.2022 | 12.03.2022 | 13.03.2022 | 12.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 22.03.2022 | 24.03.2022 | 25.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | [47 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR DEPO AWAITING UNPACK | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KABWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY AT KANYAKHA AWAIITNG CLEARANCE | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022
BA1949 | 1 X CAT DE220E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | F5D03963 ECW05648 KRG10518 | CAT00C71LECW05648 | N/A | FML 2112DSI1370 | COD 2022 139688 | AAR7056 | AAR7028T/AAR7082T | 2112DSI1370 | 07.03.2022 | * OFFLOADED 01.04.2022 | 24.02.2022 | 25.02.2022 | BV INSPECTION WAS BOOKED AS SOON AS WE RECEIVED THE BV NUMBER. | 17.01.2022 | 07.03.2022 | 10.03.2022 | 10.03.2022 | 11.03.2022 | 11.03.2022 | 12.03.2022 | 13.03.2022 | 12.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 22.03.2022 | 24.03.2022 | 25.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | [47 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR DEPO AWAITING UNPACK | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KABWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY AT KANYAKHA AWAIITNG CLEARANCE | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022
BA1950 | 1 X CAT DE220E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | F5D03964 ECW05647 KRG10517 | CAT00C71AECW05647 | N/A | FML 2112DSI1370 | COD 2022 139688 | AAR7056 | AAR7028T/AAR7082T | 2112DSI1370 | 07.03.2022 | * OFFLOADED 01.04.2022 | 24.02.2022 | 25.02.2022 | BV INSPECTION WAS BOOKED AS SOON AS WE RECEIVED THE BV NUMBER. | 17.01.2022 | 07.03.2022 | 10.03.2022 | 10.03.2022 | 11.03.2022 | 11.03.2022 | 12.03.2022 | 13.03.2022 | 12.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 22.03.2022 | 24.03.2022 | 25.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | [47 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR DEPO AWAITING UNPACK | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE KABWE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 2 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY AT KANYAKHA AWAIITNG CLEARANCE | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022 | * OFFLOADED 01.04.2022
BA1951 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704559 ECW05639 KRG10561 | CAT00C71PECW05639 | N/A | FML 2112DSI1372 | COD 2021 366 334 | AGB6599ZM | ACG8203T . ACG8204T | ND60762 | 08.02.2022 | OFFLOADED 23.02.2022 | 18.01.2022 | 25.01.2021 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 18.01.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 21.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [46 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24.01.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - BV ON BA1955 & BA1957 TO BE DONE TODAY | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * TRUCK TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1952 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704557 ECW05626 KRG10521 | CAT00C71KECW05626 | N/A | FML 2112DSI1372 | COD 2021 366 334 | AGB6599ZM | ACG8203T . ACG8204T | ND60762 | 08.02.2022 | OFFLOADED 23.02.2022 | 18.01.2022 | 25.01.2021 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 18.01.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 21.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [46 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24.01.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - BV ON BA1955 & BA1957 TO BE DONE TODAY | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * TRUCK TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1953 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704556 ECW05627 KRG10520 | CAT00C71JECW05627 | N/A | FML 2112DSI1372 | COD 2021 366 334 | AGB6599ZM | ACG8203T . ACG8204T | ND60762 | 08.02.2022 | OFFLOADED 23.02.2022 | 18.01.2022 | 25.01.2021 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 18.01.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 21.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [46 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24.01.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - BV ON BA1955 & BA1957 TO BE DONE TODAY | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * TRUCK TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1954 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704558 ECW05625 KRG10522 | CAT00C71PECW05625 | N/A | FML 2112DSI1372 | COD 2021 366 334 | AGB6599ZM | ACG8203T . ACG8204T | ND60762 | 08.02.2022 | OFFLOADED 23.02.2022 | 18.01.2022 | 25.01.2021 | CONTAINERS LOADED OUT OF THE PORT & UNPACKED BEFORE INSPECTION COULD TAKE PLACE. BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 18.01.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 21.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [46 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24.01.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - BV ON BA1955 & BA1957 TO BE DONE TODAY | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * TRUCK TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1955 | 1 X CAT DE110E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECL04894 7K304957 JM704455 | CAT00C44HECL04894 | N/A | FML 2112DSI1372 | COD 2021 366 334 | AGB6599ZM | ACG8203T . ACG8204T | ND60762 | 08.02.2022 | OFFLOADED 23.02.2022 | 07.02.2022 | 07.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 18.01.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 21.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [46 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24.01.2022 | * CONTAINER IS AT OUR FACILITY AWAITING BV NUMBER | * CONTAINER IS AT OUR FACILITY AWAITING BV NUMBER | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * TRUCK TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1957 | 1 X CAT DE110E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704446 ECL04895 7K304956 | CAT00C44EECL04895 | N/A | FML 2112DSI1372 | COD 2021 366 334 | AGB6599ZM | ACG8203T . ACG8204T | ND60762 | 08.02.2022 | OFFLOADED 23.02.2022 | 07.02.2022 | 07.02.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 18.01.2022 | 08.02.2022 | 09.02.2022 | 10.02.2022 | 10.02.2022 | 10.02.2022 | 11.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 16.02.2022 | 17.02.2022 | 21.02.2022 | 21.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [46 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING. AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24.01.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | * BV INSPECTION COMPLETE - BV ON BA1955 & BA1957 TO BE DONE TODAY | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * TRUCK TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1963 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04964 | CAT00C33JEC507446 | N/A | FML2201DSI1391 | COD 2022 129648 | ACE1978 | ACJ4508T ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1964 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KMC04963 | CAT00C33HEC507440 | N.A | FML2201DSI1391 | COD 2022 129648 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1965 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04959 | CAT00C33CEC507439 | N.A | FML2201DSI1391 | COD 2022 129648 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1966 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04962 | CAT00C33TEC507443 | N.A | FML2201DSI1391 | COD 2022 129648 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1967 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMC04960 | CAT00C33CEC507442 | N.A | FML2201DSI1391 | COD 2022 129648 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1968 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMC04961 | CAT00C33KEC507445 | N.A | FML2201DSI1391 | COD 2022 129648 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1969 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04973 | CAT00C33PEC507444 | N.A | FML2201DSI1391 | COD 2022 134784 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1970 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04957 | CAT00C33EEC507455 | N.A | FML2201DSI1391 | COD 2022 134784 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1971 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04974 | CAT00C33EEC507441 | N.A | FML2201DSI1391 | COD 2022 134784 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1973 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04972 | CAT00C33CE507456 | N.A | FML2201DSI1391 | COD 2022 134784 | ACE1978 | ACJ4508T/ACJ4503T | 2201DSE1391 | 14.03.2022 | * OFFLOADED 04.04.2022 | 22.02.2022 | 24.02.2022 | AWAITED VALIDATION FROM BANK, BV BOOKED AS SOON AS RECEIVED | 20.02.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 15.03.2022 | 16.03.2022 | 16.03.2022 | 16.03.2022 | 17.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 18.03.2022 | 19.03.2022 | 20.03.2022 | 21.03.2022 | 21.03.2022 | 22.03.2022 | 23.03.2022 | 24.03.2022 | 03.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | [62 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14.02.2022 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNITS ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * CARGO AT OUR BONDED FACILITY AWAITNG BV NUMBER | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | * BV TO BE COMPLETED TODAY TRUCK TO DISPATCH MONDAY THE 28.02.2022 | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG ATTENDING TO A BREAKDOWN,TRUCK TO DISPTACH NEXT WEEK | * VEHICLES CURRENLTY LOADING - TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT GROBLERSBIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHOBE ENROUTE LIVINGSTONE | * VEHICLE DISPATCHING KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC DAY 1 | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 5 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 7, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 8, WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY KANYAKA CLEARING | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022 | * OFFLOADED 04.04.2022
BA1975 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04976 | CAT00C33JEC305657 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1976 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04965 | CAT00C33AEC305646 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1977 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04966 | CAT00C33LEC305650 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1978 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04970 | CAT00C33HEC305648 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1979 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04968 | CAT00C33PEC305655 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1980 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04979 | CAT00C33LEC305647 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1981 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04975 | CAT00C33CEC305658 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1982 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04980 | CAT00C33VEC305659 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1983 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04978 | CAT00C33EEC305649 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1984 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04969 | CAT00C33KEC305656 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA1986 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04967 | CAT00C33VEC305645 | N.A | FML 2202DSI1420 | COD 2022 121791 | AGB6605ZM | AAR7018T / AAR7074T | ND62958 | 07.03.2022 | * VEHICLE OFFLOADED 02.04.2022 | 21.02.2022 | 25.02.2022 | CONTAINER WAS STILL UNDER UNPACK AND BV BOOKED FOR THE 25.02.2022 AS SOON AS THE GOODS WHERE AVAILABLE | 20.02.2022 | 07.03.2022 | 10.03.2022 | 17.03.2022 | 17.03.2022 | 18.03.2022 | 20.03.2022 | 21.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 25.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | 02.04.2022 | [62 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | *CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | BV COMPLETED AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 AS WE ARE AWAITING OUR TRUCKS TO RETURN FROM DRC(CLEARING DELAY) | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO LOAD FRIDAY 04.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE DISPATCHING JOHANNESBURG TODAY | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG 17.03.2022 | * ATTENDING TO BREAKDOWN - TO DISPATCH JOHANNESBURG TODAY | * VEHICLE CURRENTLY AT GROBLERSBRIDGE SA SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE STOP FOR PHYSICAL EXAMINATION | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022 | * VEHICLE OFFLOADED 02.04.2022
BA2032 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00291 | CAT00374LRGM00291 | TBA | FML 2201DSI1402 | COD 2022 116818 | NU29242 | NU154819 . NU154820 | ND60794 | 07.02.2022 | * OFFLOADED 14.03.2022 | 31.01.2022 | 07.02.2022 | BV INSPECTION WAS BOOKED AS SOON AS WE RECEIVED THE BV NUMBER. | 02.02.2022 | 08.02.2022 | 10.02.2022 | 11.02.2022 | 12.02.2022 | 13.02.2022 | 14.02.2022 | 18.02.2022 | 25.02.2022 | 26.02.2022 | 27.02.2022 | 28.02.2022 | 01.03.2022 | 03.03.2022 | 04.03.2022 | 04.03.2022 | 05.03.2022 | 06.03.2022 | 06.03.2022 | 07.03.2022 | 08.03.2022 | 09.03.2022 | 11.03.2022 | 12.03.2022 | 14.03.2022 | 14.03.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | * BV INSPECTION BOOKED FOR TODAY 07.02.2022 | * BV INSPECTION DONE, TRUCK TO DISPATCH TODAY | TRUCK AT NEW CASTLE EN-ROUTE TO BEITBRIDGE | TRUCK AT VILLIERS EN-ROUTE TO BEITBRIDGE | TRUCK AT JNB UNDERGOING TRIP CHECK | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE - CROSSING TO ZIM SIDE | * VEHICLE CURRENLTY AT CHILILABOMBWE EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT BEIRBRIDGE ZIM SIDE | * VEHICLE CURRENLTY AT BEIRBRIDGE ZIM SIDE | * VEHICLE CURRENLTY AT MASVINGO | * VEHICLE CURRENLTY AT HARARE | * VEHICLE CURRENLTY AT HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING CHIRUNDU ENROUTE LUSAKA | * VEHICLE AT LUSAKA | * VEHICLE AT KASUMBALESA ZAM SIDE | * VEHICLE AT KASUMBALESA DRC SIDE | * VEHICLE AT WHISKEY AWAIITNG RELEASE | * VEHICLE AT WHISKEY AWAIITNG RELEASE DAY 2 | * VEHICLE ARRIVED ON SITE 12.03.2022 - AWAITING TO OFFLOAD | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022 | * OFFLOADED 14.03.2022
BA2032 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM00291 | CAT00374LRGM00291 | TBA | FML 2201DSI1402 | COD 2022 116818 | ACE5821 | ABE4043 . AAN665 | NA60794 | 08.02.2022 | OFFLOADED 23.02.2022 | 31.01.2022 | 07.02.2022 | BV WAS FULLY BOOKED AND BV WAS BOOKED ON THE FIRST AVAILABLE DATE | 02.02.2022 | 07.02.2022 | 07.02.2022 | 07.02.2022 | 08.02.2022 | 08.02.2022 | 09.02.2022 | 11.02.2022 | 12.02.2022 | 13.02.2022 | 14.02.2022 | 14.02.2022 | 14.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 15.02.2022 | 16.02.2022 | 17.02.2022 | 18.02.2022 | 19.02.2022 | 20.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | 23.02.2022 | [59 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | * BV INSPECTION BOOKED FOR TODAY 07.02.2022 | * TRUCK AT JNB UNDERGOING TRIP CHECK | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE TO DISPATCH WHISKEY EN-ROUTE TO SITE | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23..02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022 | OFFLOADED 23.02.2022
BA1660 | 1 X CAT 428 BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | L7D00901 | CAT00428HL7D00901 | C4Z13960 | FML2201DSI1399 | COD 2022 116 826 | ACT5864 | ACE5884T | ND60792 | 10.02.2022 | * VEHICLE OFFLOADED 11.04.2022 | 28.01.2022 | 22.02.2022 | BV BOOKED AS SOON AS CONTAINERS ARE UNPACKED | 10.02.2022 | 08.03.2022 | 09.03.2022 | 09.03.2022 | 10.03.2022 | 10.03.2022 | 11.03.2022 | 13.03.2022 | 13.03.2022 | 13.03.2022 | 14.03.2022 | 14.03.2022 | 14.03.2022 | 15.03.2022 | 16.03.2022 | 18.03.2022 | 19.03.2022 | 19.03.2022 | 20.03.2022 | 22.03.2022 | 24.03.2022 | 24.03.2022 | 29.03.2022 | 11.04.2022 | 11.04.2022 | 11.04.2022 | [55 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING INVOICE FOR BA1659-VESSEL ETA 01.02.2022 | AWAITING INVOICE FOR BA1659-VESSEL ETA 01.02.2022 | VESSEL ETA 01.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 02.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 02.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 05.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 05.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 05.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 05.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 05.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 05.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 10.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 10.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 10.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 10.02.2022-AWAITING VESSEL TO BERTH | THE VESSEL IS IN AND WORKING, CONTAINERS WILL BE LOADED ONCE AVAILABLE | THE VESSEL IS IN AND WORKING, CONTAINERS WILL BE LOADED ONCE AVAILABLE | THE VESSEL IS IN AND WORKING, CONTAINERS WILL BE LOADED ONCE AVAILABLE | THE VESSEL IS IN AND WORKING, CONTAINERS WILL BE LOADED ONCE AVAILABLE | THE VESSEL IS IN AND WORKING, CONTAINERS WILL BE LOADED ONCE AVAILABLE | * CONTAINER IN BONDED FACILITY - CURRENTLY UNDER UNPACK | CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION ON THE 22.02.2022 | CARGO IS AT OUR BONDED FACILITY AWAITING BV INSPECTION ON THE 22.02.2022,TRUCK TO DISPATCH LATER THIS WEEK | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH LATER THIS WEEK | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH TEUSDAY THE 01.03.2022 | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH WEDNESDAY THE 02.03.2022 | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH THURSDAY THE 03.03.2022 | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH FRIDAY THE 04.03.2022 | CARGO IS AT OUR BONDED FACILITY AND TRUCK TO DISPATCH TODAY | TRUCK DISPATCH DURBAN EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK AT MOOIRIVER EN-ROUTE TO GROBLERS BORDER | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK TO DISPATCH JOHANNESBURG TODAY-EN ROUTE TO GROBLERSBRIDGE BORDER | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE HARARE | * VEHICLE CURRENLTY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENLTY AT SENKOBO ENROUTE LUSAKA | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAIITNG TO CROSS | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 1 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE DAY 1 | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE DAY 3 | * VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 5. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 7. WAITING NEW DECLARATIONS TO BE ISSUED | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 8. | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 9. | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 10. | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 11. | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE OFFLOADED 11.04.2022 | * VEHICLE OFFLOADED 11.04.2022
BA1926 | 1 X CAT DE450E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403838 PWE06101 LWL05271 | CAT00C13ADH403838 | N/A | FML2203DSI1444 | COD 2022 134802 | AAZ3461 | ACE5858T ACE5879T | ND60612 | 31.03.2022 | OFFLOADED 27/04/2022 | 18.02.2022 | 29.03.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 03.04.2022 | 03.04.2022 | 06.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 22.04.2022 | 22.04.2022 | 27.04.2022 | 27.04.2022 | 27/04/2022 | 27/04/2022 | [77 empty] | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THURSDAY MORNING - 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE CROSSING TO BOTSWANA | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT KAPIRI | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 3 | OFFLOADED 27/04/2022 | OFFLOADED 27/04/2022
BA1925 | 1 X CAT DE450E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403810 PWE06229 LWL05151 | CAT00C13ADH403810 | N/A | FML2203DSI1443 | COD 2022 116775 | AAZ3461 | ACE5858T ACE5879T | ND60612 | 31.03.2022 | OFFLOADED 27/04/2022 | 31.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 03.04.2022 | 03.04.2022 | 06.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 22.04.2022 | 22.04.2022 | 27.04.2022 | 27.04.2022 | 27/04/2022 | 27/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THURSDAY MORNING - 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE CROSSING TO BOTSWANA | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT KAPIRI | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 3 | OFFLOADED 27/04/2022 | OFFLOADED 27/04/2022
BA1928 | 1 X CAT DE450E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403809 PWE06222 LWL05152 | CAT00C13HDH403809 | N/A | FML2203DSI1443 | COD 2022 116775 | AAZ3461 | ACE5858T ACE5879T | ND60612 | 31.03.2022 | OFFLOADED 27/04/2022 | 31.01.2022 | 29.03.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 03.04.2022 | 03.04.2022 | 06.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 22.04.2022 | 22.04.2022 | 27.04.2022 | 27.04.2022 | 27/04/2022 | 27/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THURSDAY MORNING - 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE CROSSING TO BOTSWANA | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINGSTONE | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT KAPIRI | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 3 | OFFLOADED 27/04/2022 | OFFLOADED 27/04/2022
BA1956 | 1 X CAT DE110E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECL04932 7K305026 JM704588 | CAT00C44CECL04932 | N/A | FML2203DSI1443 | COD 2022 116770 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 31.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA1958 | 1 X CAT DE110E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704589 ECL04933 7K305047 | CAT00C44TECL04933 | N/A | FML2203DSI1447 | COD 2022 116770 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 28.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION COMPLETE - VEHILCE TO DISPATCH THURSDAY 31 MARCH 2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA1959 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704592 EC902949 ZRE02960 | CAT00C44LEC902949 | N/A | FML2203DSI1447 | COD 2022 123302 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 23.03.2022 | 29.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | * UNIT IN BONDED FACILITY - AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION COMPLETE - VEHILCE TO DISPATCH THURSDAY 31 MARCH 2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA1960 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704584 EC902953 ZRE02959 | CAT00C44HEC902953 | N/A | FML2203DSI1447 | COD 2022 116771 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 31.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION COMPLETE - VEHILCE TO DISPATCH THURSDAY 31 MARCH 2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA1961 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC902951 ZRE02958 JM704594 | CAT00C44AEC902951 | N/A | FML2203DSI1447 | COD 2022 116771 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 31.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION COMPLETE - VEHILCE TO DISPATCH THURSDAY 31 MARCH 2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA1962 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM704593 EC902952 ZRE02957 | CAT00C44LEC902952 | N/A | FML2203DSI1447 | COD 2022 116771 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 31.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION COMPLETE - VEHILCE TO DISPATCH THURSDAY 31 MARCH 2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA1972 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG04971 EC507457 E3S11959 | CAT00C33TEC507457 | N.A | FML 2203DSI1447 | COD 2022 116774 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 31.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION COMPLETE - VEHILCE TO DISPATCH THURSDAY 31 MARCH 2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA1974 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC507458 E3S11968 JMG04958 | CAT00C33PEC507458 | N.A | FML 2203DSI1447 | COD 2022 116774 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 31.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [66 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * VEHICLE TO DISPATCH TODAY EN-ROUTE TO GROBLERS BRIDGE | * TRUCK DISPATCH EN-ROUTE TO GROBLERS BRIDGE BORDER | * TRUCKS ARE AT MOOIRIVER EN-ROUTE TO GROBLERS BRIDGE BORDER | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT LOADED ENROUTE BONDED FACILITY. BV INSPECTION TO BE BOOKED | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION COMPLETE - VEHILCE TO DISPATCH THURSDAY 31 MARCH 2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA1985 | 1 X CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMC04977 EC305660 E3S11907 | CAT00C33JEC305660 | N.A | FML 2203DSI1447 | COD 2022 116782 | ACG6685 | ACG7758T | ND60614 | 31.03.2022 | OFFLOADED 30/04/2022 | 31.01.2022 | 17.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | [59 empty] | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * AWAITING VESSEL ARRIVAL - CMA CGM SAVANAHNA CURRENT ETA 14.03.2022 | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR THURSDAY 17.03.2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH NEXT WEEK | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - AWAITING BA1929 AND BA1926 TO ARRIVE IN ORDER TO CO-LOAD | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * BV INSPECTION COMPLETE - UNIT TO DISPATCH THURSDAY 31.03.2022 | * VEHICLE CURRENTLY AT GROBLERSBRIDGE UNDER CLEARANCE | * VEHICLE CURRENTLY AT KAZANGULA BOTSWANA SIDE | * VEHICLE CURRENTLY AT KAZANGULA ZAM SIDE | * VEHICLE CURRENTLY AT LIVINSTON | * VEHICLE CURRENTLY AT LUSAKA | * VEHICLE CURRENTLY AT CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | OFFLOADED 30/04/2022 | OFFLOADED 30/04/2022
BA2004 | 1 X NEW CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10007 | CAT00374CRGM10007 | E4T00404 | FML2201DSI1424 | COD 2022 133269 | ND760431 | ND760424 . ND760428 | ND62941 | 22.03.2022 | OFFLOADED 25/04/2022 | 17.02.2022 | 15.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 26.03.2022 | 28.03.2022 | 30.03.2022 | 30.03.2022 | 30.03.2022 | 31.03.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | 05.04.2022 | 05.04.2022 | 06.04.2022 | 10.04.2022 | 11.04.2022 | 23.04.2022 | 23.04.2022 | 23.04.2022 | 25.04.2022 | [77 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | MACHINE IS AT OUR BONDED FACILITY | MACHINE IS AT OUR BONDED FACILITY | MACHINE IS AT OUR BONDED FACILITY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THURSDAY 17.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * VEHCILE IS AT HENDRINA EN-ROUTE TO BEITBRIDGE BORDER | * VEHCILE IS AT BEITBRIDGE BORDER RSA SIDE | * VEHCILE IS AT BEITBRIDGE BORDER CROSSING TO ZIM SIDE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT HARARE AWAITING PERMIT | * VEHICLE CURRENLTY AT MAKUTI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING PERMIT | * VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA KASUMBALESA ZAM | * VEHICLE CURRENLTY AT CHINGOLA KASUMBALESA ZAM DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 8 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 9 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 10 DRIVER EN-ROUTE TO ZAMBIA FOR MEDICAL TREATMENT | OFFLOADED 25/04/2022 | OFFLOADED 25/04/2022
BA2004 | SPARES FOR 1 X NEW CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10007 | CAT00374CRGM10007 | E4T00404 | FML2201DSI1424 | COD 2022 133269 | AGB6969ZM | AAN481T AAN5241Y | ND62941 | 22.03.2022 | OFFLOADED 27/04/2022 | 17.02.2022 | 15.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 26.03.2022 | 26.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 30.03.2022 | 31.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 11.04.2022 | 12.04.2022 | 25.04.2022 | 25.04.2022 | 26.04.2022 | [78 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | MACHINE IS AT OUR BONDED FACILITY | MACHINE IS AT OUR BONDED FACILITY | MACHINE IS AT OUR BONDED FACILITY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THURSDAY 17.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * VEHCILE IS AT JNB AWAITNG ABNORMAL PERMIT | * VEHCILE IS AT BEITBRIDGE BORDER RSA SIDE | * VEHCILE IS AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 3 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 4 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 4 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 7 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 6 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 8-DOCUMENTS CHANGED TO SOMIKA | OFFLOADED 27/04/2022 | OFFLOADED 27/04/2022
BA2005 | 1 X NEW CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10008 | CAT00374VRGM10008 | E4T00416 | FML2201DSI1425 | COD 2022 133269 | ND754967 | ND654346 ND526680 | ND62940 | 22.03.2022 | OFFLOADED 18/04/2022 | 17.02.2022 | 15.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 26.03.2022 | 28.03.2022 | 30.03.2022 | 30.03.2022 | 30.03.2022 | 31.03.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | 04.04.2022 | 05.04.2022 | 05.04.2022 | 06.04.2022 | 08.04.2022 | 11.04.2022 | 14.04.2022 | 14.04.2022 | 15.04.2022 | 15.04.2022 | [77 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | MACHINE IS AT OUR BONDED FACILITY | MACHINE IS AT OUR BONDED FACILITY | MACHINE IS AT OUR BONDED FACILITY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THURSDAY 17.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * VEHCILE IS AT HENDRINA EN-ROUTE TO BEITBRIDGE BORDER | * VEHCILE IS AT BEITBRIDGE BORDER RSA SIDE | * VEHCILE IS AT BEITBRIDGE BORDER CROSSING TO ZIM SIDE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT HARARE - ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT HARARE - ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT HARARE - ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT HARARE - ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA KASUMBALESA ZAM | * VEHICLE CURRENLTY AT CHINGOLA KASUMBALESA ZAM DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 4 | OFFLOADED 18/04/2022 | OFFLOADED 18/04/2022 | OFFLOADED 18/04/2022 | OFFLOADED 18/04/2022 | OFFLOADED 18/04/2022
BA2005 | 1 X NEW CAT 374 HYDRAULIC EXCAVATOR SPARES | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10008 | CAT00374VRGM10008 | E4T00416 | FML2201DSI1425 | COD 2022 133269 | AGB6968ZM | ACJ6118T ACJ6119T | ND62940 | 22.03.2022 | OFFLOADED 18/04/2022 | 17.02.2022 | 15.03.2022 | BV BOOKED AS SOON AS UNIT WAS LOADED FROM THE PORT & AVAILABLE AT OUR FACILITY - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.03.2022 | 22.03.2022 | 23.03.2022 | 23.03.2022 | 23.03.2022 | 23.03.2022 | 24.03.2022 | 27.03.2022 | 27.03.2022 | 28.03.2022 | 28.03.2022 | 28.03.2022 | 29.03.2022 | 30.03.2022 | 31.03.2022 | 31.03.2022 | 01.04.2022 | 02.04.2022 | 03.04.2022 | 04.04.2022 | 11.04.2022 | 12.04.2022 | 14.04.2022 | 14.04.2022 | 15.04.2022 | 15.04.2022 | [77 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.03.2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | MACHINE IS AT OUR BONDED FACILITY | MACHINE IS AT OUR BONDED FACILITY | MACHINE IS AT OUR BONDED FACILITY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH THURSDAY 17.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 21.03.2022 | * VEHCILE IS AT JNB AWAITNG ABNORMAL PERMIT | * VEHCILE IS AT BEITBRIDGE BORDER RSA SIDE | * VEHCILE IS AT BEITBRIDGE BORDER CROSSING TO ZIM SIDE | * VEHICLE CURRENLTY AT SHURUGWI ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CROSS | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE D | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DAY 5 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | OFFLOADED 18/04/2022 | OFFLOADED 18/04/2022 | OFFLOADED 18/04/2022 | OFFLOADED 18/04/2022 | OFFLOADED 18/04/2022
BA1929 | 1 X CAT DE450E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403835 PWE06251 LWL05238 | CAT00C13JDH403835 | N/A | FML2203DSI1444 | COD 2022 134802 | ACG6686 | AAZ4510T AAZ4513T | ND60613 | 01.04.2022 | * OFFLOADED 04.05.2022 | 18.02.2022 | 29.03.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.03.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 05.04.2022 | 06.04.2022 | 06.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 09.04.2022 | 09.04.2022 | 10.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 04.05.2022 | 04.05.2022 | 04.05.2022 | 04.05.2022 | [77 empty] | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH TODAY | * VEHICLE CURRENTLY LOADING - TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE AT GROBLERS BRIDGE CLEARING | * VEHICLE AT GROBLERS BRIDGE CLEARING | * VEHICLE TO DISPATCH GROBLERS BRIDGE TODAY | * VEHICLE AT PANDAMATENGA EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT LIVINGSTON | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 3 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE - DAY 12 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE - DAY 13 | * VEHICLE CURRENTLY AT KANYAKA AWAITING CLEARANCE | * OFFLOADED 04.05.2022 | * OFFLOADED 04.05.2022
BA1943 | 1 X CAT DE400E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403837 PWE06165 LWL05268 | CAT00C13VDH403837 | N/A | FML2203DSI1446 | COD 2022 121838 | ACG6686 | AAZ4510T AAZ4513T | ND60613 | 01.04.2022 | * OFFLOADED 04.05.2022 | 18.02.2022 | 29.03.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.03.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 05.04.2022 | 06.04.2022 | 06.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 09.04.2022 | 09.04.2022 | 10.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 04.05.2022 | 04.05.2022 | 04.05.2022 | 04.05.2022 | [77 empty] | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | VESSEL IS IN AND WORKING | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH TODAY | * VEHICLE CURRENTLY LOADING - TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE AT GROBLERS BRIDGE CLEARING | * VEHICLE AT GROBLERS BRIDGE CLEARING | * VEHICLE TO DISPATCH GROBLERS BRIDGE TODAY | * VEHICLE AT PANDAMATENGA EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT LIVINGSTON | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 3 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE - DAY 12 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE - DAY 13 | * VEHICLE CURRENTLY AT KANYAKA AWAITING CLEARANCE | * OFFLOADED 04.05.2022 | * OFFLOADED 04.05.2022
BA1944 | 1 X CAT DE400E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403836 PWE06003 LWL05269 | CAT00C13CDH403836 | N/A | FML2203DSI1446 | COD 2022 121838 | ACG6686 | AAZ4510T AAZ4513T | ND60613 | 01.04.2022 | * OFFLOADED 04.05.2022 | 18.02.2022 | 29.03.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.03.2022 | 01.04.2022 | 02.04.2022 | 02.04.2022 | 03.04.2022 | 03.04.2022 | 04.04.2022 | 05.04.2022 | 05.04.2022 | 06.04.2022 | 06.04.2022 | 07.04.2022 | 07.04.2022 | 08.04.2022 | 08.04.2022 | 09.04.2022 | 09.04.2022 | 10.04.2022 | 10.04.2022 | 11.04.2022 | 21.04.2022 | 21.04.2022 | 04.05.2022 | 04.05.2022 | 04.05.2022 | 04.05.2022 | [77 empty] | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | AWAITING VESSEL ARRIVAL ON THE 21.03.2022 | VESSEL IS IN AND WORKING | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | UNIT IS AT OUR FACILITY AWAITING BV INSPECTION | * BV INSPECTION BOOKED FOR TUESDAY 29 MARCH 2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH TODAY | * VEHICLE CURRENTLY LOADING - TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE AT GROBLERS BRIDGE CLEARING | * VEHICLE AT GROBLERS BRIDGE CLEARING | * VEHICLE TO DISPATCH GROBLERS BRIDGE TODAY | * VEHICLE AT PANDAMATENGA EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT LIVINGSTON | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC SIDE THIS MORNING | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 2 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE DAY 3 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE - DAY 12 | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE - DAY 13 | * VEHICLE CURRENTLY AT KANYAKA AWAITING CLEARANCE | * OFFLOADED 04.05.2022 | * OFFLOADED 04.05.2022
BA1854 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20890 | CAT0030JFEK20944 | E7A48440 | FML2111DSI1322 | COD 2022 165474 | ND706468 | NS256330 | ND60176 | 11.04.2022 | OFFLOADED 09.05.2022 | 31.03.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 24.11.2021 | 13.04.2022 | 14.04.2022 | 14.04.2022 | 16.04.2022 | 18.04.2022 | 20.04.2022 | 22.04.2022 | 23.04.2022 | 25.04.2022 | 25.04.2022 | 26.04.2022 | 26.04.2022 | 27.04.2022 | 27.04.2022 | 27.04.2022 | 27.04.2022 | 27.04.2022 | 27.04.2022 | 28.04.2022 | 05.04.2022 | 06.05.2022 | 08.05.2022 | 08.05.2022 | 08.05.2022 | 09.05.2022 | [100 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR MONDAY 04.04.2022 | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * MACHINE TO LOAD TODAY AND DISPATCH TOMMROW THE 08/04/2022 | * THE MACHINE WILL DISPATCH DURBAN ON MONDAY THE 11/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON WEDNESDAY THE 13/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON WEDNESDAY THE 13/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * VEHICLE DISPATCHED DURBAN THIS MORNING. CURRENTLY AT MARIANHILL ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT ROEDTAN EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | KASUMBULESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALES ZAM SIDE ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENTLY AT KASUMBALES ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | OFFLOADED 09.05.2022
BA1855 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20853 | CAT00330LFEK20853 | E7A47800 | FML2111DSI1322 | COD 2022 165474 | ND834401 | ND854241 | ND60177 | 11.04.2022 | OFFLOADED 09.05.2022 | 31.03.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 24.11.2021 | 20.04.2022 | 21.04.2022 | 21.04.2022 | 22.04.2022 | 22.04.2022 | 22.04.2022 | 25.04.2022 | 26.04.2022 | 27/04/2022 | 27/04/2022 | 27/04/2022 | 27/04/2022 | 29/04/2022 | 29/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 03.05.2022 | 05.04.2022 | 06.05.2022 | 08.05.2022 | 08.05.2022 | 08.05.2022 | 09.05.2022 | [100 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR MONDAY 04.04.2022 | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * THE MACHINE WILL DISPATCH DURBAN ON WEDNESDAY THE 13/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON WEDNESDAY THE 13/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * PLANNING TO DISPATCH TOMMROW THE 20/04/2022 | * TRUCK AT ESCORT EN-ROUTE TO BEIT BRIDGE | * TRUCK AT MIDDELBURG EN-ROUTE TO BEIT BRIDGE | CHILILABOMBWE ENROUTE KASUMBALASE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | OFFLOADED 09.05.2022
BA1856 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20849 | CAT0030AFEK20849 | E7A47796 | FML2111DSI1322 | COD 2022 165474 | ND142761 | ND542263 | ND60178 | 11.04.2022 | OFFLOADED 09.05.2022 | 31.03.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 24.11.2021 | 20.04.2022 | 21.04.2022 | 21.04.2022 | 22.04.2022 | 22.04.2022 | 22.04.2022 | 25.04.2022 | 26.04.2022 | 27/04/2022 | 27/04/2022 | 27/04/2022 | 27/04/2022 | 29/04/2022 | 29/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 03.05.2022 | 05.04.2022 | 06.05.2022 | 08.05.2022 | 08.05.2022 | 08.05.2022 | 09.05.2022 | [100 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR MONDAY 04.04.2022 | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * THE MACHINE WILL DISPATCH DURBAN ON WEDNESDAY THE 13/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON WEDNESDAY THE 13/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * PLANNING TO DISPATCH TOMMROW THE 20/04/2022 | * TRUCK AT ESCORT EN-ROUTE TO BEIT BRIDGE | * TRUCK AT MIDDELBURG EN-ROUTE TO BEIT BRIDGE | CHILILABOMBWE ENROUTE KASUMBALASE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | OFFLOADED 09.05.2022
BA1927 | 1 X CAT DE450E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403829 PWE06286 LWL05222 | CAT00C13TDH403829 | N/A | FML2203DSI1445 | COD 2022 121717 | TBA | TBA | TBA | TBA | OFFLOADED 10.05.2022 | 03.04.2022 | 08.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.04.2022 | 19.04.2022 | 20.04.2022 | 21.04.2022 | 22.04.2022 | 22.04.2022 | 22.04.2022 | 23.04.2022 | 23.04.2022 | 24.04.2022 | 24.04.2022 | 24.04.2022 | 24.04.2022 | 24.04.2022 | 25.04.2022 | 26.04.2022 | 26.04.2022 | 28/04/2022 | 28/04/2022 | 28/04/2022 | 03.05.2022 | 04.05.2022 | 06.05.2022 | 09.05.2022 | 09.05.2022 | 10.05.2022 | [77 empty] | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | VESSEL IS IN AND WORKING | AWAITING TO LOAD THE CONTAINER FROM THE PORT | BV INSPECTION DONE, PLANNING TO LOAD AND DISPATCH ON MONDAY THE 11/04/2022 | BV INSPECTION DONE, PLANNING TO LOAD AND DISPATCH ON MONDAY THE 11/04/2022 | BV INSPECTION DONE, PLANNING TO LOAD AND DISPATCH ON MONDAY THE 11/04/2022 | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * TRUCK TO DISPATCH TODAY EN-ROUTE TO GROBLERSBRIDGE BORDER | * TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | * TRUCK TO DISPATCH JNB EN-ROUTE TO GROBLERSBRIDGE | KASUMBULESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE - AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | OFFLOADED 10.05.2022
BA1930 | 1 X CAT DE450E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH403822 PWE06282 LWL05209 | CAT00C13CDH403822 | N/A | FML2203DSI1445 | COD 2022 121717 | TBA | TBA | TBA | TBA | OFFLOADED 10.05.2022 | 03.04.2022 | 08.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.04.2022 | 19.04.2022 | 20.04.2022 | 21.04.2022 | 22.04.2022 | 22.04.2022 | 22.04.2022 | 23.04.2022 | 23.04.2022 | 24.04.2022 | 24.04.2022 | 24.04.2022 | 24.04.2022 | 24.04.2022 | 25.04.2022 | 26.04.2022 | 26.04.2022 | 28/04/2022 | 28/04/2022 | 28/04/2022 | 03.05.2022 | 04.05.2022 | 06.05.2022 | 09.05.2022 | 09.05.2022 | 10.05.2022 | [77 empty] | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAIITNG FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 14.03.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | AWAITING VESSEL ARRIVAL ON THE 04.04.2022 | VESSEL IS IN AND WORKING | AWAITING TO LOAD THE CONTAINER FROM THE PORT | BV INSPECTION DONE, PLANNING TO LOAD AND DISPATCH ON MONDAY THE 11/04/2022 | BV INSPECTION DONE, PLANNING TO LOAD AND DISPATCH ON MONDAY THE 11/04/2022 | BV INSPECTION DONE, PLANNING TO LOAD AND DISPATCH ON MONDAY THE 11/04/2022 | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * TRUCK TO DISPATCH TODAY EN-ROUTE TO GROBLERSBRIDGE BORDER | * TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | * TRUCK TO DISPATCH JNB EN-ROUTE TO GROBLERSBRIDGE | KASUMBULESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE - AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 2 | OFFLOADED 10.05.2022
BA2000 | 1 X NEW CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF300018 | CAT00345CKEF300018 | NTB10158 | FML2203DSI1487 | COD 2022 125236 | CR84FXGP | WGR358GP / WGR365GP | ND60707 | TBA | OFFLOADED 09.05.2022 | 08.02.2022 | 20.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.04.2022 | 21.04.2022 | 22.04.2022 | 23.04.2022 | 25.04.2022 | 25.04.2022 | 25.04.2022 | 26.04.2022 | 26.04.2022 | 27/04/2022 | 28/04/2022 | 29/04/2022 | 29/04/2022 | 29/04/2022 | 29/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 30/04/2022 | 05.05.2022 | 06.05.2022 | 08.05.2022 | 08.05.2022 | 08.05.2022 | 09.05.2022 | [77 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD / LOADING DELAYED DUE TO BAD WEATHER CONDITIONS IN RSA | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD / LOADING DELAYED DUE TO BAD WEATHER CONDITIONS IN RSA | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED ON FIRST AVAILABLE DATE | * BV INSPECTION BOOKED FOR TOMMROW THE 20/04/2022 | * BV INSPECTION BOOKED FOR TODAY THE 20/04/2022 | * VEHICLE TO BE DISPATCH TOMMROW THE 22.04.2022 EN-ROUTE TO BEITBRIDGE BORDER | KASUMBULESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBULESA ZAM SIDE - WAITING TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE AWAITING CLEARANCE | OFFLOADED 09.05.2022
BA2001 | 1 X NEW CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30021 | CAT00345CKEF30021 | NTB10197 | FML2203DSI1487 | COD 2022 125236 | JP79VKGP | CS71TPGP / CS88PXGP | ND60708 | TBA | OFFLOADED 09.05.2022 | 08.02.2022 | 20.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.04.2022 | 21.04.2022 | 24.04.2022 | 27.04.2022 | 27.04.2022 | 27.04.2022 | 27.04.2022 | 29/04/2022 | 29/04/2022 | 30.04.2022 | 30.04.2022 | 30.04.2022 | 30.04.2022 | 01.05.2022 | 01.05.2022 | 01.05.2022 | 02.05.2022 | 03.05.2022 | 03.05.2022 | 04.05.2022 | 05.05.2022 | 06.05.2022 | 08.05.2022 | 08.05.2022 | 08.05.2022 | 09.05.2022 | [77 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD / LOADING DELAYED DUE TO BAD WEATHER CONDITIONS IN RSA | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD / LOADING DELAYED DUE TO BAD WEATHER CONDITIONS IN RSA | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED ON FIRST AVAILABLE DATE | * BV INSPECTION BOOKED FOR TOMMROW THE 20/04/2022 | * BV INSPECTION BOOKED FOR TODAY THE 20/04/2022 | * VEHICLE TO BE DISPATCH TOMMROW THE 22.04.2022 EN-ROUTE TO BEITBRIDGE BORDER | CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHCILE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHCILE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | OFFLOADED 09.05.2022
BA1857 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK20848 | CAT0030VFEKI20848 | E7A47784 | FML2111DSI1322 | COD 2022 165474 | ND570587 | ND702944 | ND60179 | 11.04.2022 | * OFFLOADED 26 MAY 2022 | 31.03.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 24.11.2021 | 04.05.2022 | 04.05.2022 | 05.05.2022 | 06.05.2022 | 06.05.2022 | 06.05.2022 | 11.05.2022 | 12.05.2022 | 12.05.2022 | 16.05.2022 | 16.05.2022 | 16.05.2022 | 16.05.2022 | 17.05.2022 | 19.05.2022 | 20.05.2022 | 21.05.2022 | 22.05.2022 | 23.05.2022 | 23.05.2022 | 24.05.2022 | 25.05.2022 | 25.05.2022 | 26.05.2022 | [101 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR INSPECTION | * BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR MONDAY 04.04.2022 | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * AWAITING TRUCK DETAILS AND DISPATCH DATE | * THE MACHINE WILL DISPATCH DURBAN ON WEDNESDAY THE 13/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON WEDNESDAY THE 13/04/2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * THE MACHINE WILL DISPATCH DURBAN ON TUESDAY THE 19.04.2022 DUE TO BAD WEATHER CONDITIONS IN RSA | * PLANNING TO DISPATCH TOMMROW THE 20/04/2022 | * PLANNING TO DISPATCH TOMMROW THE 21/04/2022 | * TRUCK TO DISPATCH MONDAY THE 25/04/2022 | Loaded - Awaiting abnormal permit. - Wasn’t received on Friday due to the long weekend in RSA | * VEHICLE TO DISPATCH DURBAN TOMORROW 04.05.2022 | * VEHICLE CURRENTLY AT CATO RIDGE ENROUTE PIETERMARITZBURG | * VEHICLE CURRENLTY AT MIDDELBURG ENROUTE POLOKWANE | MAKUTI ENROUTE CHIRUNDU | KAPRI EN ROUTE KASUMBALESA | DISPATCHING KAPRI EN ROUTE KASUMBALESA | CHILILABOMBWE EN ROUTE KASUMBALESA | CHILILABOMBWE IN KASUMBALESA QUEUE | CHILILABOMBWE IN KASUMBALESA QUEUE | CHILILABOMBWE IN KASUMBALESA QUEUE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHING WHISKEY ENROUTE SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 26 MAY 2022
BA2003 | 1 X NEW CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30022 | CAT00345VKEF30022 | NTB10152 | FML2203DSI1487 | COD 2022 125234 | ND568309 | ND566910 / ND566910 | ND60709 | 04.05.2022 | * OFFLOADED 26 MAY 2022 | 08.02.2022 | 20.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 14.04.2022 | 04.05.2022 | 05.05.2022 | 06.05.2022 | 06.05.2022 | 07.05.2022 | 07.05.2022 | 11.05.2022 | 11.05.2022 | 12.05.2022 | 12.05.2022 | 16.05.2022 | 16.05.2022 | 16.05.2022 | 16.05.2022 | 16.05.2022 | 17.05.2022 | 17.05.2022 | 17.05.2022 | 18.05.2022 | 23.05.2022 | 24.05.2022 | 25.04.2022 | 25.05.2022 | 26.05.2022 | 26.05.2022 | [77 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | AWAITING VESSEL ARRIVAL ON THE 08.04.2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD / LOADING DELAYED DUE TO BAD WEATHER CONDITIONS IN RSA | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD / LOADING DELAYED DUE TO BAD WEATHER CONDITIONS IN RSA | * UNIT IN BONDED FACILITY - BV INSPECTION TO BE BOOKED ON FIRST AVAILABLE DATE | * BV INSPECTION BOOKED FOR TOMMROW THE 20/04/2022 | * BV INSPECTION BOOKED FOR TODAY THE 20/04/2022 | * VEHICLE PLANNING TO DISPATCH THE 27.04.2022 AWAITING TRUCK DETAILS | LOADED, WAITING POLICE ESCORT - PUBLIC HOLIDAY IN RSA TODAY | * VEHICLE AWAITING POLICE ESCORT - TO DISPATCH WEDNESDAY 04.05.2022 | * VEHICLE CURRENTLY AT CATO RIDGE ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT CATO RIDGE ENROUTE PIETERMARITZBURG | CHIRUNDU ZIM SIDE | KAFUE EN-ROUTE KASUMBALESA | CHINGOLA EN-ROUTE KASUMBALESA | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE IN QUEUE | KASUMBALESA ZAM SIDE IN QUEUE | KASUMBALESA ZAM SIDE IN QUEUE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHING WHISKEY ENROUTE SITE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 26 MAY 2022
BA2030 | 1 X NEW CAT D9 TRACTOR MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | AK4000470 | CAT000D9LAK400470 | TNR00236 | FML2204DSI1513 | COD 2022 183386 | HJT796MP | JPC983MP | ND60649 | 09.05.2022 | * OFFLOADED 26 MAY 2022 | 22.04.2022 | 28.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 26.04.2022 | 03.05.2022 | 04.05.2022 | 10.05.2022 | 10.05.2022 | 10.05.2022 | 10.05.2022 | 12.05.2022 | 14.05.2022 | 14.05.2022 | 16.05.2022 | 16.05.2022 | 16.05.2022 | 16.05.2022 | 17.05.2022 | 19.05.2022 | 19.05.2022 | 21.05.2022 | 22.05.2022 | 23.05.2022 | 23.05.2022 | 23.05.2022 | 25.05.2022 | 25.05.2022 | 26.05.2022 | 26.05.2022 | [113 empty] | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL IN ORDER TO TRACK VESSEL | AWAIITNG FINAL BILL IN ORDER TO TRACK VESSEL | AWAIITNG FINAL BILL IN ORDER TO TRACK VESSEL | * VESSEL OPAL ACE CURRENT ETA 25.04.2022 | * VESSEL OPAL ACE CURRENT ETA 25.04.2022 | * VESSEL OPAL ACE CURRENT ETA 25.04.2022 | * VESSEL OPAL ACE CURRENT ETA 25.04.2022 | BV INSPECTION COMPLETED - LOADING TUESDAY 02/05 | BV INSPECTION COMPLETED - LOADING TUESDAY 02.05.2022 - DISPATCH DATE TO BE CONFIRMED | * VEHICLE CURRENTLY AT JOHANNESBURG EBROUTE MUSINA | * VEHICLE CURRENTLY AT JOHANNESBURG WAITING SPARES VEHICLE IN ORDER TO PROCEED | CHIVHI ENROUTE HARARE | CHIRUNDU ZAM SIDE | LUSAKA EN-ROUTE KASUMBALESA | DISPATCHING LUSAKA EN-ROUTE KASUMBALESA | CHILILABOMBWE EN-ROUTE KASUMBALESA | CHILILABOMBWE IN QUEUE TO KASUMBALESA | CHILILABOMBWE IN QUEUE TO KASUMBALESA | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 26 MAY 2022
BA1893 | 1 X NEW CAT 336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | E7A43831 | CAT00336CJFW20939 | JFW20939 | FML2201DSI1400 | COD 2022174507 | JF47HVGP | HK63LCGP | ND62906 | 11.05.2022 | OFFLOADED 27-05-2022 | 19.04.2022 | 22.04.2022 | BV BOOKED AS SOON AS THE NUMBER WAS RECEIVED | 02.02.2022 | 11.05.2022 | 12.05.2022 | 13.05.2022 | 13.05.2022 | 13.05.2022 | 14.05.2022 | 14.05.2022 | 15.05.2022 | 15.05.2022 | 16.05.2022 | 16.05.2022 | 16.05.2022 | 18.05.2022 | 19.05.2022 | 20.05.2022 | 21.05.2022 | 22.05.2022 | 22.05.2022 | 23.05.2022 | 26.05.2022 | 26.05.2022 | 26.05.2022 | 27.05.2022 | 27.05.2022 | 27-05-2022 | [110 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | Dispatch date to be advise waiting return vehicle from the DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | JOHANNESBURG | CHIRUNDU ZAM SIDE | KAROI EN-ROUTE KASUMBALESA | CHIRUNDU EN-ROUTE KASUMBALESA | CHIRUNDU ZIM SIDE AWAIITNG RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | KAFUE EN-ROUTE TO KASUMBALESA | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALES DRC, IN QUEUE TO CROSS OVER TO WHISKEY | OFFLOADED 27-05-2022
BA1864 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F602063 | TBA | TBA | FML2204DSI1527 | COD 2022 180454 | JRT719MP | JMT934MP | ND60672 | 10.05.2022 | OFFLOADED 01-06-2022 | 21.04.2022 | 25.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.05.2022 | 12.05.2022 | 16.05.2022 | 17.05.2022 | 17.05.2022 | 17.05.2022 | 18.05.2022 | 20.05.2022 | 21.05.2022 | 22.05.2022 | 22.05.2022 | 23.05.2022 | 23.05.2022 | 23.05.2022 | 24.05.2022 | 24.05.2022 | 25.05.2022 | 26.05.2022 | 26.05.2022 | 27.05.2022 | 30-05-2022 | 30-05-2022 | 31-05-2022 | 01-06-2022 | 01-06-2022 | 01-06-2022 | [66 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 03.05.2022 | * VESSEL TORTUGAS CURRENT ETA 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * COLLECTING UNIT FROM PORT TODAY | LADYSMITH ENROUTE JOHANNESBURG | JOHANNESBURG UNDERGOING TRIP CHECK | JOHANNESBURG UNDERGOING TRIP CHECK | BEITBRIDGE RSA SIDE | BEITBRIDGE ZIM SIDE | CHINOYI EN-ROUTE TO HARARE | CHINOYI EN-ROUTE TO HARARE | * VEHICLE CURRENTLY AT LUSAKAENROUTE KABWE | * VEHICLE CURRENTLY AT KABWE ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT CHAMBISI ENROUTE CHINGOLA | OFFLOADED 01-06-2022
BA2030 | 1 X NEW CAT D9 TRACTOR PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | AK4000470 | CAT000D9LAK400470 | TNR00236 | FML2204DSI1513 | COD 2022 183386 | AAV1948 | ACG5153T / ACG5154T | ND60649 | 09.05.2022 | OFFLOADED 03-06-2022 | 22.04.2022 | 28.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 26,04,2022 | 06,05,2022 | 06,05,2022 | 10.05.2022 | 10.05.2022 | 10,05,2022 | 10.05.2022 | 12.05.2022 | 14.05.2022 | 14.05.2022 | 15.05.2022 | 15.05.2022 | 15.05.2022 | 15.05.2022 | 16.05.2022 | 16.05.2022 | 17.05.2022 | 17.05.2022 | 18.05.2022 | 18.05.2022 | 23.05.2022 | 23.05.2022 | 01-06-2022 | 01-06-2022 | 02-06-2022 | 03-06-2022 | [113 empty] | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL IN ORDER TO TRACK VESSEL | AWAIITNG FINAL BILL IN ORDER TO TRACK VESSEL | AWAIITNG FINAL BILL IN ORDER TO TRACK VESSEL | * VESSEL OPAL ACE CURRENT ETA 25.04.2022 | * VESSEL OPAL ACE CURRENT ETA 25.04.2022 | * VESSEL OPAL ACE CURRENT ETA 25.04.2022 | * VESSEL OPAL ACE CURRENT ETA 25.04.2022 | BV INSPECTION COMPLETED - LOADING TUESDAY 02/05 | BV INSPECTION COMPLETED - LOADING TUESDAY 02.05.2022 - DISPATCH DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING TUESDAY 02.05.2022 - DISPATCH DATE TO BE CONFIRMED | * VEHICLE PLANNING TO DISPATCH DURBAN THIS AFTERNOON | CHINOYI ENROUTE HARARE | NDOLA EN-ROUTE KASUMBALESA | CHINGOLA EN-ROUTE KASUMBALESA | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE IN QUEUE | KASUMBALESA ZAM SIDE IN QUEUE | KASUMBALESA ZAM SIDE IN QUEUE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY WHISKEY AWAITING CLEARANCE | OFFLOADED 03-06-2022 | OFFLOADED 03-06-2022
BA1903 | 1 X NEW CAT 336-07B HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12125 | CAT00336TGDY12125 | NTB05878 | FML2201DSI1385 | COD 2022174507 | JB32HLGP | JZ86SRGP | ND60763 | 11.05.2022 | OFFLOADED | 19.04.2022 | 22.04.2022 | BV BOOKED AS SOON AS THE NUMBER WAS RECEIVED | 28.01.2022 | 18.05.2022 | 19.05.2022 | 20.05.2022 | 20.05.2022 | 21.05.2022 | 21.05.2022 | 22.05.2022 | 22.05.2022 | 23.05.2022 | 24.05.2022 | 27-05-2022 | 27-05-2022 | 29-20-2022 | 30-05-2022 | 30-05-2022 | 30-05-2022 | 31-05-2022 | 31-05-2022 | 31-05-2022 | 03-06-2022 | 04-06-2022 | 05-06-2022 | 06-06-2022 | 06-06-2022 | 06-06-2022 | [110 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | Loading 12/05 - waiting return vehicle from the DRC | * VEHICLE PLANNING TO LOAD 12.05.2022 - WAITING RETURN VEHICLE FROM THE DRC | * VEHICLE PLANNING TO LOAD 12.05.2022 - WAITING RETURN VEHICLE FROM THE DRC | * VEHICLE PLANNING TO LOAD 12.05.2022 - WAITING RETURN VEHICLE FROM THE DRC | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | DISPTACHING DURBAN TODAY EN-ROUTE BEITBRIDGE | GROBLERSDAL EN-ROUTE BEITBRIDGE | MUSINA EN-ROUTE BEITBRIDGE | MUSINA EN-ROUTE BEITBRIDGE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM - ATTENDING TO MINOR BREAKDOWN | KASUMBULESA DRC SIDE | LUBUMBASHI EN-ROUTE TO SITE | OFFLOADED
BA1996 | 1 X CAT 950GC WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M5K05795 | CAT00950WM5K05795 | E7A50983 | FML2203DSI1462 | COD 2022 175165 | KG17GHGP | BX45RWGP | ND62996 | 14.04.2022 | OFFLOADED | 12.04.2022 | 14.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 29.03.2022 | 21.04.2022 | 25.04.2022 | 27.04.2022 | 27.04.2022 | 27.04.2022 | 27.04.2022 | 15.05.2022 | 16.05.2022 | 16.05.2022 | 20.05.2022 | 23.05.2022 | 24.05.2022 | 26.05.2022 | 27-05-2022 | 28-05-2022 | 28-05-2022 | 28-05-2022 | 29-05-2022 | 30-05-2022 | 02-06-2022 | 02-06-2022 | 06-06-2022 | 06-06-2022 | 06-06-2022 | 06-06-2022 | [96 empty] | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING MACHINE FROM THE PORT TODAY, AWAIITNG BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY. BV INSPECTION DELAYED DUE TO BAD WEATHER IN RSA. | * MACHINE IS AT OUR FACILITY. BV INSPECTION DELAYED DUE TO BAD WEATHER IN RSA. | * BV INSPECTION BOOKED FOR TODAY | * TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT JNB UNDERGOING TRIP CHECK | * VEHICLE TO BE DISPATCH TOMMROW THE 22.04.2022 EN-ROUTE TO BEITBRIDGE BORDER | BEIT BRIDGE ZIM SIDE CLEARING | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING PERMITS | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING PERMITS | MASVINGO ENROUTE HARARE | HARARE EN-ROUTE CHIRUNDU | DISPATCHING HARARE EN-ROUTE CHIRUNDU | TRUCK AT HARARE ATTENDING TO MINOR BREAKDOWN | TRUCK AT HARARE ATTENDING TO MINOR BREAKDOWN | TRUCK DISPATCHING HARARE TODAY EN-ROUTE TO CHIRUNDU | TRUCK DISPATCHING HARARE TODAY EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHICLE DISPATCHING CHIRUNDU ENROUTE LUSAKA | WHISKEY | LUBUMBASHI EN-ROUTE TO SITE | OFFLOADED
BA2059 | 1 X CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201124 | CAT00140TW9201124 | E7A50957 | FML2203DSI1463 | COD 2022 175169 | HB 03 ZN GP | KG66HXGP | ND62998 | 14.04.2022 | OFFLOADED | 14.04.2022 | 14.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 31.03.2022 | 19.04.2022 | 20.04.2022 | 25.04.2022 | 25.04.2022 | 25.04.2022 | 25.04.2022 | 20.05.2022 | 21.05.2022 | 22.05.2022 | 23.05.2022 | 23.05.2022 | 24.05.2022 | 27.05.2022 | 27-05-2022 | 28-05-2022 | 28-05-2022 | 28-05-2022 | 29-05-2022 | 30-05-2022 | 02-06-2022 | 02-06-2022 | 04-06-2022 | 06-06-2022 | 06-06-2022 | 06-06-2022 | [96 empty] | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING MACHINE FROM THE PORT TODAY, AWAIITNG BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * BV NUMBER RECEIVED - BV NOT VALIDATED ON THE SYSTEM | * BV NUMBER RECEIVED - BV NOT VALIDATED ON THE SYSTEM | * BV INSPECTION BOOKED FOR TODAY | * TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT JNB UNDERGOING TRIP CHECK | * TRUCK TO DISPATCH JNB TOMMROW THE 22/04/2022 EN-ROUTE TO BEIR BRIDGE BORDER | BEIT BRIDGE ZIM SIDE CLEARING | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING PERMITS | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING PERMITS | MASVINGO ENROUTE HARARE | BEITBRIDGE ZIM SIDE | BEITBRIDGE ZIM SIDE | BEITBRIDGE ZIM SIDE AWAIITNG RELEASE | BEITBRIDGE ZIM SIDE AWAIITNG RELEASE | TRUCK AT BUBI EN-ROUTE TO HARARE | TRUCK AT BUBI EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAIITNG RELEASE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAIITNG RELEASE | WHISKEY | LUBUMBASHI EN-ROUTE TO SITE | OFFLOADED
BA2082 | 1 X CAT 320GC-07E HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DKJ40137 | CAT00320KDKJ40137 | 2W232572 | FML2203DSI1466 | COD 2022 175159 | KG 17 GH GP | KHM039MP | ND62997 | 14.04.2022 | OFFLOADED | 14.04.2022 | 14.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 29.03.2022 | 19.04.2022 | 25.04.2022 | 06,05,2022 | 09.05.2022 | 09.05.2022 | 09.05.2022 | 20.05.2022 | 22.05.2022 | 22.05.2022 | 23.05.2022 | 23.05.2022 | 24.05.2022 | 26-05-2022 | 26-05-2022 | 27-05-2022 | 27-05-2022 | 28-05-2022 | 29-05-2022 | 30-05-2022 | 02-06-2022 | 02-06-2022 | 04-06-2022 | 06-06-2022 | 06-06-2022 | 06-06-2022 | [96 empty] | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAIITNG VESSEL ARRIVAL | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | AWAITNG VESSEL ARRIVAL ON THE 29.03.2022 | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING MACHINE FROM THE PORT TODAY, AWAIITNG BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY, AWAITING BV NUMBER | * MACHINE IS AT OUR FACILITY. BV INSPECTION DELAYED DUE TO BAD WEATHER IN RSA. | * MACHINE IS AT OUR FACILITY. BV INSPECTION DELAYED DUE TO BAD WEATHER IN RSA. | * BV INSPECTION BOOKED FOR TODAY | * TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT JNB UNDERGOING TRIP CHECK | * TRUCK TO DISPATCH JNB TOMMROW THE 22/04/2022 EN-ROUTE TO BEIR BRIDGE BORDER | POLOKWANE - VEHICLE STOPPED BY POLICE DUE TO THE LONG WEEKEND IN RSA | * VEHICLE CURRENTLY AT POLOKWANE - AWAITING POLICE ESCORT | * VEHICLE CURRENTLY AT POLOKWANE - AWAITING POLICE ESCORT & PERMITS | * VEHICLE CURRENTLY AT POLOKWANE - AWAITING POLICE ESCORT & PERMITS | BEIT BRIDGE ZIM SIDE - WAITING ZIM PERMITS | BEIT BRIDGE ZIM SIDE - WAITING ZIM PERMITS | BEIT BRIDGE ZIM SIDE - WAITING ZIM PERMITS | BEIT BRIDGE ZIM SIDE - WAITING RELEASE | BEIT BRIDGE ZIM SIDE - WAITING RELEASE | TRUCK AT BUBI EN-ROUTE TO HARARE | TRUCK AT BUBI EN-ROUTE TO HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | WHISKEY | LUBUMBASHI EN-ROUTE TO SITE | OFFLOADED
BA1678 | 1 X NEW CAT 777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KYD00236 | CAT0777EAKYD00236 | FZS01816 | FML2109DSI1279 | COD 2022 168417 | FS26XSGP | KB37RRGP / KB35KCGP | ND60108 | 03.05.2022 | OFFLOADED | 01.04.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 28.09.2022 | 03.05.2022 | 10.05.2022 | 10.05.2022 | 15.05.2022 | 16.05.2022 | 19.05.2022 | 20.05.2022 | 21.05.2022 | 22.05.2022 | 23.05.2022 | 24.05.2022 | 25.05.2022 | 01-06-2022 | 01-06-2022 | 02-06-2022 | 02-06-2022 | 04-06-2022 | 04-06-2022 | 06-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | [99 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | * BV INSPECTION BOOKED FOR TODAY - PLANNING TO DISPATCH ON THE 19/04/2022 | * PLANNING TO LOAD AND DISPATCH ON WEDNESDAY THE 20/04/2022 | * PLANNING TO LOAD AND DISPATCH ON THURSDAY THE 21/04/2022 | * PLANNING TO LAOD NEXT WEEK MONDAY THE 25/04/2022 | Loaded on Truck - Awaiting issuance of Permits on the B Route. Dispatch date to be confirmed once permit is issued | * VEHICLE AWAITING POLICE ESCORT | * VEHICLE CURRENTLY AT CAMPERDOWN ENROUTE PIETERMARITZBURG | * VEHICLE CURRENTLY AT CAMPERDOWN AWAITING ESCORTS | DELMAS ENROUTE BEIT BRIDGE | POLOKWANE EN ROUTE BEIT BRIDGE | POLOKWANE AWAITING COPS IN ORDER TO PROCEED TO BEITBRIDGE | VIVO EN-ROUTE TO BEITBRIDGE | BEITBRIDGE RSA SIDE | BEITBRIDGE RSA SIDE AWAITING RELEASE | BEITBRIDGE RSA SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAIITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITING PERMIT | NDOLA ENROUTE KASUMBULESA | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE | DISPATCHING KASUMBALESA EN-ROUTE TO LUBUMBASHI | OFFLOADED | OFFLOADED | OFFLOADED
BA1679 | 1 X NEW CAT 777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KYD00237 | CAT0777ELKYD00237 | FZS01818 | FML2109DSI1279 | COD 2022 168417 | DM28SJGP | KB37DZGP / KB37CPGP | ND60109 | 03.05.2022 | OFFLOADED | 01.04.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 28.09.2022 | 09.05.2022 | 19.05.2022 | 19.05.2022 | 20.05.2022 | 21.05.2022 | 21.05.2022 | 22.05.2022 | 22.05.2022 | 23.05.2022 | 23.05.2022 | 24.05.2022 | 25.05.2022 | 02-06-2022 | 02-06-2022 | 02-06-2022 | 02-06-2022 | 04-06-2022 | 04-06-2022 | 06-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | [99 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | * BV INSPECTION BOOKED FOR TODAY - PLANNING TO DISPATCH ON THE 19/04/2022 | * PLANNING TO LOAD AND DISPATCH ON WEDNESDAY THE 20/04/2022 | * PLANNING TO LOAD AND DISPATCH ON THURSDAY THE 21/04/2022 | * PLANNING TO LAOD NEXT WEEK MONDAY THE 25/04/2022 | Truck enroute to Durban for loading. To be loaded on 05/05 due to public holidays and road closures in RSA, departure depended on the issuance of permits by the permit office | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA. DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | PIETERMARITZBURG | WEENEN EN-ROUTE BEITBRIDGE | VOLKSRUST EN-ROUTE BEITBRIDGE | BETHAL EN-ROUTE BEITBRIDGE | ROEDTAN EN-ROUTE BEITBRIDGE | VIVO EN-ROUTE BEITBRIDGE | VIVO EN-ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAIITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITING PERMIT | LUSAKA | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE | DISPATCHING KASUMBALESA EN-ROUTE TO LUBUMBASHI | OFFLOADED | OFFLOADED | OFFLOADED
BA1742 | 1 X NEW CAT 966GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW00779 | CAT00966CSGW00779 | NTB08507 | FML2204DSI1501 | COD 2022179107 | KN94WZGP | XTY811GP | ND60662 | 11.05.2022 | OFFLOADED | 21.04.2022 | 03.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 26.04.2022 | 21.05.2022 | 22.05.2022 | 24.05.2022 | 25.05.2022 | 25.05.2022 | 26.05.2022 | 27.05.2022 | 28-05-2022 | 28-05-2022 | 29-05-2022 | 30-05-2022 | 30-05-2022 | 02-06-2022 | 02-06-2022 | 02-06-2022 | 02-06-2022 | 03-06-2022 | 03-06-2022 | 04-06-2022 | 08-06-2022 | 08-06-2022 | 10-06-2022 | 10-06-2022 | 10-06-2022 | 10-06-2022 | [113 empty] | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL AND INVOICE | AWAITNG FINAL BILL AND INVOICE | AWAITNG FINAL BILL AND INVOICE | AWAITNG FINAL BILL IN ORDER TO TRACK VESSEL | AWAITNG FINAL BILL IN ORDER TO TRACK VESSEL | AWAITNG FINAL BILL IN ORDER TO TRACK VESSEL | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - anticipated load date 08/05 due to limited movement out of port due to flood damage | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - ANTICIPATED LOAD DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGES | * BV INSPECTION TO BE BOOKED FOR THURSDAY 05.05.2022 - ANTICIPATED LOAD DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGES | * ANTICIPATED LOAD DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGES | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADEING DATE 17.05.2022 - RTI COMFIRMED THAT PERMITS WILL BE ISSUED ON THE 16/05 TO DEPART 17/05 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADEING DATE 17.05.2022 - RTI COMFIRMED THAT PERMITS WILL BE ISSUED ON THE 16/05 TO DEPART 17/05 | MACHINE TO LOAD TODAY, TRUCK TO DISPATCH TOMMROW THE 18/05/2022 | MACHINE TO LOAD TODAY, TRUCK TO DISPATCH THE 20/05/2022 | TRUCK LOADED AND WILL DISPATCH MONDAY THE 23/05/2022-TRUCK UNDERGOING TRIP CHECK | TRUCK LOADED AND WILL DISPATCH MONDAY THE 23/05/2022-TRUCK UNDERGOING TRIP CHECK | TRUCK LOADED AND WILL DISPATCH MONDAY THE 23/05/2022-TRUCK UNDERGOING TRIP CHECK | * VEHICLE DISPATCHING PRETORIA ENROUTE BEITBRIDGE BORDER | * VEHICLE DISPATCHING PIENAARSRIVIER ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT BEITBRIDGE AWAITING CLEARANCE | ENROUTE KITWE | TRUCK AT KASUMBALESA ZAM SIDE | TRUCK AT KASUMBALESA DRC SIDE | TRUCK AT WHISKEY AWAITING FINAL RELEASE | TRUCK AT WHISKEY AWAITING FINAL RELEASE | OFFLOADED | OFFLOADED
BA1743 | 1 X NEW CAT 966GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW00778 | CAT00966ESGW00778 | NTB09919 | FML2204DSI1502 | COD 2022179107 | NJ100398 | NJ102487 | ND60663 | 11.05.2022 | OFFLOADED | 21.04.2022 | 03.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 26.04.2022 | 18.05.2022 | 20.05.2022 | 21.05.2022 | 21.05.2022 | 22.05.2022 | 23.05.2022 | 24.05.2022 | 24.05.2022 | 25.05.2022 | 27.05.2022 | 28-05-2022 | 28-05-2022 | 29-05-2022 | 30-05-2022 | 30-05-2022 | 30-05-2022 | 31-05-2022 | 31-05-2022 | 31-05-2022 | 06-06-2022 | 06-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | [113 empty] | AWAIITNG FINAL BILL AND INVOICE | AWAIITNG FINAL BILL AND INVOICE | AWAITNG FINAL BILL AND INVOICE | AWAITNG FINAL BILL AND INVOICE | AWAITNG FINAL BILL IN ORDER TO TRACK VESSEL | AWAITNG FINAL BILL IN ORDER TO TRACK VESSEL | AWAITNG FINAL BILL IN ORDER TO TRACK VESSEL | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - anticipated load date 08/05 due to limited movement out of port due to flood damage | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - ANTICIPATED LOAD DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGES | * BV INSPECTION TO BE BOOKED FOR THURSDAY 05.05.2022 - ANTICIPATED LOAD DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGES | * ANTICIPATED LOAD DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGES | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADEING DATE 18.05.2022 - RTI COMFIRMED THAT PERMITS WILL BE ISSUED ON THE 17/05 TO DEPART 18/05 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADEING DATE 18.05.2022 - RTI COMFIRMED THAT PERMITS WILL BE ISSUED ON THE 17/05 TO DEPART 18/05 | TRUCK TO LOAD AND DISPATCH TODAY THE 17/05/2022 | TRUCK DISPATCH DURBAN EN-ROUTE TO BEIT BRIDGE | VOLKRUST EN-ROUTE TO BEITBRIDGE | MIDDELBURG EN-ROUTE TO BEITBRIDGE | MIDDELBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT NGUNDU ENROUTE HARARE | * VEHICLE CURRENLTY AT CHINHOYI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT MAKUTI ENROUTE CHIRUNDU | KASUMBULESA DRC SIDE | TRUCK AT WHISKEY | TRUCK AT WHISKEY AWAIITNG RELEASE | TRUCK AT LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED
BA1894 | 1 X NEW CAT 336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | E7A43841 | CAT00336CJFW20947 | JFW20947 | FML2201DSI1400 | COD 2022174507 | JML417MP | JML416MP / JMM291MP | ND62907 | 11.05.2022 | OFFLOADED | 19.04.2022 | 22.04.2022 | BV BOOKED AS SOON AS THE NUMBER WAS RECEIVED | 02.02.2022 | 23.05.2022 | 23.05.2022 | 24.05.2022 | 24.05.2022 | 24.05.2022 | 25.04.2022 | 27.05.2022 | 28-05-2022 | 28-05-2022 | 28-05-2022 | 29-05-2022 | 29-05-2022 | 30-05-2022 | 30-05-2022 | 30-05-2022 | 30-05-2022 | 30-05-2022 | 30-05-2022 | 30-05-2022 | 07-06-2022 | 08-06-2022 | 08-06-2022 | 09-06-2022 | 09-06-2022 | 09-06-2022 | [110 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 20/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 25/05/2022 | TRUCK TO LOAD TODAY AND DISPATCH MONDAY THE 23/05/2022 | TRUCK TO LOAD TODAY AND DISPATCH MONDAY THE 23/05/2022 | * VEHICLE CURRENTLY AT PRETORIA ENROUTE JOHANNESBURG | * VEHICLE CURRENLY AT BEITBRIDGE AWAITING CLEARNCE | * VEHICLE CURRENLY AT BEITBRIDGE ZIM SIDE - AWAITING CLEARNCE | KASUMBULESA DRC SIDE | KASUMBULESA DRC SIDE | KASUMBULESA DRC SIDE | LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED
BA1719 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FEK20942 | CAT00330PFEK20942 | E7A48436 | FML2111DSI1322 | COD 2022 174507 | ND706468 | ND256330 | ND60174 | 11.05.2022 | * OFFLOADED 12.06.2022 | 19.04.2022 | 22.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 24.11.2021 | 23.05.2022 | 24.05.2022 | 24.05.2022 | 26.05.2022 | 26.05.2022 | 27.05.2022 | 28-05-2022 | 29-05-2022 | 30-05-2022 | 30-05-2022 | 31-05-2022 | 31-05-2022 | 01-06-2022 | 02-06-2022 | 02-06-2022 | 02-06-2022 | 02-06-2022 | 04-06-2022 | 06-06-2022 | 08-06-2022 | 08-06-2022 | 10.06.2022 | 11.06.20222 | 12.06.2022 | 12.06.2022 | [110 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | LOADING AND DISPATCH 16 / 17 OF MAY | LOADING AND DISPATCH 16 / 17 OF MAY | LOADING AND DISPATCH 18 / 19 OF MAY | LOADING AND DISPATCH 23RD OF MAY | LOADING AND DISPATCH 23RD OF MAY | LOADING AND DISPATCH 23RD OF MAY | LOADING AND DISPATCH 23RD OF MAY | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT POLOKWANE ENROUTE BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE BORDER | CHINGOLA | KASUMBALESA ZAM SIDE | KASUMBALESA DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE DAY 3 | * OFFLOADED 12.06.2022 | * OFFLOADED 12.06.2022
BA1721 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FEK20941 | CAT00330TFEK20941 | E7A48422 | FML2111DSI1322 | COD 2022174507 | ND834401 | ND854241 | ND60175 | 11.05.2022 | * OFFLOADED 15.06.2022 | 19.04.2022 | 22.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 24.11.2021 | 23.05.2022 | 24.05.2022 | 24.05.2022 | 26.05.2022 | 26.05.2022 | 27.05.2022 | 28-05-2022 | 29-05-2022 | 30-05-2022 | 30-05-2022 | 31-05-2022 | 31-05-2022 | 01-06-2022 | 02-06-2022 | 02-06-2022 | 02-06-2022 | 02-06-2022 | 04-06-2022 | 06-06-2022 | 08-06-2022 | 08-06-2022 | 13.06.2022 | 14.06.2022 | 15.06.2022 | 15.06.2022 | [110 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | Waiting for truck to return form DRC, Loading on the 09/05 due to public holidays and road closures in RSA | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | LOADING AND DISPATCH 16 / 17 OF MAY | LOADING AND DISPATCH 16 / 17 OF MAY | LOADING AND DISPATCH 18 / 19 OF MAY | LOADING AND DISPATCH 23RD OF MAY | LOADING AND DISPATCH 23RD OF MAY | LOADING AND DISPATCH 23RD OF MAY | LOADING AND DISPATCH 23RD OF MAY | * VEHICLE CURRENTLY AT VOLKSRUST ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT ERMELO ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE BORDER | CHINGOLA | KASUMBALESA ZAM SIDE | KASUMBALESA DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE DAY 3 | WHISKEY AWAITING RELEASE DAY 5 | * VEHICLE IN QUEUE TO DISPATCH WHISKEY | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 15.06.2022 | * OFFLOADED 15.06.2022
BA2058 | 1 X NEW CAT 140K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZL20750 | CAT0140KJSZL20750 | TX711900 | FML2204DSI1514 | COD 2022 184713 | ABQ6861 | ABJ8174 | ND60676 | 23.05.2022 | OFFLOADED 17-06-2022 | 26.04.2022 | 10.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.05.2022 | 16.05.2022 | 18.05.2022 | 20.05.2022 | 26.05.2022 | 26.05.2022 | 27.05.2022 | 31-05-2022 | 01-06-2022 | 03-06-2022 | 06-06-2022 | 07-06-2022 | 07-06-2022 | 07-06-2022 | 08-06-2022 | 10.06.2022 | 10.06.2022 | 11.06.2022 | 12.06.2022 | 13.06.2022 | 14.06.2022 | 15.06.2022 | 16.06.2022 | 17.06.2022 | 17-06-2022 | 17-06-2022 | [113 empty] | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | * VESSEL GLOVIS SONIC CURRENT ETA 03.05.2022 | * VESSEL GLOVIS SONIC CURRENT ETA 03.05.2022 | * VESSEL GLOVIS SONIC CURRENT ETA 03.05.2022 | * VESSEL GLOVIS SONIC CURRENT ETA 03.05.2022 | * VESSEL GLOVIS SONIC CURRENT ETA 04.05.2022 | * VESSEL GLOVIS SONIC CURRENT ETA 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * VESSEL CURRENT ETA 06.05.2022 | LOADING TODAY | TRUCK AT MARIANHILL TOLL EN-ROUTE TO BEITBRIDGE | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE | TRUCK AT JNB UNDERGOING TRIP CHECK | TRUCK AT JNB UNDERGOING TRIP CHECK | TRUCK TO DISPATCH JNB TODAY EN-ROUTE TO BEITBRIDGE | TRUCK TO DISPATCH JNB TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT HARRISMITH ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT HARRISMITH ENROUTE JOHANNESBURG | HARARE - MAINTENANCE CHECK | CHIRUNDI AWAITNG RELEASE | DISPATCHING CHIRUNDU | KAFUE EN-ROUTE TO KASUMBALESA BORDER | TRUCK ON BREAKDOWN AT KAFUE, TRUCK TO DISPATCH TOMMROW | TRUCK ON BREAKDOWN AT KAFUE, BUSY WITH REPAIRS | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA CUSTOMS - UNDERGOING FINAL CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 17-06-2022
BA2060 | 1 X NEW CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201154 | CAT00140CW9201154 | E7A50947 | FML2204DSI1503 | COD 2022 184713 | PWM289GP | KF38BVGP | ND60662 | TBA | OFFLOADED 18-06-2022 | 26.04.2022 | 03.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 26.04.2022 | 30-05-2022 | 31-05-2022 | 01-06-2022 | 01-06-2022 | 01-06-2022 | 01-06-2022 | 05-06-2022 | 05-06-2022 | 06-06-2022 | 07-06-2022 | 07-06-2022 | 07-06-2022 | 07-06-2022 | 08-06-2022 | 10.06.2022 | 10.06.2022 | 11.06.2022 | 12.06.2022 | 13.06.2022 | 14.06.2022 | 15.06.2022 |  | 18-06-2022 | 18-06-2022 | 18-06-2022 | [113 empty] | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - anticipated load date 08/05 due to limited movement out of port due to floud damage | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | * ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | * ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 18/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 19/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 19/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 27.05.2022 | WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 27.05.2022 | BEIT BRIDGE RSA SIDE | BEIT BRIDGE ZIM SIDE | CHIRUNDU AWAITING RELEASE | CHIRUNDU AWAITING RELEASE | CHIRUNDU AWAITING RELEASE | DISPATCHING CHIRUNDU EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | OFFLOADED 18-06-2022
BA2080 | 1 X NEW CAT CS74B VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | B7M00409 | CATCS74BAB7M00409 | E7A52827 | FML2204DSI1516 | COD 2022 178987 | ND491242 | ND629383 | ND60675 | TBA | OFFLOADED 18-06-2022 | 19.04.2022 | 03-05-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 26-04-2022 | 30-05-2022 | 31-05-2022 | 01-06-2022 | 01-06-2022 | 01-06-2022 | 01-06-2022 | 02.06.2022 | 08.06.2022 | 08.06.2022 | 08.06.2022 | 09.06.2022 | 09.06.2022 | 10.06.2022 | 10.06.2022 | 11.06.2022 | 11.06.2022 | 12.06.2022 | 12.06.2022 | 13.06.2022 | 14.06.2022 | 15.06.2022 | 18-06-2022 | 18-06-2022 | 18-06-2022 | 18-06-2022 | [113 empty] | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 18/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 19/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 19/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO STILL RETURN FROM DRC - ESTIMATED LOADING DATE 24/05/2022 | WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 27.05.2022 | WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 27.05.2022 | BEIT BRIDGE RSA SIDE | BEIT BRIDGE ZIM SIDE | CHIRUNDU ZIM SIDE AWAITING RELEASE | CHIRUNDU ZIM SIDE AWAITING RELEASE | CHIRUNDU ZIM SIDE AWAITING RELEASE | DISPATCHING CHIRUNDU EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | OFFLOADED 18-06-2022
BA1811 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F602059 | CAT00745V3F602059 | TBA | FML2204DSI1525 | COD 2022 180454 | 2580AA24 | 2581AA24 | ND60670 | 10.05.2022 | OFFLOADED 18-06-2022 | 21.04.2022 | 25.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.05.2022 | 23.05.2022 | 24.05.2022 | 24.05.202 | 25.05.2022 | 25.05.2022 | 26.05.2022 | 01-06-2022 | 02-06-2022 | 04-06-2022 | 06-06-2022 | 09-06-2022 | 09-06-2022 | 09-06-2022 | 10-06-2022 | 11.06.2022 | 12.06.2022 | 12.06.2022 | 13.06.2022 | 14.06.2022 | 16.06.2022 | 17.06.2022 | 17-06-2022 | 17-06-2022 | 17-06-2022 | 18-06-2022 | [120 empty] | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 03.05.2022 | * VESSEL TORTUGAS CURRENT ETA 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * UNIT TO BE LOADED FROM PORT TODAY | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | TRUCK TO LOAD TODAY AND DISPATCH TOMMROW THE 19.05.2022 | TRUCK TO LOAD TODAY AND DISPATCH MONDAY THE 23/05/2022 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY IN JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENLTY AT ALLDAYS ENROUTE BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE AWAITING CLEARANCE | HARARE | CHIRUNDU ZAM SIDE | CHIRUNDU ZAM SIDE AWAITING RELEASE | CHIRUNDU ZAM WAITING PERMIT | DISPATCHING CHIRUNDU EN-ROUTE LUSAKA | KITWE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE TO DISPATCH THIS MORNING | * VEHICLE CURRENLY AT WHISKEY AWAITING CLEARANCE | OFFLOADED 18-06-2022
BA1697 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F602053 | CAT00745C3F602053 | TBA | FML2204DSI1522 | COD 2022 180454 | ND705348 | ND476150 | ND60668 | 10.05.2022 | OFFLOADED 17-06-2022 | 21.04.2022 | 10.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.05.2022 | 24.05.2022 | 28-05-2022 | 28-05-2022 | 01-06-2022 | 01-06-2022 | 01-06-2022 | 04-06-2022 | 06-06-2022 | 06-06-2022 | 07-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 08-06-2022 | 09-06-2022 | 11.06.2022 | 12.06.2022 | 13.06.2022 | 14.06.2022 | 15.06.2022 | 17-06-2022 | 17-06-2022 | 17-06-2022 | 17-06-2022 | [61 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 03.05.2022 | * VESSEL TORTUGAS CURRENT ETA 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNIT ONCE AVAILABLE, | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | * VEHICLE DISPATCHING DURBAN ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT HARRYSMITH ENROUTE JOHANNESBURG | BEIT BRIDGE RSA SIDE | HARARE EN-ROUTE TO CHIRUNDU | CHIRUNDU ZIM SIDE AWAITING RELEASE | CHIRUNDU ZIM SIDE AWAITING RELEASE | KABWE EN-ROUTE TO KASUMBALESA | CHINGOLA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | OFFLOADED 17-06-2022
BA2028 | 1 X NEW CAT777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JPE00855 | N/A | N/A | FML2204DSI1533 | COD 2022 187690 | FV44CKGP | XFL528GP / XFL544GP | FK2204DSI1537A | 09.05.2022 | OFFLOADED 27-06-2022 | 02.05.2022 | 09.05.2022 | BV INSPECTION COMPLETED 05/05/2022 | 04.05.2022 | 11.05.2022 | 16.05.2022 | 17.05.2022 | 01-06-2022 | 01-06-2022 | 01-06-2022 | 02-06-2022 | 03.06.2022 | 03.06.2022 | 06.06.2022 | 08.06.2022 | 09.06.2022 | 15.06.2022 | 16.06.2022 | 16.06.2022 | 17.06.2022 | 17-06-2022 | 20-06-2022 | 22-06-2022 | 23-06-2022 | 24-06-2022 | 25-06-2022 | 26-06-2022 | 27-06-2022 | 27-06-2022 | [113 empty] | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | VESSEL: BAHRI JAZAN - AWAITING VESSEL ARRIVAL ON THE 03/05/2022 | VESSEL: BAHRI JAZAN - AWAITING VESSEL ARRIVAL ON THE 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * BV INSPECTION BOOKED FOR FRIDAY 06.05.2022 | CAMPERDOWN WAITING POLICE ESCOURTS | TRUCK AT ESTON EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH ESTON EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JAAGBAAN EN-ROUTE TO BEITBRIDGE BORDER | COLENSO EN-ROUTE TO BEITBRIDGE BORDER | LADYSMITH EN-ROUTE TO BEITBRIDGE BORDER | LADYSMITH EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT NEWCASTLE ENROUTE BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT VOLKSRUST ENROUTE BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT TRICHARDT ENROUTE BEITBRIDGE BORDER | ENROUTE MWENEZI | TRUCK AT CHIRUNDU ZIM SIDE | TRUCK AT CHIRUNDU ZIM SIDE AWAITING RELEASE | TRUCK AT CHIRUNDU ZIM SIDE AWAITING RELEASE | TRUCK AT CHIRUNDU ZAM SIDE AWAITING RELEASE | TRUCK AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHILCE AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHILCE AT CHIRUNDU ZAM SIDE - ATTENDING TO MINOR BREAKDOWN. TO DIPATCH THIS AFTERNOON | * VEHILCE AT CHIRUNDU ZAM SIDE - AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENLTY CHINGOLA ENROUTE CHILILABOMBWE | KASUMBULESA DRC SIDE | ON SITE AWAITING TO OFFLOAD
BA2029 | 1 X NEW CAT777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JPE00855 | N/A | N/A | FML2204DSI1533 | COD 2022 187690 | BG04BPGP | CL08PDGP / BG04BPGP | FK2204DSI1537B | 09.05.2022 | OFFLOADED 23-06-2022 | 02.05.2022 | 09.05.2022 | BV INSPECTION COMPLETED 05/05/2022 | 04.05.2022 | 11.05.2022 | 16.05.2022 | 17.05.2022 | 01-06-2022 | 01-06-2022 | 01-06-2022 | 02-06-2022 | 03.06.2022 | 03.06.2022 | 06.06.2022 | 08.06.2022 | 09.06.2022 | 16.06.2022 | 17.06.2022 | 17-06-2022 | 17-06-2022 | 17-06-2022 | 19-06-2022 | 19-06-2022 | 21-06-2022 | 21-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | [113 empty] | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | VESSEL: BAHRI JAZAN - AWAITING VESSEL ARRIVAL ON THE 03/05/2022 | VESSEL: BAHRI JAZAN - AWAITING VESSEL ARRIVAL ON THE 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * BV INSPECTION BOOKED FOR FRIDAY 06.05.2022 | CAMPERDOWN WAITING POLICE ESCOURTS | TRUCK AT ESTON EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH ESTON EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JAAGBAAN EN-ROUTE TO BEITBRIDGE BORDER | COLENSO EN-ROUTE TO BEITBRIDGE BORDER | LADYSMITH EN-ROUTE TO BEITBRIDGE BORDER | LADYSMITH EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT NEWCASTLE ENROUTE BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT VOLKSRUST ENROUTE BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT BETHAL ENROUTE BEITBRIDGE BORDER | ENROUTE MWENEZI | TRUCK AT CHIRUNDU ZIM SIDE | TRUCK AT CHIRUNDU ZIM SIDE AWAITING RELEASE | TRUCK AT CHIRUNDU ZIM SIDE AWAITING RELEASE | TRUCK AT CHIRUNDU ZAM SIDE AWAITING RELEASE | TRUCK AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHILCE AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHILCE AT CHIRUNDU ZAM SIDE - ATTENDING TO MINOR BREAKDOWN. TO DIPATCH THIS AFTERNOON | * VEHILCE AT CHIRUNDU ZAM SIDE - AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBULESA ZAM SIDE | OFFLOADED 23-06-2022 | OFFLOADED 23-06-2022
BA1797 | 1 X CAT D6GC-01A TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XPC00508 | CAT000D6KXPC00508 | R6J04354 | FML2203DSI1492 | COD 2022 169461 | JV80FPGP | JZ68SNGP | ND60660 | 02.05.2022 | OFFLOADED 27-06-2022 | 28.04.2022 | 03.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 26.04.2022 | 31-05-2022 | 01-06-2022 | 02-06-2022 | 04-06-2022 | 05-06-2022 | 06-06-2022 | 06-06-2022 | 07-06-2022 | 08-06-2022 | 09-06-2022 | 09.06.2022 | 09.06.2022 | 10.06.2022 | 10.06.2022 | 11.06.2022 | 11.06.2022 | 11.06.2022 | 12.06.2022 | 15.06.2022 | 16.06.2022 | 17.06.2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | 24-06-2022 | [113 empty] | AWAIITNG VESSEL ARRIVAL ON THE 25/04/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/04/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/04/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/04/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/04/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/04/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/04/2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | VESSEL CURRENTLY WORKING, WAITING RECEIPT OF CARGO FROM THE VESSEL. | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE 03.05.2022 - ANTICIPATED LOAD DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGES | * BV INSPECTION COMPLETE 03.05.2022 - ANTICIPATED LOAD DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGES | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 20/05/2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 20/05/2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 20/05/2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 23/05/2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 23/05/2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 25/05/2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 25/05/2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 25/05/2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 30.05.2022 | VEHICLE ENROUTE FROM DRC, ANTICIPATED LOADING 30.05.2022 | BELA BELA ENROUTE MUSINA | TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE | TRUCK EN-ROUTE TO HARARE | TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | CHIRUNDU ZIM SIDE AWAITNG RELEASE | CHIRUNDU ZIM SIDE AWAITNG RELEASE | * VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY IN CHILILABOMBWE QUEUE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE & RELEASE | LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 27-06-2022
BA1810 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F602057 | CAT00745J3F602057 | TBA | FML2204DSI1524 | COD 2022 180454 | ND730794 | ND443606 | ND60669 | 10.05.2022 | OFFLOADED 23-06-2022 | 21.04.2022 | 25.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.05.2022 | 31-05-2022 | 01-06-2022 | 01-06-2022 | 06-06-2022 | 07-06-2022 | 06-06-2022 | 12.06.2022 | 12.06.2022 | 13.06.2022 | 13.06.2022 | 13.06.2022 | 14.06.2022 | 15.06.2022 | 15.06.2022 | 16.06.2022 | 16.06.2022 | 17.06.2022 | 18-06-2022 | 18-06-2022 | 20-06-2022 | 20-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 23-06-2022 | [120 empty] | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 03.05.2022 | * VESSEL TORTUGAS CURRENT ETA 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * UNIT TO BE LOADED FROM PORT TODAY | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 23.05.2022 | VEHICLE TO LOAD 25.05.2022 | * VEHICLE LOADED - PLANNING TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE LOADED - PLANNING TO DISPATCH DURBAN THIS AFTERNOON | MIDDELBURG ENROUTE MUSINA | MUSINA EN-ROUTE TO BEITBRIDGE | POLOKWANE EN-ROUTE TO BEITBRIDGE | LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE | BEITBRIDGE RSA SIDE | BEITBRIDGE ZIM SIDE | * VEHICLE CURRENLTY AT KADOMA ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITING CLEARANCE | * VEHICLE CURRENTLY AT SIAVONGA ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | OFFLOADED 23-06-2022 | OFFLOADED 23-06-2022
BA1858 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FEK20853 | CAT00330CFEK20890 | E7A47800 | FML2111DSI1322 | COD 2022174507 | ND142761 | ND542263 | ND60180 | 11.05.2022 | OFFLOADED 23-06-2022 | 19.04.2022 | 22.04.2022 | BV BOOKED AS SOON AS THE NUMBER WAS RECEIVED | 24.11.2021 | 01-06-2022 | 02-06-2022 | 07-06-2022 | 09-06-2022 | 09-06-2022 | 10-06-2022 | 11.06.2022 | 12.06.2022 | 13.06.2022 | 15.06.2022 | 16.06.2022 | 16.06.2022 | 16.06.2022 | 16.06.2022 | 17.06.2022 | 17.06.2022 | 17-06-2022 | 18-06-2022 | 18-06-2022 | 20-06-2022 | 20-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | [110 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | Waiting for truck to return form DRC, Loading on the 09/05 due to public holidays and road closures in RSA | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | WAITING FOR TRUCK TO RETURN FROM DRC, LOADING ON THE 09.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, | LOADING AND DISPATCH 16 / 17 OF MAY | LOADING AND DISPATCH 19TH OF MAY,AWAITING VEHCILE TO RETURN FROM DRC | LOADING AND DISPATCH 19TH OF MAY,AWAITING VEHCILE TO RETURN FROM DRC | LOADING AND DISPATCH 23TH OF MAY,AWAITING VEHCILE TO RETURN FROM DRC | LOADING AND DISPATCH 23TH OF MAY | LOADING AND DISPATCH 23TH OF MAY | LOADING AND DISPATCH 23TH OF MAY | * VEHICLE LOADING AND ANTICIPATED TO DISPATCH 26TH OF MAY | * VEHICLE LOADING AND ANTICIPATED TO DISPATCH 26TH OF MAY | * VEHICLE LOADING AND ANTICIPATED TO DISPATCH 27TH OF MAY | JOHANNESBURG | JOHANNESBURG DISPATCHING TOMMROW | JOHANNESBURG DISPATCHING TODAY | BELA BELA EN-ROUTE TO BEITBRIDGE BORDER | LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE BORDER | BEITBRIDGE ZIM SIDE AWAITING RELEASE | * VEHICLE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE DISPATCHING KAROI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENLTY AT KASUMBULESA CUSTOMS | OFFLOADED 23-06-2022 | OFFLOADED 23-06-2022
BA2084 | 1 X NEW CAT 140K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZL20751 | CAT0140KCSZL20751 | TX711946 | FML2204DSI1515 | COD 2022 184713 | PWM289GP | KF38BVGP | ND60677 | 13.05.2022 | OFFLOADED 24-06-2022 | 26.04.2022 | 10.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.05.2022 | 16.05.2022 | 19.05.2022 | 20.05.2022 | 26.05.2022 | 26.05.2022 | 27.05.2022 | 30-05-2022 | 01-06-2022 | 03-06-2022 | 06-06-2022 | 07-06-2022 | 07-06-2022 | 08.06.2022 | 13.06.2022 | 14.06.2022 | 15.06.2022 | 17.06.2022 | 17-06-2022 | 17-06-2022 | 21-06-2022 | 21-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | 24-06-2022 | [113 empty] | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING INVOICE & VESSEL ARRIVAL. ETA 04.05.2022 | AWAITING INVOICE & VESSEL ARRIVAL. ETA 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * VESSEL CURRENT ETA 06.05.2022 | LOADING TODAY | DISPATCHING DURBAN | TRUCK AT MARIAN TOLL EN-ROUTE TO BEITBRIDGE | TRUCK AT HARRISMITH EN-ROUTE TO BEITBRIDGE | TRUCK AT JNB UNDERGOING TRIP CHECK | TRUCK TO DISPATCH JNB TODAY EN-ROUTE TO BEITBRIDGE | TRUCK TO DISPATCH JNB TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT PEITERMARITZBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT HARRISMITH ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT POLOKWANE ENROUTE MUSINA | DISPATCHING HARARE | CHIRUNDU CUSTOMS | DISPATCHING CHIRUNDU | KAFUE EN-ROUTE TO KASUMBALESA BORDER | KAPIRI EN-ROUTE TO KASUMBALESA BORDER | CHILILABOMBWE EN-ROUTE TO KASUMBALESA BORDER | * VEHICLE CURRENLTY AT KAFUE ENROUTE KITWE | * VEHICLE CURRENLTY AT KAFUE ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENTLY AT KABWE ENROUTE CHINGOLA | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA CUSTOMS | LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 24-06-2022
BA2113 | 1 X NEW CAT DE1250 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JPE00855 | N/A | N/A | FML2204DSI1533 | COD 2022 168719 | CB67PGGP | HL08BSGP | ND60680 | TBA | OFFLOADED 23-06-2022 |  | 18.05.2022 | BV BOOKED AS SOON AS CONTAINER WAS UNPACKED | 28/05/2022 | 03/06/2022 | 06/06/2022 | 07/06/2022 | 08/06/2022 | 09.06.2022 | 11.06.2022 | 12.06.2022 | 13.06.2022 | 13.06.2022 | 14.06.2022 | 14.06.2022 | 15.06.2022 | 15.06.2022 | 16.06.2022 | 16.06.2022 | 16.06.2022 | 17.06.2022 | 18-06-2022 | 18-06-2022 | 20-06-2022 | 20-06-2022 | 22-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | [113 empty] | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING VESSEL ARRIVAL ON THE 07/05/2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | CONTAINER WAITNING TO BE UNPACKED | CONTAINER WAITNING TO BE UNPACKED | BV BOOKED FOR 18/05/2022 | BV COMPLETED AWAITING DISPATCH DATE | BV COMPLETED AWAITING DISPATCH DATE | BV COMPLETED AWAITING DISPATCH DATE | BV COMPLETED AWAITING DISPATCH DATE | * BV COMPLETED AWAITING DISPATCH DATE | * BV COMPLETED AWAITING DISPATCH DATE | WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 30.05.2022 | WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 06.06.2022 | TRUCK AT JNB EN-ROUTE TO BEITBRIDGE | TRUCK DISPATCHING JNB EN-ROUTE TO BEITBRIDGE | TRUCK AT BELA BELA EN-ROUTE TO BEITBRIDGE | TRUCK AT BEITBRIDGE RSA SIDE AWAITING RELEASE | TRUCK AT CHIVHU EN-ROUTE HARARE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU CUSTOMS | * VEHICLE CURRENLTY AT KAFUE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | OFFLOADED 23-06-2022 | OFFLOADED 23-06-2022
BA1863 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | TBA | COD 2022 180454 | ND570587 | ND702944 | ND60671 | 10.05.2022 | OFFLOADED 29.06.2022 | 21.04.2022 | 25.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.05.2022 | 07.06.2022 | 08-06-2022 | 08-06-2022 | 09-06-2022 | 10-06-2022 | 10-06-2022 | 13.06.2022 | 13.06.2022 | 14.06.2022 | 15.06.2022 | 16.06.2022 | 17.06.2022 | 18-06-2022 | 19-06-2022 | 19-06-2022 | 20-06-2022 | 20-06-2022 | 22-06-2022 | 22-06-2022 | 23-06-2022 | 27-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | [66 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 30.04.2022 | * VESSEL TORTUGAS CURRENT ETA 03.05.2022 | * VESSEL TORTUGAS CURRENT ETA 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * COLLECTING UNIT FROM PORT TODAY | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 25.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 27.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD 27.05.2022 | VEHICLE CURRENTLY IN DRC TO, WAITING FOR RETURN TO LOAD, ANTICIPATING TO LOAD WEDNESDAY 08.06.2022 | TRUCK TO LOAD TODAY | TRUCK TO DISPATCH TODAY ONCE THE PERMIT HAVE BEEN RECEIVED | TRUCK AT MARIANHILL EN-ROUTE TO BEITBRIDGE BORDER | MIDDELBRUG EN-ROUTE TO BEITBRIDGE BORDER | BEITBRIDGE BORDER RSA SIDE AWAITING RELEASE | * VEHICLE AT BEITBRIDGE BORDER ZIM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT CHIBI ENROUTE HARARE | * VEHICLE CURRENTLY AT GWERU ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT KAFULAFUTA ENROUTE KASUMBULES | * VEHICLE CURRENTLY AT KASUMBULESA ZAM SIDE | * WHISKEY AWAITING RELEASE | * WHISKEY AWAITING RELEASE | ON SITE AWAITING TO OFFLOAD | OFFLOADED 29/06/2022 | OFFLOADED 29/06/2022 | OFFLOADED 29/06/2022
BA1908 | 1 X NEW CAT 336-07B HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12130 | CAT00336KGDY12130 | NTB05879 | FML 2201DSE1385 | COD 2022 185697 | HJT794MP | JMT934MP | ND60767 | 18.05.2022 | * OFFLOADED 01.07.2022 | 26.04.2022 | 09.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 28.01.2022 | 10.06.2022 | 13.06.2022 | 20-06-2022 | 20-06-2022 | 20-06-2022 | 20-06-2022 | 23-06-2022 | 26-06-2022 | 26-06-2022 | 27-06-2022 | 27-06-2022 | 27-06-2022 | 27-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 28-06-2022 | 28-06-2022 | 28-06-2022 | 29-06-2022 | 30-06-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 01.07.2022 | [8 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | BV NUMBER RECEIVED 26/04 - INSPECTION DATE, LOADING AND DISPATCH DATE TO BE ADVISE. | BV NUMBER RECEIVED 26.04.2022 - INSPECTION DATE, LOADING AND DISPATCH DATE TO BE ADVISE. | * BV INSPECTION TO BE BOOKED FOR FRIDAY 06.05.2022. LOADING AND DISPATCH DATE TO BE ADVISE. | * BV INSPECTION TO BE BOOKED FOR FRIDAY 06.05.2022. LOADING AND DISPATCH DATE TO BE ADVISE. | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 25.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 27.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING 10-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 10-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 14-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 10-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 10-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 10-06-2022 | * VEHICLE CURRENLTY AT CATO-RIDGE ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT JOHANNESBURG AWAITING PERMIT | * VEHICLE CURRENTLY AT JOHANNESBURG AWAITING PERMIT | * VEHICLE CURRENTLY AT BELA BELA ENROUTE MUSINA | KWEKWE ENROUTE HARARE | NDOLA EN-ROUTE TO KASUMBALESA | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE | WHISKEY AWAIITNG RELEASE | LUBUMBASHI AWAITING TO OFFLOAD | * OFFLOADED 01.07.2022 | * OFFLOADED 01.07.2022
BA2081 | 1 X CAT777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KYD02674 | CAT0777EPKYD02674 | ZRK00159 | FML2205DSI1560 | COD 2022 204403 | CJ68TBGP | ZGN692GP / ZGN698GP | FML2205DSI1560 | 25-05-2022 | * OFFLOADED 01.07.2022 | 23.05.2022 | 25-05-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 23-05-2022 | 26-05-2022 | 01-06-2022 | 01-06-2022 | 04-06-2022 | 06-06-2022 | 07-06-2022 | 09-06-2022 | 10-06-2022 | 10-06-2022 | 13.06.2022 | 13.06.2022 | 14.06.2022 | 17-06-2022 | 17-06-2022 | 18-06-2022 | 18-09-2022 | 19-06-2022 | 23-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 29-06-2022 | 29-06-2022 | 01.07.2022 | [19 empty] | WAITING VESSEL ARRIVAL: VESSEL - BAHRI TABUK - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - BAHRI TABUK - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - BAHRI TABUK - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - BAHRI TABUK - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - BAHRI TABUK - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - BAHRI TABUK - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - BAHRI TABUK - ETA: 21/05/2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | ELANDSDORING ENROUTE MUSINA | TRUCK AT MOGWADI EN-ROUTE TO BEITBRIDGE | BEITBRIDGE RSA SIDE AWAITING CLEARANCE | BEITBRIDGE ZIM SIDE AWAITING RELEASE | MASVINGO EN-ROUTE TO HARARE | HARARE EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAIITNG CLEARANCE | * VEHICLE AT CHIRUNDU ZAM SIDE AWAITING PERMIT | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE - AWAITING PERMIT | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE - AWAITING PERMIT | * VEHICLE CURRENLTY AT KALULUSHI ENROUTE CHINGOLA | VEHICLE CHILILABOMBWE IN QUE TO KASUMBULESA | KASUMBALESA DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | * OFFLOADED 01.07.2022 | * OFFLOADED 01.07.2022
BA1904 | 1 X NEW CAT 336-07B HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12132 | CAT00336CGDY12132 | NTB05790 | FML2201DSI1385 | COD 2022174507 | JRT722MP | JRT721MP | ND60764 | 11.05.2022 | OFFLOADED 08-07-2022 | 19.04.2022 | 22.04.2022 | BV BOOKED AS SOON AS THE NUMBER WAS RECEIVED | 28.01.2022 | 10.06.2022 | 13.06.2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 26-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 30.06.2022 | 01.07.2022 | 02.07.2022 | 02.07.2022 | 03.07.2022 | 04.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 07.07.2022 | 07-07-2022 | 08-07-2022 | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 18/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 20/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 20/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 25.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 27.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - ESTIMATED LOADING DATE 09/06/2022 | WAITING RETURN VEHICLE FROM THE DRC - ESTIMATED LOADING DATE 09/06/2022 | TRUCK TO LOAD TODAY AND DISPATCH ON THE 10/06/2022 | TRUCK TO LOAD TODAY AND DISPATCH ON THE 10/06/2022 | * VEHICLE CURRENTLY AT BRAKPAN ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT JOHANNESBURG AWAITING PERMIT | * VEHICLE CURRENTLY AT JOHANNESBURG AWAITING PERMIT | * VEHICLE CURRENTLY AT JOHANNESBURG ON BREAKDOWN NEW VEHICLE TO ARRIVE THIS AFTERNOON TO LOAD UNIT TOMORROW TO DISPATCH LATEST WEDNESDAY | BEIT BRIDGE RSA SIDE | MAKUTI EN-ROUTE HARARE | CHIRUNDU ZAM SIDE | CHIRUNDU ZAM SIDE | KAFUE EN-ROUTE TO KASUMBALESA | KAPIRI MPOSHE EN-ROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA UNDER CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | OFFLOADED 08-07-2022
BA2188 | 1 X NEW CAT D6GC-01A TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XPC00502 | CAT000D6LXPC00502 | R6J04281 | FML2205DSI1571 | COD 2022 196127 | JF92ZTGP | BX45TWGP | ND59530 | 17.06.2022 | OFFLOADED 08-07-2022 | 11.05.2022 | 01.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30/05/2022 | 17-06-2022 | 18-06-2022 | 21-06-2022 | 21-06-2022 | 21-06-2022 | 21-06-2022 | 23-06-2022 | 24-06-2022 | 24-06-2022 | 25-06-2022 | 27-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 30-06-2022 | 30-06-2022 | 07-07-2022 | 07-07-2022 | 08-07-2022 | 08-07-2022 | 08-07-2022 | 08-07-2022 | [18 empty] | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 25.05.2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 09-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 09-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 10-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 13-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 13-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 13-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 16-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 16-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 17-06-2022 | * VEHICLE DISPATCHING DURBAN TODAY - ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG | * VEHICLE CURRENTLY AT BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT LUSAKA EN-ROUTE BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | * KASUMBALESA IN QUEUE | * KASUMBALESA DRC SIDE | * VEHILE CURRENLTLY AT KASUMBALESA DRC SIDE | * VEHILE CURRENLTLY AT KASUMBALESA DRC SIDE | * VEHILE CURRENLTLY AT KASUMBALESA DRC SIDE - DAY 4 | OFFLOADED 08-07-2022
BA1680 | 1 X NEW CAT 777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KYD00303 | CAT0777EAKYD00303 | FZS01882 | FML2110DSI1298 | COD 2022 168417 | ND760431 | ND760424 / ND760428 | ND60159 | 03.05.2022 | OFFLOADED 11-07-2022 | 01.04.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.10.2022 | 18.05.2022 | 07.06.2022 | 12.06.2022 | 15.06.2022 | 15.06.2022 | 16.06.2022 | 21-06-2022 | 21-06-2022 | 23-06-2022 | 27-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 01-07-2022 | 01.07.2022 | 03.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 09-07-2022 | 09-07-2022 | 09-07-2022 | 09-07-2022 | 10-07-2022 | 11-07-2022 | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | * BV INSPECTION BOOKED FOR TODAY - PLANNING TO DISPATCH ON THE 19/04/2022 | * PLANNING TO LOAD AND DISPATCH ON WEDNESDAY THE 20/04/2022 | * PLANNING TO LOAD AND DISPATCH ON THURSDAY THE 21/04/2022 | * PLANNING TO LAOD NEXT WEEK MONDAY THE 25/04/2022 | Truck enroute to Durban for loading. To be loaded on 05/05 due to public holidays and road closures in RSA, departure depended on the issuance of permits by the permit office | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | LOADED - WAITING PERMITS AND ESCOURTS | TRUCK TO DISPATCH TOMMROW THE 17/05/2022 | TRUCK TO DISPATCH TOMMROW THE 18/05/2022 | TRUCK DISPATCH EN-ROUTE TO BEITBRIDGE | TRUCK AT MARIAN TOLL EN-ROUTE BEITBRIDGE | TRUCK AT ESTON TOLL EN-ROUTE BEITBRIDGE | TRUCK AT ESTON TOLL EN-ROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT PIETERMARITZBURG ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENTLY AT PIETERMARITZBURG ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENTLY AT PIETERMARITZBURG ATTENDING TO MINOR BREAKDOWN | DALTON ENROUTE JOHANNESBURG | WEENEN EN-ROUTE TO JNB | COLENSO EN-ROUTE TO BEITBRIDGE | NEWCASTLE EN-ROUTE TO BEITBRIDGE | VOLKSRUST EN-ROUTE TO BEITBRIDGE | HENDRINA EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT GROBLERSDAL EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT ZEBEDIELA EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT VIVO EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE | KAROI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE | CHIRUNDU ZAM SIDE AWAITING PERMIT | CHIRUNDU ZAM SIDE AWAITING PERMIT | CHIRUNDU ZAM SIDE AWAITING PERMIT TO BE RECEIVED TODAY | LUSAKA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT CHILIABOMBWE ENROUTE KASUMBALESA | * VEHICLE AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | OFFLOADED 11-07-2022 | OFFLOADED 11-07-2022
BA2128 | 1 X NEW CAT966GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW00822 | CAT00966JSGW00822 | NTB10037 | FML2205DSI1566 | COD 2022 204808 | NJ100398 | NJ102487 | ND59507 | 21.06.2022 | OFFLOADED 11-07-2022 | 23.05.2022 | 08-06-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.06.2022 | 21-06-2022 | 22-06-2022 | 22-06-2022 | 24-06-2022 | 25-06-2022 | 27-06-2022 | 28-06-2022 | 29-06-2022 | 30-06-2022 | 30-06-2022 | 30-06-2022 | 30-06-2022 | 30-06-2022 | 01.07.2022 | 02.07.2022 | 03.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 07-07-2022 | 07-07-2022 | 09-07-2022 | 09-07-2022 | 09-07-2022 | 11-07-2022 |  |  |  | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING VESSEL ARRIVAL ON THE 07/05/2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 29.05.2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 29.05.2022 | VESSEL ARRIVED - WAITING COMPLETION OF DISCHARGE | MACHINE TO BE COLLECTED FROM PORT TODAY | BV BOOKED FOR THE 08/06/2022 | BV BOOKED FOR TODAY THE 08/06/2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | LOADED TO DISPATCH DURBAN TODAY | LOUIS TRICHARDT ENROUTE BEIT BRIDGE | BEITBRIDGE RSA SIDE | BUBI EN-ROUTE HARARE | CHEGUTU EN-ROUTE TO CHIRUNDU | KAROI EN-ROUTE TO KASUMBALESA BORDER | CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT CHILIABOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | OFFLOADED 11-07-2022 | OFFLOADED 11-07-2022
BA1905 | 1 X NEW CAT 336-07B HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12133 | CAT00336VGDY12133 | NTB05885 | FML 2201DSI1401 | COD 2022 185697 | ND570587 | ND702944 | ND60793 | 18.05.2022 | OFFLOADED 14-07-2022 | 26.04.2022 | 09.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 02.02.2022 | 24.06.2022 | 25.06.2022 | 25.06.2022 | 27.06.2022 | 28.06.2022 | 30-06-2022 | 01-07-2022 | 03.07.2022 | 03.07.2022 | 04.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 06.07.2022 | 06.07.2022 | 07.07.2022 | 07-07-2022 | 07-07-2022 | 07-07-2022 | 12.07.2022 | 13.07.2022 | 13-07-2022 | 13-07-2022 | 13-07-2022 | 14-07-2022 | [8 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | BV NUMBER RECEIVED 26/04 - INSPECTION DATE, LOADING AND DISPATCH DATE TO BE ADVISE. | BV NUMBER RECEIVED 26.04.2022 - INSPECTION DATE, LOADING AND DISPATCH DATE TO BE ADVISE. | * BV INSPECTION TO BE BOOKED FOR FRIDAY 06.05.2022. LOADING AND DISPATCH DATE TO BE ADVISE. | * BV INSPECTION TO BE BOOKED FOR FRIDAY 06.05.2022. LOADING AND DISPATCH DATE TO BE ADVISE. | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 25.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 27.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING 10-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 10-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 14-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 14-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 14-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 14-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23-06-2022 | LOADED, WAITING PERMITS | CAMPERSDOWN EN-ROUTE TO BEITBRIDGE | MIDDELBURG EN-ROUTE TO BEITBRIDGE | LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE | BEITBRIDGE RSA SIDE UNDERGOING CUSTOM FORMALITIES | MASVINGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING CHIRUNDU ENROUTE LUSAKA | * VEHICLE CURRENTLY AT WHISKEY | OFFLOADED 14-07-2022
BA1906 | 1 X NEW CAT 336-07B HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12131 | CAT00336JGDY12131 | NTB05766 | FML 2201DSE1385 | COD 2022 185697 | ND706468 | ND256330 | ND60765 | 18.05.2022 | OFFLOADED 14-07-2022 | 26.04.2022 | 09.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 28.01.2022 | 21-06-2022 | 22-06-2022 | 22-06-2022 | 27-06-2022 | 28-06-2022 | 28-06-2022 | 01-07-2022 | 02.07.2022 | 03.07.2022 | 04.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 06.07.2022 | 06.07.2022 | 07.07.2022 | 07-07-2022 | 07-07-2022 | 07-07-2022 | 12.07.2022 | 13.07.2022 | 14-07-2022 | 14-07-2022 | 14-07-2022 | 14-07-2022 | [8 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | BV NUMBER RECEIVED 26/04 - INSPECTION DATE, LOADING AND DISPATCH DATE TO BE ADVISE. | BV NUMBER RECEIVED 26.04.2022 - INSPECTION DATE, LOADING AND DISPATCH DATE TO BE ADVISE. | * BV INSPECTION TO BE BOOKED FOR FRIDAY 06.05.2022. LOADING AND DISPATCH DATE TO BE ADVISE. | * BV INSPECTION TO BE BOOKED FOR FRIDAY 06.05.2022. LOADING AND DISPATCH DATE TO BE ADVISE. | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 25.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 27.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING 10-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 14-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 14-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 14-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 20-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 20-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 20-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 20-06-2022 | LOADING TOMORROW 21-06-2022 | POLOKWANE ENROUTE BEIT BRIDGE | POLOKWANE AWAIITNG PERMIT IN ORDER TO PROCEED TO BEIRBRIDGE | POLOKWANE AWAIITNG PERMIT IN ORDER TO PROCEED TO BEIRBRIDGE | BEIRBRIDGE RSA SIDE | BEIRBRIDGE RSA SIDE CROSSING TO ZIM SIDE | MASVINGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHINOYI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING CHIRUNDU ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KASUMBULESA ZAMBIAN SIDE CROSSING TO DRC SIDE | OFFLOADED 14-07-2022
BA1907 | 1 X NEW CAT 336-07B HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12129 | CAT00336CGDY12129 | NTB05834 | FML 2201DSE1385 | COD 2022 185697 | ND730794 | ND443606 | ND60766 | 18.05.2022 | OFFLOADED 14-07-2022 | 26.04.2022 | 09.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 28.01.2022 | 28.06.2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 30-06-2022 | 02.07.2022 | 04.07.2022 | 03.07.2022 | 04.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 06.07.2022 | 06.07.2022 | 07.07.2022 | 07-07-2022 | 07-07-2022 | 07-07-2022 | 12.07.2022 | 13.07.2022 | 14-07-2022 | 14-07-2022 | 14-07-2022 | 14-07-2022 | [8 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | BV NUMBER RECEIVED 26/04 - INSPECTION DATE, LOADING AND DISPATCH DATE TO BE ADVISE. | BV NUMBER RECEIVED 26.04.2022 - INSPECTION DATE, LOADING AND DISPATCH DATE TO BE ADVISE. | * BV INSPECTION TO BE BOOKED FOR FRIDAY 06.05.2022. LOADING AND DISPATCH DATE TO BE ADVISE. | * BV INSPECTION TO BE BOOKED FOR FRIDAY 06.05.2022. LOADING AND DISPATCH DATE TO BE ADVISE. | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 23/05/2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 25.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - ANTICIPATED LOADING DATE 27.05.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING DATE TO BE CONFIRMED | WAITING RETURN VEHICLE FROM THE DRC - LOADING 17-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 17-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 17-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 17-06-2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 17.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 27.06.2022 | LOADING TODAY AND MACHINE TO DISPATCH TOMMROW | MACHINE TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | MIDDELBURG EN-ROUTE TO BEITBRIDGE | BEITBRIDGE RSA SIDE UNDERGOING CUSTOM FORMALITIES | BEITBRIDGE RSA SIDE UNDERGOING CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE DISPATCHING CHIRUNDU ENROUTE LUSAKA | * VEHICLE CURRENTLY AT KASUMBULESA ZAMBIAN SIDE CROSSING TO DRC SIDE | OFFLOADED 14-07-2022
BA1923 | 1 X C18 GENSET | 1 X CAT GENERATOR ARRANGEMENT | JM704769 | CAT00C18CLXK04020 | N/A | FML2205DSI1557 | COD 2022 183394 | AEU7885 | AEU8185 / AEU8184 | ND59573 | 21.06.2022 | OFFLOADED 14-07-2022 | 19.04.2022 | 30.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.05.2022 | 21-06-2022 | 21-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 24-06-2022 | 25-06-2022 | 25-06-2022 | 26-06-2022 | 26-06-2022 | 26-06-2022 | 26-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 30-06-2022 | 02.07.2022 | 04.07.2022 | 06-07-2022 | 06-07-2022 | 12.07.2022 | 13.07.2022 | 13.07.2022 | 14-07-2022 | [11 empty] | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT ARRIVAL - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT ARRIVAL - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT ARRIVAL - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | BEIT BRIDGE RSA SIDE | LUSAKA EN-ROUTE KASUMBALESA | KITWE EN-ROUTE KASUMBALESA | CHAMBISI EN-ROUTE KASUMBALESA | CHILILABOMBWEI EN-ROUTE KASUMBALESA | CHILILABOMBWE IN QUEUE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA AWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDEAWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDEAWAITNG CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY DAY 6 | OFFLOADED 14-07-2022
BA1987 | 1 X CAT DE780E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK04021 TWS00850 C7A04124 | CAT00C18CLXK04021 | N/A | FML2205DSI1557 | COD 2022 183394 | AEU7885 | AEU8185 / AEU8184 | ND59573 | 21.06.2022 | OFFLOADED 14-07-2022 | 19.04.2022 | 30.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.05.2022 | 21-06-2022 | 21-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 24-06-2022 | 25-06-2022 | 25-06-2022 | 26-06-2022 | 26-06-2022 | 26-06-2022 | 26-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 30-06-2022 | 02.07.2022 | 04.07.2022 | 06-07-2022 | 06-07-2022 | 12.07.2022 | 13.07.2022 | 13.07.2022 | 14-07-2022 | [11 empty] | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | BEIT BRIDGE RSA SIDE | LUSAKA EN-ROUTE KASUMBALESA | KITWE EN-ROUTE KASUMBALESA | CHAMBISI EN-ROUTE KASUMBALESA | CHILILABOMBWEI EN-ROUTE KASUMBALESA | CHILILABOMBWE IN QUEUE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA AWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDEAWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDEAWAITNG CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY DAY 6 | OFFLOADED 14-07-2022
BA1988 | 1 X CAT DE780E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK04022 TWS00876 C7A04123 | CAT00C18TLXK04022 | N/A | FML2205DSI1557 | COD 2022 183394 | AEU7885 | AEU8185 / AEU8184 | ND59573 | 21.06.2022 | OFFLOADED 14-07-2022 | 19.04.2022 | 30.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.05.2022 | 21-06-2022 | 21-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 24-06-2022 | 25-06-2022 | 25-06-2022 | 26-06-2022 | 26-06-2022 | 26-06-2022 | 26-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 30-06-2022 | 02.07.2022 | 04.07.2022 | 06-07-2022 | 06-07-2022 | 12.07.2022 | 13.07.2022 | 13.07.2022 | 14-07-2022 | [11 empty] | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | BEIT BRIDGE RSA SIDE | LUSAKA EN-ROUTE KASUMBALESA | KITWE EN-ROUTE KASUMBALESA | CHAMBISI EN-ROUTE KASUMBALESA | CHILILABOMBWEI EN-ROUTE KASUMBALESA | CHILILABOMBWE IN QUEUE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA AWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDEAWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDEAWAITNG CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY DAY 6 | OFFLOADED 14-07-2022
BA1989 | 1 X CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK04025 TWS00831 C7A04121 | CAT00C18JLXK04025 | N/A | FML2205DSI1558 | COD 2022 183394 | AEU9226 | AEG7119/AEG7121 | ND59574 | 22.06.2022 | OFFLOADED 14-07-2022 | 22.04.2022 | 30.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.05.2022 | 22-06-2022 | 23-06-2022 | 24-06-2022 | 25-06-2022 | 26-06-2022 | 27-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 30-06-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 02.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 08-07-2022 | 08-07-2002 | 13-07-2022 | 13-07-2022 | 13-07-2022 | 14-07-2022 | [11 empty] | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | JOHANNESBURG | BEITBRIDGE RSA SIDE | BEITBRIDGE RSA SIDE IN QUEUE TO ZAM SIDE | CHEGUTU EN-ROUTE TO CHIRUNDU | CHIRUNDU ZAM SIDE AWAITING RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT CHILIBOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY CLEARING | OFFLOADED 14-07-2022
BA1990 | 1 X CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK04026 TWS00810 C7A04128 | CAT00C18CLXK04026 | N/A | FML2205DSI1558 | COD 2022 183394 | AEU9226 | AEG7119/AEG7121 | ND59574 | 22.06.2022 | OFFLOADED 14-07-2022 | 22.04.2022 | 30.05.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 21.05.2022 | 22-06-2022 | 23-06-2022 | 24-06-2022 | 25-06-2022 | 26-06-2022 | 27-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 30-06-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 02.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 08-07-2022 | 08-07-2022 | 13-07-2022 | 13-07-2022 | 13-07-2022 | 14-07-2022 | [11 empty] | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 14 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * AWAITING VESSEL MAUPASSANT - TRANSHIPMENT VESSEL: CEZANNE CURRENT ETA 21 MAY 2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY UNDER UNPACK - BV INSPECTION TO BE BOOKED FOR FRIDAY 27 MAY 2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 10-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | * UNIT IN BONDED FACILITY BV INSPECTION COMPLETED - ANTICIPATED LOADING DATE 13-06-2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | AWAITING TRUCK DETAILS AND LOADING DATE-ESTIMATED LOADING DATE ON THE 15/06/2022 | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | JOHANNESBURG | BEITBRIDGE RSA SIDE | BEITBRIDGE RSA SIDE IN QUEUE TO ZAM SIDE | CHEGUTU EN-ROUTE TO CHIRUNDU | CHIRUNDU ZAM SIDE AWAITING RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT CHILIBOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY CLEARING | OFFLOADED 14-07-2022
BA2192 | 1 X CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LX903864 / S9X05618 / F5D04151 | CAT000C9CLX903864 | N/A | FML2205DSI1571 | COD 2022 195173 | AEU7885 | AEU8185 / AEU8184 | ND59573 | 21.06.2022 | OFFLOADED 14-07-2022 | 25-05-2022 | 13-06-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 08.06.2022 | 21-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 22-06-2022 | 24-06-2022 | 25-06-2022 | 25-06-2022 | 26-06-2022 | 26-06-2022 | 26-06-2022 | 26-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 30-06-2022 | 02.07.2022 | 04.07.2022 | 06-07-2022 | 06-07-2022 | 12.07.2022 | 13.07.2022 | 13.07.2022 | 14-07-2022 | [18 empty] | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 05.06.2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 05.06.2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 04.06.2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 04.06.2022 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | VESSEL IN AND WORKING | VESSEL IN AND WORKING | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - LOADING DATE TBC | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | BEIT BRIDGE RSA SIDE | LUSAKA EN-ROUTE KASUMBALESA | KITWE EN-ROUTE KASUMBALESA | CHAMBISI EN-ROUTE KASUMBALESA | CHILILABOMBWEI EN-ROUTE KASUMBALESA | CHILILABOMBWE IN QUEUE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA AWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDEAWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDEAWAITNG CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY DAY 6 | OFFLOADED 14-07-2022
BA2193 | 1 X CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LX903854 / S9X05654 / F5D04147 | CAT000C9JLX903854 | N/A | FML2205DSI1571 | COD 2022 195173 | AEU9226 | AEG7119/AEG7121 | ND59574 | 22.06.2022 | OFFLOADED 14-07-2022 | 25-06-2022 | 13-06-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 08.06.2022 | 22-06-2022 | 23-06-2022 | 24-06-2022 | 25-06-2022 | 26-06-2022 | 27-06-2022 | 29-06-2022 | 29-06-2022 | 29-06-2022 | 30-06-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 01-07-2022 | 02.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 08-07-2022 | 08-07-2022 | 13-07-2022 | 13-07-2022 | 13-07-2022 | 14-07-2022 | [18 empty] | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 05.06.2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 05.06.2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 04.06.2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 04.06.2022 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | VESSEL IN AND WORKING | VESSEL IN AND WORKING | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - LOADING DATE TBC | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * AWAIITNG VEHICLE RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | JOHANNESBURG | BEIRBRIDGE RSA SIDE | BEIRBRIDGE RSA SIDE IN QUEUE TO CROSS TO ZIM SIDE | CHEGUTU EN-ROUTE TO CHIRUNDU | CHIRUNDU ZAM SIDE AWAITING RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT CHILIBOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY CLEARING | OFFLOADED 14-07-2022
BA1885 | 1 X NEW CAT 336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | E7A43831 | CAT00336CJFW20939 | JFW20939 | FML2201DSI1400 | COD 2022 209460 | ND491242 | DG44TPGP | ND62909 | 28.06.2022 | OFFLOAD 18-07-2022 | 27-05-2022 | 01.06.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 01-06-2022 | 02.02.2022 | 29.06.2022 | 30.06.2022 | 01.07.2022 | 02.07.2022 | 03.07.2022 | 04.07.2022 | 06.07.2022 | 07.07.2022 | 07-07-2022 | 08-07-2022 | 09-07-2022 | 09-07-2022 | 10-07-2022 | 11-07-2022 | 11-07-2022 | 11-07-2022 | 12.07.2022 | 12.07.2022 | 13-07-2022 | 15-07-2022 | 16-07-2022 | 17-07-2022 | 18-07-2022 | 18-07-2022 | 18-07-2022 | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | JOHANNESBURG | CHIRUNDU ZAM SIDE | KAROI EN-ROUTE KASUMBALESA | CHIRUNDU EN-ROUTE KASUMBALESA | CHIRUNDU ZIM SIDE AWAIITNG RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | KAFUE EN-ROUTE TO KASUMBALESA | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALES DRC, IN QUEUE TO CROSS OVER TO WHISKEY | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29-06-2022 | MACHINE TO LOAD TODAY AND DISPATCH TOMMROW THE 27-06-2022 | MACHINE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | DISPATCHING DURBAN | MIDDELBURG EN-ROUTE TO BEITBRIDGE | PIETERSBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BUBI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT NDOLA ENROUTE KASUMBULESA | KASUMBULESA DRC SIDE | LUBUMBASHI AWAITING TO OFFLOAD | OFFLOAD 18-07-2022
BA2085 | 1 X NEW CAT950GC WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M5K05871 | CAT00950TM5K05871 | E7A52806 | FML2205DSI1564 | COD 2022 204808 | CW07CFGP | ND46174 | ND59508 | 21.06.2022 | * OFFLOADED | 23.05.2022 | 08/06/2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.06.2022 | 21-06-2022 | 22-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | 30-06-2022 | 01-07-2022 | 03.07.2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 08-07-2022 | 09-07-2022 | 09-07-2022 | 09-07-2022 | 09-07-2022 | 10-07-2022 | 10-07-2022 | 13-07-2022 | 13-07-2022 | 15-07-2022 | 18-07-2022 | 18-07-2022 | 18-07-2022 |  |  |  | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING INVOICE & VESSEL ARRIVAL. ETA 04.05.2022 | AWAITING INVOICE & VESSEL ARRIVAL. ETA 04.05.2022 | * VESSEL DUE TO ARRIVE IN DURBAN TODAY, VEHICLES PLACED ALONGSIDE TO LOAD AS SOON AS UNIT IS MADE AVAILABLE | * VESSEL CURRENT ETA 06.05.2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 29-05-2022 | VESSEL ARRIVED - WAITING COMPLETION OF DISCHARGE | VESSEL ARRIVED - WAITING COMPLETION OF DISCHARGE | BV BOOKED FOR THE 08/06/2022 | BV BOOKED FOR TODAY THE 08/06/2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | LOADED TO DISPATCH DURBAN TODAY | BEIT BRIDGE RSA SIDE | BEIT BRIDGE RSA SIDE | BEIT BRIDGE ZIM SIDE | BEIT BRIDGE ZIM SIDE | DISPATCHING BEIRBRIDGE EN-ROUTE TO HARARE | MASVINGO EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MAKUTI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBULESA ZAM SIDE DUE TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY TO DISPATCH TODAY | OFFLOADED | * OFFLOADED
BA2187 | 1 X NEW CAT D6GC-01A TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XPC00503 | CAT000D6HXPC00503 | R6J04280 | FML2205DSI1570 | COD 2022 196127 | KG17GHGP | KHM039MP | ND59531 | 17.06.2022 | OFFLOADED | 11.05.2022 | 01.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30/05/2022 | 17-06-2022 | 18-06-2022 | 21-06-2022 | 21-06-2022 | 21-06-2022 | 21-06-2022 | 30-06-2022 | 01-07-2022 | 01-07-2022 | 04.05.2022 | 05.07.2022 | 06.07.2022 | 08-07-2022 | 08-07-2022 | 08-07-2022 | 09-07-2022 | 09-07-2022 | 10-07-2022 | 10-07-2022 | 13-07-2022 | 13-07-2022 | 15-07-2022 | 18-07-2022 | 18-07-2022 | [19 empty] | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 24-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - HERCULES LEADER - ETA: 25.05.2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 09-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 09-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 10-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 13-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 13-06-2022 | BV INSPECITON COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ANTICIPATED LOADING 13-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 16-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 16-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 17-06-2022 | * VEHICLE DISPATCHING DURBAN TODAY - ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG | * VEHICLE CURRENTLY AT BEIT BRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHCILE TO DISPATCH BBR EN-ROUTE TO HARARE | VEHCILE TO DISPATCH BBR EN-ROUTE TO HARARE | VEHCILE AT BEITBRIDGE ZIM SIDE | TRUCK TO DISPATCH BEITBRIDGE EN-ROUTE TO HARARE | MASVINGO EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MAKUTI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBULESA ZAM SIDE DUE TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY TO DISPATCH TODAY | * VEHICLE CURRENTLY AT LUBUMBASHI, AWAITING TO OFFLOAD | * VEHICLE CURRENTLY AT LUBUMBASHI, AWAITING TO OFFLOAD | OFFLOADED
BA2197 | 1 X USED CAT725 LUBE TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | B1L01117 | CAT00725EB1L01117 | RSX04965 | FML2205DSI1576 | COD 2022 209458 | KG17GHGP | KG66HXGP | ND59535 | 13.06.2022 | * OFFLOADED 26.07.2022 | 27.05.2022 | 01.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 26.05.2022 | 21-06-2022 | 22-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | 23-06-2022 | 30-06-2022 | 01-07-2022 | 01-07-2022 | 04.07.2022 | 05.07.2022 | 06.07.2022 | 08-07-2022 | 08-07-2022 | 09-07-2022 | 09-07-2022 | 10-07-2022 | 10-07-2022 | 10-07-2022 | 24.07.2022 | 25.07.2022 | 26.07.2022 | 26.07.2022 | 26.07.2022 | 26.07.2022 | [18 empty] | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 21/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 21/05/2022 | * VESSEL IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 26.06.2022 | WAITING VESSEL ARRIVAL: VESSEL - MARVELOUS ACE - ETA: 26.06.2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 09-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 09-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 09-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 13-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 13-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 13-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 16-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 16-06-2022 | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 17-06-2022 | * VEHICLE LOADING TODAY - TO DISPATCH DURBAN MONDAY 20.06.2022 | * DISPATCHING DURBAN TONDAY | BEIT BRIDGE RSA SIDE | BEIT BRIDGE RSA SIDE | BEIT BRIDGE RSA SIDE IN QUEUE TO CROSS TO ZIM SIDE | BEIT BRIDGE RSA SIDE IN QUEUE TO CROSS TO ZIM SIDE | TRUCK TO DISPATCH BEITBRIDGE EN-ROUTE TO HARARE | MASVINGO EN-ROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MAKUTI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBULESA ZAM SIDE - ATTENDING TO BREAKDOWN | * VEHICLE CURRENTLY AT KASUMBULESA ZAMBIA SDE - ATTENDING TO AIRBAG BREAKDOWN | * VEHICLE CURRENTLY AT KASUMBULESA ZAMBIA SDE IN QUEUE TO CROSS | * VEHICLE CURRENTLY AT KASUMBULESA ZAMBIA SDE IN QUEUE TO CROSS | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * OFFLOADED 26.07.2022 | * OFFLOADED 26.07.2022
BA1884 | 1 X NEW CAT 336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | E7A43831 | CAT00336CJFW20939 | JFW20939 | FML2201DSI1400 | COD 2022 209460 | ND142761 | ND542263 | ND62908 | 08.07.2022 | * OFFLOADED 27.07.2022 | 27-05-2022 | 01.06.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 01-06-2022 | 02.02.2022 | 08-07-2022 | MIDDELBURG 08-07-2022 | 12.07.2022 | 13-07-2022 | 13-07-2022 | 13-07-2022 | 15-07-2022 | 18-07-2022 | 18-07-2022 | 20-07-2022 | 21-07-2022 | 21-07-2022 | 21-07-2022 | 22-07-2022 | 22-07-2022 | 22-07-2022 | 22-07-2022 | 22-07-2022 | 22-07-2022 | 24.07.2022 | 25.07.2022 | 26.07.2022 | 27.07.2022 | 27.07.2022 | 27.07.2022 | [28 empty] | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | ESTIMATED LOADING DATE IS ON THE 17/06/2022 | ESTIMATED LOADING DATE IS ON THE 17/06/2022 | ESTIMATED LOADING DATE IS ON THE 17/06/2022 | ESTIMATED LOADING DATE IS ON THE 17/06/2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 17.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 27.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 30.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 30.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 01.07.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 06.07.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 06.07.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 06.07.2022 | * VEHICLE LOADING TODAY - PLANNING TO DISPATCH DURBAN TOMORROW MORNING | * VEHICLE LOADED - AWAITING PERMIT IN ORDER TO DISPATCH DURBAN | * VEHICLE AT MIDDELBURG WAITING PERMITS | * VEHILCLE CURRENTLY AT BEIT BRIDGE RSA SIDE | * VEHILCLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHILCLE CURRENTLY AT MAKUTI EN-ROUTE TO CHIRUNDU | * VEHILCLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHILCLE CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHILCLE CURRENTLY AT KASUMBALESA ZAM | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KANYAKA UNDER CLEARANCE | * OFFLOADED 27.07.2022 | * OFFLOADED 27.07.2022
BA1886 | 1 X NEW CAT 336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | E7A43831 | CAT00336CJFW20939 | JFW20939 | FML2201DSI1400 | COD 2022 209460 | ND705318 | ND476150 | ND62910 | 06.07.2022 | * OFFLOADED 27.07.2022 | 27-05-2022 | 01.06.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 01-06-2022 | 02.02.2022 | 06.07.2022 | MIDDELBURG 08-07-2022 | 12.07.2022 | 13-07-2022 | 13-07-2022 | 13-07-2022 | 15-07-2022 | 18-07-2022 | 18-07-2022 | 20-07-2022 | 21-07-2022 | 21-07-2022 | 21-07-2022 | 21-07-2022 | 21-07-2022 | 22-07-2022 | 23.07.2022 | 23.07.2022 | 24.07.2022 | 24.07.2022 | 25.07.2022 | 26.07.2022 | 27.07.2022 | 27.07.2022 | 27.07.2022 | [28 empty] | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29-06-2022 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29-06-2022 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29-06-2022 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2022 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 04-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 04-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | * VEHICLE LOADING TODAY - PLANNING TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE LOADED - AWAITING ABNORMAL PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED - AWAITING PERMIT IN ORDER TO DISPATCH DURBAN | * VEHICLE CURRENTLY AT MIDDELBURG WAITING PERMITS | * VEHILCLE CURRENTLY AT BEIT BRIDGE RSA SIDE | * VEHILCLE CURRENTLY AT KADOMA EN-ROUTE TO CHIRUNDU | * VEHILCLE CURRENTLY AT KAROI EN-ROUTE TO CHIRUNDU | * VEHILCLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHILCLE CURRENTLY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHILCLE CURRENTLY AT CHILILABOMBWE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KANYAKA UNDER CLEARANCE | * OFFLOADED 27.07.2022 | * OFFLOADED 27.07.2022
BA2033-BA2047 | TOWER LIGHTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML2203DSI1493 | COD 2022 198450 | ND59741 | ND95356 | ND68791 | 25.05.2022 | * OFFLOADED 29-07-2022 | 13.05.2022 | 17.05.2022 | BV BOOKED AS SOON AS CONTAINER WAS UNPACKED | 16.05.2022 | 26-05-2022 | 28-05-2022 | 03-06-2022 | GRB 04-06-2022 | GRB 06-06-2022 | MARTINSDRIFT 06-06-2022 | MARTINSDRIFT 8-06-2022 | NATA 21-06-2022 | NATA 22-06-2022 | KAZUGULA BW SIDE 23-06-2022 | 27-06-2022 | 27-06-2022 | 27-06-2022 | 28-06-2022 | 01-07-2022 | 02.07.2022 | 02.07.2022 | 03.07.2022 | 04.07.2022 | 18.07.2022 | 19.07.2022 | 21.07.2022 | 21.07.2022 | 27.07.2022 | 29-07-2022 |  |  |  | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | * VESSEL MSC TOMOKO CURRENT ETA 03.05.2022 | * VESSEL MSC TOMOKO CURRENT ETA 03.05.2022 | * VESSEL MSC TOMOKO CURRENT ETA 03.05.2022 | * VESSEL MSC TOMOKO CURRENT ETA 03.05.2022 | * VESSEL MSC TOMOKO / TRANSHIPMENT VESSEL: SANTA RITA CURRENT ETA 07.05.2022 | * VESSEL MSC TOMOKO / TRANSHIPMENT VESSEL: SANTA RITA CURRENT ETA 07.05.2022 | * VESSEL MSC TOMOKO / TRANSHIPMENT VESSEL: SANTA RITA CURRENT ETA 07.05.2022 | * VESSEL MSC TOMOKO / TRANSHIPMENT VESSEL: SANTA RITA CURRENT ETA 07.05.2022 | UNPACK DEPOT WAITNG UNPACK | UNPACK DEPOT WAITNG UNPACK, BV BOOKED FOR WEDNESDAY THE 18TH | UNPACK DEPOT WAITNG UNPACK, BV BOOKED FOR WEDNESDAY THE 18TH | LOADING AND DISPATCH FRIDAY THE 20/05/2022 | LOADING AND DISPATCH TEUSDAY THE 24/05/2022 | LOADING AND DISPATCH TEUSDAY THE 24/05/2022 | LOADING AND DISPATCH TEUSDAY THE 24/05/2022 | * VEHICLE LOADING TODAY 24TH MAY 2022 AND DISPATCHING TOMORROW MORNING 25TH OF MAY 2022 | * VEHICLE DISPATCHING DURBAN THIS MORNING - ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MOOIRIVIER ENROUTE JOHANNESBURG | TOM BURKE ENROUTE GROBLESBRIDGE | TRUCK AT GROBLESBRIDGE RSA SIDE AWAITNG CLEARANCE | TRUCK AT GROBLESBRIDGE RSA SIDE AWAITNG CLEARANCE AND RELEASE | TRUCK AT GROBLESBRIDGE RSA SIDE IN QUEUE TO CROSS TO BOTSWANA | TRUCK AT GROBLESBRIDGE BOTSWANA SIDE AWAIITNG FINAL RELEASE | TRUCK AT GROBLESBRIDGE BOTSWANA SIDE AWAITING FINAL RELEASE | * VEHICLE TO BE RELEASED FROM GROBLERSBRIDGE TODAY - ENROUTE FRANCISTOWN | * VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE MAPOSA | * VEHICLE AT MAPOPSA ENROUTE FRANCISTOWN | * VEHILCE AT BALTIMORE ENROUTE FRANCISTOWN | * VEHILCE AT FRANCISTOWN | * VEHILCE AT KASUNGULA BOTSWANA SIDE CLEARING | * VEHILCE AT KASUNGULA IN QUEUE | * VEHILCE AT LIVINGSTONE EN-ROUTE TO LUSAKA | * CHOMA EN-ROUTE TO LUSAKA | MAZABUKA EN-ROUTE TO KASUMBALESA BORDER | LUSAKA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA AWAITNG CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA IN QUEUE | * VEHICLE CURRENLTY AT KASUMBALESA DRC AWAITING RELEASE | * VEHICLE CURRENLTY AT KASUMBALESA DRC AWAITING TO DISPATCH | * VEHICLE CURRENLTY AT KASUMBALESA DUE TO DISPATCH | * VEHICLE CURRENLTY AT KASUMBALESA AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE EN-ROUTE TO SITE | * VEHICLE ON SITE AWAITING TO OFFLOAD | * VEHICLE ON SITE AWAITING TO OFFLOAD | * VEHICLE ON SITE AWAITING TO OFFLOAD - WAITING FOR CUSTOMS TO CLEAR CONTAINER IN ORDER TO OFFLOAD | * VEHICLE ON SITE AWAITING TO OFFLOAD - WAITING FOR CUSTOMS TO CLEAR CONTAINER IN ORDER TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 29-07-2022
BA1729 | 1 X NEW CAT D8GC TRACTOR | BARTRAC EQUIPMENT - CONGO EQUIPMENT | KGX00320 | CAT000D8TKGX00320 | TXJ02250 | FML2206DSI1601 | COD 2022 223319 | ND570587 | ND702944 | ND52554 | 06.07.2022 | OFFLOADED 03-08-2022 | 16-06-2022 | 28-06-2022 | AWAITNG AMENDED BV LICENSE TO SHOW PORT OF ENTRY SAKANIA BORDER POST | 16-06-2022 | 06.07.2022 | MIDDELBURG 08-07-2022 | 12.07.2022 | 13-07-2022 | 13-07-2022 | 13-07-2022 | 15-07-2022 | 18-07-2022 | 19-07-2022 | 20-07-2022 | 21-07-2022 | 21-07-2022 | 21-07-2022 | 22-07-2022 | 22-07-2022 | 22-07-2022 | 22-07-2022 | 22-07-2022 | 22-07-2022 | 24.07.2022 | 25.07.2022 | 27-07-2022 | 27-07-2022 | 28-07-2022 | 03-08-2022 | [39 empty] | AWAITNG AMENDED BV LICENSE TO SHOW PORT OF ENTRY SAKANIA BORDER POST | AWAITNG AMENDED BV LICENSE TO SHOW PORT OF ENTRY SAKANIA BORDER POST | BV BOOKED FOR TODAY AWAITING TRUCK TO RETURN FROM DRC IN ORDER TO LOAD. LOADING DATE TO BE CONFIRMED | BV BOOKED FOR TODAY AWAITING TRUCK TO RETURN FROM DRC IN ORDER TO LOAD. LOADING DATE TO BE CONFIRMED | BV BOOKED FOR TODAY AWAITING TRUCK TO RETURN FROM DRC IN ORDER TO LOAD. LOADING DATE TO BE CONFIRMED | BV BOOKED FOR TODAY AWAITING TRUCK TO RETURN FROM DRC IN ORDER TO LOAD. LOADING DATE TO BE CONFIRMED | BV COMPLETE - AWAITING TRUCK TO RETURN FROM DRC IN ORDER TO LOAD. LOADING DATE TO BE CONFIRMED | BV COMPLETE - AWAITING TRUCK TO RETURN FROM DRC IN ORDER TO LOAD. LOADING DATE TO BE CONFIRMED | * VEHICLE LOADING TODAY - PLANNING TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE CURRENTLY AT MIDDELBURG WAITING PERMITS | * VEHILCLE CURRENTLY AT BEIT BRIDGE RSA SIDE | * VEHILCLE AT GWERU EN-ROUTE TO CHIRUNDU | * VEHILCLE AT MAKUTI EN-ROUTE TO CHIRUNDU | * VEHILCLE AT CHIRUNDU ZAM SIDE | * VEHILCLE AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHILCLE AT MOKAMBO ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE RELEASE FROM WHISKEY AWAITING ESCORT | * VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 03-08-2022
BA1796 | 1 X CAT 226B3 SKID STEER LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | DXZ03280 | CAT0226BCDXZ03280 | CZ208505 | FML2206DSI1627 | COD 2022 224246 | JM22FMGP | N/A | N/A | 12.07.2022 | OFFLOADED 08.08.2022 | 16.06.2022 | 08-06-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 03.07.2022 | 12.07.2022 | 13.07.2022 | 13-07-2022 | GROBLERSBRIDGE 13-07-2022 | GROBLERSBRIDGE 14-07-2022 | MARTINSDRIFT 14-07-2022 | MARTINSDRIFT 14-07-2022 | 15-07-2022 | 16-07-2022 | 16-07-2022 | 16-07-2022 | 16-07-2022 | 17-07-2022 | 17-07-2022 | 17-07-2022 | 17-07-2022 | 18-07-2022 | 18-07-2022 | 25.07.2022 | 26.07.2022 | 27.07.2022 | 28.07.2022 | 28.07.2022 | 03-08-2022 | 08/08/2022 | [46 empty] | * AWAITING CONTAINER DISCHARGE FROM VESSEL & CONFIRMATION OF BOOKING TO COLLECT FROM PORT | * CONTAINER CURRENTLY UNDER UNPACK - BV INSPECTION TO BE BOKED FOR THURSDAY 07.07.2022 | LOADING TODAY | * VEHICLE CURRENTLY ENROUTE KAZUNGULA | * VEHICLE CURRENTLY AT KAZUNGULA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT LIVINGSTONE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY IN QUEUE TO KASUMBALESA | * VEHICLE CURRENTLY IN QUEUE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KANYAKHA ENROUTE LUBUMBASHI | ON SITE WIATING TO OFFLOAD | OFFLOADED 08.08.2022
BA2064 | 1 X NEW CAT 374-07B HYDRAULIC EXCAVATOR - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10020 | CAT00374TRM10020 | E4T00498 | FML2205DSI1567 | COD 2022 204403 | WMN927GP | BG55CXGP / BG37PLGP | ND59534-1 | 12.07.2022 | OFFLOADED 09/08/2022 | 23-05-2022 | 03-06-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 01.06.2022 | 12.07.2022 | 13.07.2022 | 14.07.2022 | 15.07.2022 | 16.07.2022 | 16.07.2022 | 17.07.2022 | 18.07.2022 | 18.07.2022 | 19.07.2022 | 20.07.2022 | 20.07.2022 | 20.07.2022 | 20.07.2022 | 20.07.2022 | 23.07.2022 | 23.07.2022 | 23.07.2022 | 24.07.2022 | 24.07.2022 | 25.07.2022 | 28.07.2022 | 29.07.2022 | 09.08.2022 | 09.08.2022 |  |  |  | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - anticipated load date 08/05 due to limited movement out of port due to floud damage | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | * ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | * ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | BV INSPECTION BOOKED FOR TODAY | BV DONE AWAITING LOADING DATE | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - PLANNING TO LOAD 13.07.2022 | * VEHILCLE CURRENTLY AT BEIT BRIDGE RSA SIDE | * VEHILCLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHILCLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHILCLE CURRENTLY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHILCLE CURRENTLY AT MOKAMBO BORDER AWAITING FEEDBACK WITH REGARDS TO THE SPLIT DECLARATION | * VEHILCLE CURRENTLY AT MOKAMBO BORDER AWAITING FEEDBACK WITH REGARDS TO THE SPLIT DECLARATION | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | OFFLOADED 09/08/2022 | OFFLOADED 09/08/2022 | OFFLOADED 09/08/2022
BA2064 | 1 X NEW CAT 374-07B HYDRAULIC EXCAVATOR - PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10020 | CAT00374TRM10020 | E4T00498 | FML2205DSI1567 | COD 2022 204403 | AGB6607ZM | ACG495T / ACG4958T | ND59534-2 | 12.07.2022 | OFFLOADED 09/08/2022 | 23-05-2022 | 03-06-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 01.06.2022 | 12.07.2022 | 13.07.2022 | 14.07.2022 | 15.07.2022 | 16.07.2022 | 16.07.2022 | 17.07.2022 | 18.07.2022 | 18.07.2022 | 19.07.2022 | 20.07.2022 | 20.07.2022 | 20.07.2022 | 20.07.2022 | 20.07.2022 | 23.07.2022 | 24.07.2022 | 24.07.2022 | 25.07.2022 | 28.07.2022 | 29.07.2022 | 09.08.2022 | 09.08.2022 | 09.08.2022 | 09.08.2022 |  |  |  | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | AWAITING FINAL BILL IN ORDER TO TRACK THE VESSEL | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY CURRENT ETA 25.04.2022 | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - anticipated load date 08/05 due to limited movement out of port due to floud damage | * VESSEL BLUE RIDGE HIGHWAY - VESSEL ARRIVED AND CURRENTLY WORKING - ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | * ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | * ANTICIPATED LOADING DATE 08.05.2022 DUE TO LIMITED MOVEMENT OUT OF PORT DUE TO FLOOD DAMAGE | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - MORNING COURIER: - ETA 29-05-2022 | BV INSPECTION BOOKED FOR TODAY | BV DONE AWAITING LOADING DATE | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITNG BARTRAC INSTRUCTION | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - PLANNING TO LOAD 13.07.2022 | * VEHILCLE CURRENTLY AT BEIT BRIDGE RSA SIDE | * VEHILCLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHILCLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHILCLE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHILCLE CURRENTLY AT KASUMBALESA BORDER AWAITING FEEDBACK WITH REGARDS TO THE SPLIT DECLARATION | * VEHILCLE CURRENTLY AT KASUMBALESA BORDER AWAITING FEEDBACK WITH REGARDS TO THE SPLIT DECLARATION | * VEHILCLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | * VEHILCLE CURRENTLY AT KASUMBALESA ZAM SIDE - IN QUEUE TO CROSS TO DRC | * VEHILCLE CURRENTLY AT KASUMBALESA ZAM SIDE - IN QUEUE TO CROSS TO DRC | * VEHILCLE CURRENTLY AT KASUMBALESA ZAM SIDE - IN QUEUE TO CROSS TO DRC | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | * VEHICLE CURRENLTY AT LUBUMBASHI AWAITING FINAL CLEARANCE | OFFLOADED 09/08/2022 | OFFLOADED 09/08/2022 | OFFLOADED 09/08/2022
BA2065 | 1 X NEW CAT 374-07B HYDRAULIC EXCAVATOR - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10017 | CAT00374TRGM10017 | E4T00496 | FML2203DSI1486 | COD 2022 169459 | ND760431 | ND760424/ND760428 | ND60606 | 19.07.2022 | * OFFLOADED 12.08.2022 | 07-04-2022 | 07-07-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 08-04-2022 | 19-07-2022 | 21-07-2022 | 21-07-2022 | 26.07.2022 | 27.07.2022 | 28.07.2022 | 01-08-2022 | 02-08-2022 | 02-08-2022 | 02-08-2022 | 03-08-2022 | 03-08-2022 | 04-08-2022 | 05-08-2022 | 06-08-2022 | 06-08-2022 | 07-08-2022 | 08-08-2022 | 08-08-2022 | 09-08-2022 | 10-08-2022 | 12-08-2022 | 12-08-2022 | 12-08-2022 | 12-08-2022 | [38 empty] | AWAITNG BARTRAC INSTRUCTION & BV NUMBER | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - PLANNING TO LOAD 19.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - PLANNING TO LOAD 26.07.2022 | MACHINE TO BE LOADED TODAY AND DISPATCH TOMMROW THE 19/07/2022 | MACHINE LOADED AND TO DISPATCH TODAY THE 19/07/2022 | TRUCK AT ESCORT EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT VOLKSRUST AWAITING MPUMALANGA PERMIT | TRUCK TO DISPATCH HENDRINA ON MONDAY THE 25/07/2022 EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT POLOKWANE ENROUTE MUSINA | * VEHICLE CURRENTLY AT ALLDAYS ENROUTE MUSINA | * VEHICLE CURRENTLY AT MUSINA TO DISPATCH FOR BEITBRIDGE THIS MORNING | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | KAFUE ENROUTE LUSAKA | KASUMBALESA DRC SIDE | WHISKEY AWAITING FINAL RELEASE | WHISKEY AWAITING FINAL RELEASE | ON SITE AWAITING TO OFFLOAD | * OFFLOADED 12.08.2022 | * OFFLOADED 12.08.2022
BA2065 | 1 X NEW CAT 374-07B HYDRAULIC EXCAVATOR - PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10017 | CAT00374TRGM10017 | E4T00496 | FML2203DSI1486 | COD 2022 169459 | TBA | TBA | TBA | TBA | * OFFLOADED 13.08.2022 | 07-04-2022 | 07-07-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 08-04-2022 | 23.07.2022 | 25.07.2022 | 26.07.2022 | 26.07.2022 | 27.07.2022 | 28.07.2022 | 29-07-2022 | 29-07-2022 | 30-07-2022 | 30-07-2022 | 01-08-2022 | 01-08-2022 | 02-08-2022 | 03-08-2022 | 03-08-2022 | 04-08-2022 | 04-08-2022 | 04-08-2022 | 04-08-2022 | 09-08-2022 | 10-08-2022 | 15.08.2022 | 15.08.2022 | 15.08.2022 | 15.08.2022 | [38 empty] | AWAITNG BARTRAC INSTRUCTION & BV NUMBER | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | AWAITING AMENDED BV LICENSE IN ORDER TO COMPLETE BV FORMALITIES BEFORE LOADING AND DISPATCHING | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - PLANNING TO LOAD 19.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - PLANNING TO LOAD 26.07.2022 | SPARE TO DISPATCH ON WEDNESDAY THE 20/07/2022 | SPARE TO DISPATCH ON WEDNESDAY THE 20/07/2022 | SPARE TO DISPATCH ON FRIDAY THE 22/07/2022 | SPARE TO DISPATCH ON FRIDAY THE 22/07/2022 | TRUCK AT MARIAN TOLL EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT MIDRAND ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT MUSINA TO DISPATCH FOR BEITBRIDGE THIS MORNING | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | KASUMBULESA ZAMBIAN SIDE | KASUMBALESA DRC SIDE | WHISKEY AWAITING FINAL RELEASE | WHISKEY AWAITING FINAL RELEASE | WHISKEY AWAITING FINAL RELEASE | WHISKEY AWAITING FINAL RELEASE | * OFFLOADED 15.08.2022
BA2103 | 1 X USED CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TFK01276 | CAT0745CCTFK01276 | RDP02978 | FML2205DSI1561 | COD 2022 183390 | ND834401 | ND854241 | ND59532 | TBA | * OFFLOADED 12.08.2022 | 22.04.2022 | 11.07.2022 | BV NUMBER RECEIVED, BV INSPECTION BOOKED | 03-06-2022 | 26.07.2022 | 27.07.2022 | 28.07.2022 | 29.07.2022 | 29-07-2022 | 29-07-2022 | 02-08-2022 | 02-08-2022 | 03-08-2022 | 04-08-2022 | 04-08-2022 | 04-08-2022 | 05-08-2022 | 06-08-2022 | 07-08-2022 | 08-08-2022 | 08-08-2022 | 08-08-2022 | 08-08-2022 | 09-08-2022 | 10-08-2022 | 12-08-2022 | 12-08-2022 | 12-08-2022 | 12-08-2022 | [47 empty] | * AWAITING VESSEL HOEGH SHANGHAI ARRIVAL - CURRENT ETA 12.07.2022 | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE TBC | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE TBC | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE TBC | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE TBC | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE TBC | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 05/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 05/08/2022 | VEHICLE LOADING TODAY - AWAITING PERMIT & ESCORT TO DISPATCH | * VEHICLE CURRENTLY AT MOOI RIVIER ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT HENDRINA ENROUTE POLOKWANE | CHIRUNU ZAMBIAN SIDE CLEARING | KASUMBALESA ZAM SIDE | WHISKEY AWAITING FINAL RELEASE | WHISKEY AWAITING FINAL RELEASE | ON SITE AWAITING TO OFFLOAD | * OFFLOADED 12.08.2022 | * OFFLOADED 12.08.2022
BA2112 | 1 X USED CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TFK00870 | CAT0745CKTFK00870 | RDP02388 | FML2205DSI1561 | COD 2022 183390 | ND730794 | ND443606 | ND59533 | TBA | * OFFLOADED 12.08.2022 | 22.04.2022 | 11.07.2022 | BV NUMBER RECEIVED, BV INSPECTION BOOKED | 03-06-2022 | 26.07.2022 | 27.07.2022 | 28.07.2022 | 29.07.2022 | 29-07-2022 | 29-07-2022 | 02-08-2022 | 02-08-2022 | 03-08-2022 | 04-08-2022 | 04-08-2022 | 04-08-2022 | 05-08-2022 | 06-08-2022 | 07-08-2022 | 08-08-2022 | 08-08-2022 | 08-08-2022 | 08-08-2022 | 09-08-2022 | 10-08-2022 | 12-08-2022 | 12-08-2022 | 12-08-2022 | 12-08-2022 | [47 empty] | * AWAITING VESSEL HOEGH SHANGHAI ARRIVAL - CURRENT ETA 12.07.2022 | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 21/22 JULY | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 25 JULY | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 25 JULY | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 25 JULY | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 25 JULY | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED LOADING DATE 27 JULY | * VEHICLE LOADING TODAY - PLANNING TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE LOADED - AWAITING PERMIT & ESCORT TO DISPATCH | * VEHICLE CURRENTLY AT MOOI RIVIER ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT HENDRINA ENROUTE POLOKWANE | CHIRUNU ZAMBIAN SIDE CLEARING | KASUMBALESA ZAM SIDE | WHISKEY AWAITING FINAL RELEASE | WHISKEY AWAITING FINAL RELEASE | ON SITE AWAITING TO OFFLOAD | * OFFLOADED 12.08.2022 | * OFFLOADED 12.08.2022
BA1840 | 1 X NEW CAT D6GC-01A TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | R6J04454 | CAT000D6LXPC00581 | XPC00581 | FML2206DSI1642 | TBA | TBA | TBA | TBA | TBA | MACHINE IS AT OUR FACILITY AWAITING BARLOWORLD TO COLLECT |  |  | WAITING BV NUMBER | 19.07.2022 | [25 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | JOHANNESBURG | CHIRUNDU ZAM SIDE | KAROI EN-ROUTE KASUMBALESA | CHIRUNDU EN-ROUTE KASUMBALESA | CHIRUNDU ZIM SIDE AWAIITNG RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | KAFUE EN-ROUTE TO KASUMBALESA | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALES DRC, IN QUEUE TO CROSS OVER TO WHISKEY | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | ESTIMATED LOADING DATE IS ON THE 17/06/2022 | ESTIMATED LOADING DATE IS ON THE 17/06/2022 | ESTIMATED LOADING DATE IS ON THE 17/06/2022 | ESTIMATED LOADING DATE IS ON THE 17/06/2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 17.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 23.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 27.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 30.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 30.06.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 01.07.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 06.07.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 06.07.2022 | WAITING RETURN VEHICLE FROM THE DRC - LOADING 06.07.2022 | * VEHICLE LOADING TODAY - PLANNING TO DISPATCH DURBAN TOMORROW MORNING | * VEHICLE LOADED - AWAITING PERMIT IN ORDER TO DISPATCH DURBAN | * VEHICLE AT MIDDELBURG WAITING PERMITS | WAITING VESSEL ARRIVAL - ETA 18-07-2022 | WAITING VESSEL ARRIVAL - ETA 18-07-2022 | THE VESSEL IS IN AND WORKING, VEHCILE ALONG SIDE VESSEL TO LOAD ONCE MACHINE IS DISCHARGED | COLLECTING MACHINE FROM PORT TODAY | MACHINE IS AT OUR FACILITY,AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR FACILITY,AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR FACILITY,AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR FACILITY,AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR FACILITY,AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR FACILITY,AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR FACILITY | MACHINE IS AT OUR FACILITY AWAIITNG TRUCK DETAILS | MACHINE IS AT OUR FACILITY AWAIITNG TRUCK DETAILS | MACHINE IS AT OUR FACILITY AWAITING BARLO WORLD TO COLLECT | MACHINE IS AT OUR FACILITY AWAITING BARLO WORLD TO COLLECT | MACHINE IS AT OUR FACILITY AWAITING BARLOWORLD TO COLLECT | MACHINE IS AT OUR FACILITY AWAITING BARLOWORLD TO COLLECT | MACHINE IS AT OUR FACILITY AWAITING BARLOWORLD TO COLLECT | MACHINE IS AT OUR FACILITY AWAITING BARLOWORLD TO COLLECT | MACHINE IS AT OUR FACILITY AWAITING BARLOWORLD TO COLLECT
BA1888 | 1 X NEW CAT 336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | E7A43831 | CAT00336CJFW20939 | JFW20939 | FML2201DSI1400 | COD 2022 209460 | TBA | TBA | TBA | TBA | OFFLOADED 19-08-2022 | 27-05-2022 | 01.06.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 01-06-2022 | 02.02.2022 | 03-08-2022 | 08-08-2022 | 09-08-2022 | 09-08-2022 | 09-08-2022 | 10-08-2022 | 12/08/2022 | 12-08-2022 | 12.08.2022 | 13.08.2022 | 13.08.2022 | 14.08.2022 | 14.08.2022 | 15.08.2022 | 15.08.2022 | 16.08.2022 | 16.08.2022 | 16.08.2022 | 17.08.2022 | 17.08.2022 | 18.08.2022 | 18.08.2022 | 19.08.2022 | 19-08-2022 | 19-08-2022 | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | JOHANNESBURG | CHIRUNDU ZAM SIDE | KAROI EN-ROUTE KASUMBALESA | CHIRUNDU EN-ROUTE KASUMBALESA | CHIRUNDU ZIM SIDE AWAIITNG RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | KAFUE EN-ROUTE TO KASUMBALESA | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALES DRC, IN QUEUE TO CROSS OVER TO WHISKEY | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 12-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 15-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 22.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | VOLKRUST WAITING PERMITS | JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE RSA SIDE AWAITING RELEASE | TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KITWE ENROUTE CHINGOLA | * VEHICL ECURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | OFFLOADED 19-08-2022
BA2061 | 1 X NEW CAT 140GC 01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201224 | CAT00140KW9201224 | E7A53532 | FML2206DSI1617 | COD 2022 224249 | ADZ5841 | ADS9985 | ND59589 | 13.07.2022 | * OFFLOADED 16.08.2022 | 17.06.2022 | 11.07.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.07.2022 | 13.07.2022 | 18.07.2022 | 21.07.2022 | 24.07.2022 | 24.07.2022 | 25.07.2022 | 26.07.2022 | 27.07.2022 | 29-07-2022 | 01-08-2022 | 01-08-2022 | 01-08-2022 | 02-08-2022 | 03-08-2022 | 03-08-2022 | 03-08-2022 | 03-08-2022 | 03-08-2022 | MOKAMBO 03-08-2022 | 09-08-2022 | 10-08-2022 | 11-08-2022 | 11-08-2022 | 16.08.2022 | 16.08.2022 | [47 empty] | * AWAITING VESSEL GLOVIS SKY ARRIVAL - CURRENT ETA 07.07.2022 | LOADING TODAY | * VEHICLE CURRENTLY AT MOOIREVIER ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG AWAITING TRIP CHECK | * VEHICLE CURRENTLY AT JOHANNESBURG AWAITING TRIP CHECK | * VEHICLE TO DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE AT MUSINA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING RELEASE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MOKAMBO CLEARING | * VEHICLE CURRENTLY AT MOKAMBO CLEARING | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | * VEHICLE CURRENTLY AT KANYAKA EN-ROUTE TO SITE | * VEHICLE CURRENTLY AT LUBUMBASHI EN-ROUTE TO SITE | * VEHICLE CURRENTLY AT LUBUMBASHI UNDER CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 16.08.2022 | * OFFLOADED 16.08.2022 | * OFFLOADED 16.08.2022
BA2121 | 1 X NEW CAT 140K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZL20820 | CAT0140KASZL20820 | TX712096 | FML2206DSI1618 | COD 2022 224249 | AAS6402 | ADC5344 | ND59571 | 13.07.2022 | * OFFLOADED 16.08.2022 | 17.06.2022 | 04.07.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.06.2022 | 13.07.2022 | 18.07.2022 | 21.07.2022 | 24.07.2022 | 24.07.2022 | 25.07.2022 | 26.07.2022 | 27.07.2022 | 29-07-2022 | 29-07-2022 | 01-08-2022 | 01-08-2022 | 02-08-2022 | 03-08-2022 | 03-08-2022 | 03-08-2022 | 03-08-2022 | 03-08-2022 | MOKAMBO 03-08-2022 | 09-08-2022 | 10-08-2022 | 11-08-2022 | 15.08.2022 | 16.08.2022 | 16.08.2022 | [47 empty] | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | LOADING TODAY | * VEHICLE CURRENTLY MOOIRIVIER ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE CURRENTLY JOHANNESBURG UNDERGOING TRIP CHECK | * VEHICLE TO DISPATCH JOHANNESBURG TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE AT MUSINA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE - AWAITING RELEASE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MOKAMBO CLEARING | * VEHICLE CURRENTLY AT MOKAMBO CLEARING | WHISKEY AWAITING FINAL RELEASE | KANYAKA EN-ROUTE TO SITE | LUBUMBASHI EN-ROUTE TO SITE | * VEHICLE AT LUBUMBASHI UNDER CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 16.08.2022 | * OFFLOADED 16.08.2022 | * OFFLOADED 16.08.2022
BA2012 | 1 X NEW CAT 330GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK30431 | CAT00330HFEK30431 | E7A53837 | FML2206DSI1607 | COD 2022 225141 | JR76FMGP | KH82PCGP | ND59575 | TBA | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | 21.06.2022 | 07.07.2022 | BV INSPECTION BOOKED FOR THURSDAY 07.07.2022 | 30.06.2022 | 28.07.2022 | 02-08-2022 | 04-08-2022 | 04-08-2022 | 04-08-2022 | 04-08-2022 | 08-08-2022 | 08-08-2022 | 09-08-2022 | 11-08-2022 | 12.08.2022 | 12.08.2022 | 12.08.2022 | 13.08.2022 | 13.08.2022 | 14.08.2022 | 14.08.2022 | 14.08.2022 | 15.08.2022 | 17.08.2022 | 18.08.2022 | [51 empty] | BV INSPECTION BOOKED FOR THUSDAY 07.07.2022 - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - ESTIMATE LOADING DAT 25.07.2022 | * BV INSPECTION COMPLETE - ESTIMATE LOADING DATE 25.07.2022 | * BV INSPECTION COMPLETE - ESTIMATE LOADING DATE 27.07.2022 | * BV INSPECTION COMPLETE - ESTIMATE LOADING DATE 27.07.2022 | * BV INSPECTION COMPLETE - ESTIMATE LOADING DATE 27.07.2022 | * BV INSPECTION COMPLETE - ESTIMATE LOADING DATE 27.07.2022 | * BV INSPECTION COMPLETE - ESTIMATE LOADING DATE 27.07.2022 | * VEHICLE LOADING TODAY - PLANNING TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE LOADED - AWAITING PERMIT TO DISPATCH | * VEHICLE LOADED - AWAITING PERMIT TO DISPATCH | * VEHICLE DISPATCHED DURBAN ENROUTE MARIANHILL | BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | TRUCK TO DISPATCH HARARE EN-ROUTE TO CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE | TRUCK AT CHIRUNDU ZAM SIDE AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT KASUMBALESA AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA UNDER CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA UNDER CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 22-08-2022
BA1681 | 1 X NEW CAT 777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KYD00304 | CAT0777ELKYD00304 | FZS01904 | FML2110DSI1298 | COD 2022 168417 | NU31292 | DM66SSGP / DM66RTGP | ND60160 | 03.05.2022 | * VEHICLE CURRENTLY AT WHISKEY - AWAITING CLEARANCE | 01.04.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.10.2022 | 02-06-2022 | 29-06-2022 | 30-06-2022 | 19-07-2022 | 19-07-2022 | 22-07-2022 | 29-07-2022 | 02-08-2022 | 03-08-2022 | 08-08-2022 | 11.08.2022 | 13.08.2022 | 13.08.2022 | 14.08.2022 | 14.08.2022 | 15.08.2022 | 16.08.2022 | 16.08.2022 | 16.08.2022 | 18.08.2022 | 19.08.202 |  |  |  |  | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | * BV INSPECTION BOOKED FOR TODAY - PLANNING TO DISPATCH ON THE 19/04/2022 | * PLANNING TO LOAD AND DISPATCH ON WEDNESDAY THE 20/04/2022 | * PLANNING TO LOAD AND DISPATCH ON THURSDAY THE 21/04/2022 | * PLANNING TO LAOD NEXT WEEK WEDNESDAY THE 27/04/2022 | Truck enroute to Durban for loading. To be loaded on 05/05 due to public holidays and road closures in RSA, departure depended on the issuance of permits by the permit office | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | LOADED - WAITING PERMITS AND ESCOURTS - RTI INFORMED US THAT THE ESCOURTS WILL NOT BE AVAILABLE UNITL THE 16 / 17 OF MAY | TRUCK TO DISPATCH TOMMROW THE 17/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 19/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 19/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 20/05/2022 | TRUCK TO LOAD AND DISPATCH TODAY THE 20/05/2022 | TRUCK TO LOAD AND DISPATCH TODAY THE 20/05/2022 | * VEHICLE CURRENLTY LOADING - PLANNING TO DISPATCH THIS AFTERNOON | * VEHILCE LOADED - AWAITING PROVIINCIAL ESCORTS | * VEHILCE LOADED - AWAITING PROVIINCIAL ESCORTS | CATO RIDGE WAITING PROVINSIAL ESCORTS | CAMPERSDOWN EN-ROUTE TO JNB | PIETERMARITZBURG AWAITING METRO POLICE EN ORDER TO DISPATCH | PIETERMARITZBURG AWAITING METRO POLICE EN ORDER TO DISPATCH | TRUCK AT GREYTOWN AWAITING POLICE ESCORTS | TRUCK AT GREYTOWN AWAITING POLICE ESCORTS | * VEHICLE AT GREYTOWN AWAITING POLICE ESCORTS | * VEHICLE AT GREYTOWN AWAITING POLICE ESCORTS | * VEHICLE AT GREYTOWN AWAITING POLICE ESCORTS | * VEHICLE CURRENTLY AT LADYSMITH ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT WEENEN WAITING ESCORTS | * VEHICLE CURRENTLY AT VOLKSRUST WAITING FOR RTI ESCORTS | * VEHICLE CURRENTLY AT VOLKSRUST WAITING FOR RTI ESCORTS | * VEHICLE CURRENTLY AT VOLKSRUST WAITING FOR RTI ESCORTS | * VEHICLE CURRENTLY AT VOLKSRUST RTI TO ESCOURT THE UNIT THIS MORNING | * TRUCK AT ERMELO AWAIITNG RTI | * TRUCK AT HENDRINA AWAITING RTI ESCOURTS | * TRUCK AT HENDRINA AWAITING RTI ESCOURTS - TO DISPATCH THIS MORNING | * VEHICLE CURRENTLY AT MIDDLEBURG AWAITING RTI ESCOURTS - TO DISPATCH THIS MORNING | * VEHICLE CURRENTLY AT MIDDLEBURG AWAITING RTI ESCOURTS - TO DISPATCH THIS MORNING | * VEHICLE STILL AT MIDDLEBURG AWAITING ABNORMAL PERMIT | * VEHICLE STILL AT STOFBERG WAITING RTI ESCORT | * VEHICLE BEING ESCOURTED TROUGH ZEBEDIELA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT POLOKWANE AWAITING RTI | * VEHICLE AT DENDRON AWAITING RTI | * VEHICLE AT MUSINA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT BEITBRIDGE AWAITING CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - IN QUEUE TO CROSS TO ZIM SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - ENTERING CUSTOMS | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING ESCORT | MAKUTI ENROUTE CHIRUNDU | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | TRUCK IS AT KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT MUFULIRA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA CROSSING TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | VEHICLE ARRIVED ON SITE 20-08-2022 | OFFLOADED 22-08-2022
BA1682 | 1 X NEW CAT 777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KYD00305 | CAT0777EHKYD00305 | FZS01916 | FML2110DSI1298 | COD 2022 168417 | NU152641 | NU57455 / NU56082 | ND60161 | 03.05.2022 | * VEHICLE CURRENTLY AT WHISKEY - AWAITING CLEARANCE | 01.04.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.10.2022 | 21-06-2022 | 29-06-2022 | 30-06-2022 | 19-07-2022 | 19-07-2022 | 22-07-2022 | 29-07-2022 | 02-08-2022 | 03-08-2022 | 08-08-2022 | 11.08.2022 | 11.08.2022 | 12.08.2022 | 12.08.2022 | 13.08.2022 | 13.08.2022 | 15.08.2022 | 15.08.2022 | 16.08.2022 | 18.08.2022 | 19.08.202 |  |  |  |  | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | * BV INSPECTION BOOKED FOR TODAY - PLANNING TO DISPATCH ON THE 19/04/2022 | * PLANNING TO LOAD AND DISPATCH ON WEDNESDAY THE 20/04/2022 | * PLANNING TO LOAD AND DISPATCH ON THURSDAY THE 21/04/2022 | * PLANNING TO LAOD NEXT WEEK WEDNESDAY THE 27/04/2022 | Truck enroute to Durban for loading. To be loaded on 05/05 due to public holidays and road closures in RSA, departure depended on the issuance of permits by the permit office | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 05.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | LOADED - WAITING PERMITS AND ESCOURTS - RTI INFORMED US THAT THE ESCOURTS WILL NOT BE AVAILABLE UNITL THE 16 / 17 OF MAY | TRUCK TO DISPATCH TOMMROW THE 17/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 19/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 19/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 24/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 24/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 24/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 25/05/2022 | * VEHICLE TO LOAD TODAY - 25 MAY 2022 | * VEHICLE TO LOAD TOMORROW 27 MAY 2022 | LOADED WAITING ABNORMAL PERMITS | TRUCK LOADING AND DISPATCHING ON WEDNESDAY THE 08/06/2022 | TRUCK LOADING AND DISPATCHING ON WEDNESDAY THE 10/06/2022 | TRUCK TO LOAD ON FRIDAY THE 10/06/2022 | TRUCK TO LOAD ON MONDAY THE 13/06/2022 | TRUCK TO LOAD ON MONDAY THE 13/06/2022 | * AWAIITNG VEHICLE RETURN TO LOAD ON WEDNESDAY THE 15.06.2022 | * AWAIITNG VEHICLE RETURN TO LOAD ON WEDNESDAY THE 15.06.2022 | * AWAIITNG VEHICLE RETURN TO LOAD ON WEDNESDAY AFTERNOON - 15.06.2022 | * AWAIITNG VEHICLE RETURN TO LOAD ON FRIDAY AFTERNOON - 17.06.2022 | RETURN VEHICLE CURRENTLY ATTENDING TO MINOR BREAKDOWN, PLANNING TO LOAD TOMORROW AND DISPATCH WEDNESDAY | PIETERMARITSBURG WAITING RTI ESCORST | CAMPERDOWN WAITING RTI ESCORST | DALTON WAITING RTI ESCORST | DISPATCHING DALTON EN-ROUTE TO WEENEN | TRUCK AT WEENEN AWAITING RTI | * TRUCK AT COLENSO AWAITING RTI ESCOURTS | * TRUCK AT COLENSO AWAITING RTI ESCOURTS | * VEHICLE CURRENTLY AT DUNDEE AWAITING RTI ESCOURTS | * VEHICLE CURRENTLY AT NEWCASTLE AWAITING RTI ESCORT TO VOLKSRUST | * VEHICLE CURRENTLY ENROUTE HENDRINA | * VEHICLE CURRENTLY AT STOFBERG AWAITING RTI ESCORT | * VEHICLE BEING ESCOURTED TROUGH ZEBEDIELA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT POLOKWANE AWAITING RTI | * VEHICLE AT DENDRON AWAITING RTI | * VEHICLE AT MUSINA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT BEITBRIDGE AWAITING CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - IN QUEUE TO CROSS TO ZIM SIDE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE - ENTERING CUSTOMS | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING ESCORT | MAKUTI ENROUTE CHIRUNDU | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | TRUCK IS AT KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARNCE | * VEHICLE CURRENTLY AT KASUMBALESA CROSSING TO DRC SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | VEHICLE ARRIVED ON SITE 20-08-2022 | OFFLOADED 22-08-2022
BA1683 | 1 X NEW CAT 777E OFF HIGHWAY TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KYD00306 | CAT0777EEKYD00306 | FZS01903 | FML2110DSI1298 | VESSEL: BAHARI JAZAN | COD 2022 168417 | NU155448 | NU12028 / NU11011 | ND60162 | 03.05.2022 | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | 01.04.2022 | 05.04.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 27.10.2022 | 08.06.2022 | 29-06-2022 | 30-06-2022 | 22-07-2022 | 22-07-2022 | 26.07.2022 | 29-07-2022 | 02-08-2022 | 03-08-2022 | 08-08-2022 | 11.08.2022 | 11.08.2022 | 15.08.2022 | 16.08.2022 | 17.08.2022 | 18.08.2022 | 19.08.2022 | [8 empty] | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | * BV WILL BE BOOKED FOR TOMMROW THE 05/04/2022.AWAITING TRUCK DETAILS AND DISPATCH DATE | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | PLANNING TO DISPATCH ON THE 19/04/2022 | * BV INSPECTION BOOKED FOR TODAY - PLANNING TO DISPATCH ON THE 19/04/2022 | * PLANNING TO LOAD AND DISPATCH ON WEDNESDAY THE 20/04/2022 | * PLANNING TO LOAD AND DISPATCH ON THURSDAY THE 21/04/2022 | * PLANNING TO LAOD NEXT WEEK WEDNESDAY THE 27/04/2022 | Truck enroute to Durban for loading. To be loaded on 13/05 due to public holidays and road closures in RSA, departure depended on the issuance of permits by the permit office | * VEHICLE TO BE LOADED ON 13.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 13.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | * VEHICLE TO BE LOADED ON 13.05.2022 DUE TO PUBLIC HOLIDAYS AND ROAD CLOSURES IN RSA, DEPARTURE DEPENDANT ON THE ISSUANCE OF PERMITS BY THE PERMIT OFFICES | LOADED - WAITING PERMITS AND ESCOURTS - RTI INFORMED US THAT THE ESCOURTS WILL NOT BE AVAILABLE UNITL THE 16 / 17 OF MAY | TRUCK TO DISPATCH TOMMROW THE 17/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 19/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 19/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 24/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 24/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 24/05/2022 | TRUCK TO LOAD AND DISPATCH ON THE 25/05/2022 | * VEHICLE TO LOAD TODAY - 25 MAY 2022 | * VEHICLE TO LOAD MONDAY 31 MAY 2022 | VEHICLE ON BREAKDOWN AND WILL LOAD WEDNESDAY 08-06-2022 | TRUCK TO LOAD AND DISPATCH TODAY THE 06/06/2022 | TRUCK TO LOAD TODAY THE 07/06/2022 | TRUCK TO LOAD AND DISPATCH TODAY THE 08/06/2022 | TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT CAMPERSDOWN AWAITING ESCORTS | * VEHICLE CURRENTLY AT CAMPERSDOWN AWAITING ESCORTS | * VEHICLE CURRENTLY AT PIETERMARITZBURG AWAITING ESCORTS | * VEHICLE CURRENTLY AT PIETERMARITZBURG AWAITING ESCORTS | * VEHICLE CURRENLTY AT DALTON ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT GREYTOWN WAITING ESCORTS | * VEHICLE CURRENLTY AT NEWCASTLE WAITING FOR RTI ESCORTS | * VEHICLE CURRENLTY AT VOLKSRUST WAITING FOR RTI ESCORTS | * VEHICLE CURRENLTY AT VOLKSRUST WAITING FOR RTI ESCORTS | * VEHICLE CURRENTLY AT VOLKSRUST RTI TO ESCOURT THE UNIT THIS MORNING | * TRUCK AT ERMELO AWAIITNG RTI | * TRUCK AT HENDRINA AWAITING RTI ESCOURTS | * TRUCK AT HENDRINA AWAITING RTI ESCOURTS - TO DISPATCH THIS MORNING | * VEHICLE CURRENTLY AT MIDDLEBURG AWAITING RTI ESCOURTS - TO DISPATCH THIS MORNING | * VEHICLE CURRENTLY AT MIDDLEBURG AWAITING RTI ESCOURTS - TO DISPATCH THIS MORNING | * VEHICLE CURRENTLY DISPATCHING VOLKSRUST | * VEHICLE CURRENTLY AT MIDDELBURG WAITING RTI ESCORT | * VEHICLE CURRENTLY AT STOFFBERG AWAIITNG RTI TO ESCOURT THEM THIS AFTERNOON | * VEHICLE CURRENTLY AT STOFFBERG AWAITING RTI TO ESCOURT THEM TO ZEBEDIELA | * VEHICLE CURRENTLY AT ZEBEDIELA AWAITING RTI | * VEHICLE CURRENTLY AT POLOKWANE EN-ROUTE TO MUSINA | * VEHICLE CURRENTLY AT DENDRON AWAITING RTI | * VEHICLE CURRENTLY AT VENETIA ENROUTE BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT VENETIA AWAITING ESCORT | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE UNDER CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE UNDER CLEARANCE | MAKUTI ENROUTE CHIRUNDU | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE | TRUCK IS CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING RELEASE | TRUCK IS AT KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE AT CHIRUNDU ZAM SIDE TO DISPATCH FOR LUSAKA THIS MORNING | * VEHICLE AT KAFUE ENROUTE LUSAKA | * VEHICLE DISPATCHING LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY | * VEHICLE CURRENTLY DISPATCHED KANYAKA ENROUTE SITE | OFFLOADED 24/08/2022
BA2122 | 1 X NEW CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201252 | CAT00140CW9201252 | E7A54361 | FML 2207DSI1654 | VESSEL: MORNING CHAMPION ETA: 27-07-2022 | COD 2022 252852 | JF92ZTGP | BX45RWGP | ND60526 | 06-08-2022 | OFFLOADED 26-08-2022 | 25-07-2022 | 03.08.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 03-08-2022 - WAITING CONFIRMATION FROM BV | 27.07.2022 | 15.08.2022 | 16.08.2022 | 17.08.2022 | 18.08.2022 | 18.08.2022 | 19.08.2022 | 20-08-2022 | 20-08-2022 | 21-08-2022 | 21-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 24-08-2022 | 24-08-2022 | 26-08-2022 | 26-08-2022 | 26-08-2022 | 26-08-2022 | OFFLOADED 26-08-2022 | [52 empty] | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 16/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 16/08/2022 | * VEHICLE LOADING TODAY | * VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENLTY AT POLOKWANE ENROUTE MUSINA | * VEHICLE CURRENLTY AT LOUIS TRICHARDT ENROUTE MUSINA | * VEHICLE CURRENLTY AT LOUIS TRICHARDT ENROUTE MUSINA | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENLTY AT KASUMBULESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBULESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY | * VEHICLE CURRENLTY DISPATCHING WHISKEY | OFFLOADED 26-08-2022
BA2186 | 1 X NEW CAT CS78B VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M7800543 | CATCS78BKM7800543 | E7A51596 | 2206DSI1602 | VESSEL: BANKOK HIGHWAY ETA: 25-06-2022 | COD 2022 216207 | BF60CSGP | DH54LYGP | ND59568 | 20-07-2022 | OFFLOADED 26-08-2022 | 07.06.2022 | 04.07.2022 | BV DONE AS SOON AS THE UNIT WAS RECEIVED ON SITE | 29/06/2022 | 20/07/2022 | 22/07/2022 | 29.07.2022 | 04-08-2022 | 04-08-2022 | 04-08-2022 | 07-08-2022 | 08-08-2022 | 09-08-2022 | 10-08-2022 | 13.08.2022 | 13.08.2022 | 14.08.2022 | 14.08.2022 | 15.08.2022 | 15-08-2022 | 15-08-2022 | 15-08-2022 | MOKAMBO 15-08-2022 | MOKAMBO 20-08-2022 | 20-08-2022 | 24-08-2022 | 24-08-2022 | 24-08-2022 | 26-08-2022 | OFFLOADED 26-08-2022 | [46 empty] | * AWAITING VESSEL CRYSTAL RAY ARRIVAL - ETA 25.06.2022 / TO CO-LOAD WITH BA2083 | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2083 - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2186 - ESTIMATE LOADING DATE 19.07.2022 | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2186 - ESTIMATE LOADING DATE 19.07.2022 | * TRUCK TO LOAD TODAY AND DISPATCH TOMMROW THE 20/07/2022 | * TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT MARIAN HILL EN-ROUTE TO BEITBRIDGE | * TRUCK AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | * TRUCK AT JOHANNESBURG ATTENDING TO MINOR BREAKDOWN - TO DISPTACH FOR BEITBRIDGE TODAY | * VEHICLE CURRENTLY AT JOHANNESBURG AWAIITNG PERMIT TO PROCEED | * VEHICLE CURRENTLY AT JOHANNESBURG AWAIITNG PERMIT TO PROCEED | * VEHICLE CURRENTLY AT JOHANNESBURG AWAIITNG PERMIT TO PROCEED | BEIT BRIDGE RSA SIDE CLEARING | HARARE EN-ROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZAM SIDE | TRUCK AT CHIRUNDU ZAM SIDE | TRUCK AT CHIRUNDU ZAM SIDE | * VEHICLE AT MOKAMBO ENROUTE LUBUMBASHI | * VEHICLE AT MOKAMBO UNDER CLEARANCE | * VEHICLE AT MOKAMBO UNDER CLEARANCE | * VEHICLE AT MOKAMBO UNDER CLEARANCE | * VEHICLE AT MOKAMBO UNDER CLEARANCE | * VEHICLE AT WHISKEY CUSTOMS | * VEHICLE AT WHISKEY CUSTOMS | * VEHICLE AT WHISKEY CUSTOMS | LUBUMBASHI WAITING TO OFFLOAD | LUBUMBASHI WAITING TO OFFLOAD - DAY 2 | OFFLOADED 26-08-2022
BA2147 | 1 XNEW CAT M317D2 WHEEL EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CA600858 | CATM317DTCA600858 | 2W233348 | 2206DSI1619 | VESSEL: MORNING COMPOSER ETA: 30-06-2022 | COD 2022 214304 | KG17GNGP | KHM039MP | ND59590 | 15-07-2022 | OFFLOADED 29-08-2022 | 07.06.2022 | 19.07.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 07.07.2022 | 12-08-2022 | 15.08.2022 | 17.08.2022 | 17.08.2022 | 17.08.2022 | 18.08.2022 | 19-08-2022 | 19-08-2022 | 20-08-2022 | 20-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 22-08-2022 | 23-08-2022 | 23-08-2022 | 23-08-2022 | 23-08-2022 | 23-08-2022 | 27-08-2022 | 27-08-2022 | 27-08-2022 | 28-08-2022 | 28-08-2022 | 29-08-2022 | [47 empty] | * AWAITING VESSEL GLOVIS SKY ARRIVAL - CURRENT ETA 07.07.2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19-07 - LOADING DATE TO BE CONFIRMED | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 25-07-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 27-07-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 27-07-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 27-07-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 27-07-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 27-07-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 03-08-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 03-08-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 03-08-2022 | BV INSPECTION BOOKED FOR WEDNESDAY 19.07.2022 - ESTIMATED LOADING DATE 03-08-2022 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 08-08-2022 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 10-08-2022 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 12-08-2022 | TRUCK TO LOAD TODAY AND DISPATCH TOMMROW THE 12/08/2022 | TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEITBRIDGE | TRUCK AT HARRYSMITH L EN-ROUTE TO BEITBRIDGE | TRUCK AT MARIANHILL EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT PRETORIA ENROUTE MUSINA | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBULESA | * VEHICLE CURRENTLY AT KASUMBULESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE | * VEHICLE CURRENTLY AT KASUMBULESA DRC SIDE | ON SITE WIATING TO OFFLOAD | OFFLOADED 29-08-2022 | OFFLOADED 29-08-2022 | OFFLOADED 29-08-2022 | OFFLOADED 29-08-2022 | OFFLOADED 29-08-2022
BA2063 | 1 X NEW CAT 345GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30150 | CAT00345CKEF30150 | NTB10266 | FML2206DSI1610 | VESSEL: BANKOK HIGHWAY ETA: 25-06-2022 | COD 2022 224266 | JP79VKGP | CS71TPGP / CS88PXGP | ND59566 | 28-06-2022 | OFFLOADED 29-08-2022 | 17.06.2022 | 28.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.06.2022 | 11.08.2022 | 13.08.2022 | 14.08.2022 | 15.08.2022 | 15.08.2022 | 16.08.2022 | 19-08-2022 | 19-08-2022 | 20-08-2022 | 20-08-2022 | 20-08-2022 | 20-08-2022 | 23-08-2022 | 23-08-2022 | 23-08-2022 | 23-08-2022 | 24-08-2022 | 24-08-2022 | 24-08-2022 | 27-08-2022 | 27-08-2022 | 28-08-2022 | 28-08-2022 | 28-08-2022 | 29-08-2022 | [47 empty] | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - PLANNING TO LOAD 18.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - PLANNING TO LOAD 21.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 08.08.2022 TO 12.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 12.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 12.08.2022 | TRUCK DISPATCHING DURBAN TODAY | TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEITBRIDGE | TRUCK AT PRETORIA EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENLTY AT CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENLTY AT KABWE ENROUTE KASUMBULESA | * VEHICLE CURRENLTY AT KASUMBULESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBULESA DRC SIDE | ON SITE WAITING TO OFFLOAD | OFFLOADED 29-08-2022 | OFFLOADED 29-08-2022 | OFFLOADED 29-08-2022 | OFFLOADED 29-08-2022 | OFFLOADED 29-08-2022
BA2196 | 1 X USED CAT745 ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F601191 | CAT0075H3F601191 | TWX04527 | FML2206DSI1603 | VESSEL: SERENITY ACE Voy. 0106A ETA: 10-06-2022 | COD 2022 223374 | ND754967 | ND654346 | ND60671 | 28-08-2022 | * OFFLOADED 01.09.2022 | 16-06-2022 | 28.06.2022 | BV NUMBER RECEIVED - AWAITING AMENDED LICENSE TO SHO PORT OF ENTRY SAKANIA BORDER POST | 10-06-2022 | 11-08-2022 | 13.08.2022 | 14.08.2022 | 15.08.2022 | 15.08.2022 | 16.08.2022 | 18.08.2022 | 19-08-2022 | 19-08-2022 | 19-08-2022 | 20-08-2022 | 20-08-2022 | 24-08-2022 | 24-08-2022 | 24-08-2022 | 24-08-2022 | 26-08-2022 | 26-08-2022 | 27-08-2022 | 01-09-2022 | 01-09-2022 | 01-09-2022 | 01-09-2022 | 01-09-2022 | 01-09-2022 | [39 empty] | AWAITNG AMENDED BV LICENSE TO SHOW PORT OF ENTRY SAKANIA BORDER POST | AWAITING BV INSPECTION, LOADING DATE TO BE ADVISED | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | * BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED - ESTIMATED DATE OF LOADING 15.07.2022 | * BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED - ESTIMATED DATE OF LOADING 15.07.2022 | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 21/22 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 23 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 23 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 23 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 23 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 28 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 29 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 03 AUG 2022 | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 03 AUG 2022 | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 03 AUG 2022 | VEHICLE CURRENTLY IN DURBAN. UNDERGOING MAINTENANCE CHECK BEFORE LOADING | TRUCK LOADED AND WILL DISPATCH ON THE 10/08/2022 | LOADING TODAY AND TRUCK TO DISPATCH TOMMROW THE 11/08/2022 | TRUCK AT CATO RIDGE EN-ROUTE TO BEITBRIDGE | TRUCK AT VOLKSRUST RIDGE EN-ROUTE TO BEITBRIDGE | * VEHICLE AT MIDDLEBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE WAITING RELEASE | * VEHICLE CURRENTLY DISPATCHING CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENTLY NDOLA ENROUTE KASUMBULESA | * VEHICLE CURRENTLY KASUMBULESA ZAMBIAN SIDE | KASUMBULESA DRC SIDE | KASUMBULESA DRC SIDE | WHISKEY AWAITING RELEASE | LUBUMBASHI AWAITING TO OFFLOAD | LUBUMBASHI AWAITING TO OFFLOAD | * OFFLOADED 01.09.2022 | * OFFLOADED 01.09.2022
BA2195 | 1 X USED CAT745 ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F601190 | CAT00745L3F601190 | TXW04557 | FML2206DSI1603 | VESSEL: MORNING CHAMPION ETA: 27-07-2022 | COD 2022 223374 | ND730794 | ND443606 | ND59557 | 28-08-2022 | * OFFLOADED 05.09.2022 | 16-06-2022 | 28.06.2022 | BV NUMBER RECEIVED - AWAITING AMENDED LICENSE TO SHO PORT OF ENTRY SAKANIA BORDER POST | 10-06-2022 | 16.08.2022 | 18.08.2022 | 18.08.2022 | 18.08.2022 | 18.08.2022 | 19.08.2022 | 22-08-2022 | 23-08-2022 | 24-08-2022 | 26-08-2022 | 26-08-2022 | 26-08-2022 | 28-08-2022 | 28-08-2022 | 28-08-2022 | 29-08-2022 | 29-08-2022 | 29-08-2022 | 29-08-2022 | 01-09-2022 | 01-09-2022 | 04.09.2022 | 05.09.2022 | 05.09.2022 | 05.09.2022 | [39 empty] | AWAITNG AMENDED BV LICENSE TO SHOW PORT OF ENTRY SAKANIA BORDER POST | AWAITING BV INSPECTION, LOADING DATE TO BE ADVISED | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY AWAITING LOADING DATE | * BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED - ESTIMATED DATE OF LOADING 15.07.2022 | * BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED - ESTIMATED DATE OF LOADING 15.07.2022 | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 21/22 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 23 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 23 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 23 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 23 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 25 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 25 JULY | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 01 AUG TO 05 AUG 2022 | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 01 AUG TO 05 AUG 2022 | * BV INSPECTION COMPLETE - WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 01 AUG TO 05 AUG 2022 | VEHICLE CURRENTLY IN DURBAN. UNDERGOING MAINTENANCE CHECK BEFORE LOADING | TRUCK LOADED AND WILL DISPATCH ON THE 10/08/2022 | TRUCK LOADED AND WILL DISPATCH ON THE 12/08/2022 | TRUCK LOADED AND WILL DISPATCH ON THE 15/08/2022 | TRUCK LOADED AND WILL DISPATCH ON THE 15/08/2022 | * VEHICLE LOADED - PLANNING TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT NEWCASTLE ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MIDDLEBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT BEITBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT HARARE | * VEHICLE CURRENTLY AT CHINOYI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU CUSTOMS | CHILIBOMBWE ENROUTE KASUMBULESA | KASUMBULESA ZAM SIDE | KASUMBULESA ZAM SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 05.09.2022
BA2048 | 1 X CAT C32 EPG PKG GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TZJ00165 / JP500167 / G1K00554 | N/A | N/A | FML2205DSI1577 | VESSEL: MSC RAYSHMI ETA: 20-07-2022 | COD 2022 195164 | AAR7040 | ACB9821T | ND60541 | 29-07-2022 | * OFFLOADED 06.09.2022 | 10.05.2022 | 28.07.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 08/06/2022 | 01-08-2022 | 02-08-2022 | 03-08-2022 | GRB 03-08-2022 | GRB 04-08-2022 | MARTINSDRIFT 04-08-2022 | MARTINSDRIFT 05-08-2022 | 07-08-2022 | 07-08-2022 | 08-08-2022 | 09-08-2022 | 09-08-2022 | 09-08-2022 | 10-08-2022 | 11.08.2022 | 11.08.2022 | 12.08.2022 | 12.08.2022 | 13.08.2022 | 25-08-2022 | 25-08-2022 | 01-09-2022 | 02-09-2022 | 05.09.2022 | 06.09.2022 | [18 empty] | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 28/05/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 01/06/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 01/06/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 01/06/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 01/06/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 01/06/2022 | WAITING VESSEL ARRIVAL: VESSEL - MSC ROMANE - ETA: 04/06/2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - LOADING DATE TBC | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - LOADING DATE TBC | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - LOADING DATE TBC | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - LOADING DATE TBC | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - LOADING DATE TBC | BV INSPECTION COMPLETE - WAITING VEHICLE TO RETURN FROM DRC - LOADING DATE TBC | BV INSPECTION COMPLETE - WAITING GENSET TO ARRIVE AT DURBAN ETA 12.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING GENSET TO ARRIVE AT DURBAN ETA 12.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING GENSET TO ARRIVE AT DURBAN ETA 12.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING GENSET TO ARRIVE AT DURBAN ETA 12.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING GENSET TO ARRIVE AT DURBAN ETA 12.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING GENSET TO ARRIVE AT DURBAN ETA 12.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING GENSET TO ARRIVE AT DURBAN ETA 12.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING GENSET TO ARRIVE AT DURBAN ETA 12.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING VESSEL MSC RAYSHMI TO ARRIVE DURBAN ETA 15.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING VESSEL MSC RAYSHMI TO ARRIVE DURBAN ETA 15.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING VESSEL MSC RAYSHMI TO ARRIVE DURBAN ETA 18.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING VESSEL MSC RAYSHMI TO ARRIVE DURBAN ETA 20.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING VESSEL MSC RAYSHMI TO ARRIVE DURBAN ETA 27.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING VESSEL MSC RAYSHMI TO ARRIVE DURBAN ETA 27.07.2022 IN ORDER TO TRANSPORT TO SITE | BV INSPECTION COMPLETE - WAITING VESSEL MSC RAYSHMI TO ARRIVE DURBAN ETA 27.07.2022 IN ORDER TO TRANSPORT TO SITE | * TO LOAD UNIT FROM PORT AS SOON AS BOOKING IS AVAILABLE | * TO LOAD UNIT FROM PORT TODAY | * UNIT AT OUR BONDED FACILITY. BV INSPECTION TO BE DONE & LOADING 29.07.2022 TO DISPATCH DURBAN | * UNIT AT OUR BONDED FACILITY. BV INSPECTION TO BE DONE TODAY & LOADING 29.07.2022 TO DISPATCH DURBAN | DISPATCHING MARTINSDRIFT BORDER | KAZANGULA ZAM SIDE | TRUCK AT LUSAKA EN-ROUTE TO KASUMBALESA | TRUCK AT NDOLA EN-ROUTE TO KASUMBALESA | TRUCK AT CHINGOLA EN-ROUTE TO KASUMBALESA | * VEHICLE AT KASUMBALESA ZAM SIDE AWAIITNG CLEARANCE | * VEHICLE AT KASUMBALESA ZAM SIDE IN QUEUE TO CROSS | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALESA DRC SIDE AWAITING RELEASE | * VEHICLE AT KASUMBALESA DRC SIDE STILL AWAITING RELEASE | * VEHICLE AT KASUMBALESA DRC SIDE STILL AWAITING RELEASE | * VEHICLE AT WHISKEY | * VEHICLE AT WHISKEY WAITING RELEASE | * VEHICLE AT WHISKEY WAITING RELEASE - DAY 5 | * VEHICLE AT WHISKEY WAITING RELEASE - DAY 6 | TRUCK EN-ROUTE TO SITE | TRUCK AT KANYAKA CLEARING | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 06.09.2022
BA1889 | 1 X NEW CAT 336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | E7A43831 | CAT00336CJFW20939 | JFW20939 | FML2201DSI1400 | VESSEL: GRAND PAVO Voy. 103 ETA: 30-01-2022 | COD 2022 209460 | ND706468 | ND256330 | ND62913 | 28-06-2022 | OFFLOADED 08/09/2022 | 27-05-2022 | 01.06.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 01-06-2022 | 02.02.2022 | 16.08.2022 | 17.08.2022 | 19.08.2022 | 21.08.2022 | 21.08.2022 | 22.08.2022 | 24.08.2022 | 26.08.2022 | 28.08.2022 | 29.08.2022 | 31.08.2022 | 31.08.2022 | 31.08.2022 | 01.09.2022 | 01.09.2022 | 01.09.2022 | 02.09.2022 | 02.09.2022 | 02.09.2022 | 04.09.2022 | 05.09.2022 | 07.09.2022 | 08.09.2022 | 08.09.2022 | 08/09/2022 | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | JOHANNESBURG | CHIRUNDU ZAM SIDE | KAROI EN-ROUTE KASUMBALESA | CHIRUNDU EN-ROUTE KASUMBALESA | CHIRUNDU ZIM SIDE AWAIITNG RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | KAFUE EN-ROUTE TO KASUMBALESA | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALES DRC, IN QUEUE TO CROSS OVER TO WHISKEY | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 12-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 15-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 25.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 25.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 25.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 25.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 28.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 28.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 08.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 09.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | TRUCK TO LOAD AND DISPATCH ON THE 11/08/2022 | TRUCK IN WORKSHOP, PLANNING TO LOAD AND DISPATCH THE 15/08/2022 | TRUCK IN WORKSHOP, PLANNING TO LOAD AND DISPATCH THE 15/08/2022 | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE CURRENTLY AT CATO RIDGE ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT NEWCASTLE ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT NEWCASTLE ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT MIDDELBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT MIDDELBURG WAITING PERMITS | * VEHICLE CURRENTLY AT BEIT BRIDGE RSA SIDE | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT MVUMA ENROUTE HARARE | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KABWE EN-ROUTE TO KASUMBALESA | TRUCK AT KASUMBALESA DRC | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | * VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 08/09/2022
BA1887 | 1 X NEW CAT 336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | E7A43831 | CAT00336CJFW20939 | JFW20939 | FML2201DSI1400 | VESSEL: GRAND PAVO Voy. 103 ETA: 30-01-2022 | COD 2022 209460 | ND570587 | ND702944 | ND62911 | 28-06-2022 | OFFLOADED | 27-05-2022 | 01.06.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 01-06-2022 | 12.07.2022 | 23-08-2022 | MIDDELBURG 24-08-2022 | MIDDELBURG 25-08-2022 | 26-08-2022 | 26-08-2022 | 31-08-2022 | 07.09.2022 | 09-09-2022 | 10-09-2022 | 11-09-2022 | 12-09-2022 | 12-09-2022 | 13.09.2022 | 13.09.2022 | 13.09.2022 | 14.09.2022 | 15-09-2022 | 15-09-2022 | 15-09-2022 | 18-09-2022 | 19-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO ARRANGE FOR BV INSPECTION | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 20/04/2022 | * BV RECEIVED AWAITING INSPECTION ON THE 21/04/2022 | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | * DISPATCH DATE TO BE ADVISED - WAITING RETURN VEHICLE FROM THE DRC | JOHANNESBURG | CHIRUNDU ZAM SIDE | KAROI EN-ROUTE KASUMBALESA | CHIRUNDU EN-ROUTE KASUMBALESA | CHIRUNDU ZIM SIDE AWAIITNG RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | KAFUE EN-ROUTE TO KASUMBALESA | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHCILE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE AT KASUMBALES DRC, IN QUEUE TO CROSS OVER TO WHISKEY | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRM | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 08-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 08-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 08-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 08-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 12-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 14-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 18.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 29.07.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 03.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 10.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 10.08.2022 AWAITING VEHCILE TO RETURN FROM DRC | TRUCK IN WORKSHOP, PLANNING TO LOAD AND DISPATCH TOMMROW THE 11/08/2022 | TRUCK IN WORKSHOP, PLANNING TO LOAD AND DISPATCH THE 15/08/2022 | TRUCK IN WORKSHOP, PLANNING TO LOAD AND DISPATCH THE 15/08/2022 | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT - PLANNING TO DISPATCH THIS AFTERNOON | * VEHICLE CURRENLTY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT ESTCOURT ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT ESTCOURT ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT WARDEN ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT VILLIERS ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT DISPATCHING VILLIERS | * VEHICLE CURRENLTY AT VILLIERS ON BREAKDOWN | * VEHICLE CURRENLTY AT VILLIERS ON BREAKDOWN | DISPATCHING VILLIERS TODAY | NEW CASTLE ENROUTE MUSINA | MIDDLEBURG EN-ROUTE TO BEITBRIDGE | MIDDLEBURG EN-ROUTE TO BEITBRIDGE | TRUCK AT BEITBRIDGE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE AWAITING CLEARANCE | * VEHICLE IN QUEUE TO CROSS TO BEITBRIDGE ZIM SIDE | * VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | * VEHICLE CURRENLTY AT MVUMA ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | * VEHCILE CURRENTLY AT KABWE ENROUTE CHINGOLA | * VEHCILE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHCILE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHCILE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHCILE CURRENTLY AT WHISKEY AWAITING RELEASE DAY 2 | LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA1945 | 1 X NEW CAT DE275E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LX903870 | CAT000C9KLX903870 | N/A | FML2208DSI1679 | VESSEL: SEAMAX NORWALK Voy. 0SSCOE1MA ETA: 28-08-2022 | COD 2022 251400 | BCC1016ZM | BCC1015ZM / BCC1014ZM | 2208DSI1679 | 14.09.2022 | OFFLOADED | 25-07-2022 | 05.09.2022 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 28.08.2022 | 14-09-2022 | 14-09-2022 | 14-09-2022 | GROBLESBRIDGE ARR 14-09-2022 | 19-09-2022 | GROBLERS 19-09-2022 | GROBLERS 19-09-2022 | FRANCIST TOWN 19-09-2022 | FRANCIST TOWN 19-09-2022 | 19-09-2022 | 19-09-2022 | 19-09-2022 | 19-09-2022 | 20-09-2022 | 20-09-2022 | 22-09-2022 | 22-09-2022 | 24-09-2022 | 24-09-2022 | 29-09-2022 | 29-09-2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 08.10.2022 | [53 empty] | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | THE CARGO IS AT OUR FACILITY AWAIITNG BV INSPECTION TODAY, AWAITING LOADING DATE | THE CARGO IS AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | LOADING TODAY | VEHICLE WAS DELAIDED - LOADING TOMORROW 14-09-2022 | VEHICLE WAS DELAIDED - LOADING TODAY 14-09-2022 | GROBLERSBRIDGE BORDER CLEARIING | GROBLERSBRIDGE BORDER CLEARIING / RELEASE | LIVINGSTONE EN-ROUTE TO KASUMBALESA | LIVINGSTONE EN-ROUTE TO KASUMBALESA | LIVINGSTONE AWAITING RELEASE IN ORDER TO PROCEED TO KASUMBALESA | CHICHILO EN-ROUTE TO KASUMBALESA | CHIBOMBO EN-ROUTE TO KASUMBALESA | KASUMBALESA CLEARING | KASUMBALESA WAITING CLEARANCE & RELEASE | KASUMBALESA WAITING CLEARANCE & RELEASE | KASUMBALESA WAITING CLEARANCE & RELEASE - DAY 5 | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | TO DISPATCH WHISKEY THIS MORNING ENOUTE LUBUMBASHI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 PLEASE ASISST | ON SITE WAITING TO OFFLOAD - DAY 3 / WILL OFFLOAD TODAY | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA1946 | 1 X NEW CAT DE275E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LX903867 | CAT000C9KLX903867 | N/A | FML2208DSI1679 | VESSEL: SEAMAX NORWALK Voy. 0SSCOE1MA ETA: 28-08-2022 | COD 2022 251400 | BCC1016ZM | BCC1015ZM / BCC1014ZM | 2208DSI1679 | 14.09.2022 | OFFLOADED | 25-07-2022 | 05.09.2022 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 28.08.2022 | 14-09-2022 | 14-09-2022 | 14-09-2022 | GROBLESBRIDGE ARR 14-09-2022 | 19-09-2022 | GROBLERS 19-09-2022 | GROBLERS 19-09-2022 | FRANCIST TOWN 19-09-2022 | FRANCIST TOWN 19-09-2022 | 19-09-2022 | 19-09-2022 | 19-09-2022 | 19-09-2022 | 20-09-2022 | 20-09-2022 | 22-09-2022 | 22-09-2022 | 24-09-2022 | 24-09-2022 | 29-09-2022 | 29-09-2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 08.10.2022 | [53 empty] | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | THE CARGO IS AT OUR FACILITY AWAIITNG BV INSPECTION TODAY, AWAITING LOADING DATE | THE CARGO IS AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | LOADING TODAY | VEHICLE WAS DELAIDED - LOADING TOMORROW 14-09-2022 | VEHICLE WAS DELAIDED - LOADING TODAY 14-09-2022 | GROBLERSBRIDGE BORDER CLEARIING | GROBLERSBRIDGE BORDER CLEARIING / RELEASE | LIVINGSTONE EN-ROUTE TO KASUMBALESA | LIVINGSTONE EN-ROUTE TO KASUMBALESA | LIVINGSTONE AWAITING RELEASE IN ORDER TO PROCEED TO KASUMBALESA | CHICHILO EN-ROUTE TO KASUMBALESA | CHIBOMBO EN-ROUTE TO KASUMBALESA | KASUMBALESA CLEARING | KASUMBALESA WAITING CLEARANCE & RELEASE | KASUMBALESA WAITING CLEARANCE & RELEASE | KASUMBALESA WAITING CLEARANCE & RELEASE - DAY 5 | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | TO DISPATCH WHISKEY THIS MORNING ENOUTE LUBUMBASHI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 PLEASE ASISST | ON SITE WAITING TO OFFLOAD - DAY 3 / WILL OFFLOAD TODAY | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA1947 | 1 X NEW CAT DE250E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LX903868 | CAT000C9JLX903868 | N/A | FML2208DSI1680 | VESSEL: SEAMAX NORWALK Voy. 0SSCOE1MA ETA: 28-08-2022 | COD 2022 251400 | BCC1016ZM | BCC1015ZM / BCC1014ZM | 2208DSI1679 | 14.09.2022 | OFFLOADED | 25-07-2022 | 05.09.2022 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 28.08.2022 | 14-09-2022 | 14-09-2022 | 14-09-2022 | GROBLESBRIDGE ARR 14-09-2022 | 19-09-2022 | GROBLERS 19-09-2022 | GROBLERS 19-09-2022 | FRANCIST TOWN 19-09-2022 | FRANCIST TOWN 19-09-2022 | 19-09-2022 | 19-09-2022 | 19-09-2022 | 19-09-2022 | 20-09-2022 | 20-09-2022 | 22-09-2022 | 22-09-2022 | 24-09-2022 | 24-09-2022 | 29-09-2022 | 29-09-2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 08.10.2022 | [53 empty] | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 27.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED - CURRENTLY DISCHARGING CONTAINERS | THE CARGO IS AT OUR FACILITY AWAIITNG BV INSPECTION TODAY, AWAITING LOADING DATE | THE CARGO IS AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | THE CARGO IS AT OUR FACILITY - LOADING & DISPATCHING DURBAN MONDAY 12 AUG 2022 | LOADING TODAY | VEHICLE WAS DELAIDED - LOADING TOMORROW 14-09-2022 | VEHICLE WAS DELAIDED - LOADING TODAY 14-09-2022 | GROBLERSBRIDGE BORDER CLEARIING | GROBLERSBRIDGE BORDER CLEARIING / RELEASE | LIVINGSTONE EN-ROUTE TO KASUMBALESA | LIVINGSTONE EN-ROUTE TO KASUMBALESA | LIVINGSTONE AWAITING RELEASE IN ORDER TO PROCEED TO KASUMBALESA | CHICHILO EN-ROUTE TO KASUMBALESA | CHIBOMBO EN-ROUTE TO KASUMBALESA | KASUMBALESA CLEARING | KASUMBALESA WAITING CLEARANCE & RELEASE | KASUMBALESA WAITING CLEARANCE & RELEASE | KASUMBALESA WAITING CLEARANCE & RELEASE - DAY 5 | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | TO DISPATCH WHISKEY THIS MORNING ENOUTE LUBUMBASHI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 PLEASE ASISST | ON SITE WAITING TO OFFLOAD - DAY 3 / WILL OFFLOAD TODAY | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA1991 | 1 X NEW CAT DE330E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LX903871 | CAT000C9JLX903871 | N/A | FML2208DSI1681 | VESSEL: MAERSK STRALSUND Voy. 0SSCME1MA ETA: 20-08-2022 | COD 2022 254799 | BCD4305ZM | BCC7783ZM | 2208DSI1681 | 06.09.2022 | OFFLOADED 29-09-2022 | 27-07-2022 | 29-08-2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED AS SOON AS CARGO WAS AVAILABLE | 20.08.2022 | 06.09.2022 | 09-09-2022 | 09-09-2022 | GROBLESBRIDGE ARR 10-09-2022 | GROBLERSBRIDGE DSP 13-09-2022 | MARTINS DRIFT ARR 13-09-2022 | MARTINSDRIFT DSP 13-09-2022 | FRANCISTOWN 14-09-2022 | FRANCISTOWN 14-09-2022 | KAZUNGULA ARR 15-09-2022 | KITWE 19-09-2022 | KITWE 19-09-2022 | KITWE 19-09-2022 | 20-09-2022 | 20-09-2022 | 20-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 23-09-2022 | 23-09-2022 | 27-09-2022 | 27-09-2022 | [55 empty] | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED AND IS CURRENTLY WORKING | VESSEL ARRIVED AND IS CURRENTLY WORKING | VESSEL ARRIVED AND IS CURRENTLY WORKING | VESSEL STILLWORKING - WAITING COMPLETION OF DISCHARGE | VESSEL STILLWORKING - WAITING COMPLETION OF DISCHARGE | BV INSPECTION BOOKED FOR 29-08-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | * VEHICLE CURRENLTY AT MARIAN HILL ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT JOHANNESBURG | GROBLES BRIDGE BORDER - CLEARING | GROBLES BRIDGE BORDER - CLEARING | * VEHICLE CURRENLTY AT KAZUNGULA - AWAITING RELEASE | * VEHICLE CURRENLTY AT KAZUNGULA - AWAITING RELEASE | * VEHICLE CURRENLTY AT KAZUNGULA - AWAITING CLEARANCE / RELEASE | * VEHICLE CURRENLTY AT KITWE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT GARNETON EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA AWAITING CLEARANCE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE - DAY 4 | LUBUMBASHI WAITING TO OFFLOAD | LUBUMBASHI WAITING TO OFFLOAD - DAY 2 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022
BA1992 | 1 X NEW CAT DE330E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | LX903869 | CAT000C9CLX903869 | N/A | FML2208DSI1681 | VESSEL: MAERSK STRALSUND Voy. 0SSCME1MA ETA: 20-08-2022 | COD 2022 254799 | BCD4305ZM | BCC7783ZM | 2208DSI1681 | 06.09.2022 | OFFLOADED 29-09-2022 | 27-07-2022 | 29-08-2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED AS SOON AS CARGO WAS AVAILABLE | 20.08.2022 | 06.09.2022 | 09-09-2022 | 09-09-2022 | GROBLESBRIDGE ARR 10-09-2022 | GROBLERSBRIDGE DSP 13-09-2022 | MARTINS DRIFT ARR 13-09-2022 | MARTINSDRIFT DSP 13-09-2022 | FRANCISTOWN 14-09-2022 | FRANCISTOWN 14-09-2022 | KAZUNGULA ARR 15-09-2022 | KITWE 19-09-2022 | KITWE 19-09-2022 | KITWE 19-09-2022 | 20-09-2022 | 20-09-2022 | 20-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 23-09-2022 | 23-09-2022 | 27-09-2022 | 27-09-2022 | [55 empty] | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28/08/2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED AND IS CURRENTLY WORKING | VESSEL ARRIVED AND IS CURRENTLY WORKING | VESSEL ARRIVED AND IS CURRENTLY WORKING | VESSEL STILLWORKING - WAITING COMPLETION OF DISCHARGE | VESSEL STILLWORKING - WAITING COMPLETION OF DISCHARGE | BV INSPECTION BOOKED FOR 29-08-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 06-09-2022 | * VEHICLE CURRENLTY AT MARIAN HILL ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT JOHANNESBURG | GROBLES BRIDGE BORDER - CLEARING | GROBLES BRIDGE BORDER - CLEARING | * VEHICLE CURRENLTY AT KAZUNGULA - AWAITING RELEASE | * VEHICLE CURRENLTY AT KAZUNGULA - AWAITING RELEASE | * VEHICLE CURRENLTY AT KAZUNGULA - AWAITING CLEARANCE / RELEASE | * VEHICLE CURRENLTY AT KITWE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT GARNETON EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA AWAITING CLEARANCE DAY 2 | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE - DAY 4 | LUBUMBASHI WAITING TO OFFLOAD | LUBUMBASHI WAITING TO OFFLOAD - DAY 2 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022
BA1786 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F602055 | CAT00745P3F602055 | TXW06501 | FML2206DSI1641 | VESSEL: HOEGH SHANGHAI Voy. 101 ETA: 12-07-2022 | COD 2022 252236 | ND834401 | ND854241 | ND60501 | 12-08-2022 | OFFLOADED 12-09-2022 | 25.07.2022 | 26.07.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 12.07.2022 | 23-08-2022 | MIDDELBURG 24-08-2022 | MIDDELBURG 25-08-2022 | 26-08-2022 | 26-08-2022 | 26-08-2022 | 29-09-2022 | 31/08/2022 | 01-09-2022 | 02-09-2022 | 03.09.2022 | 04.09.2022 | 04.09.2022 | 04.09.2022 | 05.09.2022 | 05.09.2022 | 05.09.2022 | 05.09.2022 | 06.09.2022 | 07.09.2022 | 08.09.2022 | 10-09-2022 | 10-09-2022 | 10-09-2022 | 12-09-2022 | [47 empty] | * AWAIITNG VESSEL HOEGH SHANGHAI ARRIVAL - CURRENT ETA 12.07.2022 | * VESSEL DUE TO BERTH TODAY HOEGH SHANGHAI - CURRENT ETA 12.07.2022 | VEHICLE COLLECTED FROM PORT, WAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION - LOADING DATE TBC | VEHICLE COLLECTED FROM PORT, WAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION - LOADING DATE TBC | VEHICLE COLLECTED FROM PORT, WAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION - LOADING DATE TBC | VEHICLE COLLECTED FROM PORT, WAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION - LOADING DATE TBC | VEHICLE COLLECTED FROM PORT, WAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION - LOADING DATE TBC | VEHICLE COLLECTED FROM PORT, WAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION - LOADING DATE TBC | VEHICLE COLLECTED FROM PORT, WAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION - LOADING DATE TBC | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 01 AUG TO 05 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 01 AUG TO 05 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 01 AUG TO 05 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 18 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 18 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 18 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 18 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 18 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 22 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 22 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 22 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 22 AUG 2022 | * WAITING FOR VEHICLE TO RETURN FROM DRC - ESTIMATED DATE 22 AUG 2022 | DISPATCHING DURBAN TODAY | CATO RIDGE ENROUTE JOHANNESBURG | HENDRINA ENROUTE MUSINA | MIDDELBURG ENROUTE MUSINA | GROBLESDAL ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE EN-ROUTE TO CHIRUNDU | CHINOYI EN-ROUTE TO CHIRUNDU | TRUCK IS AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022
BA2083 | 1 X NEW CAT CS11GC VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801384 | CAT0CS11LRK801384 | MFX12351 | FML2206DSI1611 | VESSEL: MORNING COMPOSER ETA: 30-06-2022 | COD 2022 223320 | NU112272 | ND629383 | ND60549 | 15-07-2022 | OFFLOADED 12-09-2022 | 16.06.2022 | 04.07.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.06.2022 | 24-08-2022 | MIDDELBURG 26-08-2022 | MIDDELBURG 26-08-202 | 27-08-2022 | 28-08-2022 | 28-08-2022 | 29-08-2022 | 31-08-2022 | 01-09-2022 | 02-09-2022 | 03.09.2022 | 03.09.2022 | 04.09.2022 | 04.09.2022 | 04.09.2022 | 05.09.2022 | 05.09.2022 | 05.09.2022 | 06.09.2022 | 07.09.2022 | 08.09.2022 | 11-09-2022 | 11-09-2022 | 11-09-2022 | 12-09-2022 | [47 empty] | * BV INSPECTION COMPLETE - AWAITING VESSEL CRYSTAL RAY ARRIVAL (BA2186 CO-LOAD) - ETA 25.06.2022 | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2186 - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2186 - ESTIMATE LOADING DATE 19.07.2022 | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2186 - ESTIMATE LOADING DATE 19.07.2022 | * TRUCK TO LOAD TODAY AND DISPATCH TOMMROW THE 20/07/2022 | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | ESTIMATED LOADING DATE 11-08-2022 | ESTIMATED LOADING DATE 11-08-2022 | ESTIMATED LOADING DATE 15-08-2022 | ESTIMATED LOADING DATE 15-08-2022 | ESTIMATED LOADING DATE 15-08-2022 | ESTIMATED LOADING DATE 17-08-2022 | ESTIMATED LOADING DATE 19-08-2022 | ESTIMATED LOADING DATE 19-08-2022 | ESTIMATED LOADING DATE 19-08-2022 | ESTIMATED LOADING DATE 19-08-2022 | LOADING TODAY | DISPATCHING DURBAN TODAY | CAMPERDOWN ENROUTE JOHANNESBURG | HOWICK ENROUTE JOHANNESBURG | MIDDELBURG ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE EN-ROUTE TO CHIRUNDU | CHINOYI EN-ROUTE TO CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022
BA2132 | 1 X NEW CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M8D00331 | CAT000D8VM8D00331 | TXJ02243 | FML 2207DSI1674 | VESSEL: BRILLIANT ACE Voy. 0092A ETA: 03-08-2022 | COD 2022 261473 | JNP005MP | JRJ981MP | ND60542 | 09-08-2022 | * OFFLOADED 13.09.2022 | 05.08.2022 | 08.08.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 03-08-2022 | 31-08-2022 | 01-09-2022 | 01-09-2022 | 02-09-2022 | 02-09-2022 | 02-09-2022 | 03.09.2022 | 03.09.2022 | 04.09.2022 | 04.09.2022 | 04.09.2022 | 05.09.2022 | 05.09.2022 | 06.09.2022 | 06.09.2022 | 07.09.2022 | 07.09.2022 | 08.09.2022 | 08-09-2022 | 10-09-2022 | 10-09-2022 | 11-09-2022 | 12-09-2022 | 12-09-2022 | 13.09.2022 | [53 empty] | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAITING VESSEL ARRIVAL ON THE 27/07/2022 | AWAITING VESSEL ARRIVAL ON THE 27/07/2022 | AWAITING VESSEL ARRIVAL ON THE 27/07/2022 | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | UNIT TO BE COLLECTED FROM PORT - WAITING BV NUMBER | UNIT TO BE COLLECTED FROM PORT - WAITING BV NUMBER | UNIT TO BE COLLECTED FROM PORT - WAITING BV NUMBER | UNIT TO BE COLLECTED FROM PORT - WAITING BV NUMBER | UNIT TO BE COLLECTED FROM PORT - WAITING BV NUMBER | UNIT TO BE COLLECTED FROM PORT - WAITING BV NUMBER | UNIT IN BONDED FACILITY - LOADING DATE TO BE CONFIRMED | UNIT IN BONDED FACILITY - LOADING DATE TO BE CONFIRMED | UNIT IN BONDED FACILITY - LOADING DATE TO BE CONFIRMED | UNIT IN BONDED FACILITY - LOADING DATE TO BE CONFIRMED | UNIT IN BONDED FACILITY - LOADING DATE TO BE CONFIRMED | UNIT IN BONDED FACILITY - LOADING DATE TO BE CONFIRMED | UNIT IN BONDED FACILITY - ESTIMATED LOADING DATE 05/09 - 10-09 | UNIT IN BONDED FACILITY - ESTIMATED LOADING DATE TUESDAY 30-08-2022 | UNIT IN BONDED FACILITY - ESTIMATED LOADING DATE TUESDAY 30-08-2022 | UNIT IN BONDED FACILITY - ESTIMATED LOADING DATE TUESDAY 30-08-2022 | LOADING TODAY | TRUCK AT VOLKSRUST EN-ROUTE TO BEITBRIDGE | TRUCK AT BELA BELA EN-ROUTE TO BEITBRIDGE | TRUCK AT BEITBRIDGE RSA SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KAPIRI MPOSHE ENROUTE KITWE | * VEHICLE CURRENLTY AT CHILIBOMBWE ENROUTE KASUMBLAESA | * VEHICLE CURRENLTY AT KASUMBLAESA ZAM SIDE | ENROUTE LUBUMBASHI | ON SITE WAITING TO OFFLAOD | * OFFLOADED 13.09.2022
BA2083 | 1 X NEW CAT CS11GC VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801384 | CAT0CS11LRK801384 | MFX12351 | FML2206DSI1611 | VESSEL: MORNING COMPOSER ETA: 30-06-2022 | COD 2022 223320 | NU112272 | ND629383 | ND60549 | 15-07-2022 | OFFLOADED 12-09-2022 | 16.06.2022 | 04.07.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.06.2022 | 24-08-2022 | MIDDELBURG 26-08-2022 | MIDDELBURG 26-08-202 | 27-08-2022 | 28-08-2022 | 28-08-2022 | 29-08-2022 | 31-08-2022 | 01-09-2022 | 02-09-2022 | 03.09.2022 | 03.09.2022 | 04.09.2022 | 04.09.2022 | 04.09.2022 | 05.09.2022 | 05.09.2022 | 05.09.2022 | 06.09.2022 | 07.09.2022 | 08.09.2022 | 11-09-2022 | 11-09-2022 | 11-09-2022 | 12-09-2022 | [47 empty] | * BV INSPECTION COMPLETE - AWAITING VESSEL CRYSTAL RAY ARRIVAL (BA2186 CO-LOAD) - ETA 25.06.2022 | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2186 - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2186 - ESTIMATE LOADING DATE 19.07.2022 | * BV INSPECTION COMPLETE - TO CO-LOAD WITH BA2186 - ESTIMATE LOADING DATE 19.07.2022 | * TRUCK TO LOAD TODAY AND DISPATCH TOMMROW THE 20/07/2022 | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | LOADING DATE TO BE CONFIRMED, AWAIITNG ARRIVAL OF BA2048 IN ORDER TO CO-LOAD | ESTIMATED LOADING DATE 11-08-2022 | ESTIMATED LOADING DATE 11-08-2022 | ESTIMATED LOADING DATE 15-08-2022 | ESTIMATED LOADING DATE 15-08-2022 | ESTIMATED LOADING DATE 15-08-2022 | ESTIMATED LOADING DATE 17-08-2022 | ESTIMATED LOADING DATE 19-08-2022 | ESTIMATED LOADING DATE 19-08-2022 | ESTIMATED LOADING DATE 19-08-2022 | ESTIMATED LOADING DATE 19-08-2022 | LOADING TODAY | DISPATCHING DURBAN TODAY | CAMPERDOWN ENROUTE JOHANNESBURG | HOWICK ENROUTE JOHANNESBURG | MIDDELBURG ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE EN-ROUTE TO CHIRUNDU | CHINOYI EN-ROUTE TO CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKY - AWAITING CLEARANCE | LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022 | OFFLOADED 12-09-2022
BA2111 | 1 X USED CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TFK01288 | CAT0745CKTFK01288 | RDP02977 | FML2206DSI1640 | VESSEL: HOEGH SHANGHAI Voy. 101 ETA: 12-07-2022 | COD 2022 229303 | ND730794 | ND443606 | ND60502 | 09-08-2022 | OFFLOADED 18-10-2022 | 23.06.2022 | 15.07.2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 12.07.2022 | 14.09.2022 | MIDDELBURG-19/09/2022 |  | 22/09/2022 | 23/09/2022 | 23-09-2022 | 26-09-2022 | 27-09-2022 | 29-09-2022 | 29-09-2022 | 29-09-20220 | 29-09-2022 | 30.09.2022 | 01.10.2022 | 02.10.2022 | 02.10.2022 | 03.10.2022 | 04.10.2022 | 10.10.2022 | 11-10-2022 | 11-10-2022 | 12-10-2022 | 13-10-2022 | 18-10-2022 | 18-10-2022 | [47 empty] | * AWAITING VESSEL HOEGH SHANGHAI ARRIVAL - CURRENT ETA 12.07.2022 | * VESSEL DUE TO BERTH TODAY HOEGH SHANGHAI - CURRENT ETA 12.07.2022 | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - LOADING DATE TBC | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - LOADING DATE TBC | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - LOADING DATE TBC | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - LOADING DATE TBC | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - LOADING DATE TBC | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - PLANNING TO LOADING 05/08/2022 | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - PLANNING TO LOADING 05/08/2022 | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - PLANNING TO LOADING 05/08/2022 | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - PLANNING TO LOADING 05/08/2022 | BV INSPECTION BOOKED FOR FRIDAY 15-07-2022 - PLANNING TO LOADING 05/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 18/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 18/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 18/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 18/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 18/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 22/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 22/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 22/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 22/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 22/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 29/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 29/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 29/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 29/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 29/08/2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 02-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 05-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 05-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 05-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 06-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 08-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 08-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 12-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 13-09-2022 | BV INSPECTION COMPLETED - WAITING FOR VEHICLE TO RETURN FORM DRC - PLANNING TO LOADING 13-09-2022 | LOADING TODAY | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE DISPATCHED NEWCASTLE ENROUTE JOHANNESBURG | * VEHICLE AT VOLKRUST WAITING FOR MUPUMULANGA PERMITS | * VEHICLE AT MIDDELBURG EN ROUTE TO BEITBRIDGE | * VEHICLE AT MIDDELBURG AWAITING LIMPOPO PERMIT | * VEHICLE AT TO DISPATCH MIDDELBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE TO DISPATCHED MIDDELBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE MUSINA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT BEIT BRIDGE RSA SIDE CLEARING | * VEHICLE AT MASINGO ENROUTE HARARE | * VEHICLE AT HARARE | DISPATCHING HARARE | CHIRUNDU ZAMBIAN SIDE CLEARING | CHINGOLA ENROUTE KASUMBALESA | CHILIBOMBWE IN QUEUE TO PROCEED TO KASUMBALESA | CHILIBOMBWE IN QUEUE TO PROCEED TO KASUMBALESA | CHILIBOMBWE IN QUEUE TO PROCEED TO KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI AWAITING RELEASE - DAY 2 | VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI AWAITING RELEASE - DAY 5 | VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI AWAITING RELEASE - DAY 6 | OFFLOADED 18-10-2022 | OFFLOADED 18-10-2022
BA2123 | 1 X NEW CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201257 | CAT00140CW9201257 | E7A54442 | FML 2207DSI1655 | VESSEL: MORNING CHAMPION ETA: 27-07-2022 | COD 2022 252852 | ABN1819 | ADZ9560 | ND60527 | 06-08-2022 | OFFLOADED - 23-09-2022 | 25-07-2022 | 03.08.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 03-08-2022 - WAITING CONFIRMATION FROM BV | 27.07.2022 | 23-08-2022 | 23-08-2022 | 31-08-2022 | 31-08-2022 | 01-09-2022 | 01-09-2022 | 02-09-2022 | 05.09.2022 | 06.09.2022 | 07.09.2022 | 07.09.2022 | 08.09.2022 | 09-09-2022 | 09-09-2022 | 10-09-2022 | 10-09-2022 | 10-09-2022 | 11-09-2022 | 11-09-2022 | 13.09.2022 | 14.09.2022 | 15-09-2022 | 16-09-2022 | 23-09-2022 | 23-09-2022 | [53 empty] | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 16/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 16/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 19/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 19/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 19/08/2022 | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE CURRETNLY AT MOOIRIVER ENROUTE JOHANNESBURG | * VEHICLE CURRETNLY AT JOHANNESBURG | * VEHICLE CURRETNLY AT JOHANNESBURG WAITING PERMIT | * VEHICLE CURRETNLY AT JOHANNESBURG WAITING PERMIT | * VEHICLE CURRETNLY AT JOHANNESBURG WAITING LIMPOPO PERMIT | * VEHICLE CURRETNLY AT JOHANNESBURG WAITING LIMPOPO PERMIT | * VEHICLE CURRETNLY AT BELA BELA EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRETNLY AT BEITBRIDGE RSA SIDE | * VEHICLE CURRETNLY AT MVUMA EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBULESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBULESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE - DAY 2 | LUBUMBASHI WAITING TO OFFLOAD | LUBUMBASHI WAITING TO OFFLOAD | LUBUMBASHI WAITING TO OFFLOAD | LUBUMBASHI WAITING TO OFFLOAD | TRUCK ACTUALLY AT CONNEX AWAITING RELEASE | TRUCK ACTUALLY AT CONNEX AWAITING RELEASE DAY 8 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022 | OFFLOADED - 23-09-2022
BA2127 | 1 X NEW CAT950GC WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M5K05982 | CAT00950CM5K05982 | E7A52947 | FML2205DSI1565 | VESSEL: LAKE FUXIAN ETA: 01-06-2022 | COD 2022 204808 | JV80FPGP | JZ68SNGP | ND59509 | 03-08-2022 | OFFLOADED 16/09/2022 | 23.05.2022 | 08-06-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 06.06.2022 | 01-08-2022 | 05-08-2022 | 23-08-2022 | 27-08-2022 | 27-08-2022 | 27-08-2022 | 29-08-2022 | 31-08-2022 | 03.08.2022 | 05.09.2022 | 05.09.2022 | 05.09.2022 | 06.09.2022 | 06.09.2022 | 06.09.2022 | 07.09.2022 | 08.09.2022 | 08-09-2022 | 08-09-2022 | 13.09.2022 | 14.09.2022 | 16.09.2022 | 16.09.2022 | 16.09.2022 | 16.09.2022 |  |  |  | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING FINAL BILL AND INVOICE | AWAITING VESSEL ARRIVAL ON THE 07/05/2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | AWAITING VESSEL ARRIVAL ON THE 07.05.2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 25-05-2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 29.05.2022 | WAITING VESSEL ARRIVAL: VESSEL - LAKE FUXIAN - ETA: 29.05.2022 | VESSEL ARRIVED - WAITING COMPLETION OF DISCHARGE | MACHINE TO BE COLLECTED FROM PORT TODAY | BV BOOKED FOR THE 08/06/2022 | BV BOOKED FOR TODAY THE 08/06/2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-06-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 06-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 06-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 06-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 06-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 06-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 06-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 08-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 13-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 18-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 18-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 29-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 29-07-2022 | HOWICK ENROUTE JOHANNESBURG | JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK TO DISPATCH JNB TODAY | TRUCK DISPATCH JNB EN-ROUTE TO BEITBRIDGE | TRUCK AT JNB UNDERGOING TRIP CHECK AND WILL DISPATCH MONDAY THE 15/08/2022 | * VEHICLE AWAITING PERMIT - PLANNING TO DISPATCH JHB THIS AFTERNOON | * VEHICLE AWAITING PERMIT - PLANNING TO DISPATCH JHB THIS AFTERNOON | * VEHICLE AWAITING PERMIT - PLANNING TO DISPATCH JHB THIS AFTERNOON | * VEHICLE AWAITING PERMIT - TO DISPATCH JHB AS SOON AS PERMIT IS RELEASED | * VEHICLE AWAITING PERMIT - TO DISPATCH JHB AS SOON AS PERMIT IS RELEASED | * VEHICLE AWAITING PERMIT - TO DISPATCH JHB AS SOON AS PERMIT IS RELEASED | * VEHICLE AT BELE BELA ENROUTE MUSINA | * VEHICLE AT POLOKWANE ENROUTE MUSINA | * VEHICLE AT POLOKWANE WEIGHBRIDGE WAITING PERMITS | * VEHICLE AT POLOKWANE WEIGHBRIDGE WAITING PERMITS | BEIT BRIDGE RSA SIDE CLEARING | BUBI ENROUTE HARARE | HARARE EN-ROUTE TO CHIRUNDU | DISPATCHING HARARE TODAY | DISPATCHING HARARE TODAY | * VEHICLE CURRENTLY AT CHIRUNDU UNDER CLEARANCE | * VEHICLE CURRENLTY AT KAPIRI MPOSHE ENROUTE KITWE | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | * VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE - DAY 2 | * VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE - DAY 3 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022 | OFFLOADED 16/09/2022
BA2297 | 1 X CAT D9 TRACK TYPE TRACKOR - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | AK400520 | CAT000D6AK400520 | TNR00315 | FML 2209DSI1738 | VESSEL: LAVENDER ACE Voy. 0086A ETA DURBAN: 21-09-2022 | COD 2022 287210 | CJ83LPGP | ZVM447GP | ND63614-1 | 01-10-2022 | OFFLOADED 19-10-2022 | 09.09.2022 | 28.09.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED AS SOON AS THE UNIT IS AVAILABLE | 21-09-2022 | 30-09-2022 | 03.10.2022 | 05.10.2022 | 05.10.2022 | 05.10.2022 | 06.10.2022 | 07.10.2022 | 07.10.2022 | 09.10.2022 | 10.10.2022 | 10.10.2022 | 11.10.2022 | 11.10.2022 | 11.10.2022 | 11.10.2022 | 11.10.2022 | 11.10.2022 | 12.10.2022 | 12.10.2022 | 13-10-2022 | 13-10-2022 | 15-10-2022 | 15-10-2022 | 19-10-2022 | 19-10-2022 | [86 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW - LOADING PLAN TO BE ADVISE | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLAN TO BE ADVISE | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW & FRIDAY | LOADING TODAY | DISPATCHING DURBAN | JOHANNESBURG ENROUTE MUSINA | JOHANNESBURG AWAITING LIMPOPO PERMIT | DISPATCHING JOHANNESBURG ENROUTE MUSINA | VEHICLE CURRENLTY AT BEITBRIDGE - CROSSING OT ZIM SIDE | VEHICLE CURRENTLY AT GWERU ENROUTE HARARE | VEHICLE CURRENTLY AT CHIRUDNU ZAM SIDE | VEHICLE CURRENTLY AT CHINGOLA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAM AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA ZAM AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY2 | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 3 | OFFLOADED 19-10-2022
BA2071 | 1 X NEW CAT 374-07B HYDRAULIC EXCAVATOR - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10048 | CAT00374TRGM10048 | E4T00561 | FML 2208DSI1695 | VESSEL: DONG-A GLAUCOS Voy. 058 ETA: 12-09-2022 | COD 2022 263435 | ND568309 | ND566910 / ND564162 | ND60592-1 | 20-09-2022 | * OFFLOADED 22.10.2022 | 08-08-2022 | 19-09-2022 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 21/09/2022 | 21/09/2022 | 26-09-23022 | 26-09-2022 | 27-09-2022 | 27-09-2022 | 27-09-2022 | 29-09-2022 | 02.10.2022 | 03.10.2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 05.10.2022 | 05.10.2022 | 06.10.2022 | 10.10.2022 | 10.10.2022 | 11.10.2022 | 12.10.2022 | 13.10.2022 | 14-10-23022 | 14-10-2022 | TENKE - 20-10-2022 | 22.10.2022 | [63 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | VESSEL IS IN AND WORKING | * AWAITING VESSEL ARRIVAL - CURRENT ETA 09.09.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 09.09.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 09.09.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 11.09.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 12.09.2022 | VESSEL BERTHED AND IS CURRENTLY WORKING | * VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - BV INSPECTION TO BE BOOKED FOR TOMORROW 16-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY 16-09-2022 | BV BOOKED FOR TODAY THE 19/09/2022, AWAITING TRUCK DETAILS AND LOADING DATE | TRUCK WILL LOAD TODAY AND DISPATCH WEDNESDAY THE 21/09/2022 | TRUCK WILL DISPATCH TODAY ONCE THE PERMIT IS RECEIVED | TRUCK AT PIETERMARITZBURG EN-ROUTE TO JOHANNESBURG | TRUCK AT GREYTOWN EN-ROUTE TO JOHANNESBURG | TRUCK AT LADYSMITH EN-ROUTE TO JOHANNESBURG | TRUCK AT POLOKWANE ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | MVUMA ENROUTE HARARE | VEHICLE CURRENTLY AT KAROI ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT CHILLIBOMBWE EN ROUTE KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA IN QUEUE | VEHICLE CURRENLTY AT KASUMBALESA ZAM AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY - AWAITING CLEARANCE & RELEASE - DAY 2 | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | LUBUMBASHI WAITING ESCORT TO PROCEED TO OFFLOADING POINT | TENKE WAITING TO OFFLOAD | * OFFLOADED 22.10.2022 | * OFFLOADED 22.10.2022 | * OFFLOADED 22.10.2022 | * OFFLOADED 22.10.2022
BA2129 | 1 X NEW CAT 966GC-01A WHEEL LAODER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW00853 | CAT00966JSGW00853 | NTB10923 | FML 2207DSI1656 | VESSEL: MORNING CHAMPION ETA: 27-07-2022 | COD 2022 252248 | HB92CZGP | KHM039MP | ND60528 | 06-08-2022 | * OFFLOADED 21.10.2022 | 25-07-2022 | 03.08.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 03-08-2022 - WAITING CONFIRMATION FROM BV | 27.07.2022 | 14.09.2022 | 14-09-2022 | 21-09-2022 | 22-09-2022 | 23-09-2022 | 23-09-2022 | 27-09-2022 | 27-09-2022 | 27-09-2022 | 28-09-2022 | 29-09-2022 | 29-09-2022 | 02.10.2022 | 03.10.2022 | 03.10.2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 10.10.2022 | 16-10-2022 | 16-10-2022 | 17-10-2022 | 17-10-2022 | 21-10-2022 | 21.10.2022 | [53 empty] | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAITING VESSEL ARRIVAL ON THE 27/07/2022 | AWAITING VESSEL ARRIVAL ON THE 27/07/2022 | AWAITING VESSEL ARRIVAL ON THE 27/07/2022 | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | MACHINE WILL LOAD ON MONDAY THE 05/09/2022 | MACHINE WILL LOAD ON WEDNESDAY THE 07.09.2022 | MACHINE WILL LOAD ON THURSDAY THE 08.09.2022 | MACHINE WILL LOAD ON THURSDAY THE 08.09.2022 | LOADING TODAY | LOADED - WATING PERMITS BEFORE DISPATCHING | DISPATCHING DURBAN TODAY | * VEHICLE DISPATCHED DURBAN ENROUTE PIETERMARITZBURG | * VEHICLE AT JOHANNESBURG | * VEHICLE AT JOHANNESBURG WAITING LIMPOPO PERMITS | * VEHICLE AT JOHANNESBURG WAITING LIMPOPO PERMITS | * VEHICLE AT JOHANNESBURG WAITING LIMPOPO PERMITS | * VEHICLE AT JOHANNESBURG DISPATCH TO BEITBRIDGE TODAY | * VEHICLE AT BELA BELA TO BEITBRIDGE TODAY | * VEHICLE AT BEITBRIDGE RSA SIDE | * VEHICLE AT BEITBRIDGE ZIM SIDE | * VEHICLE DISPATCHING BEIT BRIDGE ZIM SIDE | * VEHICLE AT KATOI ENROUTE CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE | CHIRUNDU ZAMBIAN SIDE CLEARING | AT LUSAKA ENROUTE KABWE | NDOLA ENROUTE KASUMBALESA | CHILIBOMBWE IN QUEUE TO PROCEED TO KASUMBALESA | CHILIBOMBWE IN QUEUE TO PROCEED TO KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - AWAITING RELEASE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - IN THE CUEUE TO CROSS TO DRC SIDE | VEHICLE CURRENLTY AT WHISKEY | VEHICLE CURRENLTY AT LUBUMBASHI WAITING ESCORT TO PROCEED TO SITE FOR OFFLOADING | VEHICLE CURRENLTY AT LUBUMBASHI WAITING ESCORT TO PROCEED TO SITE FOR OFFLOADING | VEHICLE CURRENLTY AT LUBUMBASHI WAITING ESCORT TO PROCEED TO SITE FOR OFFLOADING | DISPATCHED FROM CONNEX LUBUMBASHI ENROUTE CONGO EQUIPMENT TO OFFLOAD | * OFFLOADED 21.10.2022 | * OFFLOADED 21.10.2022 | * OFFLOADED 21.10.2022 | * OFFLOADED 21.10.2022
BA2130 | 1 X NEW CAT D6GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XPC00608 | CAT000D6CXPC00608 | TBA | FML2208DSI1723 | VESSEL: CASSIOPEIA LEADER Voy. 035 ETA: 24-09-2022 | COD 2022 296960 | ND706468 | ND256330 | ND59598 | 01-10-2022 | * OFFLOADED 24.10.2022 | 05.08.2022 | 27-09-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 22/09/2022 | 03.10.2022 | 03.10.2022 | 03.10.2022 | 05.10.2022 | 05.10.2022 | 06.10.2022 | 06.10.2022 | 10.10.2022 | 10.10.2022 | 10.10.2022 | 11.10.2022 | 11.10.2022 | 11.10.2022 | 12-10-2022 | 12-10-2022 | 13-10-2022 | 13-10-2022 | 13-10-2022 | 14-10-2022 | 16-10-2022 | 16-10-2022 | 19-10-2022 | 19-10-2022 | 24.10.2022 | [73 empty] | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 22.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 24.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 24.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 24.09.2022 | THE VESSEL IS IN AND WORKING | THE VESSEL IS IN AND WORKING | COLLECTION UNIT FROM PORT TODAY | UNIT AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW - LOADING PLAN TO BE ADVISE | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLAN TO BE ADVISE | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISE | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLAN TO BE ADVISE | LOADING TOMORROW - DISPATCHING MONDAY | ESCOURT ENROUTE JOHANNESBURG | POLOKWANE ENROUTE MUSINA | MUSINA ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENTLY AT CHIRUNDU EN ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHIRUNDU EN ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KAPIRI EN ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA EN ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHILILABOMBWE EN ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT WHISKEY - DAY 2 | VEHICLE CURRENTLY AT WHISKEY - DAY 3 | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 24.10.2022 | * OFFLOADED 24.10.2022 | * OFFLOADED 24.10.2022
BA2215 | 1 X CAT 966-14A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EL900295 | CAT00966LEL900295 | NTB10781 | FML2208DSI1690 | VESSEL: MORNING CONCERT Voy.152 ETA 28-08-2022 | COD 2022 272889 | NU112272 | ND629383 | ND60581 | 09-09-2022 | * OFFLOADED 24.10.2022 | 22-08-2022 | 02.09.2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 28-08-2022 | 29-09-2022 | 01.10.2022 | 02.10.2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 06.10.2022 | 06.10.2022 | 06.10.2022 | 07.10.2022 | 10-10-2022 | 11-10-2022 | 11-10-2022 | 12-10-2022 | 12-10-2022 | 12-10-2022 | 12-10-2022 | 12-10-2022 | 14-10-2022 | 16-10-2022 | 16-10-2022 | 19-10-2022 | 19-10-2022 | 19.10.2022 | [67 empty] | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - PLANNING TO LOAD 19-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 19-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 20-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 20-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 22-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 22-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 22-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 22-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 22-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 22-09-2022 | UNIT AT OUR FACILITY - PLANNING TO LOAD 26-09-2022 | UNIT AT OUR FACILITY - VEHICLE IN WORKSHOP - UNDERGOING MANTENANCE - PLANNING TO LOAD ONCE MAINTENANCE IS COMPLETE | UNIT AT OUR FACILITY - VEHICLE IN WORKSHOP - UNDERGOING MANTENANCE - PLANNING TO LOAD ONCE MAINTENANCE IS COMPLETE | UNIT AT OUR FACILITY - LOADING TODAY | MARIAN HILL ENROUTE JOHANNESBURG | HENDRINA ENROUTE MUSIAN | MUSINA ENROUTE BEITBRIDGE | AT BEITBRIDGE AWAITING CLEARANCE | AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | VEHICLE CURRENTLY AT KAFUE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHILLILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHILLILABOMBWE IN THE QUEUE TO PROCEED TO KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT WHISKEY - DAY 2 | VEHICLE CURRENTLY AT WHISKEY - DAY 3 | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | * ON SITE WAITING TO OFFLOAD | * OFFLOADED 24.10.2022 | * OFFLOADED 24.10.2022 | * OFFLOADED 24.10.2022
BA2288 | 1 X CAT 966GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW00885 | CAT00966CSGW00885 | NTB10828 | FML2208DSI1692 | VESSEL: MORNING CONCERT Voy.152 ETA 28-08-2022 | COD 2022 272889 | ALG1979 | ADD3951T | ND60583 | 09-09-2022 | OFFLOADED 20-10-2022 | 22-08-2022 | 02.09.2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 01/09/2022 | 20-09-2022 | 23-09-2022 | 26-09-2022 | 27-09-2022 | 27-09-2022 | 27-09-2022 | 30.09.2022 | 01.10.2022 | 02.10.2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 05.10.2022 | 05.10.2022 | 05.10.2022 | 06.10.2022 | 06.10.2022 | 07.10.2022 | 10.10.2022 | 15-10-2022 | 15-10-2022 | 16-10-2022 | 16-10-2022 | 18-10-2022 | 20-10-2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - PLANNED LOADING DATE 19-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | TRUCK WILL LOAD TODAY AND DISPATCH WEDNESDAY THE 21/09/2022 | TRUCK WILL LOAD TODAY AND DISPATCH WEDNESDAY THE 21/09/2022 | TRUCK AT CATO RIDGE EN-ROUTE TO JOHANNESBURG | TRUCK AT ESCORT EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK AT JOHANNESBURG WAITING LIMPOPO PERMITS | TRUCK AT POLOKWANE ENROUTE MUSINA | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT BEIT BRIDGE ZIM SIDE | KWEKWE ENROUTE HARARE | CHIRUNDU ZAM SIDE WAITING CLEARANCE | CHIRUNDU ZAM SIDE WAITING CLEARANCE | CHISAMBA ENROUTE LUSAKA | VEHICLE CURRENLTY AT KITWE ENROUTE CHINGOLA | VEHICLE CURRENTLY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHILILABOMBWE IN QUEUE EN ROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 20-10-2022 | OFFLOADED 20-10-2022 | OFFLOADED 20-10-2022 | OFFLOADED 20-10-2022 | OFFLOADED 20-10-2022
BA2296 | 1 X CAT 950GC WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M5K06174 | CAT00950HM5K06174 | E7A55877 | FML2208DSI1693 | VESSEL: MORNING CONCERT Voy.152 ETA 28-08-2022 | COD 2022 272889 | ND491242 | ND627367 | ND60584 | 09-09-2022 | OFFLOADED 24-10-2022 | 22-08-2022 | 02.09.2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 01/09/2022 | 19/09/2022 | 23/09/2022 | 28-09-2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 06.10.2022 | 07.10.2022 | 08.10.2022 | 10.10.2022 | 10.10.2022 | 11.10.2022 | 11.10.2022 | 11-10-2022 | 11-10-2022 | 12-10-2022 | 12-10-2022 | 12-10-2022 | 14-10-2022 | 16-10-2022 | 16-10-2022 | 19-10-2022 | 19-10-2022 | 19.10.2022 | 24.10.2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | LOADING TODAY - DISPATCHING MORNDAY | TRUCK AT MARIANHILL TOLL EN ROUTE TO JOHANNESBURG | TRUCK AT HARRISMITH EN ROUTE TO JOHANNESBURG | TRUCK AT HARRISMITH - STOPED DUE TO BAD WEATHER IN RSA | TRUCK AT MOOIRIVER EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK AT JOHANNESBURG WAITING LIMPOPO PERMITS | TRUCK AT JOHANNESBURG WAITING LIMPOPO PERMITS | TRUCK AT JOHANNESBURG WAITING LIMPOPO PERMITS | MIDDELBURG | MIDDELBURG ON BREAKDOWN - TO DISPATCH ON MONDAY | MUSINA ENROUTE BEITBRIDGE | AT BEITBRIDGE AWAITING CLEARANCE | AT BEITBRIDGE ZIM AWAITING CLEARANCE | VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | VEHICLE CURRENTLY AT KAFUE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY ATNDOLA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHILLILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT WHISKEY - DAY 2 | VEHICLE CURRENTLY AT WHISKEY - DAY 3 | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | * ON SITE WAITING TO OFFLOAD | OFFLOADED 24-10-2022 | OFFLOADED 24-10-2022 | OFFLOADED 24-10-2022
BA1752 | 1 X HAMMER KIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML 2201DSI1409 |  | COD 2022 291376 | ND491242 | ND627367 | ND60584 | 26-09-2022 | OFFLOADED 24-10-2022 | 16-09-2022 | 19-09-2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 01/09/2022 | 19/09/2022 | 23/09/2022 | 28-09-2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 06.10.2022 | 07.10.2022 | 08.10.2022 | 10.10.2022 | 10.10.2022 | 11.10.2022 | 11.10.2022 | 11-10-2022 | 11-10-2022 | 12-10-2022 | 12-10-2022 | 12-10-2022 | 14-10-2022 | 16-10-2022 | 16-10-2022 | 19-10-2022 | 19-10-2022 | 19.10.2022 | [107 empty] | VEHICLE CURRENTLY AT CHILLILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT WHISKEY - DAY 2 | VEHICLE CURRENTLY AT WHISKEY - DAY 3 | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | * ON SITE WAITING TO OFFLOAD | OFFLOADED 24-10-2022 | OFFLOADED 24-10-2022 | OFFLOADED 24-10-2022
BA2190 | 1 X CAT426F2 BACKHOE LOADER & ACCESSORIES | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ405362 | CAT0426FHEJ405362 | CC205550 | FML 2206DSI1629 | VESSEL: BUXCOAST Voy. 0206W - ETA: 01-07-2022 | COD 2022 291007 | ACG1646 | ACE4202T | ND63605 | 23-09-2022 | * OFFLOADED 25.10.2022 | 15-09-2022 | 16.09.2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR 16-09-2022 | 01-07-2022 | 23-09-2022 | 27-09-2022 | 29-09-2022 | GRB 29-09-2022 | 30.09.2022 | 01.10.2022 | 02.10.2022 | 02.10.2022 | 03.10.2022 | 03.10.2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 05.10.2022 | 06.10.2022 | 06.10.2022 | 06.10.2022 | 12.10.2022 | 16-10-2022 | 16-10-2022 | 19-10-2022 | 25.10.2022 | 25.10.2022 | 25.10.2022 | [86 empty] | BV NUMBER RECEIVED 15-09-2022 - BV INSPECTION TO BE BOOKED FOR TOMORROW | BV NUMBER RECEIVED 15-09-2022 - BV INSPECTION BOOKED FOR TODAY 16-09-2022 - LOADING PLANNED FOR NEXT WEEK | BV COMPLETE AWAITING TRUCK DETAILS AND DISPATCH DATE THIS WEEK | BV COMPLETE AWAITING TRUCK DETAILS AND DISPATCH DATE THIS WEEK | BV COMPLETE AWAITING BV TO BE DONE ON THE BUCKETS IN ORDER TO DISPATCH THE TRUCKS | BV COMPLETE AWAITING BV TO BE DONE ON THE BUCKETS IN ORDER TO DISPATCH THE TRUCKS | TRUCK WILL DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | CATO RIDGE ENROUTE JOHANNESBURG | PIETERMARITSBURG ENROUTE JOHANNESBURG | JOHANNESBURG | DISPATCHING JOHANNESBURG | GROBLERS BRIDGE BORDER CLEARING | * VEHICLE CURRENTLY AT NATA ENROUTE KAZUNGULA | VEHICLE CURRENTLY AT KAZUNGULA - ENROUTE LUSAKA | LUSAKA ENROUTE KABWE | VEHICLE CURRENLTY AT NDOLA ENROUTE LUBUMBASHI | VEHICLE CURRENLTY AT NDOLA - WAITING FOR QUEUE TO SUBSIDE IN ORDER TO PROCEED TO KASUMBALESA | VEHICLE CURRENLTY AT CHILLIBOMBWE EN ROUTE KASUMBALESA | VEHICLE CURRENLTY AT CHILLIBOMBWE EN ROUTE KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM IN THE QUEUE TO CROSS | VEHICLE CURRENLTY AT WHISKEY | VEHICLE CURRENLTY AT WHISKEY - DAY 3 | VEHICLE CURRENLTY AT WHISKEY - DAY 4 | KANYAKA CLEARING | KANYAKA CLEARING | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 25.10.2022 | * OFFLOADED 25.10.2022
BA2288 | 1 X CAT 966GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW00885 | CAT00966CSGW00885 | NTB10828 | FML2208DSI1692 | VESSEL: MORNING CONCERT Voy.152 ETA 28-08-2022 | COD 2022 272889 | ALG1979 | ADD3951T | ND60583 | 09-09-2022 | OFFLOADED 20-10-2022 | 22-08-2022 | 02.09.2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 01/09/2022 | 20-09-2022 | 23-09-2022 | 26-09-2022 | 27-09-2022 | 27-09-2022 | 27-09-2022 | 30.09.2022 | 01.10.2022 | 02.10.2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 05.10.2022 | 05.10.2022 | 05.10.2022 | 06.10.2022 | 06.10.2022 | 07.10.2022 | 10.10.2022 | 15-10-2022 | 15-10-2022 | 16-10-2022 | 16-10-2022 | 18-10-2022 | 20-10-2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - PLANNED LOADING DATE 19-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | TRUCK WILL LOAD TODAY AND DISPATCH WEDNESDAY THE 21/09/2022 | TRUCK WILL LOAD TODAY AND DISPATCH WEDNESDAY THE 21/09/2022 | TRUCK AT CATO RIDGE EN-ROUTE TO JOHANNESBURG | TRUCK AT ESCORT EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK AT JOHANNESBURG WAITING LIMPOPO PERMITS | TRUCK AT POLOKWANE ENROUTE MUSINA | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | TRUCK AT BEIT BRIDGE ZIM SIDE | KWEKWE ENROUTE HARARE | CHIRUNDU ZAM SIDE WAITING CLEARANCE | CHIRUNDU ZAM SIDE WAITING CLEARANCE | CHISAMBA ENROUTE LUSAKA | VEHICLE CURRENLTY AT KITWE ENROUTE CHINGOLA | VEHICLE CURRENTLY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHILILABOMBWE IN QUEUE EN ROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE AND RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 20-10-2022 | OFFLOADED 20-10-2022 | OFFLOADED 20-10-2022 | OFFLOADED 20-10-2022 | OFFLOADED 20-10-2022
BA2296 | 1 X CAT 950GC WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M5K06174 | CAT00950HM5K06174 | E7A55877 | FML2208DSI1693 | VESSEL: MORNING CONCERT Voy.152 ETA 28-08-2022 | COD 2022 272889 | ND491242 | ND627367 | ND60584 | 09-09-2022 | OFFLOADED 24-10-2022 | 22-08-2022 | 02.09.2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 01/09/2022 | 19/09/2022 | 23/09/2022 | 28-09-2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 06.10.2022 | 07.10.2022 | 08.10.2022 | 10.10.2022 | 10.10.2022 | 11.10.2022 | 11.10.2022 | 11-10-2022 | 11-10-2022 | 12-10-2022 | 12-10-2022 | 12-10-2022 | 14-10-2022 | 16-10-2022 | 16-10-2022 | 19-10-2022 | 19-10-2022 | 19.10.2022 | 24.10.2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | UNIT AT OUR FACILITY - PLANNED LOADING DATE 15-09-2022 | LOADING TODAY - DISPATCHING MORNDAY | TRUCK AT MARIANHILL TOLL EN ROUTE TO JOHANNESBURG | TRUCK AT HARRISMITH EN ROUTE TO JOHANNESBURG | TRUCK AT HARRISMITH - STOPED DUE TO BAD WEATHER IN RSA | TRUCK AT MOOIRIVER EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDER GOING TRIP CHECK | TRUCK AT JOHANNESBURG WAITING LIMPOPO PERMITS | TRUCK AT JOHANNESBURG WAITING LIMPOPO PERMITS | TRUCK AT JOHANNESBURG WAITING LIMPOPO PERMITS | MIDDELBURG | MIDDELBURG ON BREAKDOWN - TO DISPATCH ON MONDAY | MUSINA ENROUTE BEITBRIDGE | AT BEITBRIDGE AWAITING CLEARANCE | AT BEITBRIDGE ZIM AWAITING CLEARANCE | VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | VEHICLE CURRENTLY AT KAFUE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY ATNDOLA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHILLILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT WHISKEY - DAY 2 | VEHICLE CURRENTLY AT WHISKEY - DAY 3 | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | * ON SITE WAITING TO OFFLOAD | OFFLOADED 24-10-2022 | OFFLOADED 24-10-2022 | OFFLOADED 24-10-2022
BA1752 | 1 X HAMMER KIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML 2201DSI1409 |  | COD 2022 291376 | ND491242 | ND627367 | ND60584 | 26-09-2022 | OFFLOADED 24-10-2022 | 16-09-2022 | 19-09-2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 01/09/2022 | 19/09/2022 | 23/09/2022 | 28-09-2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 06.10.2022 | 07.10.2022 | 08.10.2022 | 10.10.2022 | 10.10.2022 | 11.10.2022 | 11.10.2022 | 11-10-2022 | 11-10-2022 | 12-10-2022 | 12-10-2022 | 12-10-2022 | 14-10-2022 | 16-10-2022 | 16-10-2022 | 19-10-2022 | 19-10-2022 | 19.10.2022 | [107 empty] | VEHICLE CURRENTLY AT CHILLILABOMBWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT WHISKEY - DAY 2 | VEHICLE CURRENTLY AT WHISKEY - DAY 3 | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBAHSI - WAITING FINAL CLEARANCE & RELEASE | * ON SITE WAITING TO OFFLOAD | OFFLOADED 24-10-2022 | OFFLOADED 24-10-2022 | OFFLOADED 24-10-2022
BA2002 | 1 X NEW CAT 345GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30153 | CAT00345LKEF30153 | NTB10325 | FML2206DSI1610 | VESSEL: BANKOK HIGHWAY ETA: 25-06-2022 | COD 2022 224266 | ND754967 | ND654346 | ND52680 | 28-06-2022 | OFFLOADED 01.10.2022 | 17.06.2022 | 28.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 25.06.2022 | 12-09-2022 | MIDDELBURG 12-09-2022 | MIDDELBURG 14-09-2022 | 14-09-2022 | 15-09-2022 | 15-09-2022 | 17-09-2022 | 19-09-2022 | 19-09-2022 | 20-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 22-09-2022 | 22-09-2022 | 22-09-2022 | 22-09-2022 | 23-09-2022 | 23-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 01.10.2022 | 01.10.2022 | [47 empty] | ESTIMATED LOADING DATE 14-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | ESTIMATED LOADING DATE 18-07-2022 AWAITING VEHCILE TO RETURN FROM DRC | ESTIMATED LOADING DATE 01-08-2022 AWAITING VEHICLE TO RETURN FROM DRC | ESTIMATED LOADING DATE 01-08-2022 AWAITING VEHICLE TO RETURN FROM DRC | ESTIMATED LOADING DATE 01-08-2022 AWAITING VEHICLE TO RETURN FROM DRC | ESTIMATED LOADING DATE 01-08-2022 AWAITING VEHICLE TO RETURN FROM DRC | ESTIMATED LOADING DATE 01-08-2022 AWAITING VEHICLE TO RETURN FROM DRC | ESTIMATED LOADING DATE 01-08-2022 AWAITING VEHICLE TO RETURN FROM DRC | ESTIMATED LOADING DATE 01-08-2022 AWAITING VEHICLE TO RETURN FROM DRC | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | VEHICLE CURRENTLY IN DURBAN. UNDERGOING MAINTENANCE CHECK BEFORE LOADING | MACHINE TO LOAD TODAY AND DISPATCH ON WEDNESDAY THE 10/08/2022 | TRUCK DISPATCHING DURBAN TODAY EN-ROUTE BEITBRIDGE BORDER | TRUCK IS LOADED, AWAITING PERMIT TO DISPATCH ON THE 15/08/2022 | TRUCK IS LOADED, AWAITING PERMIT TO DISPATCH ON THE 15/08/2022 | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH - SHOULD RECEIVE PERMIT PM TODAY | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH - MAJOR DELAY IN ISSUING PERMITS AS DISCUSSED WITH VIDOUSHA | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH - MAJOR DELAY IN ISSUING PERMITS AS DISCUSSED WITH VIDOUSHA - SHOULD RECEIVE PERMIT TODAY | * VEHICLE LOADED - DISPATCHING 01-09-2022 | * VEHICLE LOADED - DISPATCHING 01-09-2022 | * VEHICLE STILL IN WORKSHOP DUE TO BREAKDOWN | * VEHICLE STILL IN WORKSHOP DUE TO BREAKDOWN | * VEHICLE STILL IN WORKSHOP DUE TO BREAKDOWN | * VEHICLE PLANNING TO DISPATCH DURBAN TOMORROW MORNING - 08.09.2022 | * VEHICLE LOADING THIS AFTERNOON - PLANNING TO DISPATCH DURBAN TODAY | LOADED TO DISPATCH TODAY | DISPATCHED DURBAN ENROUTE JOHANNESBURG | MIDDELBURG | * VEHILE AT MIDDELBURG AWAITING PERMIT | * VEHILE AT MUSINA | * VEHILE AT BEIT BRIDGE RSA SICE | * VEHILE AT HARARE EN-ROUTE TO CHIRUNDU | * VEHILE AT CHIRUNDU ZAM SIDE | * VEHILE AT CHIRUNDU ZAM SIDE AWAITING RELEASE | * VEHCILE AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHCILE AT KASUMBALESA ZAM SIDE | * VEHCILE AT KASUMBALESA ZAM SIDE | * VEHCILE AT LUBUMBASHI | * VEHCILE AT CONNEX LUBUMBASHI - WAITING RELEASE | * VEHCILE AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 3 | * VEHCILE AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 4 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022 | OFFLOADED 01.10.2022
BA2015 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F602148 | CAT000745C3F602148 | TXW06762 | FML2208DSI1694 | VESSEL: GOLDEN KAROO Voy. 2262 ETA: 29-08-2022 | COD 2022 272446 | ND834401 | ND854241 | ND60580 | 26-09-2022 | OFFLOADED 19-10-2022 | 22-08-2022 | 12-09-2022 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 02-09-2022 | 26-09-2022 | MIDDELBURG 26-09-2022 | MIDDELBURG 27-09-2022 | 27-09-2022 | 28-09-2022 | 28-09-2022 | 29-09-2022 | 01.10.2022 | 02.10.2022 | 03.10.2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 05.10.2022 | 05.10.2022 | 06.10.2022 | 07.10.2022 | 10.10.2022 | 11.10.2022 | 12.10.2022 | 13.10.2022 | 15-10-2022 | 15-10-2022 | 18-10-2022 | 19-10-2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 29-08-2022 | AWAITING VESSEL ARRIVAL ON THE 29-08-2022 | AWAITING VESSEL ARRIVAL ON THE 29-08-2022 | AWAITING VESSEL ARRIVAL ON THE 29-08-2022 | AWAITING VESSEL ARRIVAL ON THE 29-08-2022 | AWAITING VESSEL ARRIVAL ON THE 29-08-2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | THE VESSEL IS IN AND WORKING | * VESSEL CURRENLY IN & WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNIT ONCE AVAILABLE | * VESSEL CURRENLY IN & WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNIT ONCE AVAILABLE | * COLLECTING UNIT FROM PORT TODAY | UNIT AT OUR FACILITY - BV PLANNED FOR MONDAY 12-09-2022 - LOADING DATE TO BE CONFIRMED | UNIT AT OUR FACILITY - BV BOOKED FOR TODAY 12-09-2022 - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - BV BOOKED FOR TODAY 12-09-2022 - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - BV BOOKED FOR TODAY 12-09-2022 - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNED LOADING DATE 20-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNED LOADING DATE 21-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNED LOADING DATE 21-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNED LOADING DATE 21-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNED LOADING DATE 26-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNED LOADING DATE 26-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNED LOADING DATE 27-09-2022 | MIDDELBURG WAITING PERMITS | MUSINA | BEIT BRIDGE RSA SIDE CLEARING | NGUNDU ENROUTE HARARE | VEHICLE CURRENTLY AT KAROI ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | DISPATCHING CHIRUNDU ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT CHILLIBOMBWE EN ROUTE KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM IN QUEUE | VEHICLE CURRENLTY AT KASUMBALESA ZAM AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY - AWAITING CLEARANCE - DAY 2 | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 | ON SITE WAITING TO OFFLOAD | OFFLOADED 19-10-2022 | OFFLOADED 19-10-2022 | OFFLOADED 19-10-2022 | OFFLOADED 19-10-2022 | OFFLOADED 19-10-2022 | OFFLOADED 19-10-2022
BA2145 | 1 X CAT330 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEL30356 | CAT00330VKEL30356 | E7A53455 | 2206DSI1613 | VESSEL: BRILLIANT ACE Voy. 0092A ETA: 03-08-2022 | COD 2022 224266 | ND705348 | ND476150 | ND59576 | 12-08-2022 | OFFLOADED 29-09-2022 | 17.06.2022 | 28.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.06.2022 | 09-09-2022 | MIDDELBURG 12-09-2022 | 13.09.2022 | 14.09.2022 | 15-09-2022 | 15-09-2022 | 15-09-2022 | 17-09-2022 | 17-09-2022 | 19-09-2022 | 20-09-2022 | 20-09-2022 | 20-09-2022 | 20-09-2022 | 20-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 26-09-2022 | 26-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 29-09-2022 | [47 empty] | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 08-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 10-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 12-08-2022 | TRUCK TO LOAD TODAY AND DISPATCH TOMMROW THE 12/08/2022 | TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 09.09.2022 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 09.09.2022 | * VEHICLE LOADED - PLANNING TO DISPATCH DURBAN TODAY | * VEHICLE LOADED - DISPATCHED DURBAN ENROUTE JOHANNESGURG | VOLKSRUST WAIITNG PERMITS | MIDDELBURG | * VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE CLEARING | * VEHICLE CURRENTLY AT CHIVI ENROUTE HARARE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 2 | LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022
BA2146 | 1 X CAT330 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEL30357 | CAT00330AKEL30357 | E7A53243 | 2206DSI1613 | VESSEL: MORNING COMPOSER ETA: 30-06-2022 | COD 2022 224266 | ND142761 | ND542263 | ND59577 | 12-08-2022 | OFFLOADED | 17.06.2022 | 28.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.06.2022 | 15-09-2022 | HENDRINA-19/09/2022 | HENDRINA-19/09/2022 | 20-09-2022 | 20-09-2022 | 21-09-2022 | 23-09-2022 | 23-09-2022 | 24-09-2022 | 24-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 28-09-2022 | 28-09-2022 | 29-09-2022 | 29-09-2022 | 29-09-2022 | 30-09-2022 | 09.10.2022 | 10.10.2022 | 12.10.2022 | 12.10.2022 | 13.10.2022 | 13.10.2022 | [47 empty] | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 05-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 10-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 10-08-2022 | * BV INSPECTION COMPLETE - AWAITING TRUCKS TO RETURN FROM DRC - ESTIMATED LOADING DATE 12-08-2022 | TRUCK TO LOAD TODAY AND DISPATCH TOMMROW THE 12/08/2022 | TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE CURRENLTY AT MARIAN HILL - MAJOR BREAKDOWN. NEW VEHICLE TO BE ALLOCATED | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 05/09 - 10/09 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 09.09.2022 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 12.09.2022 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 12.09.2022 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 14.09.2022 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 14.09.2022 | * VEHICLE AT OUR FACILITY. NEW VEHICLE TO BE ALLOCATED - ESTIMATED LOADING DATE 14.09.2022 | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE DISPATCHING DURBAN | * VEHICLE AT VOLKRUST WAITING FOR MUPUMULANGA PERMITS | * VEHICLE AT VOLKRUST HENDRINA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT MUSINA EN-ROUTE TO BEITBRIDGE | * VEHICLE AT BEITBRIDGE RSA SIDE | * VEHICLE AT BEITBRIDGE ZIM SIDE | * VEHICLE AT CHIVI EN-ROUTE TO CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE | * VEHICLE DISPATCHING CHIRUNDU ZAM SIDE | * VEHICLE KAPIRI ENROUTE KASUMBALESA | * VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE - BORDER CLOSED (25KM QUEUE) | KASUMBALESA ZAM SIDE - BORDER CLOSED (25KM QUEUE) | KASUMBALESA ZAM SIDE - IN QUEUE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY ON SITE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2148 | 1 X CAT M320D2 WHEEL EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | CH900483 | CATM320DHCH900483 | E7A54780 | FML2208DSI1689 | VESSEL: MORNING CONCERT ETA: 28-08-2022 | COD 2022 272445 | JF922TGP | BX45RWGP | ND60582 | 06.09.2022 | OFFLOADED 27-09-2022 | 22-08-2022 | 02.09.2022 | BV NUMBER RECEIVED. BV TO BE BOOKED ONCE UNIT IS AVAILABLE | 28.08.2022 | 06.09.2022 | 07.09.2022 | 09-09-2022 | 12-09-2022 | 12-09-2022 | 12-09-2022 | 19-09-2022 | 20-09-2022 | 20-09-2022 | 20-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 22-09-2022 | 22-09-2022 | 23-09-2022 | 23-09-2022 | 27-09-2022 | 27-09-2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE IS AT OUR DEPO AWAITING BV INSPECTION AND TRUCK DETAILS | MACHINE WILL LOAD ON MONDAY THE 05/09/2022 | * UNIT LOADING TODAY - TO DISPATCH DURBAN THIS AFTERNOON | * VEHICLE CURRENTLY AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * VEHICLE CURRENTLY AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | DISPATCHING JOHANNESGURG | BELE BELA ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE CLEARING | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE CLEARING & ON BREAKDOWN | * VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT MASVINGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENTLY AT CONNEX LUBUMBASHI AWAIITNG FINAL RELEASE | * VEHICLE CURRENTLY AT CONNEX LUBUMBASHI AWAIITNG FINAL RELEASE - DAY 4 - PLEASE ASSIST | * VEHICLE CURRENTLY AT CONNEX LUBUMBASHI AWAIITNG FINAL RELEASE - DAY 5 - PLEASE ASSIST | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022 | OFFLOADED 27-09-2022
BA2151 | 1 X CAT CS74B VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | B7M00423 | CATCS74BJBM00423 | E7A54536 | FML 2207DSI1658 | VESSEL: MORNING CONCERT Voy.152 ETA 28-08-2022 | COD 2022 252220 | SBG558GP | JXD441GP | ND60531 | 06-08-2022 | OFFLOADED | 25-07-2022 | 04-08-2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 03-08-2022 - WAITING CONFIRMATION FROM BV | 27.07.2022 | 30-08-2022 | 31-08-2022 | 01-09-2022 | 02-09-2022 | 03.09.2022 | 05.09.2022 | 06.09.2022 | 07.09.2022 | 09-09-2022 | 10-09-2022 | 12-09-2022 | 12-09-2022 | 13.09.2022 | 13.09.2022 | 13.09.2022 | 14.09.2022 | 14-09-2022 | 14-09-2022 | 15-09-2022 | 18-09-2022 | 19-09-2022 | 21-09-2022 | 22-09-2022 | 22-09-2022 | 23-09-2022 | [53 empty] | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - PLANNING TO LOAD 22.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 22.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 22.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 22.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 22.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 25.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 25.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 30.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 30.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 30.08.2022 | BV INSPECTION COMPLETED - PLANNING TO LOAD 30.08.2022 | HARRISMITH ENROUTE JOHANNESBURG | JOHANNESBURG UNDER GOING TRIP CHECK | DISPATCHING JOHANNESBURG TODAY | TRUCK AT BELA BELA EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE AWAIITNG CLEARANCE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE DISPATCHING HARARE ENROUTE CHIRUNDU | * VEHICLE ENROUTE CHIRUNDU | * VEHICLE AT CHIRUNDU ZIM SIDE | * VEHICLE AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENLTY AT KAPIRI MPOSHE ENROUTE KITWE | * VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT WHISKEY | * VEHICLE CURRENLTY AT WHISKEY DAY 2 | * VEHICLE CURRENLTY AT KANYAKA AWAITING FINAL CLEARANCE | ON SITE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2183 | 1 X CAT330 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | CAT00330EFEK30432 | TBA | FML 2206DSI1614 | VESSEL: MORNING CHAMPION ETA: 27-07-2022 | COD 2022 224266 | JN38KXGP | XVD958GP | ND59565 | 28-06-2022 | OFFLOADED | 17.06.2022 | 28.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 25.06.2022 | 01-08-2022 | 05-08-2022 | 10-08-2022 | 27-08-2022 | 27-08-2022 | 27-08-2022 | 29-08-2022 | 31-08-2022 | 01-09-2022 | 05.09.2022 | 05.09.2022 | 05.09.2022 | 06.09.2022 | 06.09.2022 | 06.09.2022 | 07.09.2022 | 08.09.2022 | 08-09-2022 | 08-09-2022 | 13.09.2022 | 14.09.2022 | 19.09.2022 | 19.09.2022 | 19.09.2022 | 19.09.2022 | [47 empty] | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 13-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 25-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 25-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 27-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 29-07-2022 | BV COMPLETED AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH TO SITE - ESTIMATED DATE OF LOADING 29-07-2022 | HOWICK ENROUTE JOHANNESBURG | JOHANNESBURG UNDERGOING TRIP CHECK | DISPATCHING JNB TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT STANDERTON EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JNB EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JNB AWAITING PERMIT - PLANNING TO DISPATCH THIS AFTERNOON | TRUCK AT JNB AWAITING PERMIT IN ORDER TO DISPATCH | TRUCK AT JNB AWAITING PERMIT IN ORDER TO DISPATCH | TRUCK AT JNB AWAITING PERMIT IN ORDER TO DISPATCH | TRUCK AT JNB AWAITING PERMIT IN ORDER TO DISPATCH | TRUCK AT JNB AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE CURRENTLY AT BELA BELA ENROUTE MUSINA | VEHICLE CURRENTLY AT POLOKWANE ENROUTE MUSINA | VEHICLE CURRENTLY AT POLOKWANE WEIGHBRIDGE WAITING PERMIT | VEHICLE CURRENTLY AT POLOKWANE WEIGHBRIDGE WAITING PERMIT | BEIT BRIDGE RSA SIDE CLEARING | BUBI ENROUTE HARARE | HARARE EN-ROUTE TO CHIRUNDU | DISPATCHING HARARE TODAY | TRUCK AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KAPIRI MPOSHE ENROUTE KITWE | * VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | * VEHCILE CURRENTLY AT WHISKY AWAITING CLEARANCE | * VEHCILE CURRENTLY AT WHISKY AWAITING CLEARANCE - DAY 2 | * VEHCILE CURRENTLY AT WHISKY AWAITING CLEARANCE - DAY 3 | LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2194 | 1 X NEW CAT 140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201251 | CAT00140EW9201251 | E7A54317 | FML 2207DSI1657 | VESSEL: MORNING CHAMPION ETA: 27-07-2022 | COD 2022 252852 | ABN3409 | ACL1499 | ND60529 | 06-08-2022 | OFFLOADED 28-09-2022 | 25-07-2022 | 03.08.2022 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR 03-08-2022 - WAITING CONFIRMATION FROM BV | 27.07.2022 | 31-08-2022 | 06.09.2022 | 08-09-2022 | 09-09-2022 | 10-09-2022 | 10-09-2022 | 14-09-2022 | 14-09-2022 | 16-09-2022 | 19-09-2022 | 20-09-2022 | 20-09-2022 | 20-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 21-09-2022 | 26-09-2022 | 26-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | [53 empty] | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | AWAIITNG VESSEL ARRIVAL ON THE 27/07/2022 | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | * VESSEL CURRENLTY IN AND WORKING - VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 16/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 16/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 22/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 22/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 22/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 22/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 22/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 25/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 25/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 30/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 30/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 30/08/2022 | AWAITING TRUCKS TO RETURN FROM DRC ESTIMATED LOADING DATE THE 30/08/2022 | LOADING TODAY | TRUCK TO DISPATCH TODAY | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE | TRUCK AT MARIAN HILL TOLL EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT HARRISMITH ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK | * VEHICLE DISPATCHING JOHANNESBURG TODAY - ENROUTE MUSINA | * VEHICLE AT BELA BELA ENROUTE MUSINA | * VEHICLE AT BEIT BRIDGE SA SIDE IN QUEUE TO CROSS TO ZIM SIDE | * VEHICLE AT BEIT BRIDGE ZIM SIDE | * VEHICLE DISPATCHING BEITBRIDGE ZIM SIDE - ENROUTE HARARE | * VEHICLE AT HARARE UNDER GOING MAINTENANCE CHECK | DISPATCHING HARARE | CHIRUNDU ZIM SIDE CROSSING TO ZAM SIDE | CHIRUNDU ZAM SIDE AWAITING RELEASE | KABWE EN-ROUTE TO KASUMBALESA | TRUCK AT KASUMBALESA ZAM SIDE AWAITING FINAL CLEARANCE | TRUCK AT KASUMBALESA DRC SIDE AWAITING FINAL CLEARANCE | TRUCK AT KASUMBALESA DRC SIDE AWAITING FINAL CLEARANCE - DAY 3 | TRUCK AT WHISKEY WAITING RELEASE | TRUCK AT WHISKEY WAITING RELEASE - DAY 2 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022 | OFFLOADED 28-09-2022
BA2200 | 1 X CAT D9GC-03B TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | AK400307 | CAT000D9LAK400307 | TNR00102 | FML2208DSI1710 | VESSEL: COURAGEOUS ACE Voy. 0152A ETA: 26-08-2022 | COD 2022 273405 | ZKB404GP | CV71JLGP / DD10RDGP | NA60575 | 09-09-2022 | OFFLOADED 29-09-2022 | 22-08-2022 | 30-08-2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 26.08.2022 | 07.09.2022 | 09-09-2022 | 12-09-2022 | 13.09.2022 | 13.09.2022 | 14.09.2022 | 16.09.2022 | 17.09.2022 | 18.09.2022 | 19.09.2022 | 20.09.2022 | 20.09.2022 | 20.09.2022 | 20.09.2022 | 21.09.2022 | 22-09-2022 | 22-09-2022 | 22-09-2022 | 23-09-2022 | 25-09-2022 | 25-09-2022 | 27-09-2022 | 27-09-2022 | 28-09-2022 | 29-09-2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 28.08.2022 | AWAITING VESSEL ARRIVAL ON THE 26.08.2022 | AWAITING VESSEL ARRIVAL ON THE 26.08.2022 | AWAITING VESSEL ARRIVAL ON THE 26.08.2022 | AWAITING VESSEL ARRIVAL ON THE 26.08.2022 | AWAITING VESSEL ARRIVAL ON THE 26.08.2022 | VESSEL ARRIVED - CURRENTLY DISCHARGING CARGO | UNIT COLLECTED FROM PORT - BV INSPECTION BOOKED FOR 31-08-2022 | UNIT COLLECTED FROM PORT - BV INSPECTION BOOKED FOR 31-08-2022 | UNIT AT OUR FACILITY AND WILL BE LOADED ON THE 06/09/2022 | UNIT AT OUR FACILITY AND WILL BE LOADED ON THE 06/09/2022 | UNIT AT OUR FACILITY AND WILL BE LOADED ON THE 06/09/2022 | * UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE CURRENTLY AT VAN REENEN'S PASS ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT VILLIERS ENROUTE JOHANNESBURG | * VEHICLE CURRENTLY AT JOHANNESBURG WAITING LIMPOPO PERMITS | MOKGOPHANG ENROUTE BEIT BRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING RELEASE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING RELEASE | CHIRUNDU ZIM SIDE CROSSING TO ZAM SIDE | CHIRUNDU ZAM SIDE AWAITING RELEASE | KAFUE EN-ROUTE TO KASUMBALESA | CHINGOLA EN-ROUTE TO KASUMBALESA | TRUCK AT KASUMBALESA AWAITING CLERAANCE | TRUCK AT WHISKEY WAITING DUTIES AND RELEASE | TRUCK AT WHISKEY WAITING DUTIES AND RELEASE - DAY 2 | AT CONNEX LUBUMBASHI - WAITING RELEASE | ON SITE WIATING TO OFFLOAD | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022 | OFFLOADED 29-09-2022
BA2201 | 1 X CAT 325-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00725 | CAT00352LHLW00725 | P4E05150 | FML2208DSI1697 | VESSEL: DONG-A GLAUCOS Voy. 058 ETA: 12-09-2022 | COD 2022 272445 | ND760431 | ND760424 / ND760428 | ND60590 | 17-09-2022 | OFFLOADED 17-10-2022 | 22-08-2022 | 16-09-2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 13/09/2022 | 19/09/2022 | 22/09/2022 | 22/09/2022 | 22/09/2022 | 23-09-2022 | 23-09-2022 | 26-09-2022 | 27-09-2022 | 28-09-2022 | 29-09-2022 | 29-09-2022 | 29-09-2022 | 30.09.2022 | 01.10.2022 | 02.10.2022 | 02.10.2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 10.10.2022 | 11.10.2022 | 12.10.2022 | 13.10.2022 | 15-10-2022 | 17-10-2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | VESSEL IS IN AND WORKING | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 11.09.2022 | AWAITING VESSEL ARRIVAL ON THE 12.09.2022 | VESSEL BERTHED AND IS CURRENTLY WORKING | VESSEL BERTHED AND IS CURRENTLY WORKING | UNIT AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 16-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY 16-09-2022 | DISPATCHING TODAY EN-ROUTE TO BEITBRIDGE | TRUCK AT LADYSMITH-STOPPED DUE TO HEAVY RAINS | TRUCK AT LADYSMITH-AWAITING MPU PERMIT | TRUCK AT ERMELO EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MARBLE HALL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEIT BRIDGE ZIM SIDE | MASVINGO ENROUTE HARARE | HARARE | MAPINGA ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE CLEARING | CHINGOLA ENROUTE KASUMBALESA | CHILIBOMBWE IN QUEUE TO PROCEED TO KASUMBALESA | KASUMBALESA ZAM SIDE - BORDER CLOSED (25KM QUEUE) | KASUMBALESA ZAM SIDE - IN QUEUE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENLTY AT COMEXAS LUBUMBASHI AWAITING RELEASE - DAY 2 | VEHICLE CURRENLTY ON SITE WAITING TO OFFLOAD | OFFLOADED 17-10-2022 | OFFLOADED 17-10-2022 | OFFLOADED 17-10-2022 | OFFLOADED 17-10-2022 | OFFLOADED 17-10-2022 | OFFLOADED 17-10-2022 | OFFLOADED 17-10-2022 | OFFLOADED 17-10-2022
BA2277 | 1 X CAT 352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00734 | CAT00352KHLW00734 | P4E04998 | FML2208DSI1697 | VESSEL: DONG-A GLAUCOS Voy. 058 ETA: 12-09-2022 | COD 2022 272445 | WMN927GP | BG55CXGP / BG37PLGP | ND60594 | 17-09-2022 | OFFLOADED | 22-08-2022 | 16-09-2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 13/09/2022 | 19/09/2022 | 20/09/2022 | 21/09/2022 | 22/09/2022 | 23-09-2022 | 23-09-2022 | 25-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 06.10.2022 | 07.10.2022 | 10.10.2022 | 12.10.2022 | 12.10.2022 | 13.10.2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 11.09.2022 | AWAITING VESSEL ARRIVAL ON THE 12.09.2022 | VESSEL BERTHED AND IS CURRENTLY WORKING | VESSEL BERTHED AND IS CURRENTLY WORKING | UNIT AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 16-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY 16-09-2022 | DISPATCHING TODAY EN-ROUTE TO BEITBRIDGE | TRUCK AT ESCORT-STOPPED DUE TO HEAVY RAINS | TRUCK AT VAN REENEN-STOPPED DUE TO HEAVY RAINS | TRUCK AT BELA BELA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER RSA | TRUCK AT MAKUTI ENROUTE HARARE | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE - BORDER CLOSED DUE TO XENOPHOBIA CASE (25KM QUEUE) | KASUMBALESA ZAM SIDE - BORDER CLOSED (25KM QUEUE) | KASUMBALESA ZAM SIDE - BORDER CLOSED (25KM QUEUE) | KASUMBALESA ZAM SIDE - IN QUEUE | VEHICLE AT WHISKEY AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING DUTIES PAYMENT | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE AT LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2278 | 1 X CAT 352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00733 | CAT00352PHLW00733 | P4E05168 | FML2208DSI1697 | VESSEL: DONG-A GLAUCOS Voy. 058 ETA: 12-09-2022 | COD 2022 272445 | CR84FXGP | WGR358GP / WGR365GP | ND60595 | 17-09-2022 | OFFLOADED | 22-08-2022 | 16-09-2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 13/09/2022 | 19/09/2022 | 20/09/2022 | 21/09/2022 | 22/09/2022 | 23-09-2022 | 23-09-2022 | 25-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 26-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 28-09-2022 | 07.10.2022 | 07.10.2022 | 10.10.2022 | 12.10.2022 | 12.10.2022 | 13.10.2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 11.09.2022 | AWAITING VESSEL ARRIVAL ON THE 12.09.2022 | VESSEL BERTHED AND IS CURRENTLY WORKING | * COLLECTING UNIT FROM PORT TODAY | UNIT AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 16-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY 16-09-2022 | DISPATCHING TODAY EN-ROUTE TO BEITBRIDGE | TRUCK AT ESCORT-STOPPED DUE TO HEAVY RAINS | TRUCK AT VAN REENEN-STOPPED DUE TO HEAVY RAINS | TRUCK AT BELA BELA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER RSA | TRUCK AT MAKUTI ENROUTE HARARE | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE | KASUMBALESA ZAM SIDE - BORDER CLOSED DUE TO XENOPHOBIA CASE (25KM QUEUE) | KASUMBALESA ZAM SIDE - BORDER CLOSED (25KM QUEUE) | KASUMBALESA ZAM SIDE - BORDER CLOSED (25KM QUEUE) | KASUMBALESA ZAM SIDE - IN QUEUE | VEHICLE AT WHISKEY AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING DUTIES PAYMENT | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE AT LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2062 | 1 X NEW CAT 345GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30157 | CAT00345TKEF30157 | NTB10245 | FML2206DSI1609 | VESSEL: MORNING COMPOSER ETA: 30-06-2022 | COD 2022 224266 | KB15LCGP | JM62HNGP / KG03VLGP | ND59569 | TBA | OFFLOADED | 17.06.2022 | 28.06.2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 30.06.2022 | 31/08/2022 | 01-09-2022 | 07.09.2022 | 07.09.2022 | 07.09.2022 | 08.09.2022 | 10-09-2022 | 11-09-2022 | 12-09-2022 | 12-09-2022 | 12-09-2022 | 12-09-2022 | 13.09.2022 | 14.09.2022 | 14-09-2022 | 14-09-2022 | 14-09-2022 | 14-09-2022 | 14-09-2022 | 16-09-2022 | 18-09-2022 | 19-09-2022 | 19-09-2022 | 19-09-2022 | 20-09-2022 | [47 empty] | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 25.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 29.07.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01.08.2022 TO 05.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 16.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 16.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 16.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 16.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 16.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 23.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 23.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 23.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 23.08.2022 | BV INSPECTION COMPLETE - AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 23.08.2022 | AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 25.08.2022 | AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 25.08.2022 | AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 26.08.2022 | AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 30.08.2022 | AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 30.08.2022 | AWAITING VEHCILE TO RETURN FROM DRC - ESTIMATE LOADING DATE 01-09 / 02-09 | LOADED - DISPATCHING TODAY | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE | TRUCK AT JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK TO DISPATCH JOHANNESBURG EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENTLY AT JOHANNESBURG AWAITING PERMIT IN ORDER TO DISPATCH | * VEHICLE DISPATCHING JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT HARARE | CHIRUNDU ZAM SIDE CLEARING | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENTLY AT LUBUMBASHI AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2071 | 1 X NEW CAT 374-07B HYDRAULIC EXCAVATOR - PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10048 | CAT00374TRGM10048 | E4T00561 | FML 2208DSI1695 | VESSEL: DONG-A GLAUCOS Voy. 058 ETA: 12-09-2022 | COD 2022 263435 | BAE5141 | ACM3356 / ACM3357 | ND60592-2 | 20-09-2022 | * OFFLOADED 27.10.2022 | 08-08-2022 | 19-09-2022 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 21/09/2022 | 20/09/2022 | 21/09/2022 | 24-09-2022 | 24-09-2022 | 25-09-2022 | 25-09-2022 | 28-09-2022 | 29-09-2022 | 29-09-2022 | 29-09-2022 | 29-09-2022 | 29-09-2022 | 30.09.2022 | 01.10.2022 | 02.10.2022 | 04.10.2022 | 04.10.2022 | 06.10.2022 | 10.10.2022 | 15-10-2022 | 15-10-2022 | 20-10-2022 | 20-10-2022 | 26.10.2022 | 27.10.2022 | [63 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | VESSEL IS IN AND WORKING | * AWAITING VESSEL ARRIVAL - CURRENT ETA 09.09.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 09.09.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 09.09.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 11.09.2022 | * AWAITING VESSEL ARRIVAL - CURRENT ETA 12.09.2022 | VESSEL BERTHED AND IS CURRENTLY WORKING | * VESSEL BERTHED AND IS CURRENTLY WORKING | COLLECTING FROM PORT TODAY - BV INSPECTION TO BE BOOKED FOR TOMORROW 16-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY 16-09-2022 | BV BOOKED FOR TODAY THE 19/09/2022, AWAITING TRUCK DETAILS AND LOADING DATE | TRUCK WILL LOAD TODAY AND DISPATCH WEDNESDAY THE 21/09/2022 | TRUCK IN JNB UNDER GOING TRIP CHECK | TRUCK IN JNB AWAITING MAIN BODY IN ORDER TO DISPATCH TO BEITBRIDGE | TRUCK IN JNB AWAITING MAIN BODY IN ORDER TO DISPATCH TO BEITBRIDGE | TRUCK IN BEIT BRIDGE RSA SIDE AWAITING MAIN BODY IN ORDER TO START WITH CUSTOMS CLEARANCE | TRUCK IN BEIT BRIDGE RSA SIDE AWAITING MAIN BODY IN ORDER TO START WITH CUSTOMS CLEARANCE | BEIT BRIDGE RSA SIDE CLEARING | SELUKWE ZIM | CHIRUNDU ZAMBIAN SIDE CLEARING | KITWE ENROUTE CHINGOLA | KABWE ENROUTE CHINGOLA | CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY DISPATCHING CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA IN QUEUE | VEHICLE CURRENLTY AT KASUMBALESA ZAM AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM IN QUEUE TO CROSS TO DRC SIDE | VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE - DAY 2 | VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE - DAY 3 | VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE - DAY 4 | CONNEX LUBUMBAHSI WAITING SEAL TO BE REMOVED & RELEASE | CONNEX LUBUMBAHSI WAITING SEAL TO BE REMOVED & RELEASE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 22.10.2022 | ON SITE WAITING TO OFFLOAD | * OFFLOADED 27.10.2022
BA2202 | 1 X CAT 325-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00761 | CAT00352EHLW00761 | P4E05228 | FML2209DSI1733 | VESSEL: TARIFA - VOY. 127 ETA 27.09.2022 | TBA | CR83TPGP | KR05VLGP / KS98MPGP | ND63617 | 05.10.2022 | OFFLOADED 26-10-2022 | 21.09.2022 | 05.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 27-09-2022 | 05.10.2022 | 06.10.2022 | 10.10.2022 | 12-10-2022 | 12-10-2022 | 12-10-2022 | 13-10-2022 | 14-20-2022 | 15-10-2022 | 16-10-2022 | 17-10-2022 | 17-10-2022 | 18-10-2022 | 18-10-2022 | 19-10-2022 | 19-10-2022 | 19-10-2022 | 20-10-2022 | 20-10-2022 | 24.10.2022 | 25.10.2022 | 26.10.2022 | [84 empty] | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 25.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 22.09.2022 | AWAITING VESSEL ARRIVAL ON THE 22.09.2022 | AWAITING VESSEL ARRIVAL ON THE 25.09.2022 | AWAITING VESSEL ARRIVAL ON THE 25.09.2022 | AWAITING VESSEL ARRIVAL ON THE 25.09.2022 | AWAITING VESSEL ARRIVAL ON THE 27.09.2022 | AWAITING VESSEL ARRIVAL ON THE 27.09.2022 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | COLLECTING FROM PORT TODAY - WAITING BV NUMBER IN ORDER TO ARRANGE BV INSPECTION | WAITING BV NUMBER IN ORDER TO ARRANGE BV INSPECTION | WAITING BV NUMBER IN ORDER TO ARRANGE BV INSPECTION | WAITING BV NUMBER IN ORDER TO ARRANGE BV INSPECTION | VEHICLE CURRENTLY AT MOOI RIVER ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT PRETORIA ENROUTE JOHANNESBURG | VEHICLE CURRENTLY DISPATCHING PRETORIA EN-ROUTE TO BEITBRIDGE | VEHICLE CURRENTLY AT LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT MASVINGO EN-ROUTE CHIRUNDU | VEHICLE CURRENTLY AT HARARE | VEHICLE CURRENTLY CHIRUNDU ZIM SIDE CLEARING | VEHICLE CURRENTLY DISPATCHING CHIRUNDU ZAM | VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | OFFLOADED 26-10-2022 | OFFLOADED 26-10-2022
BA2279 | 1 X CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30321 | CAT00345CKEF30321 | NTB10462 | FML2208DSI1691 | VESSEL: DONG-A GLAUCOS Voy. 058 ETA: 12-09-2022 | COD 2022 272445 | WLS011GP | YVB995GP / XTP634GP | ND60596 | 26-09-2022 | OFFLOADED | 22-08-2022 | 16-09-2022 | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED AS SOON AS CARGO IS AVAILABLE | 12-09-2022 | 10.10.2022 | 11.10.2022 | 12.10.2022 | 12.10.2022 | 12.10.2022 | 13.10.2022 | 16-10-2022 | 17-10-2022 | 18-10-2022 | 18-10-2022 | 18-10-2022 | 18-10-2022 | 20-10-2022 | 20-10-2022 | 20-10-2022 | 20-10-2022 | 22.10.2022 | 23.10.2022 | 24.10.2022 | 27.10.2022 | 28.10.2022 | 28-10-2022 | 28-10-2022 | 11.10.2022 | 02.11.2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 05.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 09.09.2022 | AWAITING VESSEL ARRIVAL ON THE 11.09.2022 | AWAITING VESSEL ARRIVAL ON THE 12.09.2022 | VESSEL BERTHED AND IS CURRENTLY WORKING | * COLLECTING UNIT FROM PORT TODAY | UNIT AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW 16-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY 16-09-2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | BV DONE, AWAITING TRUCK TO RETURN FROM DRC TO LOAD ON THE 05.10.2022 | UNIT TO LOAD AND DISPATCH THIS AFTERNOON | VEHICLE LOADED AWARITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWARITING PERMIT IN ORDER TO DISPATCH | VEHICLE AT PIETERMARITZBURG EN-ROUTE TO JOHANNESBURG | VEHICLE AT PRETORIA UNDERGOING TRIP CHECK | VEHICLE AT DISPATCHING PRETORIA EN-ROUTE TO BEITBRIDGE | VEHICLE AT BEITBRIDGE RSA SIDE | VEHICLE AT BEITBRIDGE RSA SIDE | VEHICLE AT MASVINGO ENROUTE HARARE | VEHICLE AT HARARE | VEHICLE AT CHIRUNDU ZAMBIAN SIDE CLEARING | VEHICLE AT CHIRUNDU ZAMBIAN SIDE CLEARING | VEHICLE AT KABWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY WAITING CLEARANCE | * VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING RELEASE | * VEHICLE CURRENLTY AT CONGO EQUIPMENT AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED
BA1997 | 1 X CAR D6GC-01A TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | XPC00597 | CAT000D6EXPC00597 | R6J04480 | FML2208DSI1687 | VESSEL: PAGNA Voy. 17 ETA: 04-09-2022 | COD 2022 273405 | JR76FMGP | KH82PCGP | ND60576 | 26-09-2022 | OFFLOADED 04-11-2022 | 22.09.2022 | 09-09-2022 | BV BOOKED AS SOON AS WE RECEIVED THE BV NUMBER - BOOKING WAS MADE FOR FIRST AVAILABLE DATE | 04.09.2022 | 29-09-2022 | 03.10.2022 | 04.10.2022 | 05.10.2022 | 05.10.2022 | 06.10.2022 | 07.10.2022 | 10.10.2022 | 11.10.2022 | 12.10.2022 | 13-10-2022 | 13-10-2022 | 13-10-2022 | 13-10-2022 | 13-10-2022 | 14-10-2022 | 15-10-2022 | 16-10-2022 | 16-10-2022 | 24.10.2022 | 25.10.2022 | 28.10.2022 | 28-10-2022 | 04-11-2022 | 04-11-2022 | [66 empty] | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 30.08.2022 | AWAITING VESSEL ARRIVAL ON THE 30.08.2022 | AWAITING VESSEL ARRIVAL ON THE 30.08.2022 | AWAITING VESSEL ARRIVAL ON THE 30.08.2022 | AWAITING VESSEL ARRIVAL ON THE 30.08.2022 | AWAITING VESSEL ARRIVAL ON THE 30.08.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | AWAITING VESSEL ARRIVAL ON THE 01.09.2022 | THE VESSEL IS IN AND WORKING | * VESSEL CURRENLY IN & WORKING - VEHICLES PLACED ALONGSIDE TO LOAD UNIT ONCE AVAILABLE | * UNIT TO BE COLLECTED FROM PORT TODAY- AWAITING BV NUMBER IN ORDER OT BOOK INSPECTION | * BV INSPECTION BOOKED FOR FRIDAY 09.09.2022 | * BV INSPECTION BOOKED FOR FRIDAY 09.09.2022 | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING PLANNED FOR 23-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 23-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 23-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 24-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 24-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 26-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 28-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 28-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 30-09-2022 | BV INSPECTION COMPLETED - LOADING PLANNED FOR 30-09-2022 | ESCORT ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | VEHICLE CURRENTLY AT JOHANNESBURG UNDERGOING FINAL TRIP CHECK - TO DISPATCH FOR MUSINA THIS AFTERNOON | MOKOPANE ENROUTE MUSINA | VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT KAROI EN ROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU CUSTOMS | VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE CURRENTLY AT KASUMBALESA ON BREAKDOWN | VEHICLE CURRENTLY AT KASUMBALESA ON BREAKDOWN | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE - DAY 3 | * VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | TRUCK AT CONNEX AWAITING CUSTOMS RELEASE | TRUCK AT CONNEX AWAITING CUSTOMS RELEASE | CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 04-11-2022
BA2284 | CAT330GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK30675 | CAT00330TFEK30675 | E7A55013 | FML 2209DSI1734 | VESSEL: TARIFA - VOY. 127 ETA 27.09.2022 | COD 2022 296959 | JF92ZTGP | BX45RWGP | ND63624 | 06-10-2022 | OFFLOADED 05-11-2022 | 22.09.2022 | 03.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 27-09-2022 | 13.10.2022 | MIDDELBURG 14-10-2022 | MIDDELBURG 14-10-2022 | 14-10-2022 | 15-10-2022 | 15-10-2022 | 15-10-2022 | 16-10-2022 | 17-10-2022 | 17-10-2022 | 18-10-2022 | 18-10-2022 | 18-10-2022 | 18-10-2022 | 20-10-2022 | 20-10-2022 | 20-10-2022 | 20-10-2022 | 24.10.2022 | 26-10-2022 | 26-10-2022 | 01.11.2022 | 02.11.2022 | 02.11.2022 | 05-11-2022 | [72 empty] | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 25.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 27.09.2022 | AWAITING VESSEL ARRIVAL ON THE 27.09.2022 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR MONDAY 03-10-2022 | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR MONDAY 03-10-2022 | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | VEHICLE LOADED AWARITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWARITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH TODAY | VEHICLE TO DISPATCH DURBAN TODAY EN-ROUTE TO BEITBRIDGE | VEHICLE AT MIDDELBURG | VEHICLE AT HARARE | VEHICLE AT CHIRUNDU ZAMBIAN SIDE CLEARING | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE DISPATCHING LUSAKA | VEHICLE CHILLIABOMBWE IN QUEUE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY ON BREAKDOWN - WAIITNG MECHANIC TO ASSIST | * VEHICLE DISPATCHING WHISKEY EN-ROUTE TO CONNEX LUBUMBASHI | ON SITE AWAITING TO OFFLOAD | CONNEX AFRICA AWAIITNG RELEASE TO PROCEED TO SITE | CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 05-11-2022
BA2019 | 1 X CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F602156 | CAT00745C3F602156 | TXW06661 | FML2209DSI1743 | VESSEL: HOEGH ST. PETERSBURG Voy. 77 ETA: 04-10-2022 | COD 2022 287207 | ND705348 | ND476150 | ND63618 | 20-10-2022 | OFFLOADED 07-11-2022 | 09.09.2022 | 19-10-2022 | BV NUMBER RECEIVED - BV TO BE BOOKED AS SOON AS UNIT IS AT OUR FACILITY | 06.10.2022 | 20-10-2022 | MIDDELBURG 21-10-2022 | 22.10.2022 | 22.10.2022 | 23.10.2022 | 24.10.2022 | 26.10.2022 | 27.10.2022 | 27.10.2022 | 28.10.2022 | 31.10.2022 | 31.10.2022 | 31.10.2022 | 31.10.2022 | 31.10.2022 | 01.11.2022 | 01.11.2022 | 01.11.2022 | 01.11.2022 | 03.11.2022 | 03.11.2022 | 04-11-2022 | 04-11-2022 | 04-11-2022 | 07-11-2022 | [87 empty] | WAITING VESSEL ARRIVAL - ETA DURBAN 04.10.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 04.10.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 04.10.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 04.10.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 25.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 25.09.2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 05-10-2022 | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - UNABLE TO ACCESS PORT DUE TO STRIKE ACTION | VESSEL CURRENLTY IN AND WORKING - PLANNING TO COLLECT TOMMROW THE 14/10/2022 | COLLECTING UNIT FROM PORT TODAY - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | UNIT TO BE COLLECTED FORM PORT - TRANSNET STILL STRIKING | UNIT TO BE COLLECTED FORM PORT - TRANSNET STILL STRIKING | UNIT COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TODAY 19-10-2022 | PIETERMARITZBURG ENROUTE JOHANNESBURG | MIDDULBURG ENOUTE BEIT BRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | * VEHICLE CURRENLTY AT KABOMA ENROUTE HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHILLIALABOMBWE IN QUE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING FINAL RELEASE | ON SITE WIAITING TO OFFLOAD | OFFLOADED 07-11-2022 | OFFLOADED 07-11-2022
BA2297 | 1 X CAT D9 TRACK TYPE TRACKOR - PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | AK400520 | CAT000D6AK400520 | TNR00315 | FML 2209DSI1738 | VESSEL: LAVENDER ACE Voy. 0086A ETA DURBAN: 21-09-2022 | COD 2022 287210 | AGB6601ZM | AAR7011T / AAR7067T | ND63614-2 | 010-10-2022 | OFFLOADED 09-11-2022 | 09.09.2022 | 28.09.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED AS SOON AS THE UNIT IS AVAILABLE | 21-09-2022 | 30-09-2022 | 03.10.2022 | 04.10.2022 | 04.10.2022 | 04.10.2022 | 05.10.2022 | 06.10.2022 | 07.10.2022 | 09.10.2022 | 10.10.2022 | 10.10.2022 | 11.10.2022 | 13-10-2022 | 14-10-2022 | 14-10-2022 | 15-10-2022 | 15-10-2022 | 17-10-2022 | 20-10-2022 | 26.10.2022 | 27.10.2022 | 07-11-2022 | 07-11-2022 | 08-11-2022 | 09-11-2022 | [86 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | UNIT AT OUR FACILITY - BV INSPECTION TO BE BOOKED FOR TOMORROW - LOADING PLAN TO BE ADVISE | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING PLAN TO BE ADVISE | UNIT AT OUR FACILITY - BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW & FRIDAY | LOADING TOMORROW | LOADING TODAY | JOHANNESBURG ENROUTE MUSINA | JOHANNESBURG AWAITING LIMPOPO PERMIT | AT BEITBRIDGE SA AWAITING CLEARANCE | VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUDNU ZAM SIDE | VEHICLE CURRENTLY AT CHIRUDNU ZAM SIDE | VEHICLE CURRENTLY AT CHIRUDNU ZAM SIDE | VEHICLE CURRENTLY AT DISPATCHING CHIRUDNU | VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHILLILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHILLILABOMBWE IN THE QUEUE TO PROCEED TO KASUMBALESA | VEHICLE CURRENTLY AT CHILLILABOMBWE IN THE QUEUE TO PROCEED TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA DRC AWAITING CLEARANCE | * VEHICLE DISPATCHING KASUMBALESA ENROUTE WHISKEY | * VEHICLE KASUMBALESA IN QUE TO WHISKEY | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE - DAY 5 | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE - DAY 6 (HORSE DETAILS NEEDS TO BE AMENDED) | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE - DAY 7 (HORSE DETAILS NEEDS TO BE AMENDED) | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE - DAY 8(HORSE DETAILS NEEDS TO BE AMENDED) | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE - DAY 9 WAITING SEAL & SEGUCE DOCS | TO DISPATCH WHISKEY FOR OFFLOADING | KANYAKA | ON SITE WAITING TO OFFLOAD | OFFLOADED 09-11-2022 | OFFLOADED 09-11-2022
BA1772 | 1 X NEW CAT C4.4 ENGINE | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 44627413 | N/A | N/A | FML2208DSI1715 | VESSEL: MSC CORUNA Voy. NY232A - TRANSHIPMENT VESSEL: MSC DOMITILLE ETA: 20-09-2022 | COD 2022 271699 | CS04WTGP | VSR119GP / VST289GP | POR5426 | 07-10-2022 | * OFFLOADED 12.11.2022 | 19-08-2022 | 06/10/2022 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 21/09/2022 | 07/10/2022 | 08/10/2022 | 10/10/2022 | GRB 07-10-2022 | GRB DSP 08-10-2022 | MARTINS DRIFT 08-10-2022 | MARTINSDRIFT DSP 09-10-2022 | FRANCISTOWN 09-10-2022 | FRANCISTOWN DSP 10-10-2022 | KAZUNGULA BW ARR 11-10-2022 | KAZUNGULA BW DSP 12-10-2022 | KAZUNGULA ZM ARR 12-10-2022 | KAZUNGULA ZM DSP 13-10-2022 | 16-10-2022 | 17-10-2022 | 17-10-2022 | 19-10-2022 | 22.10.2022 | 24.10.2022 | 25-10-2022 | 25-10-2022 | 06-11-2022 | 06-11-2022 | 12.11.2022 | 12.11.2022 | [63 empty] | AWAIITNG VESSEL ARRIVAL ON THE 25/08/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/08/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/08/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/08/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/08/2022 | AWAIITNG VESSEL ARRIVAL ON THE 25/08/2022 | AWAIITNG VESSEL ARRIVAL ON THE 12-09-2022 | AWAIITNG VESSEL ARRIVAL ON THE 12-09-2022 | AWAIITNG VESSEL ARRIVAL ON THE 12-09-2022 | AWAIITNG VESSEL ARRIVAL ON THE 12-09-2022 | AWAIITNG VESSEL ARRIVAL ON THE 12-09-2022 | AWAIITNG VESSEL ARRIVAL ON THE 12-09-2022 | AWAIITNG VESSEL ARRIVAL ON THE 15/09/2022 | AWAIITNG VESSEL ARRIVAL ON THE 15/09/2022 | AWAIITNG VESSEL ARRIVAL ON THE 15/09/2022 | AWAIITNG VESSEL ARRIVAL ON THE 15/09/2022 | AWAIITNG VESSEL ARRIVAL ON THE 15/09/2022 | AWAIITNG VESSEL ARRIVAL ON THE 15/09/2022 | AWAIITNG VESSEL ARRIVAL ON THE 15.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 18.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 18.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 18.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 18.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 19.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 18.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 20.09.2022 | VESSEL WILL BERTH TODAY THE 20/09/2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | CONTAINER AT UNPACK FACILITY - WAITING UNPACK | COLLECTING FROM UNPACK DEPOT TODAY | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING PLANNED FOR NEXT WEEK | BV INSPECTION COMPLETED - LOADING PLANNED FOR NEXT WEEK | AT TRANSPORTERS DEPORT AWAIITNG CONSOLE VEHICLE - LOADING DATE TO BE CONFIRMED | AT TRANSPORTERS DEPORT AWAIITNG CONSOLE VEHICLE - LOADING DATE TO BE CONFIRMED | AT TRANSPORTERS DEPORT AWAIITNG CONSOLE VEHICLE - LOADING DATE TO BE CONFIRMED | AT TRANSPORTERS DEPORT AWAIITNG CONSOLE VEHICLE - LOADING DATE TO BE CONFIRMED | AT TRANSPORTERS DEPORT AWAIITNG CONSOLE VEHICLE - LOADING DATE TO BE CONFIRMED | TRUCK AT JNB AND WILL DISPATCH TO THE BORDER TODAY | TRUCK AT KAZANGULA BOTSWANNA SIDE AWAITING CLEARANCE | TRUCK AT KAZANGULA BOTSWANNA SIDE AWAITING CLEARANCE | TRUCK AT KAZANGULA BOTSWANNA SIDE AWAITING FINAL CLEARANCE | TRUCK AT LINGSTONE ENROUTE KASUMBALESA | LUSAKA ENROUTE KASUMBALESA | NDOLA ENROUTE KASUMBALESA | KITWE ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | CHILLIABOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE FROM CUSTOMS AS THIS IS AN CONSOLIDATION TRUCK | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE FROM CUSTOMS AS THIS IS AN CONSOLIDATION TRUCK | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE FROM CUSTOMS AS THIS IS AN CONSOLIDATION TRUCK | * VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE FROM CUSTOMS AS THIS IS AN CONSOLIDATION TRUCK | * VEHICLE CURRENLTY AT IN LUBUMBASHI - THIS IS AN CONSOLIDATION TRUCK | * VEHICLE CURRENLTY IN LUBUMBASHI - THIS IS AN CONSOLIDATION TRUCK | * VEHICLE CURRENLTY IN LUBUMBASHI - THIS IS AN CONSOLIDATION TRUCK | * VEHICLE CURRENLTY IN LUBUMBASHI - THIS IS AN CONSOLIDATION TRUCK | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022
BA2285 | CAT330GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK30676 | CAT00330PFEK30676 | E7A54999 | FML 2209DSI1734 | VESSEL: TARIFA - VOY. 127 ETA 27.09.2022 | COD 2022 296959 | ALC9531 | ACZ7653T | ND63622 | 13-10-2022 | * OFFLOADED 14.11.2022 | 22.09.2022 | 03.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 27-09-2022 | 14-10-2022 | 15-10-2022 | 21-10-2022 | 23.10.2022 | 23.10.2022 | 24.10.2022 | 25.10.2022 | 26.10.2022 | 26-10-2022 | 26-10-2022 | 27.10.2022 | 28.10.2022 | 29-10-2022 | 29-10-2022 | 30-10-2022 | 30-10-2022 | 01.11.2022 | 03-11-2022 | 04-11-2022 | 09-11-2022 | 09-11-2022 | 13.11.2022 | 13.11.2022 | 14.11.2022 | 14.11.2022 | [72 empty] | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 25.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 27.09.2022 | AWAITING VESSEL ARRIVAL ON THE 27.09.2022 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR MONDAY 03-10-2022 | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR MONDAY 03-10-2022 | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | TRUCK TO LOAD TODAY AND DISPATCH ON MONDAY THE 17/10/2022 | TRUCK TO LOAD TODAY AND DISPATCH ON MONDAY THE 17/10/2022 | VEHICLE CURRENTLY AT JOHANNESBURG | VEHICLE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHICLE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHICLE DISPATCHING JOHANNESBURG TODAY | VEHICLE DISPATCHED JOHANNESBURG ENROUTE MUSIAN | * VEHICLE CURRENTLY AT PRETORIA ENROUTE BEITBRIDGE | * VEHICLE CURRENLTY AT RUNDE ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENLTY AT KITWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KITWE ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT KITWE ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT KITWE ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT CHAMBISI ENROUTE KASUBMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE IN QUEUE TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY - DAY 1 | * VEHICLE CURRENLTY AT WHISKEY - DAY 2 | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD
BA2315 | 1 X CAT 140K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZL20890 | CAT0140KTSZL20890 | TX712430 | FML 2209DSI1745 | VESSEL: TARIFA Voy. 127 ETA DURBAN: 27-09-2022 | COD 2022 296949 | ABQ6861 | ABJ8174 | ND63621 | 06-10-2022 | * OFFLOADED 14.11.2022 | 22.09.2022 | 03.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 27-09-2022 | 13-10-2022 | 15-10-2022 | 20-10-2022 | 20-10-2022 | 23.10.2022 | 24.10.2022 | 25.10.2022 | 26.10.2022 | 27.10.2022 | 28-10-2022 | 29-10-2022 | 29-10-2022 | 31.10.2022 | 31.10.2022 | 31.10.2022 | 31.10.2022 | 01.11.2022 | 02.11.2022 | 02.11.2022 | 06-07-2022 | 06-07-2022 | 13.11.2022 | 14.11.2022 | 14.11.2022 | 14.11.2022 | [90 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-09-2022 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | COLLECTING FROM PORT TODAY - BV INSPECTION TO BE BOOKED FOR MONDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR MONDAY 03-10-2022 | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | VEHICLE LOADED AWARITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWARITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | HOWICK ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT JOHANNESBURG | VEHICLE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHICLE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHICLE CURRENTLY AT BELA BELA ENROUTE BEIT BRIDGE | VEHICLE CURRENTLY AT MUSIAN | * VEHICLE CURRENTLY AT AT BEITBRIDGE - CROSSING TO ZIM SIDE | * VEHICLE CURRENTLY AT BUBI ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT HARARE | * VEHICLE CURRENTLY AT KAROI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE CLEARING | * VEHICLE CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE IN QUEUE TO CROSS TO DRC | * VEHICLE CURRENTLY AT WHISKEY | * VEHICLE CURRENTLY AT WHISKEY - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY - DAY 5 | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD
BA2026 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F800330 | CAT00740E3F800330 | TXY07298 | FML2208DSI1724 | VESSEL: HOEGH TROOPER Voy. 197 ETA: 20-09-2022 | COD 2022 305650 | ND730794 | ND443606 | ND63608 | 24-10-2022 | OFFLOADED 21-11-2022 | 05.10.2022 | 06.10.2022 | BV NUMBER RECEIVED AND INSPECTION COMPLETED | 22/09/2022 | 31-10-2022 | 02.11.2022 | 02.11.2022 | 03.11.2022 | 03-11-2022 | 03-11-2022 | 05-11-2022 | 05-11-2022 | 06-11-2022 | 07-11-2022 | 07-11-2022 | 07-11-2022 | 08-11-2022 | 08-11-2022 | 08-11-2022 | 09-11-2022 | 09-10-2022 | 10-11-2022 | 10-11-2022 | 13.11.2022 | 14.11.2022 | 17.11.2022 | 18-11-2022 | 18-11-2022 | 21-11-2022 | [72 empty] | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAIITNG VESSEL ARRIVAL ON THE 15.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 20.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 20.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | NATRANS DEPO AWAITING BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | UNIT AT OUR DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | UNIT AT OUR DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | TRUCK AT KASUMBALESA BORDER AWAITING TO RETURN TO LOAD BA2026 | TRUCK AT KASUMBALESA BORDER AWAITING TO RETURN TO LOAD BA2026 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2026 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2026 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2026 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2026 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2026 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2026 | TRUCK CURRENTLY RETURNING TO LOAD BA2026 | TRUCK CURRENTLY RETURNING TO LOAD BA2026 | TRUCK CURRENTLY RETURNING TO LOAD BA2026 | LOADING MONDAY 31-10-2022 | LOADING MONDAY 31-10-2022 | LOADING MONDAY 31-10-2022 | * VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | DISPATCHING DURBAN TODAY | TRUCK AT DUNDEE EN-ROUTE TO BEITBRIDGE | TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | BEIT BRIDGE RSA SIDE CLEARING | CHINOYI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | KABWE ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE - DAY 3 | * VEHICLE CURRENTLY AT KANYAKA AWAITING FINAL RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 21-11-2022 | OFFLOADED 21-11-2022
BA2027 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F800331 | CAT00740C3F800331 | TXY07300 | FML2208DSI1725 | VESSEL: HOEGH TROOPER Voy. 197 ETA: 20-09-2022 | COD 2022 305650 | ND760431 | ND760424 / ND760428 | ND63609 | 25-11-2022 | OFFLOADED 21-11-2022 | 05.10.2022 | 06.10.2022 | BV NUMBER RECEIVED AND INSPECTION COMPLETED | 22/09/2022 | 02.11.2022 | MIDDELBURG 03-11-2022 | MIDDELBURG 04-11-2022 | 04-11-2022 | 05-11-2022 | 05-11-2022 | 07-11-2022 | 08-11-2022 | 09-11-2022 | 10-11-2022 | 10-11-2022 | 10-11-2022 | 11.11.2022 | 11.11.2022 | 12.11.2022 | 12.11.2022 | 13.11.2022 | 13.11.2022 | 15.11.2022 | 15.11.2022 | 16.11.2022 | 19-11-2022 | 19-11-2022 | 21-11-2022 | 21-11-2022 | [72 empty] | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAITING VESSEL ARRIVAL ETA DURBAN PORT 15-09-2022 | AWAIITNG VESSEL ARRIVAL ON THE 15.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | AWAIITNG VESSEL ARRIVAL ON THE 22.09.2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | NATRANS DEPO AWAITING BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | NATRANS DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | UNIT AT OUR DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | UNIT AT OUR DEPO AWAITING BV NUMBER IN ORDER TO DO THE BV INSPECTION | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | TRUCK AT KASUMBALESA BORDER AWAITING TO RETURN TO LOAD BA2027 | TRUCK AT KASUMBALESA BORDER AWAITING TO RETURN TO LOAD BA2027 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2027 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2027 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2027 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2027 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2027 | TRUCK AT LUBUMBASHI AWAITING TO RETURN TO LOAD BA2027 | LOADING MONDAY 24-10-2022 | LOADING MONDAY 24-10-2022 | LOADING MONDAY 31-10-2022 | LOADING MONDAY 31-10-2022 | LOADING MONDAY 31-10-2022 | LOADING MONDAY 31-10-2022 | LOADING MONDAY 03-11-2022 | LOADING MONDAY 03-11-2022 | LOADED AWAITING PERMIT IN ORDER TO DISPATCH | LOADED AWAITING PERMIT IN ORDER TO DISPATCH | TRUCK AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE | MIDDLEBURG ENROUTE MUSINA | BEIT BRIDGE ZIM SIDE | MVUMA ENROUTE HARARE | HARARE | MAPINGA ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENTLY AT CHILILABOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT CHILILABOMBWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE - DAY 3 | CONNEX LUBUMBASHI - WAITNG FINAL CLEARANCE AND RELEASE | OFFLOADED 21-11-2022 | OFFLOADED 21-11-2022
BA2134 | 1 X NEW CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KGX00372 | CAT000D8CKGX00372 | TXJ02291 | FML 2209DSI1767 | VESSEL: STRAITS CHALLENGER Voy. 261 - Transhipment Vessel: Daedalus Leader Voy. 101 ETA: 22-10-2022 | COD 2022 302829 | ND570587 | ND702944 | ND63644 | 14-11-2022 | * OFFLOADED 05.12.2022 | 14.10.2022 | 28.10.2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 21.10.2022 | 15.11.2022 | 16.11.2022 | 16.11.2022 | 16.11.2022 | 16.11.2022 | 17.11.2022 | 19-11-2022 | 19-11-2022 | 20-11-2022 | 21-11-2022 | 22-11-2022 | 22-11-2022 | 23-11-2022 | 23-11-2022 | 24-11-2022 | 25-11-2022 | 26-11-2022 | 26-11-2022 | 28-11-2022 | 29-11-2022 | 29-11-2022 | 02.12.2022 | 02.12.2022 | 03.12.2022 | 05.12.2022 | [104 empty] | AWAITING VESSEL ARRIVAL ON THE 17.10.2022 | AWAITING VESSEL ARRIVAL ON THE 17.10.2022 | AWAITING VESSEL ARRIVAL ON THE 17.10.2022 | AWAITING VESSEL ARRIVAL ON THE 19.10.2022 | AWAITING VESSEL ARRIVAL ON THE 19.10.2022 | AWAITING VESSEL ARRIVAL ON THE 19.10.2022 | AWAITING VESSEL ARRIVAL ON THE 19.10.2022 | AWAITING VESSEL ARRIVAL ON THE 22.10.2022 | AWAITING VESSEL ARRIVAL ON THE 22.10.2022 | * UNIT TO BE COLLECTED FROM PORT TODAY | * UNIT AT BONDED FACILTIY | * UNIT AT BONDED FACILTIY | * UNIT AT BONDED FACILTIY - BV INSPECTION TO BE BOOKED FOR TOMOROOW 28-10-2022 - LOADING PLANNED FOR NEXT WEEK | * UNIT AT BONDED FACILTIY - LOADING DATE TO BE CONFIRMED | * UNIT AT BONDED FACILTIY - LOADING DATE TO BE CONFIRMED | * UNIT AT BONDED FACILTIY - LOADING DATE TO BE CONFIRMED | * UNIT AT BONDED FACILTIY - LOADING DATE TO BE CONFIRMED | * UNIT AT BONDED FACILTIY - LOADING DATE TO BE CONFIRMED | * UNIT AT BONDED FACILTIY - LOADING DATE TO BE CONFIRMED | * UNIT AT BONDED FACILTIY - LOADING DATE TO BE CONFIRMED | * UNIT AT BONDED FACILTIY - LOADING PLANNED FOR 11-11-2022 | * UNIT AT BONDED FACILTIY - LOADING PLANNED FOR 11-11-2022 | * UNIT AT BONDED FACILTIY - LOADING PLANNED FOR 11-11-2022 | * UNIT AT BONDED FACILTIY - LOADING PLANNED FOR 15-11-2022 | * UNIT AT BONDED FACILTIY - LOADING PLANNED FOR 15-11-2022 | * UNIT AT BONDED FACILTIY - LOADING PLANNED FOR 15-11-2022 | VEHICLE CURRENLTY AT MIDDLEBURG AWAIITNG PERMIT | VEHICLE CURRENLTY AT MIDDLEBURG AWAIITNG PERMIT | VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | KAROI ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE | DISPATCHED CHIRUNDU ENROUTE KASUMBALESA | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA AWAIITNG RELEASE | TRUCK AT WHISKEY AWAITING DOCUMENTS | TRUCK AT WHISKEY AWAITING DOCUMENTS | TRUCK AT WHISKEY AWAITING SEGUCE AND SYDONIA DOCUMENTS | TRUCK AT WHISKEY AWAITING SEGUCE AND SYDONIA DOCUMENTS DAY 5 | * ON SITE WAITING TO OFFLOAD | * ON SITE WAITING TO OFFLOAD | * OFFLOADED 05.12.2022
BA2286 | CAT 930K WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | P3K01293 | CAT0930KHP3K01293 | 45017035 | FML 2209DSI1766 | VESSEL: TARIFA - VOY. 127 ETA 27.09.2022 | COD 2022 302826 | NU112272 | ND629383 | ND63627 | 25-11-2022 | * OFFLOADED 06.12.2022 | 30-09-2022 | 19-10-2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 10.10.2022 | 07-11-2022 | MIDDELBURG 08-11-2022 | MIDDELBURG 09-11-2022 | 09-11-2022 | 10.11.2022 | 11.11.2022 | 13.11.2022 | 14.11.2022 | 15.11.2022 | 16.11.2022 | 17.11.2022 | 17.11.2022 | 17.11.2022 | 18.11.2022 | 18.11.2022 | 18.11.2022 | 18-11-2022 | 18-11-2022 | 18-11-2022 | 27-11-2022 | 28-11-2022 | 05.12.2022 | 05.12.2022 | 06.12.2022 | 06.12.2022 | [104 empty] | MACHINE IN PORT AND CAN NOT BE COLLECTED DUE TO STRIKE ACTION | MACHINE IN PORT AND WILL BE COLLECTED TODAY | MACHINE AT OUR FACILITY AWAITING BV AND LOADING DATE | MACHINE AT OUR FACILITY AWAITING LOADING DATE - BV INSPECTION TO BE BOOKED NEXT WEEK | MACHINE AT OUR FACILITY AWAITING LOADING DATE - BV INSPECTION TO BE BOOKED FOR TEUSDAY 18-10-2022 | MACHINE AT OUR FACILITY AWAITING LOADING DATE - BV INSPECTION BOOKED FOR 19-10-2022 | MACHINE AT OUR FACILITY AWAITING LOADING DATE - BV INSPECTION BOOKED FOR 19-10-2022 | MACHINE AT OUR FACILITY AWAITING LOADING DATE - BV INSPECTION COMPLETED | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - LOADING WEDNESDAY 26-10-2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 31.10.2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 31.10.2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 31.10.2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 01.11.2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 01.11.2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 02.11.2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 02.11.2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 04.11.2022 | MACHINE AT OUR FACILITY - BV INSPECTION COMPLETED - PLANNING TO LOAD 04.11.2022 | LOADING TODAY TO DISPATCH MONDAY | WAITING PERMIT, DISPATCHING TODAY | CATO RIDGE ENROUTE JOHANNESBURG | MIDDELBURG | MUSINA TO PROCEED TO BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | * VEHCILE CURRENLTY AT MASVINGO ENROUTE HARARE | * VEHCILE CURRENLTY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENTLY AT MVUMA ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT MVUMA ENROUTE CHIRUNDU | * VEHILCE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE - DAY 3 | COLLECTED FROM PORT YESTERDAY - BV INSPECTION BOOKED FOR TODAY | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE - DAY 5 | * VEHILCE CURRENTLY AT WHISKEY AWAIITNG RELEASE | * VEHILCE CURRENTLY AT WHISKEY AWAITING RELEASE DAY 8 IN DRC | * VEHILCE CURRENTLY AT WHISKEY AWAITING RELEASE DAY 9 IN DRC | * VEHILCE CURRENTLY AT WHISKEY AWAITING SYNDONIA AND SEGUCE DOCUMENTS DAY 10 IN DRC | * VEHILCE CURRENTLY AT WHISKEY AWAITING SYNDONIA AND SEGUCE DOCUMENTS DAY 12 IN DRC | * VEHILCE CURRENTLY AT WHISKEY AWAITING SYNDONIA AND SEGUCE DOCUMENTS DAY 14 IN DRC | * VEHILCE CURRENTLY AT WHISKEY AWAITING SYNDONIA AND SEGUCE DOCUMENTS DAY 14 IN DRC | * OFFLOADED 06.12.2022
BA2285 | CAT330GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK30676 | CAT00330PFEK30676 | E7A54999 | FML 2209DSI1734 | VESSEL: TARIFA - VOY. 127 ETA 27.09.2022 | COD 2022 296959 | ALC9531 | ACZ7653T | ND63622 | 13-10-2022 | * OFFLOADED 14.11.2022 | 22.09.2022 | 03.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 27-09-2022 | 14-10-2022 | 15-10-2022 | 21-10-2022 | 23.10.2022 | 23.10.2022 | 24.10.2022 | 25.10.2022 | 26.10.2022 | 26-10-2022 | 26-10-2022 | 27.10.2022 | 28.10.2022 | 29-10-2022 | 29-10-2022 | 30-10-2022 | 30-10-2022 | 01.11.2022 | 03-11-2022 | 04-11-2022 | 09-11-2022 | 09-11-2022 | 13.11.2022 | 13.11.2022 | 14.11.2022 | 14.11.2022 | [72 empty] | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 21.09.2022 | AWAITING VESSEL ARRIVAL ON THE 25.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 26.09.2022 | AWAITING VESSEL ARRIVAL ON THE 27.09.2022 | AWAITING VESSEL ARRIVAL ON THE 27.09.2022 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR MONDAY 03-10-2022 | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR MONDAY 03-10-2022 | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | TRUCK TO LOAD TODAY AND DISPATCH ON MONDAY THE 17/10/2022 | TRUCK TO LOAD TODAY AND DISPATCH ON MONDAY THE 17/10/2022 | VEHICLE CURRENTLY AT JOHANNESBURG | VEHICLE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHICLE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHICLE DISPATCHING JOHANNESBURG TODAY | VEHICLE DISPATCHED JOHANNESBURG ENROUTE MUSIAN | * VEHICLE CURRENTLY AT PRETORIA ENROUTE BEITBRIDGE | * VEHICLE CURRENLTY AT RUNDE ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENLTY AT KITWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KITWE ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT KITWE ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT KITWE ATTENDING TO MINOR BREAKDOWN | * VEHICLE CURRENLTY AT CHAMBISI ENROUTE KASUBMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE IN QUEUE TO CROSS TO DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY - DAY 1 | * VEHICLE CURRENLTY AT WHISKEY - DAY 2 | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | COLLECTED FROM PORT YESTERDAY - BV INSPECTION BOOKED FOR TODAY | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022
BA2300 | 1 X CAT 966-14A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EL900320 | CAT00966CEL900320 | NTB11642 | FML 2209DSI1746 | VESSEL: GLOVIS SONIC Voy. 037 ETA DURBAN: 12-10-2022 | COD 2022 296944 | KG17GNGP | KHM039MP | ND63626 | 31-10-2022 | OFFLOADED | 22-09-2022 | 20-10-2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 12-10-2022 | 03.11.2022 | MIDDELBURG 03-11-2022 | MIDDELBURG 07-11-2022 | 07-11-2022 | 08-11-2022 | 08-11-2022 | 13.11.2022 | 14.11.2022 | 15.11.2022 | 15.11.2022 | 15.11.2022 | 16.11.2022 | 17.11.2022 | 18.11.2022 | 18.11.2022 | 18-11-2022 | 18-11-2022 | 19-11-2022 | 19-11-2022 | 22-11-2022 | 22-11-2022 | 30-11-2022 | 30-11-2022 | 30-11-2022 | 01-12-2022 | [90 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 12-10-2022 | PLANNING TO COLLECT FROM PORT TODAY | VESSEL IS IN BUT NOT WORKING, TRUCK ON STANDBY TO COLLECT | VESSEL IS IN AND WORKING, | UNIT TO BE COLLECTED FORM PORT - TRANSNET STILL STRIKING | UNIT TO BE COLLECTED FORM PORT - TRANSNET STILL STRIKING | OUR FACILITY - BV INSPOECTION TO BE BOOKED FOR TOMORROW 20-10-2022 | OUR FACILITY - BV INSPOECTION TO BE BOOKED FOR TODAY 20-10-2022 | OUR FACILITY - BV INSPOECTION COMPLETED - LOADING DATE TO BE CONFIRM | OUR FACILITY - BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRM | OUR FACILITY - BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRM | OUR FACILITY - BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRM | OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 01-11-2022 | OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 01-11-2022 | OUR FACILITY - BV INSPECTION COMPLETED - LOADING PLANNED FOR 03-11-2022 | TRUCK TO LOAD TODAY AND DISPATCH ONCE PERMIT IS RECEIVED | TRUCK TO LOAD TODAY AND DISPATCH ONCE PERMIT IS RECEIVED | TRUCK TO DISPATCH DURBAN TODAY EN-ROUTE TO BEIT BRIDGE BORDER | MIDDELBURG ENROUTE MUSINA | MIDDELBURG WAITING LIMPOPO PERMITS | MUSINA TO PROCEED TO BEIT BRIDGE FOR CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHILCE CURRENTLY AT CHIRUNDU ZAM SIDE WAITING CLEARANCE | * VEHILCE CURRENTLY AT CHIRUNDU ZAM SIDE WAITING CLEARANCE | * VEHILCE CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHILCE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE | * VEHILCE CURRENTLY AT WHISKEY - DAY 1 | * OFFLOADED 14.11.2022 | * VEHILCE CURRENTLY AT WHISKEY - DAY 4 | * VEHILCE CURRENTLY AT CONNEX LUBUMBASHI AWAITING DUTIES TO BE PAID | * VEHILCE CURRENTLY AT CONNEX LUBUMBASHI AWAITING DUTIES TO BE PAID DAY 8 IN DRC | * VEHILCE CURRENTLY AT CE AWAITING TO OFFLOAD DAY 9 IN DRC | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2315 | 1 X CAT 140K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZL20890 | CAT0140KTSZL20890 | TX712430 | FML 2209DSI1745 | VESSEL: TARIFA Voy. 127 ETA DURBAN: 27-09-2022 | COD 2022 296949 | ABQ6861 | ABJ8174 | ND63621 | 06-10-2022 | * OFFLOADED 14.11.2022 | 22.09.2022 | 03.10.2022 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED ONCE UNIT IS AVAILABLE | 27-09-2022 | 13-10-2022 | 15-10-2022 | 20-10-2022 | 20-10-2022 | 23.10.2022 | 24.10.2022 | 25.10.2022 | 26.10.2022 | 27.10.2022 | 28-10-2022 | 29-10-2022 | 29-10-2022 | 31.10.2022 | 31.10.2022 | 31.10.2022 | 31.10.2022 | 01.11.2022 | 02.11.2022 | 02.11.2022 | 06-07-2022 | 06-07-2022 | 13.11.2022 | 14.11.2022 | 14.11.2022 | 14.11.2022 | [90 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 27-09-2022 | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED AND IS CURRENTLY DISCHARGING CARGO | COLLECTING FROM PORT TODAY - BV INSPECTION TO BE BOOKED FOR MONDAY | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR MONDAY 03-10-2022 | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | VEHICLE LOADED AWARITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWARITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE LOADED AWAITING PERMIT IN ORDER TO DISPATCH | HOWICK ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT JOHANNESBURG | VEHICLE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHICLE CURRENTLY AT JOHANNESBURG WAITING PERMITS | VEHICLE CURRENTLY AT BELA BELA ENROUTE BEIT BRIDGE | VEHICLE CURRENTLY AT MUSIAN | * VEHICLE CURRENTLY AT AT BEITBRIDGE - CROSSING TO ZIM SIDE | * VEHICLE CURRENTLY AT BUBI ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT HARARE | * VEHICLE CURRENTLY AT KAROI ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE CLEARING | * VEHICLE CURRENTLY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE IN QUEUE TO CROSS TO DRC | * VEHICLE CURRENTLY AT WHISKEY | * VEHICLE CURRENTLY AT WHISKEY - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY - DAY 5 | * VEHICLE ON SITE WAITING TO OFFLOAD | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * VEHILCE CURRENTLY AT KASUMBALESA DRC SIDE - DAY 4 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022 | * OFFLOADED 14.11.2022
BA2014 | 1 X CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMENT | 3F602146 | CAT00745H3F602146 | TBA | FML2209DSI1775 | VESSEL: BLUE MASTER II Voy. 2266 ETA: 05-11-2022 | COD 2022 326313 | ND706468 | ND627367 | ND63668 | 10-11-2022 | OFFLOADED 08-12-2022 | 01-11-2022 | 10-11-2022 | BV NUMBER RECEIVED - BV TO BE BOOKED AS SOON AS UNIT IS AT OUR FACILITY | 05-11-2022 | 10-11-2022 | 15.11.2022 | 15.11.2022 | 16.11.2022 | 16.11.2022 | 17.11.2022 | 20-11-2022 | 21-11-2022 | 22-11-2022 | 23-11-2022 | 23-11-2022 | 23-11-2022 | 24-11-2022 | 25-11-2022 | 26-11-2022 | 27-11-2022 | 28-11-2022 | 28-11-2022 | 29-11-2022 | 02.12.2022 | 04.12.2022 | 05.12.2022 | 06.12.2022 | 08-12-2022 | 08-12-2022 | [116 empty] | AWITING VESSEL ARRIVAL - ETA DURBAN : 05-11-2022 | AWITING VESSEL ARRIVAL - ETA DURBAN : 05-11-2022 | AWITING VESSEL ARRIVAL - ETA DURBAN : 05-11-2022 | AWITING VESSEL ARRIVAL - ETA DURBAN : 05-11-2022 | AWITING VESSEL ARRIVAL - ETA DURBAN : 05-11-2022 | AWITING VESSEL ARRIVAL - ETA DURBAN : 05-11-2022 | AWITING VESSEL ARRIVAL - ETA DURBAN : 05-11-2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | COLLECTING UNIT FROM PORT TODAY - BV INSPECTION BOOKED FOR TOMORROW 10-11-2022 | BV INSPECTION BOOKED FOR TODAY 10-11-2022 | PIETERMARITZBURG ENROUTE JOHANNESBURG | * VEHILCE CURRENLTY AT VOLKSRUST ENROUTE JOHANNESBURG | * VEHILCE CURRENLTY AT VOLKSRUST ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT POLOKWANE ENROUTE MUSINA | * VEHICLE CURRENLTY AT POLOKWANE ENROUTE MUSINA | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE ATTENDING TO BREAKDOWN | * VEHICLE CURRENLTY AT MVUMA ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE | * VEHICLE CURRENLTY AT KAROI ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT KAROI ENROUTE CHIRUNDU | KAFUE ENROUTE KASUMBALESA | CHILLIBOMBWE IN KASUMBALESA QUEUE | KASUMBALESA ZAM AWAITING CLEARANCE | KASUMBALESA ZAM AWAITING CLEARANCE | KASUMBALESA DRC AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAIITNG SYDONIA AND SEGUCE DOCUMENTS | * VEHICLE CURRENTLY AT KANYAKHA AWITING CLEARANCE | * VEHICLE CURRENTLY AT KANYAKHA AWITING CLEARANCE | * VEHICLE AT LUBUMBASHI - CONNEX ATTENDING TO BREAKDOWN | * VEHICLE AT LUBUMBASHI - CONNEX ATTENDING TO BREAKDOWN | OFFLOADED 08-12-2022
BA2136 | 1 X CAT374-07D HYDRAULIC EXCAVATOR - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10056 | CAT00374VRGM10056 | E4T00754 | FML 2211DSI1814 | VESSEL: ASIAN EMPEROR Voy. 033 ETA: 21-11-2023 | COD 2022 333448 | WMN927GP | BG55CXGP / BG37PLGP | ND63694-1 | 28-11-2022 | OFFLOADED 19-12-2022 | 11-11-2022 | 24-11-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 21-11-2022 | 25-11-2022 | 30-11-2022 | 01-12-2022 | 01-12-2022 | 02-12-2022 | 02-12-2022 | 03.12.2022 | 03.12.2022 | 04.12.2022 | 05.12.2022 | 05.12.2022 | 06.12.2022 | 06.12.2022 | 07.12.2022 | 07-12-2022 | 07-12-2022 | 08-12-2022 | 08-12-2022 | 08-12-2022 | 12-12-2022 | 12-12-2022 | 14-12-2022 | 14-12-2022 | 18-12-2022 | 19-12-2022 | [123 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | VESSEL ARRIVED AND CURRENTLY WORKING | VESSEL ARRIVED AND CURRENTLY WORKING | LUSAKA ENROUTE KASUMBALESA | DISPATCHING DURBAN | TRUCK AT VAN REENEN EN-ROUTE TO JOHANNESBURG | TRUCK AT VAN REENEN EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG AWAIITNG PERMIT IN ORDER TO DISPATCH | TRUCK AT JOHANNESBURG AWAIITNG PERMIT IN ORDER TO DISPATCH | TRUCK AT BEITBRIDGE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KAPIRI MPOSE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE | * VEHICLE CURRENTLY AT KASUMBALESA DRC CUSTOMS IN QUEUE TO MOVE TO WHISKEY | * VEHICLE CURRENTLY AT WHISKEY | * VEHICLE CURRENTLY DISPATCHING WHISKEY | * VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE | OFFLOADED 19-12-2022
BA2349 | 1 X USED CAT745 ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F600822 | CAT00745C3F600822 | TXW04015 | FML 2210DSI1783 | VESSEL: ANDROUSA Voy. 239N - Transhipment Vessel: CMA CGM LA SCALA V. 239S ETA: 14-11-2022 | COD 2022 315944 | ND61605 | ND868372 | ND63649 | 29-11-2022 | OFFLOADED | 18-10-2022 | 28-11-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 14-11-2022 | 29-11-2022 | 02-12-2022 | 06.12.2022 | 07-12-2022 | 08-12-2022 | 08-12-2022 | 11-12-2022 | 11-12-2022 | 12-12-2022 | 13-12-2022 | 13-12-2022 | 13-12-2022 | 14-12-2022 | 15-12-2022 | 15-12-2022 | 15-12-2022 | 16-12-2022 | 16-12-2022 | 16-12-2022 | 20-12-2022 | 20-12-2022 | 23-12-2022 | 23-12-2022 | 23-12-2022 | 23-12-2022 | [108 empty] | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | * VESSEL CURRENTLY IN AND WORKING | * VESSEL CURRENTLY IN AND WORKING | * VESSEL CURRENTLY IN AND WORKING | COLLECTING FROM PORT TODAY | AT UNPACK FACILITY WAITING UNPACK OF FLATRACK | COLLECTING FROM UNPACK FACILITY TODAY | * VEHILCE CURRENTLY AT WHISKEY - DAY 2 | COLLECTED FROM UNPACT DEPOT - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | COLLECTED FROM UNPACT DEPOT - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT PINETOWN EN-ROUTE TO HARRISMITH | TRUCK AT HARRISMITH EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK AND AWAITING LIMPOPO PERMIT | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK AND AWAITING LIMPOPO PERMIT | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK AND AWAITING LIMPOPO PERMIT | * VEHICLE CURRENTLY AT GROBLERSDAL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT MAPINGA ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE WAITING PERMIT | * VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA DRC | * VEHICLE CURRENTLY AT WHISKEY - DAY 1 | * VEHICLE CURRENTLY AT WHISKEY - DAY 2 | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2350 | 1 X USED CAT745 ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F600831 | CAT00745V3F600831 | TXW04004 | FML 2210DSI1783 | VESSEL: ANDROUSA Voy. 239N - Transhipment Vessel: CMA CGM LA SCALA V. 239S ETA: 14-11-2022 | COD 2022 315944 | ND730794 | ND443606 | ND63650 | 29-11-2022 | OFFLOADED | 18-10-2022 | 28-11-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 14-11-2022 | 05.12.2022 | 06.12.2022 | 06.12.2022 | 07-12-2022 | 08-12-2022 | 08-12-2022 | 11-12-2022 | 11-12-2022 | 12-12-2022 | 13-12-2022 | 13-12-2022 | 13-12-2022 | 14-12-2022 | 14-12-2022 | 14-12-2022 | 15-12-2022 | 16-12-2022 | 16-12-2022 | 16-12-2022 | 19-12-2022 | 19-12-2022 | 23-12-2022 | 23-12-2022 | 23-12-2022 | 23-12-2022 | [108 empty] | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | * VESSEL CURRENTLY IN AND WORKING | * VESSEL CURRENTLY IN AND WORKING | * VESSEL CURRENTLY IN AND WORKING | COLLECTING FROM PORT TODAY | AT UNPACK FACILITY WAITING UNPACK OF FLATRACK | COLLECTING FROM UNPACK FACILITY TODAY | * OFFLOADED 14.11.2022 | COLLECTED FROM UNPACT DEPOT - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | COLLECTED FROM UNPACT DEPOT - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | * VEHICLE CURRENTLY AT GROBLERSDAL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT MAPINGA ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE WAITING PERMIT | * VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT WHISKEY - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY IN THE QUEUE TO DISPATCH | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2352 | 1 X USED CAT745 ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F600838 | CAT00745P3F600838 | TXW03745 | FML 2210DSI1783 | VESSEL: ANDROUSA Voy. 239N - Transhipment Vessel: CMA CGM LA SCALA V. 239S ETA: 14-11-2022 | COD 2022 315944 | ND142761 | ND542263 | ND63652 | 29-11-2022 | OFFLOADED | 18-10-2022 | 28-11-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 14-11-2022 | 05.12.2022 | 06.12.2022 | 06.12.2022 | 07-12-2022 | 08-12-2022 | 08-12-2022 | 11-12-2022 | 11-12-2022 | 12-12-2022 | 13-12-2022 | 13-12-2022 | 13-12-2022 | 14-12-2022 | 14-12-2022 | 14-12-2022 | 15-12-2022 | 16-12-2022 | 16-12-2022 | 16-12-2022 | 19-12-2022 | 19-12-2022 | 23-12-2022 | 23-12-2022 | 23-12-2022 | 23-12-2022 | [108 empty] | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | * VESSEL CURRENTLY IN AND WORKING | * VESSEL CURRENTLY IN AND WORKING | * VESSEL CURRENTLY IN AND WORKING | COLLECTING FROM PORT TODAY | AT UNPACK FACILITY WAITING UNPACK OF FLATRACK | COLLECTING FROM UNPACK FACILITY TODAY | WAITING TO LOAD UNIT FROM UNPACK FACILITY | COLLECTED FROM UNPACT DEPOT - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | COLLECTED FROM UNPACT DEPOT - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | * VEHICLE CURRENTLY AT GROBLERSDAL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT MAPINGA ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIAN SIDE WAITING PERMIT | * VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT WHISKEY - DAY 2 | * VEHICLE CURRENTLY AT WHISKEY - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY IN THE QUEUE TO DISPATCH | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2136 | 1 X CAT374-07D HYDRAULIC EXCAVATOR - PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10056 | CAT00374VRGM10056 | E4T00754 | FML 2211DSI1814 | VESSEL: ASIAN EMPEROR Voy. 033 ETA: 21-11-2023 | COD 2022 333448 | AGB6327ZM | ABE4045T / ABE490T | ND63694-2 | 28-11-2022 | OFFLOADED 08-01-2023 | 11-11-2022 | 24-11-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 21-11-2022 | 25-11-2022 | 28-11-2022 | 29-11-2022 | 29-11-2022 | 29-11-2022 | 30-11-2022 | 02.12.2022 | 03.12.2022 | 03.12.2022 | 04.12.2022 | 04.12.2022 | 05.12.2022 | 07-12-2022 | 07-12-2022 | 08-12-2022 | 08-12-2022 | 10-12-2022 | 13-12-2022 | 16-12-2022 | 19-12-2022 | 19-12-2022 | 04-01-2023 | 05-01-2023 | 06-01-2023 | 08-01-2023 | [123 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 21-11-2022 | VESSEL ARRIVED AND CURRENTLY WORKING | VESSEL ARRIVED AND CURRENTLY WORKING | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | DISPATCHING DURBAN | TRUCK AT VAN REENEN EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG DISPATCHING TODAY | TRUCK AT BBR RSA SIDE AWAITING CLEARANCE | TRUCK AT BBR RSA SIDE AWAITING CLEARANCE | TRUCK AT BBR ZIM SIDE AWAITING RELEASE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT LUSAKA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT KAPIRI MPOSE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA IN THE QUEUE TO PROCEED TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA IN THE QUEUE TO PROCEED TO KASUMBALESA | * VEHICLE CURRENLTY AT CHINGOLA IN THE QUEUE TO PROCEED TO KASUMBALESA | * VEHICLE CURRENLTY IN THE QUEUE BEFORE KASUMBALESA ZAMBIA | * VEHICLE CURRENLTY AT WHISKEY - DAY 1 | * VEHICLE CURRENLTY AT WHISKEY - DAY 2 | * VEHICLE CURRENLTY AT WHISKEY - DAY32 | * VEHICLE CURRENLTY AT WHISKEY - DAY 4 | * VEHICLE CURRENLTY AT WHISKEY - DAY 8 | * VEHICLE CURRENLTY AT WHISKEY - DAY 9 | * VEHICLE CURRENLTY AT WHISKEY - DAY 10 | * VEHICLE CURRENLTY AT WHISKEY - DAY 13 | * VEHICLE CURRENLTY AT WHISKEY - DAY 13 | * VEHICLE CURRENTLY AT KANYAKA UNDER CLEARANCE | * VEHICLE CURRENTLY AT CONNEX YARD AWAITING CLEARANCE | OFFLOADED 08-01-2023 | OFFLOADED 08-01-2023 | OFFLOADED 08-01-2023
BA1773 | 1 X NEW CAT C4,4 DIESEL ENGINE | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 44627498 | TBA | PART NR: 3213042 | FML2209DSI1768 | VESSEL: MSC LETIZIA Voy. NZ237A Transhipmnet Vessel: SANTA ISABEL Voy. 224S ETA DURBAN: 06-11-2022 | COD 2022 320310 | JBH393MP | JDH770MP / JDH756MP | POR5489 | 20-12-2022 | OFFLOADED 23-01-2023 | 25-10-2022 | 11-11-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 25.10.2022 | 29-10-2022 | 12-12-2022 | GRB20-12-2022 | GRB 14-12-2022 | GRB20-12-2022 | MARTINS DRIFT 20-12-2022 | MARTINS DRIFT 20-12-2022 | FRANCISTOWN 20-12-2022 | FRANCISTOWN 20-12-2022 | KAZUNGULA BW SIDE 21-12-2022 | KAZUNGULA BW SIDE 21-12-2022 | KAZUNGULA BW SIDE 21-12-2022 | KAZUNGULA BW SIDE | 27-12-2022 | 28-12-2022 | 29-12-2022 | 30-12-2022 | 30-12-2022 | 01-01-2023 | 01-01-2023 | 03-01-2023 | 16.01.2023 | 17-01-2023 | 20-01-2023 | 23-01-2023 | [86 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-09-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-10-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-10-2022 | * VESSEL IN AND WORKING | * VESSEL IN AND WORKING | * VESSEL IN AND WORKING | * VESSEL IN AND WORKING | VESSEL DUE TO ARRIVE 02-11-2022 | VESSEL DUE TO ARRIVE 02-11-2022 | VESSEL DUE TO ARRIVE TODAY THE 02-11-2022 | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | VESSEL IS IN AND WORKING | CONTAINER AT UNPACK DEPOT WAITING UNPACK | CONTAINER AT UNPACK DEPOT WAITING UNPACK | CONTAINER UNPACKED & COLLECTED FROM UNPACK DEPOT - BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR THURSDAY 17.11.2022 | * BV INSPECTION BOOKED FOR THURSDAY 17.11.2022 | * BV INSPECTION BOOKED FOR THURSDAY 17.11.2022 | * BV INSPECTION BOOKED FOR THURSDAY 17.11.2022 | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH ON THE 01/12/2022 | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH ON THE 01/12/2022 | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH ON THE 01/12/2022 | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH ON THE 05/12/2022 | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH ON THE 05/12/2022 | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH ON THE 05/12/2022 | THE UNIT IS AT THE CONSOLIDATION FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH ON THE 05/12/2022 | * VEHICLE LOADING TOPDAY - PLANNING TO DISPATCH OVER THE WEEKEND ONCE ALL VEHICLE CHECKS ARE COMPLETE | * VEHICLE LOADED - PLANNING TO DISPATCH OVER THE WEEKEND ONCE ALL VEHICLE CHECKS ARE COMPLETE | * VEHICLE LOADED - PLANNING TO DISPATCH OVER THE WEEKEND ONCE ALL VEHICLE CHECKS ARE COMPLETE | VEHICLE DISPATCH & IS CURRENTLY AT MOKOPANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE DISPATCH & IS CURRENTLY AT VAALWATER GROBLERSBRIDGE BORDER | VEHICLE DISPATCH & IS CURRENTLY AT MARNITS ENROUTE GROBLERSBRIDGE BORDER | VEHICLE CURRENTLY AT GROBLERSBRIDGE ON BREAKDOWN | VEHICLE CURRENTLY AT GROBLERSBRIDGE CLEARING | VEHICLE CURRENTLY AT NATA ENROUTE KAZUNGULA | VEHICLE CURRENTLY AT KAZUNGULA ZAMBIAN SIDE | VEHICLE CURRENTLY AT KAZUNGULA ZAMBIAN SIDE CLEARING | VEHICLE CURRENTLY AT KAZUNGULA ZAMBIAN SIDE CLEARING | VEHICLE CURRENTLY AT KITWE EN-ROUTE TO CHINGOLA | VEHICLE CURRENTLY AT CHINGOLA | VEHICLE CURRENTLY AT CHINGOLA IN THE QUEUE TO PROCEED TO KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA IN THE QUEUE TO PROCEED TO KASUMBALESA | * VEHICLE CURRENTLY AT WHISKEY AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAIITNG CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAIITNG RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAIITNG RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAIITNG RELEASE | * VEHICLE CURRENTLY AT WHISKEY AWAIITNG RELEASE | * VEHICLE CURRENTLY AT KANYAKHA ENROUTE LUBUMBASHI | * VEHICLE CURRENTLY AT LUBUMBASHI WAITING TO OFFLOAD | * VEHICLE CURRENTLY AT LUBUMBASHI WAITING TO OFFLOAD | * VEHICLE CURRENTLY AT LUBUMBASHI WAITING TO OFFLOAD | * VEHICLE CURRENTLY AT LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 23-01-2023
BA2351 | 1 X USED CAT745 ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F600837 | CAT00745T3F600837 | TXW03719 | FML 2210DSI1783 | VESSEL: ANDROUSA Voy. 239N - Transhipment Vessel: CMA CGM LA SCALA V. 239S ETA: 14-11-2022 | COD 2022 315944 | ND706468 | ND476150 | ND63651 | 29-11-2022 | OFFLOADED 23-01-2023 | 18-10-2022 | 28-11-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 14-11-2022 | 05.12.2022 | 06.12.2022 | 06.12.2022 | 07-12-2022 | 08-12-2022 | 08-12-2022 | 28-12-2022 | 28-12-2022 | 28-12-2022 | 29-12-2022 | 29-12-2022 | 29-12-2022 | 04-01-2023 | 05-01-2023 | 05-01-2023 | 06-01-2023 | 06-01-2023 | 08-01-2023 | 09-01-2023 | 10-01-2023 | 11-01-2023 | 20-01-2023 | 23-01-2023 | 23-01-2023 | 23-01-2023 | [108 empty] | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN TBA | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 12-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | WAITING VESSEL ARRIVAL - ETA DURBAN 14-11-2022 | * VESSEL CURRENTLY IN AND WORKING | * VESSEL CURRENTLY IN AND WORKING | * VESSEL CURRENTLY IN AND WORKING | COLLECTING FROM PORT TODAY | AT UNPACK FACILITY WAITING UNPACK OF FLATRACK | COLLECTING FROM UNPACK FACILITY TODAY | WAITING TO LOAD UNIT FROM UNPACK FACILITY | COLLECTED FROM UNPACT DEPOT - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | COLLECTED FROM UNPACT DEPOT - BV INSPECTION BOOKED FOR MONDAY 28-11-2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | TRUCK WILL LOAD AND DISPATCH ON THE 06/12/2022 | * VEHICLE CURRENTLY AT GROBLERSDAL ENROUTE POLOKWANE | * VEHICLE CURRENTLY AT MUSINA | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE ON BREAKDOWN | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE ON BREAKDOWN - WAITING PARTS | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE ON BREAKDOWN - MACHANIC WORKING ON VEHICLE | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE ON BREAKDOWN - MACHANIC WORKING ON VEHICLE | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE ON BREAKDOWN - MACHANIC WORKING ON VEHICLE | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE ON BREAKDOWN - WAITING FOR REPLACEMENT VEHICLE | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE ON BREAKDOWN - WAITING FOR REPLACEMENT VEHICLE | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE REPLACEMENT VEHICLE ARRIVED, FINALIZING CLEARANCE | * VEHICLE CURRENTLY AT BEIT BRIDGE ZIM SIDE AWAITING RELEASE | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIA SIDE | * VEHICLE CURRENTLY AT CHIRUNDU ZAMBIA SIDE | * VEHICLE CURRENTLY AT NDOLA ENROUTE CHINGOLA | * VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE CLEARING | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE CLEARING | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 3 | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 4 | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 7 | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 7. CHANGED HORSE & DRIVER DUE TO BREAKDOWN - AWAITING AMENDED DOCUMENTS IN ORDER TO DISPATCH | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 7. CHANGED HORSE & DRIVER DUE TO BREAKDOWN - AWAITING AMENDED DOCUMENTS IN ORDER TO DISPATCH | * VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE - DAY 7. CHANGED HORSE & DRIVER DUE TO BREAKDOWN - AWAITING AMENDED DOCUMENTS IN ORDER TO DISPATCH | VEHICLE AT WHISKEY IN QUEUE TO DISPATCH - LUBUMBASHI | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 23-01-2023
BA1761 | 1 X NEW CAT988K WHEEL LOADER - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | L8X00456 | CAT0988KJL8X00456 | TXW06867 | FML2212DSI1867 | VESSEL: MARVELOUS ACE Voy. 0125A - ETA DURBAN: 22-12-2022 | COD 2022 360374 | ND760431 | ND760424 / ND760428 | ND63786 | 30-12-2022 | OFFLOADED | 19-12-2022 | 29-12-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 25-12-2022 | 28-12-2022 | 30-12-2022 | 30-12-2022 | 02-01-2023 | 02-01-2023 | 03-01-2023 | 04-01-2023 | 06-01-2023 | 07-01-2023 | 07-01-2023 | 07-01-2023 | 07-01-2023 | 13-01-2023 | 13-01-2023 | 14-01-2023 | 15-01-2023 | 16-01-2023 | 17.01.2023 | 19-01-2023 | 20-01-2023 | 20-01-2023 | 24-01-2023 | 24-01-2023 | 31-01-2023 | 31-01-2023 | [150 empty] | AWAITING VESSEL ARRILAL - ETA DURBAN 21-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 21-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 21-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 22-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 22-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 23-12-2022 | UNIT TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT GREYTOWN EN-ROUTE TO JOHANNESBURG | TRUCK AT GROBLERSDAL EN-ROUTE TO JOHANNESBURG | TRUCK AT BEIT BRIDGE ZIM SIDE WAITING RELEASE | TRUCK AT BEIT BRIDGE ZIM SIDE WAITING RELEASE | * VEHICLE CURRENLTY AT MVUMA ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENLTY AT CHIRUNDU ZAMBIAN SIDE | * VEHICLE CURRENLTY AT CHIRUNDU ZAMBIAN SIDE - WAITING PERMIT | * VEHICLE CURRENLTY AT CHIRUNDU ZAMBIAN SIDE - WAITING PERMIT | * VEHICLE CURRENLTY AT CHIRUNDU ZAMBIAN SIDE - WAITING PERMIT | * VEHICLE CURRENLTY AT CHINGOLA | * VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTEKASUMBALESA | * VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO CROSS TO KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE IN QUEUE TO CROSS | VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE - DAY 2 | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 2 | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 3 | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 4 | OFFLOADED | OFFLOADED
BA1761 | 1 X NEW CAT988K WHEEL LOADER - BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | L8X00456 | CAT0988KJL8X00456 | TXW06867 | FML2212DSI1867 | VESSEL: MARVELOUS ACE Voy. 0125A - ETA DURBAN: 22-12-2022 | COD 2022 360374 | AJB9958 | N/A | 2212DSI1867 | 30-12-2022 | OFFLOADED | 19-12-2022 | 29-12-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 25-12-2022 | 07-01-2023 | 07-01-2023 | 08.01.2023 | 09.01.2023 | 10-01-2023 | 10-01-2023 | 12-01-2023 | 12-01-2023 | 12-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | 14-01-2023 | 14-01-2023 | 15-01-2023 | 16-01-2023 | 16.01.2023 | 17.01.2023 | 19-01-2023 | 23-01-20233 | 23-01-2023 | 25-01-2023 | 25-01-2023 | 31-01-2023 | 31-01-2023 | [150 empty] | AWAITING VESSEL ARRILAL - ETA DURBAN 21-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 21-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 21-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 22-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 22-12-2022 | AWAITING VESSEL ARRILAL - ETA DURBAN 23-12-2022 | UNIT TO DISPATCH TODAY EN-ROUTE TO BEIT BRIDGE BORDER | TRUCK AT GREYTOWN EN-ROUTE TO JOHANNESBURG | TRUCK AT GROBLERSDAL EN-ROUTE TO JOHANNESBURG | VEHICLE LOADING THE BUCKET THIS AFTERNOON / TOMORROW MORNING | VEHICLE LOADING THE BUCKET THIS AFTERNOON / TOMORROW MORNING | VEHICLE LOADING THE BUCKET THIS AFTERNOON | VEHICLE CURRENTLY LOADING - TO DISPATCH DURBAN THIS AFTERNOON | VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE MUSINA | * VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE IN THE QUEUE TO CROSS TO ZIM SIDE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE IN THE QUEUE TO CROSS TO ZIM SIDE | * VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENLTY AT KABWE ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT NDOLA ENROUTE KASUMBALESA | * VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO CROSS TO KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE IN QUEUE TO CROSS | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY WAITING RELEASE - DAY 2 | VEHICLE CURRENLTY IN LUBUMBASHIWAITING RELEASE FROM CONNEX | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 4 | OFFLOADED | OFFLOADED
BA2135 | 1 X CAT374-07D HYDRAULIC EXCAVATOR IN CKD FORM - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10064 | CAT00374CRGM10064 | E4T00778 | FML 2211DSI1813 | VESSEL: GLOVIS SKY Voy. 033 ETA: 15-12-2023 | COD 2022 333448 | ND568309 | ND566910 / ND564162 | ND63693-1 | 23-12-2022 | OFFLOADED | 11-11-2022 | 22-12-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 19-12-2022 | 04-01-2023 | MIDDELBURG 06-01-2023 | MIDDELBURG 06-01-2023 | 06-01-2023 | 07-01-2023 | 07-01-2023 | 09.01.2023 | 10-01-2023 | 11-01-2023 | 11-01-2023 | 12-01-2023 | 12-01-2023 | 18-01-2023 | 18-01-2023 | 19-01-2023 | 19-01-2023 | 20-01-2023 | 20-01-2023 | 20-01-2023 | 25-01-2023 | 25-01-2023 | 27-01-2023 | 30-01-2023 | 30-01-2023 | 30-01-2023 | [123 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | CHIRUNDU ZAMBIAN SIDE | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 14-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 14-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 15-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 15-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 15-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 15-12-2022 | MAIN UNIT COLLECTED FROM PORT | MAIN UNIT COLLECTED FROM PORT | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - LOADED - FULL EMBARGO STARTS TODAY TO DISPATCH 28-12-2022 | TRUCK TO DISPATCH TOMMROW THE 29/12/2022 | TRUCK TO DISPATCH FIRST WEEK IN JAN DUE TO MAJOR BREAKDOWN | TRUCK TO DISPATCH FIRST WEEK IN JAN DUE TO MAJOR BREAKDOWN | WAITING PERMIT TO DISPATCH | WAITING PERMIT TO DISPATCH | * VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT HENDRINA ENROUTE JOHANNESBURG | * VEHICLE CURRENLTY AT BEIT BRIDGE ZIM SIDE WAITING RELEASE | * VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | * VEHICLE CURRENLTY AT HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZIM SIDE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING CLEARANCE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING CLEARANCE | VEHICLE CURRENTLY AT CHISAMBA ENROUTE CHINGOLA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT WHISKEY - WAITING RELEASE - DAY 1 | VEHICLE CURRENTLY AT WHISKEY - WAITING RELEASE - DAY 2 | VEHICLE CURRENLTY AT TENKE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2135 | 1 X CAT374-07D HYDRAULIC EXCAVATOR IN CKD FORM - PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10064 | CAT00374CRGM10064 | E4T00778 | FML 2211DSI1813 | VESSEL: GLOVIS SKY Voy. 033 ETA: 15-12-2023 | COD 2022 333448 | AGB6781ZM | ACG7261T / ACG7262T | ND63693-2 | 23-12-2022 | OFFLOADED 31-01-2023 | 11-11-2022 | 22-12-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 19-12-2022 | 23-12-2022 | 24-12-2022 | 26-12-2022 | 27-12-2022 | 27-12-2022 | 27-12-2022 | 27-12-2022 | 27-12-2022 | 30-12-2022 | 30-12-2022 | 30-12-2022 | 30-12-2022 | 30-12-2022 | 30-12-2022 | 03-01-2022 | 03-01-2022 | 03-01-2022 | 06-01-2023 | 06-01-2023 | 12-01-2023 | 12-01-2023 | 20-01-2023 | 20-01-2023 | 30-01-2023 | 31-01-2023 | [123 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 23-11-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | CHIRUNDU ZAMBIAN SIDE | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 10-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 14-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 14-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 15-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 15-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 15-12-2022 | AWAITING VESSEL ARRIVAL - ETA DURBAN : 15-12-2022 | PARTS STILL TO BE COLLECTED FROM PORT | PARTS STILL TO BE COLLECTED FROM PORT | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - LOADED - FULL EMBARGO STARTS TODAY TO DISPATCH 28-12-2022 | TRUCK AT BEITBRIDGE AWAITING MAIN UNIT | TRUCK AT BEITBRIDGE RSA SIDE CROSSING TO ZIM SIDE | TRUCK AT BEITBRIDGE RSA SIDE CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHINGOLA | VEHICLE CURRENTLY AT CHINGOLA | VEHICLE CURRENTLY AT CHILLILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE CURRENTLY AT CHILLILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE CLEARING | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE CLEARING | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE CLEARING - DAY 3 | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE DOCUMENTS RECEIVED, TO BE RELEASED TO PROCEED TO WHISKEY | VEHICLE CURRENTLY AT WHISKEY - DAY 1 | VEHICLE CURRENTLY AT WHISKEY - DAY 4 | VEHICLE CURRENTLY AT WHISKEY - DAY 4 | VEHICLE CURRENTLY AT WHISKEY AWAIITNG CLEARANCE - DAY 4 | VEHICLE CURRENTLY AT WHISKEY AWAIITNG CLEARANCE - DAY 5 | VEHICLE AT WHISKEY IN QUEUE TO DISPATCH - LUBUMBASHI | VEHICLE AT KANYAKA WAITING SEAL REMOVAL | VEHICLE AT KANYAKA WAITING SEAL REMOVED - WAITING RELEASE FROM CONNEX | VEHICLE AT KANYAKA WAITING SEAL REMOVED - WAITING RELEASE FROM CONNEX | VEHICLE AT KANYAKA WAITING SEAL REMOVED - WAITING RELEASE FROM CONNEX - DAY 3 | VEHICLE AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 4 | VEHICLE AT LUBEMBE EN-ROUTE TO SITE | ON SITE AWAITING TO OFFLOAD | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023
BA2360 | 1 X CAT DE13,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB904391 | CAT00C15PGB904391 | PART NR: 4512481 | FML2211DSI1835 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 358270 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 15-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR MONDAY 09TH JAN | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2369 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01692 | CAT00C71EGTY01692 | PART NR: 4677716 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2370 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01691 | CAT00C71HGTY01691 | PART NR: 4677716 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2371 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01690 | CAT00C71LGTY01690 | PART NR: 4677716 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2372 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01689 | CAT00C71EGTY01689 | PART NR: 4677716 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2373 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06673 | CAT00C71EECW06673 | PART NR: 4594468 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2374 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06674 | CAT00C71CECW06674 | PART NR: 4594468 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2375 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06672 | CAT00C71HECW06672 | PART NR: 4594468 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2376 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06668 | CAT00C71LECW06668 | PART NR: 4594468 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2377 | 1 X CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06681 | CAT00C71JECW06681 | PART NR: 4512506 | FML2211DSI1835 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR MONDAY 09TH JAN | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2378 | 1 X CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06682 | CAT00C71CECW06682 | PART NR: 4512506 | FML2211DSI1835 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR MONDAY 09TH JAN | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2379 | 1 X CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06684 | CAT00C71AECW06684 | PART NR: 4512506 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2380 | 1 X CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06683 | CAT00C71VECW06683 | PART NR: 4512506 | FML2211DSI1835 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR MONDAY 09TH JAN | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2389 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903394 | CAT00C44TEC903394 | PART NR: 4512502 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2390 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903396 | CAT00C44KEC903396 | PART NR: 4512502 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2391 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903393 | CAT00C44CEC903393 | PART NR: 4512502 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2393 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903395 | CAT00C44PEC903395 | PART NR: 4512502 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 16-01-2023 | OFFLOADED 08-02-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 15-01-2023 | MARTINS DRIFT BW ARR 15-01-2023 | MARTINS DRIFT BW DSP 16-01-2023 | FRANCISTOWN 16-01-2023 | FRANCISTOWN 17-01-2023 | KAZUNGULA BW SIDE 18-01-2023 | KAZUNGULA BW SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | KAZUNGULA ZA SIDE 19-01-2023 | 20-01-2023 | 21-01-2023 | 22-01-2023 | 27-01-2023 | 30-07-2023 | 31-01-2023 | 05-02-2023 | 06-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | [148 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 01-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-01-2023 | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED & CURRENTLY DISCHARGING CONTAINERS | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023
BA2281 | 1 X CAT140K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZL20896 | CAT0140KASZL20896 | TX712668 | FML2209DSI1770 | VESSEL: FREMANTLE HIGHWAY Voy. 71 ETA: 09-11-2022 | COD 2022 360375 | ACQ2112 | ABJ8863 | ND63665 | 23-01-2023 | OFFLOADED 23-02-2023 | 19-12-2022 | 22-12-2022 | BV INSPECTION COMPLETED | 09-11-2022 | 20-01-2022 | 21-01-2023 | 25-01-2023 | 26-01-2023 | 26-01-2023 | 26-01-2023 | 30-01-2023 | 31-01-2023 | 03-02-2023 | 04-02-2023 | 04-02-2023 | 05-02-2023 | 05-02-2023 | 06-02-2023 | 06-02-2023 | 07-02-2023 | 07-02-2023 | 07-02-2023 | 09-02-2023 | 11-02-2023 | 11-02-2023 | 17-02-2023 | 17-02-2023 | 23-02-2023 | 23-02-2023 | [154 empty] | BV INSPECTION TO BE DONE TODAY 22-12-2022 - TO DISPATCH FIRST WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH FIRST WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH FIRST WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH FIRST WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH FIRST WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH SECOND WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH SECOND WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH SECOND WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH SECOND WEEK IN JANUARY 2023 | BV INSPECTION COMPLETED - TO DISPATCH THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - TO DISPATCH THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - TO DISPATCH THIS WEEK - VEHICLE DETAILS TO FOLLOW | BV INSPECTION COMPLETED - TO DISPATCH THIS WEEK - VEHICLE DETAILS TO FOLLOW | LOADING WEDNESDAY 18-01-2023 | LOADING WEDNESDAY 18-01-2023 | PLANNING TO LOAD WEDNESDAY 18-01-2023 | VEHICLE LOADING THIS MORNING - PLANNING TO DISPATCH THIS AFTERNOON | UNIT LOADED - AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE DISPATCHING DURBAN ENROUTE JOHANNESBURG | VEHICLE CURRENTLY IN JOHANNESBURG | VEHICLE CURRENTLY IN JOHANNESBURG WAITING PERMIT | VEHICLE DISPATCHING JOHANNESBURG TO PROCEED TO MUSINA | VEHICLE DISPATCHING POLOKWANE ENROUTE MUSINA | VEHICLE BEIT BRIDGE RSA SIDE CLEARING | VEHICLE BEIT BRIDGE RSA SIDE CROSSING TO ZIM | TRUCK IS AT MASVINGO EN-ROUTE TO CHIRUNDU | TRUCK IS AT HARARE WORKSHOP FOR MAINTENANCE CHECK - TO DISPATCH TOMORROW | TRUCK TO DISPATCH HARARE EN-ROUTE CHIRUNDU | TRUCK TO DISPATCH HARARE EN-ROUTE CHIRUNDU | VEHICLE CURRENLTY AT SIYAVONGA ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT NDOLA ENROUTE KITWE | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBULESA | VEHICLE CURRENLTY AT KASUMBULESA ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBULESA CUSTOMS - AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY - AWAITING RELEASE - DAY 2 | VEHICLE CURRENLTY AT WHISKEY - AWAITING RELEASE - DAY 3 | VEHICLE CURRENLTY AT WHISKEY - IN THE QUEUE TO DISPATCH | VEHICLE CURRENLTY AT WHISKEY - STILL IN THE QUEUE TO DISPATCH | VEHICLE CURRENLTY AT WHISKEY - STILL IN THE QUEUE TO DISPATCH | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE AND RELEASE | VEHICLE AT LUBUMBASHI WAITING TO OFFLOAD | VEHICLE AT LUBUMBASHI WAITING TO OFFLOAD | OFFLOADED 23-02-2023
BA2358 | 1 X CAT DE9,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB800567 | CAT00C11AGB800567 | PART NR: 4486883 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114583 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2359 | 1 X CAT DE9,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB800566 | CAT00C11VGB800566 | PART NR: 4486883 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114583 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2360 | 1 X CAT DE13,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB904391 | CAT00C15PGB904391 | PART NR: 4512481 | FML2211DSI1835 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 358270 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 15-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2361 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY14659 | CAT00C22TGBY14659 | PART NR: 4489035 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114583 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2362 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY14660 | CAT00C22EGBY14660 | PART NR: 4489035 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114583 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2363 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY14658 | CAT00C22CGBY14658 | PART NR: 4489035 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114583 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2364 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GBY14657 | CAT00C22EGBY14657 | PART NR: 4489035 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114583 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2369 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01692 | CAT00C71EGTY01692 | PART NR: 4677716 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2370 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01691 | CAT00C71HGTY01691 | PART NR: 4677716 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2371 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01690 | CAT00C71LGTY01690 | PART NR: 4677716 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2372 | 1 X CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GTY01689 | CAT00C71EGTY01689 | PART NR: 4677716 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2373 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06673 | CAT00C71EECW06673 | PART NR: 4594468 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2374 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06674 | CAT00C71CECW06674 | PART NR: 4594468 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2375 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06672 | CAT00C71HECW06672 | PART NR: 4594468 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2376 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06668 | CAT00C71LECW06668 | PART NR: 4594468 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2377 | 1 X CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06681 | CAT00C71JECW06681 | PART NR: 4512506 | FML2211DSI1835 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2378 | 1 X CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06682 | CAT00C71CECW06682 | PART NR: 4512506 | FML2211DSI1835 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2379 | 1 X CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06684 | CAT00C71AECW06684 | PART NR: 4512506 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2380 | 1 X CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECW06683 | CAT00C71VECW06683 | PART NR: 4512506 | FML2211DSI1835 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BAX5772ZM | BCE5780ZM / BDE5781ZM | 2211DSI1835 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2389 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903394 | CAT00C44TEC903394 | PART NR: 4512502 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2390 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903396 | CAT00C44KEC903396 | PART NR: 4512502 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2391 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903393 | CAT00C44CEC903393 | PART NR: 4512502 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2392 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903417 | CAT00C44CEC903417 | PART NR: 4512502 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114574 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2393 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EC903395 | CAT00C44PEC903395 | PART NR: 4512502 | FML2211DSI1836 | VESSEL: MOL Treasure Voy. 018W - Transhipment Vessel: SEAMAX STAMFORD Voy. 135W ETA: 02-01-2023 | COD 2022 361317 | BCD4308ZM | BCD5844ZM / BCD5845ZM | 2211DSI1836 | 07-02-2023 | OFFLOADED 06-03-2023 | 19-12-2022 | 10-01-2023 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 02-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | GROBLERS BRIDGE ARR 14-01-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TOMORROW 10-01-2023 | CONTAINERS UNPACKED - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED, LOADING TODAY | LOADED - TO DISPATCH FROM DURBAN TODAY | JOHANNESBURG | ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT FRANCIS TOWN ENROUTE KAZUNGULA BORDER | VEHICLE CURRENTLY AT KAZUNGULA BORDER UNDER CLEARANCE | VEHICLE TO DISPATCH KAZUNGULA THIS MORNING ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE STILL AT CHAMBISHI IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILLABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT KANYAKA ENROUTE LUBUMBASHI | OFFLOADED 08-02-2023 | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2394 | 1 X CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECL05733 | CAT00C44CECL05733 | PART NR: 4512504 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114574 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2395 | 1 X CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECL05732 | CAT00C44JECL05732 | PART NR: 4512504 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114574 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2396 | 1 X CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | ECL05731 | CAT00C44DECL05731 | PART NR: 4512504 | FML 2212DSI1859 | VESSEL: NYK MARIA Voy. 025E - Transhipment Vessel: EVER DEVOTE V. 164W ETA: 22-01-2023 | COD 2023 114574 | BCB8679ZM | ACM2200T | 2212DSI1859 | 07-02-2023 | OFFLOADED 06-03-2023 | 24-01-2023 | 25-01-2023 | BV INSPECTION COMPLETED | 22-01-2023 | 07-02-2023 | 08-02-2023 | 09-02-2023 | GROBLERS BRIDGE ARR 10-02-2023 | GROBLERS BRIDGE DSP 11-02-2023 | MARTINS DRIFT BW ARR 11-02-2023 | MARTINS DRIFT BW DSP 11-02-2023 | FRANCISTOWN 11-02-2023 | FRANCISTOWN 11-02-2023 | KAZUNGULA BW SIDE 12-02-2023 | KAZUNGULA BW SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | KAZUNGULA ZM SIDE 13-02-2023 | 15-02-2023 | 15-02-2023 | 17-02-2023 | 19-02-2023 | 23-02-2023 | 23-02-2023 | 25-02-2023 | 25-02-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | 06-03-2023 | [10 empty] | VESSEL ARRIVED AND CURRENTLY WORKING | CONTAINER AT UNPACK DEPOT - TO BE UNPACKED TODAY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TODAY 25-01-2023 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING 01-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | BV INSPECTION COMPLETED - LOADING MONDAY 06-02-2023 | UNIT LOADING & DISPATCHING 07-02-2023 | VEHICLE CURRENLTY LOADING & PLANNING TO DISPATC THIS AFTERNOON | VEHICLE CURRENLTY AT MOOIRIVER ENROUTE JOHANNESBURG | VEHICLE ENROUTE GROBLERSBRIDGE | VEHICLE AT GROBLERSBRIDGE UNDER CLEARANCE | VEHICLE AT KAZUNGULA BORDER CLEARANCE | VEHICLE AT LIVINGSTONE ENROUTE KASUMBALESA | VEHICLE AT MAZABUKA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KONKOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT KASUMBALESA AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE TO DISPATCH FROM WHISKEY TODAY | VEHICLE TO SILL AT WHISKEY WAITING RELEASE | VEHICLE TO DISPATCH WHISKEY TODAY | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 06-03-2023
BA2412 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201317 | CAT00140TW9201317 |  | FML2211DSI1829 | VESSEL: HELIOS RAY VOY. 018 - ETA DURBAN: 31-01-2023 | COD 2023 105852 | JN38KXGP | XVD958GP | ND63733 | 05-02-2023 | OFFLOADED 09-03-2023 | 11-01-2023 | 06-02-2023 | BV INSPECTION COMPLETED | 03-02-2023 | 04-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 08-02-2023 | 09-02-2023 | 12-02-2023 | 12-02-2023 | 14-02-2023 | 14-02-2023 | 16-02-2023 | 16-02-2023 | 17-02-2023 | 17-02-2023 | 18-02-2023 | 18-02-2023 | 19-02-2023 | 21-02-2023 | 24-02-2023 | 27-02-2023 | 27-02-2023 | 01-03-2023 | 02-03-2023 | 08-03-2023 | 09-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 08-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 31-01-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-02-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 02-02-2023 | COLLECTING UNIT FROM PORT TODAY | AWAITING BV INSPECTION ON THE 06/02/2023 | BV INSPECTION BOOKED FOR TODAY | UNIT LOADED AWAITING PERMIT TO DISPATCH | VEHICLE CURRENTLY AT MOKOPANE ENROUTE BEIT BRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE AWAITING CLEARANCE | VEHICLE CURRENTLY AT BEITBRIDGE AWAITING RELEASE | VEHICLE CURRENTLY AT HARARE | VEHICLE CURRENTLY AT HARARE BUSY WITH MAINTENANCE CHECK - TO DISPATCH TODAY | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE CROSSING TO ZAMBIA | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE DISPATCHING CHINGOLA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE DISPATCHING WHISKEY SORTHLY | VEHICLE AT KANYAKA | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING DOCUMENTS & RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING DOCUMENTS & RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING DUTIES TO BE PAID & RELEASE | VEHICLE AT ON SITE WAITING TO OFFLOAD | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023 | OFFLOADED 09-03-2023
BA2323 | 1 X CAT D6GC-01A TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XPC00687 | CAT000D6CXPC00687 | R6J04645 | FML2301DSI1889 | VESSE: PHOENIX LEADER Voy. 041 ETA DURBAN: 24-02-2023 | COD 2023 133128 | ND730794 | ND443606 | ND58329 | 28-02-2023 | OFFLOADED | 16-02-2023 | 28-02-2023 | BV INSPECTION COMPLETED | 24-02-2023 | 01-03-2023 | 01-03-2023 | 01-03-2023 | 02-03-2023 | 02-03-2023 | 02-03-2023 | 05-03-2023 | 06-03-2023 | 06-03-2023 | 07-03-2023 | 07-03-2023 | 07-03-2023 | 09-03-2023 | 09-03-2023 | 09-03-2023 | 09-03-2023 | 13-03-2023 | 14-03-2023 | 16-03-2023 | 16-03-2023 | 17-03-2023 | 19-03-2023 | 20-03-2023 | 20-03-2023 | 21-03-2023 | [27 empty] | WAITING VESSEL ARRIVAL. ETA DURBAN 20-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 20-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 20-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 23-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 24-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 24-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 24-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 24-02-2023 | VESSEL ARRIVED AND CURRENTLY WORKING - UNIT TO BE COLLECTED TODAY FROM PORT | COLLECTED - BV INSPECTION BOOKED FOR TODAY | DISPATCHING DURBAN | ROEDTAN ENROUTE BORDER | VEHICLE AT BEIT BRIDGE BORDER CLEARING | VEHICLE AT KWEKWE ENROUTE HARARE | VEHICLE AT CHINHOYI ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAMBIAN SIDE | VEHICLE DISPATCHING CHIRUNDU ZAMBIAN SIDE | VEHICLE AT KAPIRI MPOSHE ENROUTE KASUMBALESA | VEHCILE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | VEHCILE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHCILE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHCILE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHCILE CURRENLTY ON SITE AWAIITNG TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED
BA2303 | 1 X CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KGX00410 | CAT000D8AKGX00410 | TXJ02404 | 2301DSI1891 | VESSEL: PHOENIX LEADER Voy. 71 ETA: 0920-02-2023 | COD 2023 139919 | NJ100398 | NJ1022487 | ND58320 | 02-03-2023 | OFFLOADED | 23-02-2023 | 01-03-2023 | BV INSPECTION COMPLETED | 24-02-2023 | 01-03-2023 | 02-03-2023 | 02-03-2023 | 03-03-2023 | 04-03-2023 | 04-03-2023 | 06-03-2023 | 07-03-2023 | 09-03-2023 | 09-03-2023 | 09-03-2023 | 09-03-2023 | 10-03-2023 | 11-03-2023 | 11-03-2023 | 12-03-2023 | 12-03-2023 | 13-03-2023 | 14-03-2023 | 15-03-2023 | 15-03-2023 | 17-03-2023 | 21-03-2023 | 21-03-2023 | 21-03-2023 | [33 empty] | AWAITING BV NUMBER IN ORDER TO ARRANGE INSPECTION AND BOOK A TRUCK | AWAITING BV NUMBER IN ORDER TO ARRANGE INSPECTION AND BOOK A TRUCK | VESSEL ARRIVED AND CURRENTLY WORKING - UNIT TO BE COLLECTED TODAY FROM PORT | COLLECTING UNIT FROM PORT TODAY | COLLECTED - BV INSPECTION BOOKED FOR TODAY | COLENSO ENROUTE BORDER | VEHICLE CURRENTLY AT ROEDTAN ENROUTE BORDER | VEHICLE CURRENTLY AT BEIT BRIDGE SA SIDE WAITING ZIM NOTIFICATION | VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY DISPATCHING HARARE FOR CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE | VEHICLE CURRENTLY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI AWAITING RELEASE | OFFLOADED | OFFLOADED | OFFLOADED
BA2442 | 1 X CAT AP655FL ASPHALT PAVER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | AC600132 | CATAP655EAC600132 | E7A46363 | FML2301DSI1906 | VESSEL: GLOVIS CLIPPER Voy. 097 ETA DURBAN: 14-02-2023 | COD 2023 131236 | FZ81LMGP | DN73WTGP | 2301DSI1906 | 23-02-2023 | OFFLOADED 13-04-2023 | 15-02-2023 | 17-02-2023 | BV INSPECTION COMPLETED | 14-02-2023 | 23-02-2023 | 25-02-2023 | 01-03-2023 | 06-03-2023 | 09-03-2023 | 09-03-2023 | 13-03-2023 | 15-03-2023 | 15-03-2023 | 17-03-2023 | 23-03-2023 | 23-03-2023 | 23-03-2023 | 24-03-2023 | 24-03-2023 | 26-03-2023 | 28-03-2023 | 29-03-2023 | 29-03-2023 | 31-03-2023 | 31-03-2023 | 07-04-2023 | 07-04-2023 | 12-04-2023 | 13-04-2023 | VESSEL ARRIVED AND IS CURRENTLY DISCHARING CARGO | COLLECTING UNIT FROM PORT TODAY | BV INSPECTION BOOKED FOR TODAY 17-02-2023 - PLANNING TO LOAD TUESDAY 21/02/2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD TUESDAY 21/02/2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD TODAY 21/02/2023 | UNIT LOADED AND WILL DISPATCH DURBAN TOMMROW THE 23/02/2023 | UNIT LOADED AWAIITNG PERMIT IN ORDER TO DISPATCH | UNIT LOADED AWAITING PERMIT, TO DISPATCH MONDAY THE 27/02/2023 | POMONA - BUSY WITH MAINTANANCE CHECK IN WORKSHOP BEFORE DISPATCHING FOR THE BORDER | POMONA - BUSY WITH MAINTANANCE CHECK IN WORKSHOP BEFORE DISPATCHING FOR THE BORDER | POMONA - DISPATCHING THIS MORNING FOR THE BORDER | VEHICLE CURRENTLY IN MIDRAND ENROUTE MUSINA | VEHICLE CURRENTLY IN PIETERSBURG ENROUTE MUSINA | VEHICLE CURRENTLY AT MUSINA | VEHICLE CURRENTLY AT MUSINA CLEARING | VEHICLE CURRENTLY AT MUSINA CLEARING | VEHICLE CURRENTLY AT BEIT BRIDGE CLEARING | VEHICLE CROSSING TO ZIM SIDE | VEHICLE AT BEITBRIDGE ZIM SIDE - TO DISPATCH FOR HARARE TODAY | VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT KAROI ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU AWAIITNG CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | VEHICLE CURRENTLY AT CHIRUNDU AWAITING RELEASE | VEHICLE CURRENTLY AT KAFUE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT NDOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KITWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT MUSINA CLEARING | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY WAITING RELEASE DAY 4 | VEHICLE CURRENTLY AT CONNEX AFRICA AWAITING RELEASE DAY 11 IN DRC | VEHICLE CURRENTLY AT CONNEX AFRICA AWAITING RELEASE DAY 12 IN DRC | VEHICLE CURRENTLY AT CONGO EQUIPMENT WAITING TO OFFLOAD - 13 DAYS IN DRC | OFFLOADED 13-04-2023 | OFFLOADED 13-04-2023
BA2418 | 1 X CAT 980H BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML2301DSI1911 | VESSEL: HOEGH LONDON - Voy. 104 ETA: 20-02-2023 | COD 2023 131406 | JP33ZWGP | N/A | 2301DSI1911 | 06-03-2023 | OFFLOADED 14-04-2023 | 15-02-2023 | 23-02-2023 | BV INSPECTION COMPLETED | 20-02-2023 | 27-02-2023 | 28-02-2023 | 03-03-2023 | GRB 04-03-2023 | GRB DSP 10-03-2023 | MARTINS DRIFT 10-03-2023 | 12-03-2023 | 14-03-2023 | 15-03-2023 | 16-03-2023 | 16-03-2023 | 16-03-2023 | 17-03-2023 | 17-03-2023 | 18-03-2023 | 20-03-2023 | 21-03-2023 | 21-03-2023 | 22-03-2023 | 04-04-2023 | 04-04-2023 | 07-04-2023 | 07-04-2023 | 12-04-2023 | 14-04-2023 | AWAITING VESSEL ARRIVAL : HOEGH LONDON - Voy. 104 ETA: 19-02-2023 | AWAITING VESSEL ARRIVAL : HOEGH LONDON - Voy. 104 ETA: 19-02-2023 | AWAITING VESSEL ARRIVAL : HOEGH LONDON - Voy. 104 ETA: 19-02-2023 | AWAITING VESSEL ARRIVAL : HOEGH LONDON - Voy. 104 ETA: 20-02-2023 | BUCKET TO BE COLLECTED FROM PORT TODAY | BUCKET TO BE COLLECTED FROM PORT TODAY | BUCKET AT OUR FACILITY AND BV TO BE DONE TODAY | BUCKET AT OUR FACILITY AND BV TO BE DONE TODAY, AWAITING TRUCK LOADING DATE | BV INSPECTION COMPLETED - LOADING TODAY | VEHICLE CURRENTLY IN JOHANNESBURG | VEHICLE CURRENTLY IN JOHANNESBURG BUSY WITH MAINTANANCE CHECK | VEHICLE CURRENTLY IN JOHANNESBURG BUSY WITH MAINTANANCE CHECK | VEHICLE CURRENTLY IN JOHANNESBURG TO DISPATCH FOR THE BORDER TODAY | VEHICLE AT GROBLERSBRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | VEHICLE AT GROBLERSBRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | VEHICLE AT GROBLERSBRIDGE BORDER | VEHICLE AT GROBLERSBRIDGE BORDER FINALIZING CLEARING | VEHICLE DISPATCHING GROBLERSBRIDGE BORDER | VEHICLE CURRENTLY AT FRANCISTOWN ENROUTE KAZUNGULA | VEHICLE CURRENTLY AT KAZUNGULA ZAM WAITING RELEASE | VEHICLE CURRENTLY AT KAZUNGULA ZAM WAITING RELEASE | VEHICLE CURRENTLY AT KALOMO ENROUTE KAFUE | VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | VEHICLE CURRENTL AT KABWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTL AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTL AT KASUMBALESA ZAM SIDE IN QUEUE AWAITING CLEARANCE | VEHICLE CURRENTL AT KASUMBALESA ZAM SIDE IN QUEUE AWAITING CLEARANCE | VEHICLE CURRENTL AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTL AT KASUMBALESA ZAM SIDE CROSSING TO DRC SIDE | VEHICLE CURRENTL AT KASUMBALESA ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VEHICLE CURRENTL AT KASUMBALESA ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | VEHICLE CURRENTL AT KASUMBALESA DRC SIDE CLEARING | VEHICLE CURRENTL AT KASUMBALESA DRC SIDE FINALIZING CLEARANCE AND WAITING RELEASE | VEHICLE CURRENTL AT WHISKEY WAITING RELEASE | VEHICLE CURRENTL AT WHISKEY WAITING RELEASE DAY 2 | VEHICLE CURRENTL AT CONNEX LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTL AT CONNEX LUBUMBASHI AWAITING RELEASE DAY 12 IN DRC | VEHICLE CURRENTL AT CONGO EQUIPMENT WAITING TO OFFLOAD - 13 DAYS IN DRC | VEHICLE CURRENTL AT KOLWEZI WAITING RELEASE TO PROCEED TO KAMOA - 14 DAYS IN DRC | OFFLOADED 14-04-2023 | OFFLOADED 14-04-2023
BA1998 | 1 X CAT D6GC-01A TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XPC00688 | CAT000D6VXPC00688 | R6J04641 | FML2301DSI1890 | VESSE: PHOENIX LEADER Voy. 041 ETA DURBAN: 24-02-2023 | COD 2023 133128 | AFJ7393 | AFQ1809 | ND58321 | 02-03-2023 | OFFLOADED 20-04-2023 | 16-02-2023 | 01-03-2023 | BV INSPECTION COMPLETED | 24-02-2023 | 01-03-2023 | PRETORIA 02-03-2023 | PRETORIA 07-03-2023 | 08-03-2023 | 08-03-2023 | 08-03-2023 | 16-03-2023 | 17-03-2023 | 24-03-2023 | 29-03-2023 | 06/04/2023 | 06/04/2023 | 06/04/2023 | 06/04/2023 | 07/04/2023 | 08/04/2023 | 09/04/2023 | 10/04/2023 | 11/04/2023 | 18-04-2023 | 18-04-2023 | 20-04-2023 | 20-04-2023 | 20-04-2023 | 20-04-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 20-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 20-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 20-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 23-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 24-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 24-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 24-02-2023 | WAITING VESSEL ARRIVAL. ETA DURBAN 24-02-2023 | VESSEL ARRIVED AND CURRENTLY WORKING - UNIT TO BE COLLECTED TODAY FROM PORT | COLLECTING UNIT FROM PORT TODAY | COLLECTED - BV INSPECTION BOOKED FOR TODAY | HEIDELBERG ENROUTE BORDER | VEHICLE AT PRETORIA | VEHICLE AT PRETORIA MINOR BREAKDOWN ATTENDING TO IT. | VEHICLE AT PRETORIA MINOR BREAKDOWN ATTENDING TO IT. | VEHICLE AT POLOKWANE ENROUTE MUSINA | VEHICLE AT BEIT BRIDGE RSA SIDE CLEARING | VEHICLE AT BEIT BRIDGE RSA SIDE WAITING ZIM NOTIFICATION | VEHICLE AT BEITBRIDGE ZIM SIDE AWAITING FIANL CLEARANCE | VEHICLE AT BEITBRIDGE ZIM SIDE AWAITING FINAL CLEARANCE | VEHICLE DISPATCHING BEITBRIDGE ENROUTE HARARE | VEHICLE DISPATCHING BEITBRIDGE ENROUTE HARARE | VEHCILE CURRENLTY AT HARARE ENROUTE CHIRUNDU | VEHCILE CURRENLTY DISPATCHING HARARE ENROUTE CHIRUNDU | VEHCILE CURRENLTY DISPATCHING HARARE EN ROUTE CHIRUNDU AS TRUCK HAD A MINOR REPAIR TO BE DONE AT HARARE WORKSHOP | VEHCILE CURRENLTY AT HARARE WORKSHOP AWAITING FEEDBACK ONTO WHEN THE TRUCK WILL BE REPAIRED. TRUCK IS ON BREAKDOWN | VEHCILE CURRENLTY AT HARARE WORKSHOP AWAITING FEEDBACK ONTO WHEN THE TRUCK WILL BE REPAIRED. TRUCK IS ON BREAKDOWN | VEHCILE CURRENLTY AT KAROI ENROUTE CHIRUNDU | VEHCILE CURRENLTY AT VUTI ENROUTE CHIRUNDU | VEHCILE CURRENLTY AT MAKUTI ENROUTE CHIRUNDU | VEHCILE CURRENLTY AT MAKUTI ENROUTE CHIRUNDU | VEHCILE CURRENLTY AT CHIRUNDU ZIM SIDE | VEHCILE CURRENLTY AT CHIRUNDU ZIM SIDE TO CROSS TO ZAMBIAN SIDE | VEHCILE CURRENLTY DISPATCHING CHIRUNDU | VEHICLE AT LUWANYA ENROUTE LUSAKA | VEHICLE AT LUSAKA EN ROUTE TO KASUMBALESA BORDER | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA ZAM SIDE WAITING TO CROSS TO DRC SIDE | VEHICLE AT KASUMBALESA DRC MOVING TO WHISKEY | VEHICLE AT KASUMBALESA DRC DISATCHING FOR WHISKEY | VEHICLE AT KASUMBALESA DRC - CUSTOMS REQUIRE VECHILE TO STOP AT WHISKEY | VEHICLE AT WHISKEY WAITING RELEASE | VEHICLE AT WHISKEY WAITING RELEASE | VEHICLE ENROUTE LUBUMBASHI | OFFLOADED 20-04-2023 | OFFLOADED 20-04-2023
BA1772 | 1 X NEW CAT C4.4 ENGINE | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 44627413 | N/A | N/A | FML2208DSI1715 | VESSEL: MSC CORUNA Voy. NY232A - TRANSHIPMENT VESSEL: MSC DOMITILLE ETA: 20-09-2022 | COD 2022 271699 | CS04WTGP | VSR119GP / VST289GP | POR5426 | 07-10-2022 | * OFFLOADED 12.11.2022 | 19-08-2022 | 06/10/2022 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 21/09/2022 | 07/10/2022 | 08/10/2022 | 10/10/2022 | GRB 07-10-2022 | GRB DSP 08-10-2022 | MARTINS DRIFT 08-10-2022 | MARTINSDRIFT DSP 09-10-2022 | FRANCISTOWN 09-10-2022 | FRANCISTOWN DSP 10-10-2022 | KAZUNGULA BW ARR 11-10-2022 | KAZUNGULA BW DSP 12-10-2022 | KAZUNGULA ZM ARR 12-10-2022 | KAZUNGULA ZM DSP 13-10-2022 | 16-10-2022 | 17-10-2022 | 17-10-2022 | 19-10-2022 | 22.10.2022 | 24.10.2022 | 25-10-2022 | 25-10-2022 | 06-11-2022 | 06-11-2022 | 12.11.2022 | 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 |  |  |  | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022 | * OFFLOADED 12.11.2022
BA1761 | 1 X NEW CAT988K WHEEL LOADER - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | L8X00456 | CAT0988KJL8X00456 | TXW06867 | FML2212DSI1867 | VESSEL: MARVELOUS ACE Voy. 0125A - ETA DURBAN: 22-12-2022 | COD 2022 360374 | ND760431 | ND760424 / ND760428 | ND63786 | 30-12-2022 | OFFLOADED | 19-12-2022 | 29-12-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 25-12-2022 | 28-12-2022 | 30-12-2022 | 30-12-2022 | 02-01-2023 | 02-01-2023 | 03-01-2023 | 04-01-2023 | 06-01-2023 | 07-01-2023 | 07-01-2023 | 07-01-2023 | 07-01-2023 | 13-01-2023 | 13-01-2023 | 14-01-2023 | 15-01-2023 | 16-01-2023 | 17.01.2023 | 19-01-2023 | 20-01-2023 | 20-01-2023 | 24-01-2023 | 24-01-2023 | 31-01-2023 | 31-01-2023 | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED |  |  |  | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA1761 | 1 X NEW CAT988K WHEEL LOADER - BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | L8X00456 | CAT0988KJL8X00456 | TXW06867 | FML2212DSI1867 | VESSEL: MARVELOUS ACE Voy. 0125A - ETA DURBAN: 22-12-2022 | COD 2022 360374 | AJB9958 | N/A | 2212DSI1867 | 30-12-2022 | OFFLOADED | 19-12-2022 | 29-12-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 25-12-2022 | 07-01-2023 | 07-01-2023 | 08.01.2023 | 09.01.2023 | 10-01-2023 | 10-01-2023 | 12-01-2023 | 12-01-2023 | 12-01-2023 | 13-01-2023 | 13-01-2023 | 13-01-2023 | 14-01-2023 | 14-01-2023 | 15-01-2023 | 16-01-2023 | 16.01.2023 | 17.01.2023 | 19-01-2023 | 23-01-20233 | 23-01-2023 | 25-01-2023 | 25-01-2023 | 31-01-2023 | 31-01-2023 | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED |  |  |  | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2135 | 1 X CAT374-07D HYDRAULIC EXCAVATOR IN CKD FORM - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10064 | CAT00374CRGM10064 | E4T00778 | FML 2211DSI1813 | VESSEL: GLOVIS SKY Voy. 033 ETA: 15-12-2023 | COD 2022 333448 | ND568309 | ND566910 / ND564162 | ND63693-1 | 23-12-2022 | OFFLOADED | 11-11-2022 | 22-12-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 19-12-2022 | 04-01-2023 | MIDDELBURG 06-01-2023 | MIDDELBURG 06-01-2023 | 06-01-2023 | 07-01-2023 | 07-01-2023 | 09.01.2023 | 10-01-2023 | 11-01-2023 | 11-01-2023 | 12-01-2023 | 12-01-2023 | 18-01-2023 | 18-01-2023 | 19-01-2023 | 19-01-2023 | 20-01-2023 | 20-01-2023 | 20-01-2023 | 25-01-2023 | 25-01-2023 | 27-01-2023 | 30-01-2023 | 30-01-2023 | 30-01-2023 | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED |  |  |  | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2135 | 1 X CAT374-07D HYDRAULIC EXCAVATOR IN CKD FORM - PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10064 | CAT00374CRGM10064 | E4T00778 | FML 2211DSI1813 | VESSEL: GLOVIS SKY Voy. 033 ETA: 15-12-2023 | COD 2022 333448 | AGB6781ZM | ACG7261T / ACG7262T | ND63693-2 | 23-12-2022 | OFFLOADED 31-01-2023 | 11-11-2022 | 22-12-2022 | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED ONCE VESSEL ARRIVED AND UNIT IS AVAILABLE FOR INSPECTION | 19-12-2022 | 23-12-2022 | 24-12-2022 | 26-12-2022 | 27-12-2022 | 27-12-2022 | 27-12-2022 | 27-12-2022 | 27-12-2022 | 30-12-2022 | 30-12-2022 | 30-12-2022 | 30-12-2022 | 30-12-2022 | 30-12-2022 | 03-01-2022 | 03-01-2022 | 03-01-2022 | 06-01-2023 | 06-01-2023 | 12-01-2023 | 12-01-2023 | 20-01-2023 | 20-01-2023 | 30-01-2023 | 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 |  |  |  | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023 | OFFLOADED 31-01-2023
BA2383 | CAT DE660E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK04813 | CAT00C18CLXK04813 | N/A | FML2302DSI1942 | VESSEL: COSCO SURABAYA Voy. 109W ETA DURBAN: 15-03-2023 | COD 2023 152650 | AJC3519 (403) | AJC3803T / AJC3810T | 2302DSI1943 | 07-04-2023 | OFFLOADED 21-04-2023 | 13-03-2023 | 24-03-2023 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 15-03-2023 | 29-03-2023 | MIDDELBURG 29-03-2023 | MIDDELBURG 29-03-2023 | 30-03-2023 | 30-03-2023 | 30-03-2023 | 31-03-2023 | 01-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 03-04-2023 | 04-04-2023 | 04-04-2023 | 05-04-2023 | 07-04-2023 | 11-04-2023 | 12-04-2023 | 12-04-2023 | 14-04-2023 | 14-04-2023 | 20-04-2023 | 21-04-2023 | [16 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | VESSEL CURRENLTY IN AND WORKING | VESSEL CURRENLTY IN AND WORKING | VESSEL CURRENLTY IN AND WORKING,AWAITING CONTAINER TO BECOME AVAILABLE FOR COLLECTION FROM PORT | UNITS TO LOAD ON MONDAY THE 27/03/2023 | BV INSPECTION BOOKED FOR TODAY 24-03-2023 - UNITS TO LOAD ON MONDAY THE 27/03/2023 | BV INSPECTION COMPLETED - LOADING TODAY | LOADED - DISPATCHING DURBAN TODAY | VEHICLE ENROUTE JOHANNESBURG | VEHCILE CURRENLTY AT CHIRUNDU ZIM SIDE | VEHICLE CURRENTLY ENROUTE HARARE | VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | VEHICLE CURRENTLY ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA IN QUEUE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY CLEARING | VEHICLE CURRENTLY ENROUTE KANYAKA | CONNEX LUBUMBAHSHI UNDER CLEARANCE | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE - DAY 3 | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | OFFLOADED 21-04-2023
BA2397 | CAT DE1250GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XJ801303 | GJ700148 | N/A | FML2302DSI1943 | VESSEL: IRENES RESOLVE - ETA: 17-02-2023 | COD 2023 150729 | AJC3519 (403) | AJC3803T / AJC3810T | 2302DSI1943 | 07-04-2023 | OFFLOADED 21-04-2023 | 13-03-2023 | 24-03-2023 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 17-02-2023 | 29-03-2023 | MIDDELBURG 29-03-2023 | MIDDELBURG 29-03-2023 | 30-03-2023 | 30-03-2023 | 30-03-2023 | 31-03-2023 | 01-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 03-04-2023 | 04-04-2023 | 04-04-2023 | 05-04-2023 | 07-04-2023 | 11-04-2023 | 12-04-2023 | 12-04-2023 | 14-04-2023 | 14-04-2023 | 20-04-2023 | 21-04-2023 | [16 empty] | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNITS TO LOAD ON MONDAY THE 27/03/2023 | BV INSPECTION BOOKED FOR TODAY - UNITS TO LOAD ON MONDAY THE 27/03/2023 | BV INSPECTION COMPLETED - LOADING TODAY | LOADED - DISPATCHING DURBAN TODAY | VEHICLE ENROUTE JOHANNESBURG | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VEHICLE CURRENTLY ENROUTE HARARE | VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | VEHICLE CURRENTLY ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA IN QUEUE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY CLEARING | VEHICLE CURRENTLY ENROUTE KANYAKA | CONNEX LUBUMBAHSHI UNDER CLEARANCE | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE - DAY 3 | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | OFFLOADED 21-04-2023
BA2398 | CAT DE1250GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SJ801340 | GJ700149 | N/A | FML2302DSI1943 | VESSEL: IRENES RESOLVE - ETA: 17-02-2023 | COD 2023 150729 | AJC3519 (403) | AJC3803T / AJC3810T | 2302DSI1943 | 07-04-2023 | OFFLOADED 21-04-2023 | 13-03-2023 | 24-03-2023 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 17-02-2023 | 29-03-2023 | MIDDELBURG 29-03-2023 | MIDDELBURG 29-03-2023 | 30-03-2023 | 30-03-2023 | 30-03-2023 | 31-03-2023 | 01-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 02-04-2023 | 03-04-2023 | 04-04-2023 | 04-04-2023 | 05-04-2023 | 07-04-2023 | 11-04-2023 | 12-04-2023 | 12-04-2023 | 14-04-2023 | 14-04-2023 | 20-04-2023 | 21-04-2023 | [16 empty] | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNIT AT BONDED FACILITY - AWAITING CO-LOAD UNITS TO ARRIVE | UNITS TO LOAD ON MONDAY THE 27/03/2023 | BV INSPECTION BOOKED FOR TODAY - UNITS TO LOAD ON MONDAY THE 27/03/2023 | BV INSPECTION COMPLETED - LOADING TODAY | LOADED - DISPATCHING DURBAN TODAY | VEHICLE ENROUTE JOHANNESBURG | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VEHICLE CURRENTLY ENROUTE HARARE | VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | VEHICLE CURRENTLY ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA IN QUEUE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA ZAMBIA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY CLEARING | VEHICLE CURRENTLY ENROUTE KANYAKA | CONNEX LUBUMBAHSHI UNDER CLEARANCE | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE - DAY 3 | CONNEX LUBUMBAHSHI UNDER CLEARANCE / WAITING RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | OFFLOADED 21-04-2023
BA2310 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03524 | CAT0226BVDXZ03524 | CZ209651 | FML2212DSI1865 | VESSEL: TEMA EXPRESS Voy. 224W ETA: 08-01-2023 | COD 2023 146315 | HZ58FGGP | N/A | 2212DSI1865 | 05-04-2023 | OFFLOADED 26-04-2023 | 24-03-2023 | 29-03-2023 | BV INSPECTION COMPLETED | 08/01/2023 | 31-03-2023 | 01-04-2023 | 04-04-2023 | 06-04-2023 | 08-04-2023 | 11-04-2023 | 13-04-2023 | FRANCISTOWN 13-04-2023 |  | KAZ BW 14-04-2023 | KAZ BW 15-04-2023 | KAZ ZM 15-04-2023 | KAZ ZM 16-04-2023 | 17-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 22-04-2023 | 22-04-2023 | 22-04-2023 | 22-04-2023 | 25-04-2023 | 26-04-2023 | [24 empty] | AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | BV TO BE DONE ON MONDAY THE 27/03/2023, AWAITING LOADING DATE | BV TO BE DONE ON MONDAY IF THE BV NUMBER IS RECEIVED, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TOMORROW, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR WEDNESDAY 29-03-2023 - AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | DISPATCHING DURBAN TODAY | VEHICLE IN JOHANNESBURG - DOING TRIP CHECK BEFORE DISPATCHING | VEHICLE IN JOHANNESBURG - FINALIZING TRIP CHECK - DISPATCHING THIS AFTERNOON | VEHICLE AT MOKOPANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT POLOKWANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE AT GROBLERSBRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | VEHICLE DISPATCHING MARTINS DRIFT BORDER | VEHICLE AT NATA ENROUTE KAZUNGULA | VEHICLE AT KAZUNGULA BORDER CLEARING | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | VEHICLE AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | VEHICLE AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023
BA2311 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03525 | CAT0226BADXZ03525 | CZ209647 | FML2212DSI1865 | VESSEL: TEMA EXPRESS Voy. 224W ETA: 08-01-2023 | COD 2023 146315 | HZ58FGGP | N/A | 2212DSI1865 | 05-04-2023 | OFFLOADED 26-04-2023 | 24-03-2023 | 29-03-2023 | BV INSPECTION COMPLETED | 08/01/2023 | 31-03-2023 | 01-04-2023 | 04-04-2023 | 06-04-2023 | 08-04-2023 | 11-04-2023 | 13-04-2023 | FRANCISTOWN 13-04-2023 |  | KAZ BW 14-04-2023 | KAZ BW 14-04-2023 | KAZ ZM 15-04-2023 | KAZ ZM 16-04-2023 | 17-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 22-04-2023 | 22-04-2023 | 22-04-2023 | 22-04-2023 | 25-04-2023 | 26-04-2023 | [24 empty] | AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | BV TO BE DONE ON MONDAY THE 27/03/2023, AWAITING LOADING DATE | BV TO BE DONE ON MONDAY IF THE BV NUMBER IS RECEIVED, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TOMORROW, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR WEDNESDAY 29-03-2023 - AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | DISPATCHING DURBAN TODAY | VEHICLE IN JOHANNESBURG - DOING TRIP CHECK BEFORE DISPATCHING | VEHICLE IN JOHANNESBURG - FINALIZING TRIP CHECK - DISPATCHING THIS AFTERNOON | VEHICLE AT MOKOPANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT POLOKWANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE AT GROBLERSBRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | VEHICLE DISPATCHING MARTINS DRIFT BORDER | VEHICLE AT NATA ENROUTE KAZUNGULA | VEHICLE AT KAZUNGULA BORDER CLEARING | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | VEHICLE AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | VEHICLE AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023
BA2388 | 1 X CAT DE400E0(C13) GENSETS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | CAT00C13CDH404509 | N/A | FML 2302DSI1963 | VESSEL: GIULIA Voy ZF308A ETA DURBAN: 04-04-2023 | COD 2023 167387 | JP33ZWGP | N/A | 2302DSI1963B | 14-04-2023 | OFFLOADED 28-04-2023 | 04-04-2023 | 11-04-2023 | BV NUMBER RECEIVED | 30-03-2023 | 13-04-2023 | 13-04-2023 | 16-04-2023 | GRB ARR 16-04-2023 | GRB DSP 18-04-2023 | MARTINS DRIFT ARR 18-04-2023 | MARTINS DRIFT DSP 18-04-2023 | FRANCISTOWN 19-04-2023 |  | KAZ BW 19-04-2023 | 19-04-2023 | 19-04-2023 | 20-04-2023 | 20-04-2023 | 21-04-2023 | 21-04-2023 | 21-04-2023 | 21-04-2023 | 21-04-2023 | 24-04-2023 | 24-04-2023 | 25-04-2023 | 27-04-2023 | 28-04-2023 | 28-04-2023 | [24 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VESSEL ARRIVED & IS CURRENTLY WORKING | VESSEL ARRIVED, AWAITING COMPLETION OF DISCHARGE | RECEIVED AT WAREHOUSE - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 06-04-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN | VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE GROBLESBRIDGE BORDER | VEHICLE MODIMOLE ENROUTE GROBLESBRIDGE BORDER | VEHICLE GROBLESBRIDGE BORDER CLEARING | VEHICLE SERULE ENROUTE KAZUNGULA | VEHICLE AT KAZUNGULA BW SIDE IN THE QUEUE TO CROSS TO ZAM SIDE | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY WAITING CLEARANCE AND RELEASE | VEHICLE ENROUTE KANYAKA | VEHICLE CONNEX AFRICA LUBUMBASHI AWAITING RELEASE | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023
BA2384 | CAT DE660E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK04814 | CAT00C18TLXK04814 | N/A | FML2302DSI1942 | VESSEL: COSCO SURABAYA Voy. 109W ETA DURBAN: 15-03-2023 | COD 2023 152650 | ABJ4578 (997) | AAS7113 / AAS7073 | 2302DSI1946 | 07-04-2023 | OFFLOADED 11-05-2023 | 13-03-2023 | 24-03-2023 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 15-03-2023 | 31-03-2023 | MIDDELBURG 02-03-2023 | MIDDELBURG 03-03-2023 | 03-04-2023 | 04-04-2023 | 04-04-2023 | 04-04-2023 | 04-04-2023 | 12-04-2023 | 12-04-2023 | 12-04-2023 | 12-04-2023 | 13-04-2023 | 13-04-2023 | 13-04-2023 | 14-04-2023 | 20-04-2023 | 24-04-2023 | 26-04-2023 | 27-04-2023 | 28-04-2023 | 09-05-2023 | 09-05-2023 | 11-05-2023 | 11-05-2023 | [16 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-03-2023 | VESSEL CURRENLTY IN AND WORKING | VESSEL CURRENLTY IN AND WORKING | VESSEL CURRENLTY IN AND WORKING,AWAITING CONTAINER TO BECOME AVAILABLE FOR COLLECTION FROM PORT | UNITS IS AT OUR FACILITY AND BV TO BE DONE TOMMROW THE 24/03/2023 | BV INSPECTION BOOKED FOR TODAY 24-03-2023 - UNITS TO LOAD ON MONDAY THE 27/03/2023 | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETED - LOADING DATE TO BE CONFIRMED | LOADING TODAY | LOADED, DISPATCHING DURBAN TODAY | VEHICLE CURRENTLY AT MIDDELBURG ENROUTE MUSIAN | VEHICLE CURRENTLY DISPATCH BEIT BRIDGE ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT HARARE TO DISPATCH TODAY | VEHICLE CURRENTLY AT HARARE ON BREAKDOWN-ESTIMATED REPAIR TIME TO BE ADVISED | VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE ENROUTE KITWE | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT KANYAKA UNDER CLEARANCE | TRUCK EN-ROUTE TO CONGO EQUIPMENT | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | OFFLOADED 11-05-2023 | OFFLOADED 11-05-2023
BA2385 | CAT DE660E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK04825 | CAT00C18HLXK04825 | N/A | FML2302DSI1946 | VESSEL: MSC VANESSA ETA DURBAN: 25-03-2023 | COD 2023 152650 | ABJ4578 (997) | AAS7113 / AAS7073 | 2302DSI1946 | 07-04-2023 | OFFLOADED 11-05-2023 | 14-03-2023 | 29-03-2023 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 25-03-2023 |  | MIDDELBURG 02-03-2023 | MIDDELBURG 03-03-2023 | 03-04-2023 | 04-04-2023 | 04-04-2023 | 04-04-2023 | 04-04-2023 | 12-04-2023 | 12-04-2023 | 12-04-2023 | 12-04-2023 | 13-04-2023 | 13-04-2023 | 13-04-2023 | 14-04-2023 | 20-04-2023 | 24-04-2023 | 26-04-2023 | 27-04-2023 | 28-04-2023 | 09-05-2023 | 09-05-2023 | 11-05-2023 | 11-05-2023 | [16 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-04-2023 | CONTAINER AT BONDED FACILITY TO BE UNPACKED TODAY | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED, DISPATCHING DURBAN TODAY | VEHICLE CURRENTLY AT MIDDELBURG ENROUTE MUSIAN | VEHICLE CURRENTLY DISPATCH BEIT BRIDGE ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT HARARE TO DISPATCH TODAY | VEHICLE CURRENTLY AT HARARE ON BREAKDOWN-ESTIMATED REPAIR TIME TO BE ADVISED | VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE ENROUTE KITWE | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | TRUCK EN-ROUTE TO CONGO EQUIPMENT | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | OFFLOADED 11-05-2023 | OFFLOADED 11-05-2023
BA2386 | CAT DE715E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK04824 | CAT00C18LLXK04824 | N/A | FML2302DSI1946 | VESSEL: MSC VANESSA ETA DURBAN: 25-03-2023 | COD 2023 150553 | ABJ4578 (997) | AAS7113 / AAS7073 | 2302DSI1946 | 07-04-2023 | OFFLOADED 11-05-2023 | 13-03-2023 | 29-03-2023 | BV NUMBER RECEIVED - BV INPSECTION TO BE BOOKED ONCE CARGO IS AVAILABLE | 25-03-2023 |  | MIDDELBURG 02-03-2023 | MIDDELBURG 03-03-2023 | 03-04-2023 | 04-04-2023 | 04-04-2023 | 04-04-2023 | 04-04-2023 | 12-04-2023 | 12-04-2023 | 12-04-2023 | 12-04-2023 | 13-04-2023 | 13-04-2023 | 13-04-2023 | 14-04-2023 | 20-04-2023 | 24-04-2023 | 26-04-2023 | 27-04-2023 | 28-04-2023 | 09-05-2023 | 09-05-2023 | 11-05-2023 | 11-05-2023 | [16 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-04-2023 | CONTAINER AT BONDED FACILITY TO BE UNPACKED TODAY | BV INSPECTION BOOKED FOR TODAY | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | LOADED, DISPATCHING DURBAN TODAY | VEHICLE CURRENTLY AT MIDDELBURG ENROUTE MUSIAN | VEHICLE CURRENTLY DISPATCH BEIT BRIDGE ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT HARARE TO DISPATCH TODAY | VEHICLE CURRENTLY AT HARARE ON BREAKDOWN-ESTIMATED REPAIR TIME TO BE ADVISED | VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE ENROUTE KITWE | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | TRUCK EN-ROUTE TO CONGO EQUIPMENT | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | OFFLOADED 11-05-2023 | OFFLOADED 11-05-2023
| BA2388 | 1 X CAT DE400E0(C13) GENSETS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | CAT00C13CDH404509 | N/A | FML 2302DSI1963 | VESSEL: GIULIA Voy ZF308A ETA DURBAN: 04-04-2023 | COD 2023 167387 | JP33ZWGP | N/A | 2302DSI1963B | 14-04-2023 | OFFLOADED 28-04-2023 | 04-04-2023 | 11-04-2023 | BV NUMBER RECEIVED | 30-03-2023 | 13-04-2023 | 13-04-2023 | 16-04-2023 | GRB ARR 16-04-2023 | GRB DSP 18-04-2023 | MARTINS DRIFT ARR 18-04-2023 | MARTINS DRIFT DSP 18-04-2023 | FRANCISTOWN 19-04-2023 |  | KAZ BW 19-04-2023 | 19-04-2023 | 19-04-2023 | 20-04-2023 | 20-04-2023 | 21-04-2023 | 21-04-2023 | 21-04-2023 | 21-04-2023 | 21-04-2023 | 24-04-2023 | 24-04-2023 | 25-04-2023 | 27-04-2023 | 28-04-2023 | 28-04-2023 | [24 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VESSEL ARRIVED & IS CURRENTLY WORKING | VESSEL ARRIVED, AWAITING COMPLETION OF DISCHARGE | RECEIVED AT WAREHOUSE - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 06-04-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN | VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE GROBLESBRIDGE BORDER | VEHICLE MODIMOLE ENROUTE GROBLESBRIDGE BORDER | VEHICLE GROBLESBRIDGE BORDER CLEARING | VEHICLE SERULE ENROUTE KAZUNGULA | VEHICLE AT KAZUNGULA BW SIDE IN THE QUEUE TO CROSS TO ZAM SIDE | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY WAITING CLEARANCE AND RELEASE | VEHICLE ENROUTE KANYAKA | VEHICLE CONNEX AFRICA LUBUMBASHI AWAITING RELEASE | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023 | OFFLOADED 28-04-2023
BA2365 | 1 X CAT DE33GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7A00457 | CAT0DE33PN7A00457 |  | FML2303DSI1992 | VESSEL: MALIAKOS Voy. 001W ETA DURBAN: 18-04-2023 | COD 2023 174563 | AJB9958 | N/A | 2303DSI1992 | 29-04-2023 | OFFLOADED 12-05-2023 | 13-04-2023 | 24-04-2023 | BV NUMBER RECEIVED | 18-04-2023 | 27-04-2023 | 27-04-2023 | 24-07-2023 | GRB ARR 27-04-2023 | 28-04-2023 | 28-04-2023 | 29-04-2023 | 29-04-2023 | 29-04-2023 | 30-04-2023 | 30-04-2023 | 01-05-202 | 01-05-2023 | 01-05-2023 | 02-05-2023 | 03-05-2023 | 03-05-2023 | 03-05-2023 | 04-05-2023 | 06-05-2023 | 06-05-2023 | 09-05-2023 | 09-05-2023 | 11-05-2023 | 12-05-2023 | [39 empty] | AWAITING VESSEL ARRIVAL - ETA 16-04-2023 | AWAITING VESSEL ARRIVAL - ETA 18-04-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER BEING UNPACKED TODAY. BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR TOMORROW | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | GROBLERSBRIDGE BORDER CLEARING | VEHICLE CURRENTLY AT KAZUNGULA WAITING RELEASE | VEHICLE CURRENTLY AT KAZUNGULA WAITING RELEASE | VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA UNDER CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA WAITING T1 & T8 DOCUMENTS TO BE RELEASED | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE - DAY 2 | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | OFFLOADED 12-05-2023 | OFFLOADED 12-05-2023
BA2366 | 1 X CAT DE33GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7AA00458 | CAT0DE33KN7A00458 |  | FML2303DSI1992 | VESSEL: MALIAKOS Voy. 001W ETA DURBAN: 18-04-2023 | COD 2023 174563 | AJB9958 | N/A | 2303DSI1992 | 29-04-2023 | OFFLOADED 12-05-2023 | 13-04-2023 | 24-04-2023 | BV NUMBER RECEIVED | 18-04-2023 | 27-04-2023 | 27-04-2023 | 24-07-2023 | GRB ARR 27-04-2023 | 28-04-2023 | 28-04-2023 | 29-04-2023 | 29-04-2023 | 29-04-2023 | 30-04-2023 | 30-04-2023 | 01-05-202 | 01-05-2023 | 01-05-2023 | 02-05-2023 | 03-05-2023 | 03-05-2023 | 03-05-2023 | 04-05-2023 | 06-05-2023 | 06-05-2023 | 09-05-2023 | 09-05-2023 | 11-05-2023 | 12-05-2023 | [39 empty] | AWAITING VESSEL ARRIVAL - ETA 16-04-2023 | AWAITING VESSEL ARRIVAL - ETA 18-04-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER BEING UNPACKED TODAY. BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR TOMORROW | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | GROBLERSBRIDGE BORDER CLEARING | VEHICLE CURRENTLY AT KAZUNGULA WAITING RELEASE | VEHICLE CURRENTLY AT KAZUNGULA WAITING RELEASE | VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA UNDER CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA WAITING T1 & T8 DOCUMENTS TO BE RELEASED | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE - DAY 2 | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | OFFLOADED 12-05-2023 | OFFLOADED 12-05-2023
BA2367 | 1 X CATDE55GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7200158 | CAT0DE55AN7200158 |  | FML2303DSI1992 | VESSEL: MALIAKOS Voy. 001W ETA DURBAN: 18-04-2023 | COD 2023 174571 | AJB9958 | N/A | 2303DSI1992 | 29-04-2023 | OFFLOADED 12-05-2023 | 13-04-2023 | 24-04-2023 | BV NUMBER RECEIVED | 18-04-2023 | 27-04-2023 | 27-04-2023 | 24-07-2023 | GRB ARR 27-04-2023 | 28-04-2023 | 28-04-2023 | 29-04-2023 | 29-04-2023 | 29-04-2023 | 30-04-2023 | 30-04-2023 | 01-05-202 | 01-05-2023 | 01-05-2023 | 02-05-2023 | 03-05-2023 | 03-05-2023 | 03-05-2023 | 04-05-2023 | 06-05-2023 | 06-05-2023 | 09-05-2023 | 09-05-2023 | 11-05-2023 | 15-05-2023 | [39 empty] | AWAITING VESSEL ARRIVAL - ETA 16-04-2023 | AWAITING VESSEL ARRIVAL - ETA 18-04-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER BEING UNPACKED TODAY. BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR TOMORROW | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | GROBLERSBRIDGE BORDER CLEARING | VEHICLE CURRENTLY AT KAZUNGULA WAITING RELEASE | VEHICLE CURRENTLY AT KAZUNGULA WAITING RELEASE | VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA UNDER CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA WAITING T1 & T8 DOCUMENTS TO BE RELEASED | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE - DAY 2 | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | OFFLOADED 12-05-2023 | OFFLOADED 12-05-2023
BA2368 | 1 X CATDE55GC GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N7200159 | CAT0DE55LN7200159 |  | FML2303DSI1992 | VESSEL: MALIAKOS Voy. 001W ETA DURBAN: 18-04-2023 | COD 2023 174571 | AJB9958 | N/A | 2303DSI1992 | 29-04-2023 | OFFLOADED 12-05-2023 | 13-04-2023 | 24-04-2023 | BV NUMBER RECEIVED | 18-04-2023 | 27-04-2023 | 27-04-2023 | 24-07-2023 | GRB ARR 27-04-2023 | 28-04-2023 | 28-04-2023 | 29-04-2023 | 29-04-2023 | 29-04-2023 | 30-04-2023 | 30-04-2023 | 01-05-202 | 01-05-2023 | 01-05-2023 | 02-05-2023 | 03-05-2023 | 03-05-2023 | 03-05-2023 | 04-05-2023 | 06-05-2023 | 06-05-2023 | 09-05-2023 | 09-05-2023 | 11-05-2023 | 15-05-2023 | [39 empty] | AWAITING VESSEL ARRIVAL - ETA 16-04-2023 | AWAITING VESSEL ARRIVAL - ETA 18-04-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER BEING UNPACKED TODAY. BV INSPECTION BOOKED FOR TODAY - LOADING PLANNED FOR TOMORROW | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | GROBLERSBRIDGE BORDER CLEARING | VEHICLE CURRENTLY AT KAZUNGULA WAITING RELEASE | VEHICLE CURRENTLY AT KAZUNGULA WAITING RELEASE | VEHICLE CURRENTLY AT KABWE ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA UNDER CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA WAITING T1 & T8 DOCUMENTS TO BE RELEASED | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE - DAY 2 | VEHICLE CURRENTLY ON SITE WAITING TO OFFLOAD | OFFLOADED 12-05-2023 | OFFLOADED 12-05-2023
BA2381 | 1 X CAT DE400E0(C13) GENSETS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | CAT00C13KDH404501 | N/A | FML 2302DSI1963 | VESSEL: GIULIA Voy ZF308A ETA DURBAN: 04-04-2023 | COD 2023 167387 | AAZ6912 (175) | AAF6747 / AAF6746 | 2302DSI1963A | 14-04-2023 | OFFLOADED 24-05-2023 | 04-04-2023 | 11-04-2023 | BV COMPLETED | 30-03-2023 | 13-04-2023 | 13-04-2023 | 15-04-2023 | 15-04-2023 | 16-04-2023 | 16-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 20-04-2023 | 20-04-2023 | 21-04-2023 | 22-04-2023 | 24-04-2023 | 29-04-2023 | 29-04-2023 | 03-05-20203 | 28-04-2023 | 05-05-2023 | 08-05-2023 | 23-05-2023 | 23-05-2023 | [24 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VESSEL ARRIVED & IS CURRENTLY WORKING | VESSEL ARRIVED, AWAITING COMPLETION OF DISCHARGE | RECEIVED AT WAREHOUSE - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 06-04-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN | JOHANNESBURG ENROUTE MUSINA | ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE TO DISPATCH FOR CHIRUNDU | VEHICLE CURRENTLY ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAIITNG SEGUCE DAY 9 | TRUCK EN-ROUTE TO KANYAKHA | TRUCK AT KANYAKHA WAITING RELEASE | TRUCK AT LUBUMBASHI WAITING RELEASE | TRUCK AT ENROUTE CONGO EQUIPMENT | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | ENROUTE SITE FOR OFFLOADING | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - UNDER CLEARANCE | VEHICLE DISPATCHED LUBUMBASHI ENROUTE SITE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023
BA2382 | 1 X CAT DE400E0(C13) GENSETS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | CAT00C13JDH404502 | N/A | FML 2302DSI1963 | VESSEL: GIULIA Voy ZF308A ETA DURBAN: 04-04-2023 | COD 2023 167387 | AAZ6912 (175) | AAF6747 / AAF6746 | 2302DSI1963A | 14-04-2023 | OFFLOADED 24-05-2023 | 04-04-2023 | 11-04-2023 | BV COMPLETED | 30-03-2023 | 13-04-2023 | 13-04-2023 | 15-04-2023 | 15-04-2023 | 16-04-2023 | 16-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 20-04-2023 | 20-04-2023 | 21-04-2023 | 22-04-2023 | 24-04-2023 | 29-04-2023 | 29-04-2023 | 03-05-20203 | 28-04-2023 | 05-05-2023 | 08-05-2023 | 23-05-2023 | 23-05-2023 | [24 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VESSEL ARRIVED & IS CURRENTLY WORKING | VESSEL ARRIVED, AWAITING COMPLETION OF DISCHARGE | RECEIVED AT WAREHOUSE - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 06-04-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN | JOHANNESBURG ENROUTE MUSINA | ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE TO DISPATCH FOR CHIRUNDU | VEHICLE CURRENTLY ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAIITNG SEGUCE DAY 9 | TRUCK EN-ROUTE TO KANYAKHA | TRUCK AT KANYAKHA WAITING RELEASE | TRUCK AT LUBUMBASHI WAITING RELEASE | TRUCK AT ENROUTE CONGO EQUIPMENT | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | ENROUTE SITE FOR OFFLOADING | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - UNDER CLEARANCE | VEHICLE DISPATCHED LUBUMBASHI ENROUTE SITE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023
BA2387 | 1 X CAT DE400E0(C13) GENSETS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | CAT00C13EDH404508 | N/A | FML 2302DSI1963 | VESSEL: GIULIA Voy ZF308A ETA DURBAN: 04-04-2023 | COD 2023 167387 | AAZ6912 (175) | AAF6747 / AAF6746 | 2302DSI1963A | 14-04-2023 | OFFLOADED 24-05-2023 | 04-04-2023 | 11-04-2023 | BV COMPLETED | 30-03-2023 | 13-04-2023 | 13-04-2023 | 15-04-2023 | 15-04-2023 | 16-04-2023 | 16-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 20-04-2023 | 20-04-2023 | 21-04-2023 | 22-04-2023 | 24-04-2023 | 29-04-2023 | 29-04-2023 | 03-05-20203 | 28-04-2023 | 05-05-2023 | 08-05-2023 | 23-05-2023 | 23-05-2023 | [24 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VESSEL ARRIVED & IS CURRENTLY WORKING | VESSEL ARRIVED, AWAITING COMPLETION OF DISCHARGE | RECEIVED AT WAREHOUSE - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 06-04-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN | JOHANNESBURG ENROUTE MUSINA | ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE TO DISPATCH FOR CHIRUNDU | VEHICLE CURRENTLY ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAIITNG SEGUCE DAY 9 | TRUCK EN-ROUTE TO KANYAKHA | TRUCK AT KANYAKHA WAITING RELEASE | TRUCK AT LUBUMBASHI WAITING RELEASE | TRUCK AT ENROUTE CONGO EQUIPMENT | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | ENROUTE SITE FOR OFFLOADING | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - UNDER CLEARANCE | VEHICLE DISPATCHED LUBUMBASHI ENROUTE SITE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023
BA2174 | 1 X CAT988K WHEEL LOADER BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | L8X00483 | CAT0988KCL8X00483 | TXW07246 | FML2304DSI2021 | VESSEL:VICTORIOUS ACE Voy. 0065A ETA: 23-04-2023 | COD 2023 184331 | KS24BNGP | N/A | 2304DSI2021 | 08-05-2023 | OFFLOADED 25-05-2023 | 26-04-2023 | 02-05-2023 | BV COMPLETED | 23-04-2023 | 05-05-2023 | 06-05-2023 | 09-05-2023 | 09-05-2023 | 09-05-2023 | 09-05-2023 | 10-05-2023 | 10-05-2023 | 11-05-2023 | 11-05-2023 | 12-05-2023 | 12-05-2023 | 12-05-2023 | 12-05-2023 | 12-05-2023 | 12-05-2023 | 12-05-2023 | 13-05-2023 | 13-05-2023 | 18-05-2023 | 18-05-2023 | 21-05-2023 | 22-05-2023 | 25-05-2023 | 25-05-2023 | [24 empty] | AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | BV TO BE DONE ON MONDAY THE 27/03/2023, AWAITING LOADING DATE | BV TO BE DONE ON MONDAY IF THE BV NUMBER IS RECEIVED, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TOMORROW, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR WEDNESDAY 29-03-2023 - AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | DISPATCHING DURBAN TODAY | VEHICLE IN JOHANNESBURG - DOING TRIP CHECK BEFORE DISPATCHING | VEHICLE IN JOHANNESBURG - FINALIZING TRIP CHECK - DISPATCHING THIS AFTERNOON | VEHICLE AT MOKOPANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT POLOKWANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE AT GROBLERSBRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | VEHICLE DISPATCHING MARTINS DRIFT BORDER | VEHICLE AT NATA ENROUTE KAZUNGULA | VEHICLE AT KAZUNGULA BORDER CLEARING | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | VEHICLE AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | VESSEL ARRIVED 23-04-2023 - UNIT TO BE COLLECTED FROM PORT | UNIT COLLECTED FROM PORT - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TUESDAY 02-05-2023 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TODAY 02-05-2023 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TODAY 02-05-2023 | ESTIMATE LOADING DATE MONDAY 08-05-2023 | ESTIMATE LOADING DATE MONDAY 08-05-2023 | VEHICLE LOADING TODAY | TRUCK IN JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT HARARE ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE | TRUCK AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | TRUCK AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | TRUCK AT KASUMBALESA DRC SIDE WAITING TO PROCEED TO WHISKEY | TRUCK AT KASUMBALESA DRC SIDE WAITING TO PROCEED TO WHISKEY | TRUCK AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - AWAITING RELEASE | VEHICLE ENROUTE SITE TO OFFLOAD | VEHICLE ENROUTE SITE TO OFFLOAD | VEHICLE ENROUTE SITE TO OFFLOAD | OFFLOADED 25-05-2023 | OFFLOADED 25-05-2023 | OFFLOADED 25-05-2023 | OFFLOADED 25-05-2023 | OFFLOADED 25-05-2023 | OFFLOADED 25-05-2023 | OFFLOADED 25-05-2023
BA2310 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03524 | CAT0226BVDXZ03524 | CZ209651 | FML2212DSI1865 | VESSEL: TEMA EXPRESS Voy. 224W ETA: 08-01-2023 | COD 2023 146315 | HZ58FGGP | N/A | 2212DSI1865 | 05-04-2023 | OFFLOADED 26-04-2023 | 24-03-2023 | 29-03-2023 | BV INSPECTION COMPLETED | 08/01/2023 | 31-03-2023 | 01-04-2023 | 04-04-2023 | 06-04-2023 | 08-04-2023 | 11-04-2023 | 13-04-2023 | FRANCISTOWN 13-04-2023 |  | KAZ BW 14-04-2023 | KAZ BW 15-04-2023 | KAZ ZM 15-04-2023 | KAZ ZM 16-04-2023 | 17-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 22-04-2023 | 22-04-2023 | 22-04-2023 | 22-04-2023 | 25-04-2023 | 26-04-2023 | [24 empty] | AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | BV TO BE DONE ON MONDAY THE 27/03/2023, AWAITING LOADING DATE | BV TO BE DONE ON MONDAY IF THE BV NUMBER IS RECEIVED, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TOMORROW, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR WEDNESDAY 29-03-2023 - AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | DISPATCHING DURBAN TODAY | VEHICLE IN JOHANNESBURG - DOING TRIP CHECK BEFORE DISPATCHING | VEHICLE IN JOHANNESBURG - FINALIZING TRIP CHECK - DISPATCHING THIS AFTERNOON | VEHICLE AT MOKOPANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT POLOKWANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE AT GROBLERSBRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | VEHICLE DISPATCHING MARTINS DRIFT BORDER | VEHICLE AT NATA ENROUTE KAZUNGULA | VEHICLE AT KAZUNGULA BORDER CLEARING | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | VEHICLE AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | VEHICLE AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023
BA2311 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03525 | CAT0226BADXZ03525 | CZ209647 | FML2212DSI1865 | VESSEL: TEMA EXPRESS Voy. 224W ETA: 08-01-2023 | COD 2023 146315 | HZ58FGGP | N/A | 2212DSI1865 | 05-04-2023 | OFFLOADED 26-04-2023 | 24-03-2023 | 29-03-2023 | BV INSPECTION COMPLETED | 08/01/2023 | 31-03-2023 | 01-04-2023 | 04-04-2023 | 06-04-2023 | 08-04-2023 | 11-04-2023 | 13-04-2023 | FRANCISTOWN 13-04-2023 |  | KAZ BW 14-04-2023 | KAZ BW 14-04-2023 | KAZ ZM 15-04-2023 | KAZ ZM 16-04-2023 | 17-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 22-04-2023 | 22-04-2023 | 22-04-2023 | 22-04-2023 | 25-04-2023 | 26-04-2023 | [24 empty] | AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | BV TO BE DONE ON MONDAY THE 27/03/2023, AWAITING LOADING DATE | BV TO BE DONE ON MONDAY IF THE BV NUMBER IS RECEIVED, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TOMORROW, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR WEDNESDAY 29-03-2023 - AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | DISPATCHING DURBAN TODAY | VEHICLE IN JOHANNESBURG - DOING TRIP CHECK BEFORE DISPATCHING | VEHICLE IN JOHANNESBURG - FINALIZING TRIP CHECK - DISPATCHING THIS AFTERNOON | VEHICLE AT MOKOPANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT POLOKWANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE AT GROBLERSBRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | VEHICLE DISPATCHING MARTINS DRIFT BORDER | VEHICLE AT NATA ENROUTE KAZUNGULA | VEHICLE AT KAZUNGULA BORDER CLEARING | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | VEHICLE AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE AND RELEASE | VEHICLE AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023 | OFFLOADED 26-04-2023
BA2381 | 1 X CAT DE400E0(C13) GENSETS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | CAT00C13KDH404501 | N/A | FML 2302DSI1963 | VESSEL: GIULIA Voy ZF308A ETA DURBAN: 04-04-2023 | COD 2023 167387 | AAZ6912 (175) | AAF6747 / AAF6746 | 2302DSI1963A | 14-04-2023 | OFFLOADED 24-05-2023 | 04-04-2023 | 11-04-2023 | BV COMPLETED | 30-03-2023 | 13-04-2023 | 13-04-2023 | 15-04-2023 | 15-04-2023 | 16-04-2023 | 16-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 20-04-2023 | 20-04-2023 | 21-04-2023 | 22-04-2023 | 24-04-2023 | 29-04-2023 | 29-04-2023 | 03-05-20203 | 28-04-2023 | 05-05-2023 | 08-05-2023 | 23-05-2023 | 23-05-2023 | [24 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VESSEL ARRIVED & IS CURRENTLY WORKING | VESSEL ARRIVED, AWAITING COMPLETION OF DISCHARGE | RECEIVED AT WAREHOUSE - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 06-04-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN | JOHANNESBURG ENROUTE MUSINA | ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE TO DISPATCH FOR CHIRUNDU | VEHICLE CURRENTLY ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAIITNG SEGUCE DAY 9 | TRUCK EN-ROUTE TO KANYAKHA | TRUCK AT KANYAKHA WAITING RELEASE | TRUCK AT LUBUMBASHI WAITING RELEASE | TRUCK AT ENROUTE CONGO EQUIPMENT | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | ENROUTE SITE FOR OFFLOADING | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - UNDER CLEARANCE | VEHICLE DISPATCHED LUBUMBASHI ENROUTE SITE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023
BA2382 | 1 X CAT DE400E0(C13) GENSETS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | CAT00C13JDH404502 | N/A | FML 2302DSI1963 | VESSEL: GIULIA Voy ZF308A ETA DURBAN: 04-04-2023 | COD 2023 167387 | AAZ6912 (175) | AAF6747 / AAF6746 | 2302DSI1963A | 14-04-2023 | OFFLOADED 24-05-2023 | 04-04-2023 | 11-04-2023 | BV COMPLETED | 30-03-2023 | 13-04-2023 | 13-04-2023 | 15-04-2023 | 15-04-2023 | 16-04-2023 | 16-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 20-04-2023 | 20-04-2023 | 21-04-2023 | 22-04-2023 | 24-04-2023 | 29-04-2023 | 29-04-2023 | 03-05-20203 | 28-04-2023 | 05-05-2023 | 08-05-2023 | 23-05-2023 | 23-05-2023 | [24 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VESSEL ARRIVED & IS CURRENTLY WORKING | VESSEL ARRIVED, AWAITING COMPLETION OF DISCHARGE | RECEIVED AT WAREHOUSE - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 06-04-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN | JOHANNESBURG ENROUTE MUSINA | ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE TO DISPATCH FOR CHIRUNDU | VEHICLE CURRENTLY ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAIITNG SEGUCE DAY 9 | TRUCK EN-ROUTE TO KANYAKHA | TRUCK AT KANYAKHA WAITING RELEASE | TRUCK AT LUBUMBASHI WAITING RELEASE | TRUCK AT ENROUTE CONGO EQUIPMENT | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | ENROUTE SITE FOR OFFLOADING | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - UNDER CLEARANCE | VEHICLE DISPATCHED LUBUMBASHI ENROUTE SITE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023
BA2387 | 1 X CAT DE400E0(C13) GENSETS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | CAT00C13EDH404508 | N/A | FML 2302DSI1963 | VESSEL: GIULIA Voy ZF308A ETA DURBAN: 04-04-2023 | COD 2023 167387 | AAZ6912 (175) | AAF6747 / AAF6746 | 2302DSI1963A | 14-04-2023 | OFFLOADED 24-05-2023 | 04-04-2023 | 11-04-2023 | BV COMPLETED | 30-03-2023 | 13-04-2023 | 13-04-2023 | 15-04-2023 | 15-04-2023 | 16-04-2023 | 16-04-2023 | 17-04-2023 | 17-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 19-04-2023 | 20-04-2023 | 20-04-2023 | 21-04-2023 | 22-04-2023 | 24-04-2023 | 29-04-2023 | 29-04-2023 | 03-05-20203 | 28-04-2023 | 05-05-2023 | 08-05-2023 | 23-05-2023 | 23-05-2023 | [24 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | VESSEL ARRIVED & IS CURRENTLY WORKING | VESSEL ARRIVED, AWAITING COMPLETION OF DISCHARGE | RECEIVED AT WAREHOUSE - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR TOMORROW 06-04-2023 | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV NUMBER RECEIVED - BV INSPECTION BOOKED FOR THE 11/04/2023 DUE TO PUBLIC HOLIDAY IN RSA THIS WEEKEND | BV INSPECTION COMPLETED - LOADING TODAY | LOADED, DISPATCHING DURBAN | JOHANNESBURG ENROUTE MUSINA | ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE TO DISPATCH FOR CHIRUNDU | VEHICLE CURRENTLY ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE AT LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE AND RELEASE | VEHICLE AT KASUMBALESA DRC SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY AWAIITNG SEGUCE DAY 9 | TRUCK EN-ROUTE TO KANYAKHA | TRUCK AT KANYAKHA WAITING RELEASE | TRUCK AT LUBUMBASHI WAITING RELEASE | TRUCK AT ENROUTE CONGO EQUIPMENT | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | TRUCK AT LUBUMBASHI, WAITING DOCUMENTS AND RELEASE | ENROUTE SITE FOR OFFLOADING | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - UNDER CLEARANCE | VEHICLE DISPATCHED LUBUMBASHI ENROUTE SITE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023 | OFFLOADED 24-05-2023
BA2462 | 1 X CAT D8 TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M8D00382 | CAT000D8HM8D00382 | N/A | FML2304DSI2030 | VESSEL: VICTORIOUS ACE 65A ETA DURBAN: 25-04-2023 | COD 2023 189411 | ND705348 | ND184465 | ND63878 | 09-05-2023 | OFFLOADED 29-05-2023 | 04-05-2023 | 05-05-2023 | BV COMPLETED | 25-04-2023 | 09-05-2023 | MIDDELBURG 10-05-2023 | MIDDELBURG 10-05-2023 | 11-05-2023 | 11-05-2023 | 11-05-2023 | 14-05-2023 | 15-05-2023 | 15-05-2023 | 15-05-2023 | 16-05-2023 | 16-05-2023 | 17-05-2023 | 17-05-2023 | 17-05-2023 | 18-05-2023 | 19-05-2023 | 23-05-2023 | 24-05-2023 | 25-05-2023 | 25-05-2023 | 26-05-2023 | 26-05-2023 | 26-05-2023 | 29-05-2023 | [16 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 25-03-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-04-2023 | CONTAINER AT BONDED FACILITY TO BE UNPACKED TODAY | BV INSPECTION BOOKED FOR TODAY | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-03-2023 | LOADED, DISPATCHING DURBAN TODAY | VEHICLE CURRENTLY AT MIDDELBURG ENROUTE MUSIAN | VEHICLE CURRENTLY DISPATCH BEIT BRIDGE ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT HARARE TO DISPATCH TODAY | VEHICLE CURRENTLY AT HARARE ON BREAKDOWN-ESTIMATED REPAIR TIME TO BE ADVISED | VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE CLEARING | VEHICLE ENROUTE KITWE | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT WHISKY AWAITING CLEARANCE AND RELEASE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | VEHICLE CURRENLTY AT WHISKY UNDER CLEARANCE | TRUCK EN-ROUTE TO CONGO EQUIPMENT | TRUCK TO LOAD TODAY | TRUCK AT HENDRINA ENROUTE MUSINA | TRUCK AT MARBLE HALL ENROUTE MUSINA | TRUCK AT BEIT BRIDGE RSA SIDE CLEARING | KWEKWE ENROUTE HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAPIRI MPOSHE ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA IN QUEUE TO PROCEED TO KASUMBLAESA | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | ON SITE AWAITING TO OFFLOAD | OFFLOADED 29-05-2023 | OFFLOADED 29-05-2023 | OFFLOADED 29-05-2023 | OFFLOADED 29-05-2023 | OFFLOADED 29-05-2023
BA2307 | 1 X CAT426F2 BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | EJ405995 | CAT0426FTEJ405995 | CC206201 | FML2303DSI2012 | VESSEL: SEASPAN LAHORE V. 2241W - ETA DURBAN 08-11-2022 | COD 2023 199321 | BCD4142ZM | DRS624MP | N/A | 22-05-2023 | OFFLOADED 13-06-2023 | 16-05-2023 | 18-05-2023 | BV COMPLETED | 08-11-2022 | 23-05-2023 | 26-05-2023 | 29-05-2023 | 29-05-2023 | 30-05-2023 | 30-05-2023 | 30-05-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 08-06-2023 | 08-06-2023 | MOKAMBO 08-06-2023 | MOKAMBO 09-06-2023 | 09-06-2023 | 10-06-2023 | 11-06-2023 | 12-06-2023 | 13-06-2023 | [57 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION TO BE DONE TOMORROW 18-05-2023 | BV INSPECTION TO BE DONE TODAY 18-05-2023 | BV INSPECTION DONE - LOADING NEXT WEEK | VEHICLE LOADING TODAY - PLANNING TO DISPATCH TOMORROW MORNING | VEHICLE LOADING TODAY - PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE AT MARIANHILLTOLL ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG WAREHOUSE UNDERGOING FINAL TRIP CHECK | TRUCK DISPATCHING JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE BORDER | TRUCK DISPATCHING GROBLERS BRIDGE BORDER | TRUCK AT KASANGULA BORDER CLEARING | TRUCK DISPATCHING KASUNGULA EN-ROUTE TO LUSAKA | TRUCK NDOLA EN-ROUTE TO KASUMBALESA | TRUCK AT NDOLA IN THE QUEUE TO KASUMBALESA | DISPATHCING NDOLA FOR KASUMBALESA | NDOLA IN THE QUEUE TO DISPATCH FOR KASUMBALESA | DISPATCHING NDOLA FOR KASUMBALESA | MOKAMBO BORDER CLEARING | AT CONNEX LUBUMBASHI, WAITING RELEASE | ON SITE WAITING TO OFFLOAD - DAY 1 | OFFLOADED 13-06-2023 | OFFLOADED 13-06-2023
BA2443 | 1 X CAT336 BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML2304DSI2028 | VESSEL: SALOME Voy. EE306 ETA DURBAN 28-04-2023 | COD 2023 199325 | JM17XFGP | N/A | 2303DSI2006 | 21-05-2023 | OFFLOADED 14-06-2023 | 16-05-2023 | 18-05-2023 | BV COMPLETED | 28-04-2023 | 22-05-2023 | 22-05-2023 | 23-05-2023 | 23-05-2023 | 23-05-2023 | 23-05-2023 | 24-05-2023 | 25-05-2023 | 26-05-2023 | 27-05-2023 | 28-05-2023 | 28-05-2023 | 28-05-2023 | 29-05-2023 | 27-05-2023 | 27-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 05-06-2023 | 05-06-2023 | 07-06-2023 | 07-06-2023 | 13-06-2023 | 14-06-2023 | [60 empty] | AWAITING BV NUMBER - LOADING PLANNED FOR 19-05-2023 | BV NUMBER RECEIVED - WAITING VALIDATION OF BV NUMBER TO BOOK INSPECTIONS | BV INSPECTION TO BE DONE TODAY 18-05-2023 | BV INSPECTION DONE - LOADING NEXT WEEK | UNIT LOADED - VEHICLE TO DISPATCH TODAY | VEHICLE AT GROBLERSBRIDGE IN QUEUE TO CROSS TO BOTSWANA | VEHICLE CURRENTLY AT KAZANGULA ENROUTE LUSAKA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KITWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KITWE ON BREAKDOWN | VEHICLE CURRENTLY AT KITWE ON BREAKDOWN | TRUCK AT KASUMBALESA AWAITING CLEARANCE | TRUCK AT KASUMBALESA AWAITING CLEARANCE DAY 2 | KASUMBALESA DRC SIDE TO DISPATCH FOR WHISKEY TODAY | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | AT CONNEX LUBUMBASHI - WAITING RELEASE | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 2 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 5 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023
BA2444 | 1 X CAT336 BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML2303DSI2006 | VESSEL: TIJUCA Voy. EE305 ETA DURBAN 18-04-2023 | COD 2023 199325 | JM17XFGP | N/A | 2303DSI2006 | 21-05-2023 | OFFLOADED 14-06-2023 | 16-05-2023 | 18-05-2023 | BV COMPLETED | 18-04-2023 | 22-05-2023 | 22-05-2023 | 23-05-2023 | 23-05-2023 | 23-05-2023 | 23-05-2023 | 24-05-2023 | 25-05-2023 | 26-05-2023 | 27-05-2023 | 28-05-2023 | 28-05-2023 | 28-05-2023 | 29-05-2023 | 27-05-2023 | 27-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 05-06-2023 | 05-06-2023 | 07-06-2023 | 07-06-2023 | 13-06-2023 | 14-06-2023 | [60 empty] | AWAITING BV NUMBER - LOADING PLANNED FOR 19-05-2023 | BV NUMBER RECEIVED - WAITING VALIDATION OF BV NUMBER TO BOOK INSPECTIONS | BV INSPECTION TO BE DONE TODAY 18-05-2023 | BV INSPECTION DONE - LOADING NEXT WEEK | UNIT LOADED - VEHICLE TO DISPATCH TODAY | VEHICLE AT GROBLERSBRIDGE IN QUEUE TO CROSS TO BOTSWANA | VEHICLE CURRENTLY AT KAZANGULA ENROUTE LUSAKA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KITWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KITWE ON BREAKDOWN | VEHICLE CURRENTLY AT KITWE ON BREAKDOWN | TRUCK AT KASUMBALESA AWAITING CLEARANCE | TRUCK AT KASUMBALESA AWAITING CLEARANCE DAY 2 | KASUMBALESA DRC SIDE TO DISPATCH FOR WHISKEY TODAY | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | AT CONNEX LUBUMBASHI - WAITING RELEASE | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 2 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 5 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023
BA1860 | 1 X CAT CS11GC-01A VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801244 | CAT0CS11CRK801244 | MFX11928 | FML2201DSI1396 | MSC VIDHI Voy. ZF201A ETA DURBAN: 25-02-2022 | COD 2023 200952 | BCE13ZM | ACM6271T | 2201DSI1396 | 26-05-2023 | OFFLOADED 15-06-2023 | 18-05-2023 | 22-05-2023 | BV NUMBER RECEIVED | 25-02-2022 | 23-05-2023 | 26-05-2023 | 29-05-2023 | 30-05-2023 | 30-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 06-06-2023 | 07-06-2023 | 07-06-2023 | 09-06-2023 | 09-06-2023 | 09-06-2023 | 11-06-2023 | 14-06-2023 | 15-06-2023 | [58 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR MONDAY 22-05-2023 | BV INSPECTION BOOKED FOR TODAY | VEHICLE LOADING TODAY - PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE AT MARIANHILLTOLL ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG WAREHOUSE UNDERGOING FINAL TRIP CHECK | TRUCK DISPATCHING JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE BORDER | KAZUNGULA BW SIDE CLEARING | TRUCK AT KASANGULA BORDER CLEARING | TRUCK DISPATCHING KASUNGULA EN-ROUTE TO LUSAKA | TRUCK NDOLA EN-ROUTE TO KASUMBALESA | TRUCK AT KITWE IN THE QUEUE TO KASUMBALESA | TRUCK AT KITWE IN THE QUEUE TO KASUMBALESA | TRUCK AT CHINGOLA IN THE QUEUE TO KASUMBALESA | KASUMBALESA BORDER CLEARING | KASUMBALESA DRC SIDE CLEARING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023
BA1861 | 1 X CAT CS11GC-01A VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801246 | CAT0CS11PRK801246 | MFX11938 | FML2201DSI1396 | MSC VIDHI Voy. ZF201A ETA DURBAN: 25-02-2022 | COD 2023 200952 | BCE13ZM | ACM6271T | 2201DSI1396 | 26-05-2023 | OFFLOADED 15-06-2023 | 18-05-2023 | 22-05-2023 | BV NUMBER RECEIVED | 25-02-2023 | 23-05-2023 | 26-05-2023 | 29-05-2023 | 30-05-2023 | 30-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 06-06-2023 | 07-06-2023 | 07-06-2023 | 09-06-2023 | 09-06-2023 | 09-06-2023 | 11-06-2023 | 14-06-2023 | 15-06-2023 | [58 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR MONDAY 22-05-2023 | BV INSPECTION BOOKED FOR TODAY | VEHICLE LOADING TODAY - PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE AT MARIANHILLTOLL ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG WAREHOUSE UNDERGOING FINAL TRIP CHECK | TRUCK DISPATCHING JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE BORDER | KAZUNGULA BW SIDE CLEARING | TRUCK AT KASANGULA BORDER CLEARING | TRUCK DISPATCHING KASUNGULA EN-ROUTE TO LUSAKA | TRUCK NDOLA EN-ROUTE TO KASUMBALESA | TRUCK AT KITWE IN THE QUEUE TO KASUMBALESA | TRUCK AT KITWE IN THE QUEUE TO KASUMBALESA | TRUCK AT CHINGOLA IN THE QUEUE TO KASUMBALESA | KASUMBALESA BORDER CLEARING | KASUMBALESA DRC SIDE CLEARING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023
BA2101 | 1 X CAT CS11GC-01A VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801389 | CAT0CS11PRK01389 | MFX12436 | FML2206DSI1643 | MORNING CHAMPION Voy. 160 ETA DURBAN: 27-07-2023 | COD 2023 200952 | NJ103761 | ND256330 | ND63890 | 09-06-2023 | OFFLOADED 26-06-2023 | 18-05-2023 | 22-05-2023 | BV COMPLETED | 27-07-2023 | 03-06-2023 | 03-06-2023 | 04-06-2023 | 04-06-2023 | 04-06-2023 | 04-06-2023 | 07-06-2023 | 07-06-2023 | 08-06-2023 | 09-06-2023 | 10-06-2023 | 10-06-2023 | 12-06-2023 | 12-06-2023 | 12-06-2023 | 13-06-2023 | 13-06-2023 | 13-06-2023 | 14-06-2023 | 16-06-2023 | 17-06-2023 | 24-06-2023 | 25-06-2023 | 25-06-2023 | 26-06-2023 | [58 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR MONDAY 22-05-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | BV INSPECTION COMPLETE - LOADING DATE TO BE CONFIRMED | TRUCK LOADED AND WILL DISPATCH MONDAY THE 05/06/2023 | VEHICLE CURRETNLY AT BEIT BRIDGE RSA SIDE | VEHICLE AT BEIT BRIDGE RSA SIDE TO CROSS TO ZIM SIDE | VEHICLE AT BEIT BRIDGE ZIM SIDE | VEHICLE AT MOUNT HAMPDEN ENROUTE CHIRUDNU | VEHICLE AT CHINHOYI ENROUTE CHIRUDNU | VEHICLE AT CHIRUDNU ZAM SIDE | VEHICLE AT KABWE ENROUTE KASUMBALESA | VEHICLE AT CHILLILIBOMBWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE - DAY 3 | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE - DAY 3 | VEHICLE CURRENTLY AT WHISKEY AWAITING DOCUMENTS FOR BA2458 IN ORDER TO DISPATCH - DAY 4 | VEHICLE AT CONGO EQUIPMENT AWAIITNG TO OFFLOAD | OFFLOADED 26-06-2023 | OFFLOADED 26-06-2023 | OFFLOADED 26-06-2023 | OFFLOADED 26-06-2023 | OFFLOADED 26-06-2023
BA1860 | 1 X CAT CS11GC-01A VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801244 | CAT0CS11CRK801244 | MFX11928 | FML2201DSI1396 | MSC VIDHI Voy. ZF201A ETA DURBAN: 25-02-2022 | COD 2023 200952 | BCE13ZM | ACM6271T | 2201DSI1396 | 26-05-2023 | OFFLOADED 15-06-2023 | 18-05-2023 | 22-05-2023 | BV NUMBER RECEIVED | 25-02-2022 | 23-05-2023 | 26-05-2023 | 29-05-2023 | 30-05-2023 | 30-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 06-06-2023 | 07-06-2023 | 07-06-2023 | 09-06-2023 | 09-06-2023 | 09-06-2023 | 11-06-2023 | 14-06-2023 | 15-06-2023 | [58 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR MONDAY 22-05-2023 | BV INSPECTION BOOKED FOR TODAY | VEHICLE LOADING TODAY - PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE AT MARIANHILLTOLL ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG WAREHOUSE UNDERGOING FINAL TRIP CHECK | TRUCK DISPATCHING JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE BORDER | KAZUNGULA BW SIDE CLEARING | TRUCK AT KASANGULA BORDER CLEARING | TRUCK DISPATCHING KASUNGULA EN-ROUTE TO LUSAKA | TRUCK NDOLA EN-ROUTE TO KASUMBALESA | TRUCK AT KITWE IN THE QUEUE TO KASUMBALESA | TRUCK AT KITWE IN THE QUEUE TO KASUMBALESA | TRUCK AT CHINGOLA IN THE QUEUE TO KASUMBALESA | KASUMBALESA BORDER CLEARING | KASUMBALESA DRC SIDE CLEARING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023
BA1861 | 1 X CAT CS11GC-01A VIBRATORY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RK801246 | CAT0CS11PRK801246 | MFX11938 | FML2201DSI1396 | MSC VIDHI Voy. ZF201A ETA DURBAN: 25-02-2022 | COD 2023 200952 | BCE13ZM | ACM6271T | 2201DSI1396 | 26-05-2023 | OFFLOADED 15-06-2023 | 18-05-2023 | 22-05-2023 | BV NUMBER RECEIVED | 25-02-2023 | 23-05-2023 | 26-05-2023 | 29-05-2023 | 30-05-2023 | 30-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 01-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 02-06-2023 | 06-06-2023 | 07-06-2023 | 07-06-2023 | 09-06-2023 | 09-06-2023 | 09-06-2023 | 11-06-2023 | 14-06-2023 | 15-06-2023 | [58 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR MONDAY 22-05-2023 | BV INSPECTION BOOKED FOR TODAY | VEHICLE LOADING TODAY - PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE AT MARIANHILLTOLL ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT HARRISMITH ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG WAREHOUSE UNDERGOING FINAL TRIP CHECK | TRUCK DISPATCHING JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE BORDER | KAZUNGULA BW SIDE CLEARING | TRUCK AT KASANGULA BORDER CLEARING | TRUCK DISPATCHING KASUNGULA EN-ROUTE TO LUSAKA | TRUCK NDOLA EN-ROUTE TO KASUMBALESA | TRUCK AT KITWE IN THE QUEUE TO KASUMBALESA | TRUCK AT KITWE IN THE QUEUE TO KASUMBALESA | TRUCK AT CHINGOLA IN THE QUEUE TO KASUMBALESA | KASUMBALESA BORDER CLEARING | KASUMBALESA DRC SIDE CLEARING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023 | OFFLOADED 15-06-2023
BA2174 | 1 X CAT988K WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | L8X00483 | CAT0988KCL8X00483 | TXW07246 | FML2304DSI2021 | VESSEL:VICTORIOUS ACE Voy. 0065A ETA: 23-04-2023 | COD 2023 184331 | ND568309 | ND566910 / ND564162 | ND63855 | 08-05-2023 | OFFLOADED 23-06-2023 | 26-04-2023 | 02-05-2023 | BV COMPLETED | 23-04-2023 | 22-05-2023 | 24-05-2023 | 24-05-2023 | 25-05-2023 | 25-05-2023 | 26-05-2023 | 27-05-2023 | 29-05-2023 | 29-05-2023 | 29-05-2023 | 29-05-2023 | 29-05-2023 | 01-06-2023 | 02-06-2023 | 03-06-2023 | 03-06-2023 | 04-06-2023 | 06-06-2023 | 06-06-2023 | 07-06-2023 | 07-06-2023 | 09-06-2023 | 10-06-2023 | TENKE 14-06-2023 | 23-06-2023 | [24 empty] | AWAITING BV NUMBER IN ORDER TO BOOK BV INSPECTION | BV TO BE DONE ON MONDAY THE 27/03/2023, AWAITING LOADING DATE | BV TO BE DONE ON MONDAY IF THE BV NUMBER IS RECEIVED, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TOMORROW, AWAITING LOADING DATE | BV INSPECTION BOOKED FOR WEDNESDAY 29-03-2023 - AWAITING LOADING DATE | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | BV INSPECTION BOOKED FOR TODAY - LOADING TOMORROW 30-03-2023 | DISPATCHING DURBAN TODAY | VEHICLE IN JOHANNESBURG - DOING TRIP CHECK BEFORE DISPATCHING | VEHICLE IN JOHANNESBURG - FINALIZING TRIP CHECK - DISPATCHING THIS AFTERNOON | VEHICLE AT MOKOPANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT POLOKWANE ENROUTE GROBLERSBRIDGE BORDER | VEHICLE AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | VEHICLE AT GROBLERSBRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | VEHICLE DISPATCHING MARTINS DRIFT BORDER | VEHICLE AT NATA ENROUTE KAZUNGULA | VEHICLE AT KAZUNGULA BORDER CLEARING | VEHICLE AT KITWE ENROUTE KASUMBALESA | VEHICLE AT KITWE IN THE QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUEUE TO CROSS TO DRC SIDE | VEHICLE AT KASUMBALESA DRC SIDE WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | VESSEL ARRIVED 23-04-2023 - UNIT TO BE COLLECTED FROM PORT | UNIT COLLECTED FROM PORT - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TUESDAY 02-05-2023 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TODAY 02-05-2023 | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TODAY 02-05-2023 | ESTIMATE LOADING DATE MONDAY 08-05-2023 | ESTIMATE LOADING DATE MONDAY 08-05-2023 | ESTIMATE LOADING DATE MONDAY 08-05-2023 | ESTIMATE LOADING DATE 12-05-2023-DELAYED COMING SOUTH BOUND FROM DRC | ESTIMATE LOADING DATE 12-05-2023-DELAYED COMING SOUTH BOUND FROM DRC | ESTIMATE LOADING DATE 12-05-2023-DELAYED COMING SOUTH BOUND FROM DRC | ESTIMATE LOADING DATE 15-05-2023-DELAYED COMING SOUTH BOUND FROM DRC | ESTIMATE LOADING DATE 15-05-2023-DELAYED COMING SOUTH BOUND FROM DRC | ESTIMATE LOADING DATE 17-05-2023-DELAYED COMING SOUTH BOUND FROM DRC | ESTIMATE LOADING DATE 17-05-2023-DELAYED COMING SOUTH BOUND FROM DRC | ESTIMATE LOADING DATE 18-05-2023-DELAYED COMING SOUTH BOUND FROM DRC | VEHICLE CURRENTLY IN WORKSHOP BUSY WITH MAINTENACE CHECKS AND WILL LOAD ONCE DONE | VEHICLE CURRENTLY IN WORKSHOP BUSY WITH MAINTENACE CHECKS AND WILL LOAD ONCE DONE | VEHICLE CURRENLTY AT RICHMOND ENROUTE LADYSMITH | VEHICLE CURRENLTY AT NEWCASTLE ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT MIDDLEBURG - WAITING LIMPOPO PERMIT IN ORDER TO PROCEED | VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT HARARE EN-ROUTE TO CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU EN-ROUTE TO KASUMBALESA | TRUCK AT CHISAMBA EN-ROUTE TO KASUMBALESA | TRUCK AT CHINGOLA EN-ROUTE TO KASUMBALESA | TRUCK AT KASUMBALESA ZAM SIDE | TRUCK AT KASUMBALESA DRC SIDE | TRUCK AT WHISKEY WAITING RELEASE | TRUCK AT WHISKEY WAITING RELEASE - DAY 2 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 3 | VEHICLE AT DANGELO ENROUTE TENKE | VEHICLE AT ENROUTE TENKE (10KM BEFORE) | VEHICLE AT TENKE WAITING TO OFFLOAD | VEHICLE AT TENKE UNDER CUSTOMS CLEARANCE | VEHICLE AT TENKE UNDER CUSTOMS CLEARANCE | VEHICLE AT TENKE UNDER CUSTOMS CLEARANCE - DAY 3 | VEHICLE AT TENKE UNDER CUSTOMS CLEARANCE - DAY 3 | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED | OFFLOADED 23-06-2023 | OFFLOADED 23-06-2023 | OFFLOADED 23-06-2023 | OFFLOADED 23-06-2023 | OFFLOADED 23-06-2023
BA2443 | 1 X CAT336 BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML2304DSI2028 | VESSEL: SALOME Voy. EE306 ETA DURBAN 28-04-2023 | COD 2023 199325 | JM17XFGP | N/A | 2303DSI2006 | 21-05-2023 | OFFLOADED 14-06-2023 | 16-05-2023 | 18-05-2023 | BV COMPLETED | 28-04-2023 | 22-05-2023 | 22-05-2023 | 23-05-2023 | 23-05-2023 | 23-05-2023 | 23-05-2023 | 24-05-2023 | 25-05-2023 | 26-05-2023 | 27-05-2023 | 28-05-2023 | 28-05-2023 | 28-05-2023 | 29-05-2023 | 27-05-2023 | 27-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 05-06-2023 | 05-06-2023 | 07-06-2023 | 07-06-2023 | 13-06-2023 | 14-06-2023 | [60 empty] | AWAITING BV NUMBER - LOADING PLANNED FOR 19-05-2023 | BV NUMBER RECEIVED - WAITING VALIDATION OF BV NUMBER TO BOOK INSPECTIONS | BV INSPECTION TO BE DONE TODAY 18-05-2023 | BV INSPECTION DONE - LOADING NEXT WEEK | UNIT LOADED - VEHICLE TO DISPATCH TODAY | VEHICLE AT GROBLERSBRIDGE IN QUEUE TO CROSS TO BOTSWANA | VEHICLE CURRENTLY AT KAZANGULA ENROUTE LUSAKA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KITWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KITWE ON BREAKDOWN | VEHICLE CURRENTLY AT KITWE ON BREAKDOWN | TRUCK AT KASUMBALESA AWAITING CLEARANCE | TRUCK AT KASUMBALESA AWAITING CLEARANCE DAY 2 | KASUMBALESA DRC SIDE TO DISPATCH FOR WHISKEY TODAY | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | AT CONNEX LUBUMBASHI - WAITING RELEASE | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 2 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 5 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023
BA2444 | 1 X CAT336 BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML2303DSI2006 | VESSEL: TIJUCA Voy. EE305 ETA DURBAN 18-04-2023 | COD 2023 199325 | JM17XFGP | N/A | 2303DSI2006 | 21-05-2023 | OFFLOADED 14-06-2023 | 16-05-2023 | 18-05-2023 | BV COMPLETED | 18-04-2023 | 22-05-2023 | 22-05-2023 | 23-05-2023 | 23-05-2023 | 23-05-2023 | 23-05-2023 | 24-05-2023 | 25-05-2023 | 26-05-2023 | 27-05-2023 | 28-05-2023 | 28-05-2023 | 28-05-2023 | 29-05-2023 | 27-05-2023 | 27-05-2023 | 31-05-2023 | 31-05-2023 | 01-06-2023 | 05-06-2023 | 05-06-2023 | 07-06-2023 | 07-06-2023 | 13-06-2023 | 14-06-2023 | [60 empty] | AWAITING BV NUMBER - LOADING PLANNED FOR 19-05-2023 | BV NUMBER RECEIVED - WAITING VALIDATION OF BV NUMBER TO BOOK INSPECTIONS | BV INSPECTION TO BE DONE TODAY 18-05-2023 | BV INSPECTION DONE - LOADING NEXT WEEK | UNIT LOADED - VEHICLE TO DISPATCH TODAY | VEHICLE AT GROBLERSBRIDGE IN QUEUE TO CROSS TO BOTSWANA | VEHICLE CURRENTLY AT KAZANGULA ENROUTE LUSAKA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KAZANGULA BOTSWANA IN QUEUE TO CROSS TO ZAMBIA | VEHICLE CURRENTLY AT KITWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KITWE ON BREAKDOWN | VEHICLE CURRENTLY AT KITWE ON BREAKDOWN | TRUCK AT KASUMBALESA AWAITING CLEARANCE | TRUCK AT KASUMBALESA AWAITING CLEARANCE DAY 2 | KASUMBALESA DRC SIDE TO DISPATCH FOR WHISKEY TODAY | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | AT CONNEX LUBUMBASHI - WAITING RELEASE | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 2 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 5 | AT CONNEX LUBUMBASHI - WAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023 | OFFLOADED 14-06-2023
BA2203 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00887 | CAT00352EHLW00887 | P4E05271 | FML2211DSI1815 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | ND862322 | ND858759 / ND858588 | 130046 | 23-06-2023 | OFFLOADED 13-07-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 26-06-2023 | 28-06-2023 | 30-06-2023 | 01-07-2023 | 03-07-2023 | 03-07-2023 | 04-07-2023 | 05-07-2023 | 05-07-2023 | 06-07-2023 | 06-07-2023 | 07-07-2023 | 07-07-2023 | 08-07-2023 | 08-07-2023 | 09-07-2023 | 09-07-2023 | 10-07-2023 | 10-07-2023 | 11-07-2023 | 11-07-2023 | 12-07-2023 | 13-07-2023 | 13-07-2023 | 13-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 22-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 22-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 22-06-2023 | VEHICLE LOADED - PLANNING TO DISPATCH MONDAY 26-06-2023 UPON RECEIPT OF PERMIT | VEHICLE WILL DISPATCH TODAY-EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT LADYSMITH EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT JHB FILLING DIESEL BEFORE DISPATCH TO BEITBRIDGE BORDER | VEHICLE AT JHB AWAITING GAUTENG PROVINCE PERMIT BEFORE DISPATCH TO BEITBRIDGE BORDER | VEHICLE DISPATCHING JHB EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE BEITBRIDGE BORDER RSA SIDE CLEARING | VEHICLE BEITBRIDGE BORDER ZIM SIDE | VEHICLE AT CHIVI ENROUTE HARARE | VEHICLE AT ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT MUFULIRA ZAM ENROUTE KASUMBLAESA | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE - DAY 2 | VEHICLE CURRENLTY AT LUBUMBASHI - AWAITING CLEARANCE | OFFLOADED 13-07-2023 | OFFLOADED 13-07-2023
BA2283 | 1 X CAT330GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK30678 | CAT00330JFEK30678 | E7A55001 | FML2209DSI1734 | VESSEL: TARIFA Voy. 127 - ETA DURBAN: 26-09-2023 | COD 2022 296959 | KX54BNGP | HN85RXGP | ND63978 | 25-06-2023 | OFFLOADED 12-07-2023 | 03-10-2022 | 03-10-2022 | BV COMPLETED | 26-09-2023 | 26-06-2023 | 26-06-2023 | 27-06-2023 | 28-06-2023 | 28-06-2023 | 29-06-2023 | 01-07-2023 | 02-07-2023 | 03-07-2023 | 03-07-2023 | 03-07-2023 | 03-07-2023 | 04-07-2023 | 04-07-2023 | 04-07-2023 | 04-07-2023 | 05-07-2023 | 05-07-2023 | 06-07-2023 | 06-07-2023 | 06-07-2023 | 10-07-2023 | 11-07-2023 | 12-07-2023 | 12-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING AMENDED LICINCE | AWAITING AMENDED LICENSE | AWAITING AMENDED LICENSE | AWAITING AMENDED LICENSE | AWAITING AMENDED LICENSE | AWAITING AMENDED LICENSE | DISPATCHING DURBAN EN-ROUTE TO BEITBRIDGE | JOHANNESBURG EN-ROUTE TO BEITBRIDGE | TRUCK AT POLOKWANA EN-ROUTE TO BEITBRIDGE | TRUCK AT BEITBRIDGE RSA SIDE AWAIITNG RELEASE | TRUCK AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | TRUCK AT CHINHYOI ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZAM SIDE | TRUCK AT NDOLA | TRUCK AT KASUMBALESA DRC SIDE | TRUCK AT WHISKEY WAITING RELEASE | VEHCILE CURRENLTY AT LUBUMBASHI - CONNEX AFRICA AWAITING RELEASE | VEHCILE CURRENLTY AT LUBUMBASHI - CONNEX AFRICA AWAITING RELEASE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 12-07-2023 | OFFLOADED 12-07-2023 | OFFLOADED 12-07-2023
BA2325 | 1 X CAT333-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TJT00426 | CAT00333HTJT00426 | E7A55306 | FML2209DSI1771 | VESSEL: FREMANTLE HIGHWAY Voy. 71 - ETA DURBAN 09-11-2022 | COD 2023 222678 | BT14FTGP | XVL628GP / XXZ257GP | 2209DSI1771A | 26-06-2023 | OFFLOADED 14-07-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 09-11-2022 | 28-06-2023 | 29-06-2023 | 30-06-2023 | 30-06-2023 | 30-06-2023 | 30-06-2023 | 01-07-2023 | 01-07-2023 | 02-07-2023 | 03-07-2023 | 03-07-2023 | 03-07-2023 | 06-07-2023 | 06-07-2023 | 06-07-2023 | 06-07-2023 | 08-07-2023 | 09-07-2023 | 12-07-2023 | 12-07-2023 | 12-07-2023 | 13-07-2023 | 13-07-2023 | 14-07-2023 | 14-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 07-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 07-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | TRUCK LOADING TODAY AND PLANNED FOR DISPATCH ON WEDNESDAY THE 28/06/2023 | TRUCK LOADING TODAY AND PLANNED FOR DISPATCH ON WEDNESDAY THE 28/06/2023 | TRUCK AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT PRETORIA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT LOUIS TRICHARD EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MAKUTI ENROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZAM SIDE | TRUCK AT CHIRUNDU ZAM SIDE AWAITING PERMIT | TRUCK AT CHIRUNDU ZAM SIDE AWAITING PERMIT | TRUCK AT NDOLA ENROUTE KASUMBALESA | TRUCK AT MOKAMBO ENROUTE KASUMBALESA | TRUCK AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE IN QUEUE TO EXIT MOKAMBO - DELAYED DUE TO HEAVY TRAFFIC | VEHICLE AT CONNEX LUBUMBASHI - AWIAITNG RELEASE | VEHICLE AT CONNEX LUBUMBASHI - AWIAITNG INSPECTION AND RELEASE | OFFLOADED 14-07-2023 | OFFLOADED 14-07-2023
BA2258 | 1 X CAT330-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEL30575 | CAT00330TKEL30575 | E7A54948 | FML2208DSI1696 | VESSEL: DONG-A GLAUCOS Voy. 058 - ETA DURBAN: | COD 2023 222678 | CR83TPGP | KR05VLGP / KS98MPGP | ND63980 | 28-06-2023 | OFFLOADED 17-07-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED |  | 28-06-2023 | 29-06-2023 | 30-06-2023 | 30-06-2023 | 30-06-2023 | 30-06-2023 | 01-07-2023 | 02-07-2023 | 03-07-2023 | 04-07-2023 | 05-07-2023 | 05-07-2023 | 05-07-2023 | 06-07-2023 | 06-07-2023 | 06-07-2023 | 06-07-2023 | 07-07-2023 | 07-07-2023 | 09-07-2023 | 10-07-2023 | 14-07-2023 | 14-07-2023 | 14-07-2023 | 17-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 21-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 21-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 21-06-2023 | ESTIMATED LOADING DATE 27-06-2023 | TRUCK LOADED AWAITING CUSTOM DOCUMENTS AND PERMIT IN ORDER TO DISPATCH | TRUCK LOADED AWAITING CUSTOM DOCUMENTS AND PERMIT IN ORDER TO DISPATCH | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT PRETORIA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT HARARE EN-ROUTE CHIRUNDU | TRUCK AT MAKUTI EN-ROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE | TRUCK AT KAFUE ENROUTE KASUMBALESA | TRUCK AT NDOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING SEGUCE PAYMENT | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE DEPARTED FROM WHISKEY ENROUTE LUBUMBASHI | OFFLOADED 14-07-2023 | OFFLOADED 17-07-2023 | OFFLOADED 17-07-2023
BA2282 | 1 X CAT330GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK30677 | CAT00330KFEK30677 | E7A55014 | FML2209DSI1734 | VESSEL: TARIFA Voy. 127 - ETA DURBAN: 26-09-2023 | COD 2022 296959 | ND72757 | ND613163 | ND63977 | 25-06-2023 | OFFLOADED 18-07-2023 | 03-10-2022 | 03-10-2022 | BV COMPLETED | 26-09-2023 | 26-06-2023 | MIDDELBURG 26-06-2023 | MIDDELBURG 26-06-2023 | 27-06-2023 | 27-06-2023 | 28-06-2023 | 29-06-2023 | 30-06-2023 | 01-07-2023 | 02-07-2023 | 04-07-2023 | 04-07-2023 | 05-07-2023 | 05-07-2023 | 06-07-2023 | 06-07-2023 | 07-07-2023 | 09-07-2023 | 10-07-2023 | 12-07-2023 | 13-07-2023 | 14-07-2023 | 15-07-2023 | 15-07-2023 | 18-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING AMENDED LICINCE | AWAITING AMENDED LICENSE | AWAITING AMENDED LICENSE | AWAITING AMENDED LICENSE | AWAITING AMENDED LICENSE | AWAITING AMENDED LICENSE | TRUCK DISPATCHING THIS MORNING EN-ROUTE TO BEITBRIDGE BORDER | TRUCK MARBLE HALL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER RSA SIDE CROSSING TODAY | TRUCK AT RUTENGA EN-ROUTE TO HARARE | TRUCK AT HARARE EN-ROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT CHIRUNDU ZIM SIDE | TRUCK DISPATCHING CHIRUNDU | TRUCK AT LUSAKA ENROUTE KASUMBALESA | TRUCK AT NDOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CROSS | VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CROSS TO DRC SIDE | VEHICLE CURRENTLY AT WHISKEY UNDER CLEARANCE | VEHICLE DEPARTED FROM WHISKEY ENROUTE LUBUMBASHI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 18-07-2023 | OFFLOADED 18-07-2023
BA2436 | 1 X CAT330GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | FEK40026 | CAT00330PFEK40026 | E7A58079 | FML2301DSI1905 | VESSEL: DA FENG GANG SHUN HAU Voy. 2301 - ETA DURBAN 11-02-2023 | COD 2023 222678 | ND73512 | ND207161 | ND63976 | 23-06-2023 | OFFLOADED 18-07-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 11-02-2023 | 23-06-2023 | 24-06-2023 | 24-06-2023 | 25-06-2023 | 25-06-2023 | 26-06-2023 | 29-06-2023 | 30-06-2023 | 02-07-2023 | 02-07-2023 | 03-07-2023 | 03-07-2023 | 05-07-2023 | 05-07-2023 | 07-07-2023 | 07-07-2023 | 08-07-2023 | 09-07-2023 | 10-07-2023 | 12-07-2023 | 13-07-2023 | 14-07-2023 | 15-07-2023 | 15-07-2023 | 18-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 21-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 21-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 21-06-2023 | VEHICLE LOADED - PLANNING TO DISPATCH MONDAY 26-06-2023 UPON RECEIPT OF PERMIT | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE RSA SIDE | TRUCK AT BEITBRIDGE RSA SIDE CROSSING TODAY | TRUCK AT RUTENGA EN-ROUTE TO HARARE | TRUCK AT HARARE EN-ROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE | TRUCK DISPATCHING CHIRUNDU | TRUCK AT LUSAKA ENROUTE KASUMBALESA | TRUCK AT NDOLA ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAIITNG CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CROSS | VEHICLE CURRENTLY AT KASUMBALESA IN QUEUE TO CROSS | VEHICLE CURRENLTY AT WHISKEY UNDER CLEARANCE | VEHICLE DEPARTED FROM WHISKEY ENROUTE LUBUMBASHI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 18-07-2023 | OFFLOADED 18-07-2023
BA1791 | 1 X CAT305,5E2 MINI HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | WE216145 | CAT3055ECW216145 | 7LX1251 | FML2210DSI1780 | GLOVIS SIRIUS Voy. 044 - ETA DURBAN 06-12-2022 | COD 2023 222678 | ADC1330 | ALP2169T | 2210DSI1780 | 23-06-2023 | OFFLOADED 19-07-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 06-12-2023 | 22-06-2023 | 23-06-2023 | 23-06-2023 | 24-06-2023 | 25-06-2023 | 26-06-2023 | 28-06-2023 | 29-06-2023 | 29-06-2023 | 28-06-2023 | 29-06-2023 | 29-06-2023 | 01-07-2023 | 01-07-2023 | 02-07-2023 | 04-07-2023 | 04-07-2023 | 04-07-2023 | 04-07-2023 | 06-07-2023 | 06-07-2023 | 14-07-2023 | 15-07-2023 | 15-07-2023 | 19-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 23-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23-06-2023 | VEHICLE CURRENLTY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT GROBLERS BRIDGE CLEARING | VEHICLE CURRENLTY AT GROBLERS BRIDGE CLEARING AND RELEASE | VEHICLE CURRENLTY AT MAPE EN-ROUTE TO KAZUNGULA | VEHICLE CURRENLTY AT KAZUNGULA CLEARING | VEHICLE CURRENLTY AT KAZUNGULA CLEARING | VEHICLE CURRENLTY AT NDOLA TO DISPATCH FOR KASUMBALESA | VEHICLE DISPATCHED NDOLA FOR KASUMBALESA | VEHICLE KASUMBALESA CLEARING | VEHICLE KASUMBALESA CLEARING | VEHICLE WHISKEY WAITING RWLEASE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE WAITING FOR ESCORT IN ORDER TO PROCEED TO SITE | VEHICLE WAITING FOR ESCORT IN ORDER TO PROCEED TO SITE | DISPATCHING FROM WHISKEY THIS MORNING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 3 | ON SITE WAITING TO OFFLOAD - DAY 4 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 19-07-2023
BA2116 | 1 X CAT307,5-07A MINI HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GW703020 | CAT03075JGW703020 | 7NA7112 | FML2209DSI1769 | FREMANTLE HIGHWAY Voy. 71 - ETA DURBAN: 09-11-2022 | COD 2023 222678 | ADC1330 | ALP2169T | 2210DSI1780 | 23-06-2023 | OFFLOADED 19-07-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 09-11-2022 | 22-06-2023 | 23-06-2023 | 23-06-2023 | 24-06-2023 | 25-06-2023 | 26-06-2023 | 28-06-2023 | 29-06-2023 | 29-06-2023 | 28-06-2023 | 29-06-2023 | 29-06-2023 | 01-07-2023 | 01-07-2023 | 02-07-2023 | 04-07-2023 | 04-07-2023 | 04-07-2023 | 04-07-2023 | 06-07-2023 | 06-07-2023 | 14-07-2023 | 15-07-2023 | 15-07-2023 | 19-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 23-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23-06-2023 | VEHICLE CURRENLTY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT GROBLERS BRIDGE CLEARING | VEHICLE CURRENLTY AT GROBLERS BRIDGE CLEARING AND RELEASE | VEHICLE CURRENLTY AT MAPE EN-ROUTE TO KAZUNGULA | VEHICLE CURRENLTY AT KAZUNGULA CLEARING | VEHICLE CURRENLTY AT KAZUNGULA CLEARING | VEHICLE CURRENLTY AT NDOLA TO DISPATCH FOR KASUMBALESA | VEHICLE DISPATCHED NDOLA FOR KASUMBALESA | VEHICLE KASUMBALESA CLEARING | VEHICLE KASUMBALESA CLEARING | VEHICLE WHISKEY WAITING RWLEASE | VEHICLE WHISKEY WAITING RELEASE | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE WAITING FOR ESCORT IN ORDER TO PROCEED TO SITE | VEHICLE WAITING FOR ESCORT IN ORDER TO PROCEED TO SITE | DISPATCHING FROM WHISKEY THIS MORNING | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAT 3 | ON SITE WAITING TO OFFLOAD - DAY 4 - PLEASE ASSIST WITH OFFLOADING | OFFLOADED 19-07-2023
BA2344 | 1 X CAT160K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZM20253 | CAT0160KHSZM20253 | TX712553 | FML2211DSI1808 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222659 | ND606157 | ND702867 | ND63979 | 28-06-2023 | OFFLOADED 19-07-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 27-06-2023 | MIDDELBURG 28-06-2023 | MIDDELBURG 28-06-2023 | 29-06-2023 | 30-06-2023 | 30-06-2023 | 02-07-2023 | 03-07-2023 | 04-07-2023 | 04-07-2023 | 05-07-2023 | 05-07-2023 | 05-07-2023 | 06-07-2023 | 06-07-2023 | 07-07-2023 | 07-07-2023 | 08-07-2023 | 08-07-2023 | 12-07-2023 | 13-07-2023 | 14-07-2023 | 15-07-2023 | 15-07-2023 | 19-07-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 23-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23-06-2023 | ESTIMATED LOADING DATE 26-06-2023 | TRUCK LOADED AWAITING CUSTOM DOCUMENTS AND PERMIT IN ORDER TO DISPATCH | TRUCK LOADED AWAITING CUSTOM DOCUMENTS AND PERMIT IN ORDER TO DISPATCH | TRUCK AT BEITBRIDGE RSA SIDE AWAITING CLEARANCE | TRUCK AT LOUIS TRICHART EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER AWAITING RELEASE | TRUCK AT MASVINGO ENROUTE HARARE | TRUCK AT HARARE TO DISPATCH FOR CHIRUNDU | TRUCK AT CHIRUNDU ZIM SIDE | TRUCK AT KAFUE ENROUTE KASUMBALESA | TRUCK AT NDOLA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY IN QUEUE TO CROSS TO WHISKEY | VEHCLE CURRENTLY AT WHISKEY UNDER CLEARANCE | VEHCLE CURRENTLY AT WHISKEY UNDER CLEARANCE AND WAITING FOR DUTIES TO BE PAID | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI - WAITING TO OFFLOAD | OFFLOADED 19-07-2023
BA2473 | 1 X CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JZ200183 | CAT00426CJZ200183 | CC207101 | FML2305DSI2053 | VESSEL: MSC VANESSA V. IA319R - ETA DURBAN: 29-05-2023 | COD 2023 220295 | ACJ1507 | BK04NGGP | 2305DSI2053 | 16-06-2023 | OFFLOADED STATDING TIME APPLICABLE | 12-06-2023 | 14-06-2023 | BV COMPLETED | 29-05-2023 | 15-06-2023 | 16-06-2023 | 20-06-2023 | 21-06-2023 | 22-06-2023 | 23-06-2023 | 24-06-2023 | 25-06-2023 | 25-06-2023 | 26-06-2023 | 26-06-2023 | 26-06-2023 | 26-06-2023 | 30-06-2023 | 30-06-2023 | 05-07-2023 | 05-07-2023 | 06-07-2023 | 06-07-2023 | 10-07-2023 | 11-07-2023 | 14-07-2023 | 14-07-2023 | 22-07-2023 | 25-07-2023 | [76 empty] | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | AT BONDED FACILITY - AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECITON BOOKED FOR WEDNESDAY 14 JUNE 2023 | BV NUMBER RECEIVED - BV INSPECITON BOOKED FOR WEDNESDAY 14 JUNE 2023 | BV INSPECTION COMPLETED - LOADING TODAY FROM BONDED FACILITY | VEHICLE CURRENLTY AT JOHANNESBURG ENROUTE GROBLERSBRIDGE | VEHICLE DISPATCHING JOHANNESBURG ENROUTE POLOKWANE | VEHICLE CURRENLTY AT BELA-BELA ENROUTE GROBLERSBRIDGE | VEHICLE CURRENLTY AT BELA-BELA ENROUTE GROBLERSBRIDGE | VEHICLE CURRENLTY AT GROBLERSBRIDGE AWAITING RELEASE | VEHICLE CURRENLTY AT VIC FALLS EN-ROUTE TO LUSAKA | VEHICLE DISPATCHING VIC FALLS TODAY TO PROCEED TO LUSAKA | VEHICLE DISPATCHING VIC FALLS TODAY TO PROCEED TO LUSAKA-TRUCK HAD A MINOR DELAY | VEHICLE DISPATCHED VIC FALLS EN-ROUTE TO CHIRUNDU | VEHICLE AT CHOMA EN-ROUTE TO LUSAKA | VEHICLE AT NDOLA | VEHICLE DISPATCHED NDOLA FOR KASUMBALESA | VEHICLE ONLY DISPATCHING NDOLA TODAY | VEHICLE AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA CLEARING | VEHICLE AT KASUMBALESA UNDER CLEARANCE | VEHICLE AT KASUMBALESA UNDER CLEARANCE | VEHICLE CURRENTLY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY - UNDER CLEARANCE | VEHICLE CURRENTLY AT WHISKEY - UNDER CLEARANCE AND WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - PLEASE ASSIST | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 3 - PLEASE ASSIST | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 4 - PLEASE ASSIST | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 - PLEASE ASSIST | VEHICLE CURRENTLY AT CE AWAITING TO OFFLOAD-STANDING TIME APPLICABLE | VEHICLE CURRENTLY AT CE AWAITING TO OFFLOAD DAY 3-STANDING TIME APPLICABLE | OFFLOADED STATDING TIME APPLICABLE | OFFLOADED STATDING TIME APPLICABLE | OFFLOADED STATDING TIME APPLICABLE | OFFLOADED STATDING TIME APPLICABLE | OFFLOADED STATDING TIME APPLICABLE
BA2155 | 1 X CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805153 | CAT00740L3F805153 | TXY07643 | FML2303DSI1988 | GREEN MOUNTAIN Voy. 231206 - ETA DURBAN 16-04-2023 | COD 2023 239976 | ZDG755GP | FN90JMGP | ND60415 | 16-07-2023 | OFFLOADED 31-07-2023 | 07-07-2023 | 10-07-2023 | BV NUMBER RECEIVED | 16-04-2023 | 13-07-2023 | MIDDELBURG 14-07-2023 | MIDDELBURG 17-07-2023 | 17-07-2023 | 18-07-2023 | 18-07-2023 | 19-07-2023 | 20-07-2023 | 22-07-2023 | 24-07-2023 | 24-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023 | 25-07-2023 | 25-07-2023 | 25-07-2023 | 26-07-2023 | 27-07-2023 | 28-07-2023 | 29-07-2023 | 29-07-2023 | 29-07-2023 | 31-07-2023 | [96 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECITON TO BE BOOKED FOR MONDAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - AWAITING PERMIT IN ORDER TO DISPATCH | UNIT LOADED - AWAITING PERMIT IN ORDER TO DISPATCH | DISPATCHING DURBAN THIS AFTEROON | LADYSMITH ENROUTE JOHANNESBURG | MIDDELBURG ENROUTE MUSINA | BEIT BRIDGE RSA SIDE | DISPATCHING BEIT BRIDGE ZIM SIDE TO PROCEED TO HARARE | DISPATCHING GWERU ENROUTE HARARE | KADOMA ENROUTE HARARE | CHIRUNDU ZAM SIDE DISPATCHING TODAY | NDOLA EN-ROUTE TO KASUMBALESA BORDER | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA ZAM SIDE CROSSING TO DRC SIDE | TRUCK AT WHISKEY AWAITING FINAL RELEASE | LUBUMBASHI | OFFLOADED 31-07-2023 | OFFLOADED 31-07-2023
BA2154 | 1 X CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805152 | CAT00740A3F805152 | TXY07272 | FML2302DSI1967 | BRIGHT SKY Voy. 231205 - ETA DURBAN 30-03-2023 | COD 2023 239976 | ND747407 | ND692831 / ND692809 | 130515 | 17-07-2023 | OFFLOADED 02-08-2023 | 07-07-2023 | 10-07-2023 | BV NUMBER RECEIVED | 30-03-2023 | 17-07-2023 | 18-07-2023 | 19-07-2023 | 19-07-2023 | 19-07-2023 | 19-07-2023 | 20-07-2023 | 21-07-2023 | 22-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023 | 26-07-2023 | 27-07-2023 | 27-07-2023 | 27-07-2023 | 27-07-2023 | 27-07-2023 | MOKAMBO 29-07-2023 | MOKAMBO 30-07-2023 | 30-07-2023 | 30-07-2023 | 30-07-2023 | 31-07-2023 | 02-08-2023 | [96 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECITON TO BE BOOKED FOR MONDAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | LOADED - DISPATCHING TODAY | JOHANNESBURG DOING ROUTINE CHECK BEFORE DISPATCHING TO BEIT BRIDGE | POLOKWANE ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | CHIRUNDU ZAMBIA SIDE AWAITING CLEARANCE | CHIRUNDU ZAMBIA SIDE AWAITING CLEARANCE | TRUCK AT CHIBOMBO EN-ROUTE TO MOKAMBO BORDER | TRUCK AT KITWE EN-ROUTE TO MOKAMBO BORDER | TRUCK AT MUFULIRA ZAMBIA EN-ROUTE TO MOKAMBO BORDER | TRUCK AT LUBUMBASHI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 02-08-2023 | OFFLOADED 02-08-2023
BA2205 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00889 | CAT00352THLW00889 | P4E05390 | FML2211DSI1815 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | ND754713 | ND715801 / ND718488 | 130172 | 11-07-2023 | OFFLOADED 04-08-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 12-07-2023 | 11-07-2023 | 13-07-2023 | 14-07-2023 | 14-07-2023 | 15-07-2023 | 19-07-2023 | 20-07-2023 | 21-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023 | 26-07-2023 | 27-07-2023 | 27-07-2023 | 27-07-2023 | 28-07-2023 | 28-07-2023 | MOKAMBO 29-07-2023 | MOKAMBO 30-07-2023 | 30-07-2023 | 30-07-2023 | 30-07-2023 | 03-08-2023 | 04-08-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 05-07-2023 | ESTIMATED LOADING DATE 05-07-2023 | ESTIMATED LOADING DATE 05-07-2023 | ESTIMATED LOADING DATE 05-07-2023 | ESTIMATED LOADING DATE 05-07-2023 | LOADING TODAY | LOADED, WAITING PERMIT TO DISPATCH | LOADED, WAITING PERMIT TO DISPATCH | LOADED, WAITING PERMIT TO DISPATCH | UNIT LOADED - AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE CURRENTLY AT WARDEN ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT PRETORIA ENROUTE BEITBRIDGE | VEHICLE CURRENTLY PASSING MOKOPONG ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE | VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHICLE APPROCHING HARARE | CHIRUNDU ZAMBIA SIDE AWAITING CLEARANCE | CHIRUNDU ZAMBIA SIDE AWAITING CLEARANCE | TRUCK AT CHIBOMBO EN-ROUTE TO MOKAMBO BORDER | TRUCK AT KITWE EN-ROUTE TO MOKAMBO BORDER | TRUCK AT MUFULIRA ZAMBIA EN-ROUTE TO MOKAMBO BORDER | TRUCK AT LUBUMBASHI | TRUCK AT LUBUMBASHI | TRUCK AT LUBUMBASHI | TRUCK AT LUBUMBASHI WAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 04-07-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023
BA2152 | 1 X CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805150 | CAT00740C3F805150 | TXY07730 | FML2302DSI1966 | BRIGHT SKY Voy. 231205 - ETA DURBAN 30-03-2023 | COD 2023 239976 | ND431993 | ND923084 | 130570 | 17-07-2023 | OFFLOADED 09-08-2023 | 07-07-2023 | 10-07-2023 | BV NUMBER RECEIVED | 30-03-2023 | 17-07-2023 | 19-07-2023 | 24-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 28-07-2023 | 29-07-2023 | 29-07-2023 | 30-07-2023 | 01-08-2023 | 01-08-2023 | 02-08-2023 | 02-08-2023 | 03-08-2023 | 03-08-2023 | 04-08-2023 | 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 06-08-2023 | 07-08-2023 | 09-08-2023 | 09-08-2023 | [96 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECITON TO BE BOOKED FOR MONDAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | LOADING TODAY TO DISPATCH TOMORROW MORNING | VAN REENEN ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | JOHANNESBURG DOING ROUTINE CHECK & SERVICE BEFORE DISPATCHING FOR THE BORDER | JOHANNESBURG DOING ROUTINE CHECK & SERVICE BEFORE DISPATCHING FOR THE BORDER | DISPATCHING JOHANNESBURG TODAY EN-ROUTE TO BEITBRODGE BORDER | TRUCK AT BEITBRIDGE BORDER RSA SIDE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE BORDER RSA SIDE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE BORDER RSA SIDE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE ZIM SIDE AWAITING FINAL RELEASE | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT LUSAKA ENROUTE MOKAMBO BORDER | TRUCK AT NDOLA ENROUTE MOKAMBO BORDER | VEHICLE AT LUBUMBASHI AWAITING CLEARANCE | VEHICLE AT CONNEX YARD - AWAITING RELEASE | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023
BA2153 | 1 X CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805151 | CAT00740V3F805151 | TXY07606 | FML2303DSI1987 | GREEN MOUNTAIN Voy. 231206 - ETA DURBAN 16-04-2023 | COD 2023 239976 | ND919950 | ND820122 | 130582 | 17-07-2023 | OFFLOADED 09-08-2023 | 07-07-2023 | 10-07-2023 | BV NUMBER RECEIVED | 16-04-2023 | 18-07-2023 | 19-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023 | 26-07-2023 | 28-07-2023 | 29-07-2023 | 29-07-2023 | 30-07-2023 | 01-08-2023 | 01-08-2023 | 02-08-2023 | 02-08-2023 | 03-08-2023 | 03-08-2023 | 04-08-2023 | 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 06-08-2023 | 07-08-2023 | 09-08-2023 | 09-08-2023 | [96 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECITON TO BE BOOKED FOR MONDAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | LOADING TOMORROW AND DISPATCHING TOMORROW | VAN REENEN ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | JOHANNESBURG TO DISPATCH FOR THE BORDER | JOHANNESBURG TO DISPATCH FOR THE BORDER AFTER PERMITS IS RECEIVED | ROEDTAN EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE ZIM SIDE AWAITING FINAL RELEASE | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT LUSAKA ENROUTE MOKAMBO BORDER | TRUCK AT KITWE ENROUTE MOKAMBO BORDER | VEHICLE AT LUBUMBASHI AWAITING CLEARANCE | VEHICLE AT CONNEX YARD - AWAITING RELEASE | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023
BA2204 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00888 | CAT00352CHLW00888 | P4E05277 | FML2211DSI1815 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | ND6811744 | ND821906 / ND822365 | 130561 | 18-07-2023 | OFFLOADED 09-08-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 03-07-2023 | 18-07-2023 | 21-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 28-07-2023 | 29-07-2023 | 30-07-2023 | 30-07-2023 | 01-08-2023 | 01-08-2023 | 02-08-2023 | 03-08-2023 | 03-08-2023 | 03-08-2023 | 04-08-2023 | 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 06-08-2023 | 07-08-2023 | 09-08-2023 | 09-08-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | LOADING TODAY, AWAITING PERMIT AND TRIP CHECK IN ORDER TO DISPATCH | DISPATCHING DURBAN TODAY FOR JOHANNESBURG | WARDEN ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | JOHANNESBURG | JOHANNESBURG BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR THE BORDER | JOHANNESBURG BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR THE BORDER | JOHANNESBURG BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR THE BORDER | PLANNING TO DISPATCH MONDAY 17-07-2023 | PLANNING TO DISPATCH MONDAY 17-07-2023 | PLANNING TO DISPATCH MONDAY 17-07-2023 | PLANNING TO DISPATCH TOMORROW 18-07-2023 | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG DOING ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | JOHANNESBURG DOING ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | DISPATCHING JOHANNESBURG FOR BEITH BRIDGE | MOKOPONG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER CROSSING TODAY | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | PASSING LUSAKA ENROUTE MOKAMBO BORDER | VEHICLE AT NDOLA ENROUTE MOKAMBO BORDER | VEHICLE AT LUBUMBASHI AWAITING CLEARANCE | VEHICLE AT CONNEX YARD - AWAITING RELEASE | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023
BA2208 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00966 | CAT00352LHLW00966 | P4E05427 | FML2211DSI1816 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | ND436314 | ND646811 / ND644688 | 2211DSI1816-BA2208 | 20-07-2023 | OFFLOADED 07-08-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 20-07-2023 | 20-07-2023 | 24-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 28-07-2023 | 29-07-2023 | 30-07-2023 | 30-07-2023 | 01-08-2023 | 01-08-2023 | 02-08-2023 | 03-08-2023 | 03-08-2023 | 03-08-2023 | 04-08-2023 | 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 06-08-2023 | 07-08-2023 | 07-08-2023 | 07-08-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | JOHANNESBURG | MOKOPONG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER SIDE CLEARING | TRUCK AT BEITBRIDGE BORDER SIDE CLEARING | TRUCK AT BEITBRIDGE BORDER SIDE CLEARING | TRUCK AT BEITBRIDGE BORDER CROSSING TODAY | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT LUSAKA ENROUTE MOKAMBO BORDER | TRUCK AT NDOLA ENROUTE MOKAMBO BORDER | VEHICLE AT LUBUMBASHI AWAITING CLEARANCE | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023
BA2326 | 1 X CAT333-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TJT00427 | CAT00333ETJT00427 | E7A55305 | FML2209DSI1771 | VESSEL: FREMANTLE HIGHWAY Voy. 71 - ETA DURBAN 09-11-2022 | COD 2023 222678 | BCC5591ZM | ACL6505T / ACL3942T | 2209DSI1771B | 03-07-2023 | OFFLOADED 07-08-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 09-11-2022 | 12-07-2023 | 13-07-2023 | 13-07-2023 | 18-07-2023 | 18-07-2023 | 18-07-2023 | 20-07-2023 | 20-07-2023 | 20-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023 | 26-07-2023 | 27-06-2023 | 27-06-2023 | 27-06-2023 | 28-07-2023 | 28-07-2023 | MOKAMBO 29-07-2023 | MOKAMBO 31-07-2023 | 01-08-2023 | 01-08-2023 | 01-08-2023 | 01-08-2023 | 07-08-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 07-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 07-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | ESTIMATED LOADING DATE 07-07-2023 | LOADING TODAY | VEHICLE WAS DELAYED - LOADING TODAY | VEHICLE LOADED - PLANNING TO DISPATCH THIS AFTERNOON | UNIT LOADED - AWAITING PERMIT IN ORDER TO DISPATCH | UNIT LOADED - AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE CURRENLTY AT MOKONENE ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT PIETERMARITSBURG ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT JOHANNESBURG ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT MOKOPANE ENROUTE BEIT BRIDGE | VEHICLE CURRENLTY AT BEIT BRIDGE RSA SIDE | VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | VEHICLE CURRENLTY AT KWEKWE ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT CHIRUNDU CLEARAING | VEHICLE CURRENLTY AT CHIRUNDU CLEARAING | VEHICLE CURRENLTY AT CHINGONGO EN-ROUTE TO MOKAMBO BORDER | VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO MOKAMBO BORDER | VEHICLE CURRENLTY AT KITWE EN-ROUTE TO MOKAMBO BORDER | VEHICLE CURRENLTY AT MOKAMBO BORDER | VEHICLE CURRENLTY AT KANYAKI | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | ON SITE WAITING FINAL CLEARANCE & OFFLOADING | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023
BA2182 | 1 X CAT D9 TRACK TYPE TRACTOR - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | AK400676 | CAT000D9AAK00676 | TNR00546 | FML2303DSI1995 | VESSEL: GLOVIS COUNTESS Voy. 0029A - ETA DURBAN: 19-03-2023 | COD 2023 251360 | HNB146MP | ND795036 | ND60437 | 07-08-2023 | OFFLOADED 23-08-2023 | 24-07-2023 | 25-07-2023 | BV COMPLETED | 19-03-2023 | 31-07-2023 | MIDDELBURG 02-08-2023 | MIDDELBURG 02-08-2023 | 03-08-2023 | 03-08-2023 | 03-08-2023 | 09-08-2023 | 11-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 13-08-2023 | 14-08-2023 | 15-08-2023 | 16-08-2023 | 17-08-2023 | 17-08-2023 | 17-08-2023 | 17-08-2023 | 17-08-2023 | 18-08-2023 | 19-02-2023 | 20-08-2023 | 23-08-2023 | 23-08-2023 | [108 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION TO BE DONE TODAY AWAITING LOADING DATES | AWAITING TRUCK ALLOCATION AND LOADING DATES | AWAITING TRUCK ALLOCATION AND LOADING DATES | AWAITING TRUCK ALLOCATION AND LOADING DATES | TRUCK LOADING TODAY | DISPATCHING DURBAN TODAY | RICHARDS BAY ENROUTE BEIT BRIDGE | PIET RETIEF ENROUTE BEIT BRIDGE | POLOKWANE ENROUTE BEIT BRIDGE | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEITBRIDGE BORDER RSA SIDE AWAITING ZIM NOTIFICATION | VEHICLE AT BEITBRIDGE RSA SIDE - CROSSING TO ZIM SIDE | VEHICLE CURRENTLY AT CHIVHU ENROUTE HARARE | VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHISAMBA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT CHINGOLA EN-ROUTE TO KASUMBALESA | VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE | VEHICLE CURRENTLY AT WHISKEY AWAITING FINAL CLEARANCE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE CURRENTLY ENTERING KPM SITE | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2182 | 1 X CAT D9 TRACK TYPE TRACTOR - PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | AK400676 | CAT000D9AAK00676 | TNR00546 | FML2303DSI1995 | VESSEL: GLOVIS COUNTESS Voy. 0029A - ETA DURBAN: 19-03-2023 | COD 2023 251360 | JZ76YXGP | DJ67LWGP / DJ67LTGP | 2303DSI1995 | 07-08-2023 | OFFLOADED 23-08-2023 | 24-07-2023 | 25-07-2023 | BV COMPLETED | 19-03-2023 | 01-08-2023 | 01-08-2023 | 02-08-2023 | 03-08-2023 | 04-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 07-08-2023 | 08-08-2023 | 08-08-2023 | 08-08-2023 | 10-08-2023 | 11-08-2023 | 12-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 14-08-2023 | 14-08-2023 | 14-08-2023 | 15-08-2023 | 18-08-2023 | 23-08-2023 | 23-08-2023 | [108 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION TO BE DONE TODAY AWAITING LOADING DATES | AWAITING TRUCK ALLOCATION AND LOADING DATES | AWAITING TRUCK ALLOCATION AND LOADING DATES | TRUCK TO LOAD THE 31/07/2023 | TRUCK TO LOAD THE 31/07/2023 | TRUCK TO LOAD THE 31/07/2023 | VEHICLE LOADED - TO DISPATCH DURBAN TODAY | CURRENTLY IN JOHANNESBURG IN WORKSHOP DOING ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE TODAY | DISPATCHING JOHANNESBURG FOR BEIT BRIDGE TODAY | VEHICLE CURRENTLY AT RUTENGA ENROUTE HARARE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT KASUMBALESA CLEARING | VEHICLE CURRENLTY AT KANYAKA CLEARING | VEHICLE CURRENLTY AT KANYAKA CLEARING | VEHICLE WILL DISPATCH TO SITE TODAY | TRUCK IN LUBUMBASHI EN-ROUTE TO SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | LIKASI KPM SITE WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
| BA2152 | 1 X CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805150 | CAT00740C3F805150 | TXY07730 | FML2302DSI1966 | BRIGHT SKY Voy. 231205 - ETA DURBAN 30-03-2023 | COD 2023 239976 | ND431993 | ND923084 | 130570 | 17-07-2023 | OFFLOADED 09-08-2023 | 07-07-2023 | 10-07-2023 | BV NUMBER RECEIVED | 30-03-2023 | 17-07-2023 | 19-07-2023 | 24-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 28-07-2023 | 29-07-2023 | 29-07-2023 | 30-07-2023 | 01-08-2023 | 01-08-2023 | 02-08-2023 | 02-08-2023 | 03-08-2023 | 03-08-2023 | 04-08-2023 | 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 06-08-2023 | 07-08-2023 | 09-08-2023 | 09-08-2023 | [96 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECITON TO BE BOOKED FOR MONDAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | LOADING TODAY TO DISPATCH TOMORROW MORNING | VAN REENEN ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | JOHANNESBURG DOING ROUTINE CHECK & SERVICE BEFORE DISPATCHING FOR THE BORDER | JOHANNESBURG DOING ROUTINE CHECK & SERVICE BEFORE DISPATCHING FOR THE BORDER | DISPATCHING JOHANNESBURG TODAY EN-ROUTE TO BEITBRODGE BORDER | TRUCK AT BEITBRIDGE BORDER RSA SIDE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE BORDER RSA SIDE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE BORDER RSA SIDE AWAITING CLEARANCE | TRUCK AT BEITBRIDGE ZIM SIDE AWAITING FINAL RELEASE | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT LUSAKA ENROUTE MOKAMBO BORDER | TRUCK AT NDOLA ENROUTE MOKAMBO BORDER | VEHICLE AT LUBUMBASHI AWAITING CLEARANCE | VEHICLE AT CONNEX YARD - AWAITING RELEASE | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023
| BA2153 | 1 X CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805151 | CAT00740V3F805151 | TXY07606 | FML2303DSI1987 | GREEN MOUNTAIN Voy. 231206 - ETA DURBAN 16-04-2023 | COD 2023 239976 | ND919950 | ND820122 | 130582 | 17-07-2023 | OFFLOADED 09-08-2023 | 07-07-2023 | 10-07-2023 | BV NUMBER RECEIVED | 16-04-2023 | 18-07-2023 | 19-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023 | 26-07-2023 | 28-07-2023 | 29-07-2023 | 29-07-2023 | 30-07-2023 | 01-08-2023 | 01-08-2023 | 02-08-2023 | 02-08-2023 | 03-08-2023 | 03-08-2023 | 04-08-2023 | 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 06-08-2023 | 07-08-2023 | 09-08-2023 | 09-08-2023 | [96 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECITON TO BE BOOKED FOR MONDAY 10-07-2023 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | BV INSPECTION COMPLETE - PLANNING TO DISPATCH MONDAY 17 JULY 2023 | LOADING TOMORROW AND DISPATCHING TOMORROW | VAN REENEN ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | JOHANNESBURG TO DISPATCH FOR THE BORDER | JOHANNESBURG TO DISPATCH FOR THE BORDER AFTER PERMITS IS RECEIVED | ROEDTAN EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE ZIM SIDE AWAITING FINAL RELEASE | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT LUSAKA ENROUTE MOKAMBO BORDER | TRUCK AT KITWE ENROUTE MOKAMBO BORDER | VEHICLE AT LUBUMBASHI AWAITING CLEARANCE | VEHICLE AT CONNEX YARD - AWAITING RELEASE | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023
| BA2204 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00888 | CAT00352CHLW00888 | P4E05277 | FML2211DSI1815 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | ND6811744 | ND821906 / ND822365 | 130561 | 18-07-2023 | OFFLOADED 09-08-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 03-07-2023 | 18-07-2023 | 21-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 28-07-2023 | 29-07-2023 | 30-07-2023 | 30-07-2023 | 01-08-2023 | 01-08-2023 | 02-08-2023 | 03-08-2023 | 03-08-2023 | 03-08-2023 | 04-08-2023 | 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 06-08-2023 | 07-08-2023 | 09-08-2023 | 09-08-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | LOADING TODAY, AWAITING PERMIT AND TRIP CHECK IN ORDER TO DISPATCH | DISPATCHING DURBAN TODAY FOR JOHANNESBURG | WARDEN ENROUTE JOHANNESBURG | VILLIERS ENROUTE JOHANNESBURG | JOHANNESBURG | JOHANNESBURG BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR THE BORDER | JOHANNESBURG BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR THE BORDER | JOHANNESBURG BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR THE BORDER | PLANNING TO DISPATCH MONDAY 17-07-2023 | PLANNING TO DISPATCH MONDAY 17-07-2023 | PLANNING TO DISPATCH MONDAY 17-07-2023 | PLANNING TO DISPATCH TOMORROW 18-07-2023 | VAN REENEN ENROUTE JOHANNESBURG | JOHANNESBURG DOING ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | JOHANNESBURG DOING ROUTINE CHECK BEFORE DISPATCHING FOR THE BORDER | DISPATCHING JOHANNESBURG FOR BEITH BRIDGE | MOKOPONG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER CLEARING | TRUCK AT BEITBRIDGE BORDER CROSSING TODAY | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | PASSING LUSAKA ENROUTE MOKAMBO BORDER | VEHICLE AT NDOLA ENROUTE MOKAMBO BORDER | VEHICLE AT LUBUMBASHI AWAITING CLEARANCE | VEHICLE AT CONNEX YARD - AWAITING RELEASE | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023 | OFFLOADED 09-08-2023
| BA2205 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00889 | CAT00352THLW00889 | P4E05390 | FML2211DSI1815 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | ND754713 | ND715801 / ND718488 | 130172 | 11-07-2023 | OFFLOADED 04-08-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 12-07-2023 | 11-07-2023 | 13-07-2023 | 14-07-2023 | 14-07-2023 | 15-07-2023 | 19-07-2023 | 20-07-2023 | 21-07-2023 | 24-07-2023 | 25-07-2023 | 25-07-2023 | 26-07-2023 | 27-07-2023 | 27-07-2023 | 27-07-2023 | 28-07-2023 | 28-07-2023 | MOKAMBO 29-07-2023 | MOKAMBO 30-07-2023 | 30-07-2023 | 30-07-2023 | 30-07-2023 | 03-08-2023 | 04-08-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 30-06-2023 | ESTIMATED LOADING DATE 05-07-2023 | ESTIMATED LOADING DATE 05-07-2023 | ESTIMATED LOADING DATE 05-07-2023 | ESTIMATED LOADING DATE 05-07-2023 | ESTIMATED LOADING DATE 05-07-2023 | LOADING TODAY | LOADED, WAITING PERMIT TO DISPATCH | LOADED, WAITING PERMIT TO DISPATCH | LOADED, WAITING PERMIT TO DISPATCH | UNIT LOADED - AWAITING PERMIT IN ORDER TO DISPATCH | VEHICLE CURRENTLY AT WARDEN ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT PRETORIA ENROUTE BEITBRIDGE | VEHICLE CURRENTLY PASSING MOKOPONG ENROUTE BEITBRIDGE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE | VEHICLE CURRENTLY AT MASVINGO ENROUTE HARARE | VEHICLE APPROCHING HARARE | CHIRUNDU ZAMBIA SIDE AWAITING CLEARANCE | CHIRUNDU ZAMBIA SIDE AWAITING CLEARANCE | TRUCK AT CHIBOMBO EN-ROUTE TO MOKAMBO BORDER | TRUCK AT KITWE EN-ROUTE TO MOKAMBO BORDER | TRUCK AT MUFULIRA ZAMBIA EN-ROUTE TO MOKAMBO BORDER | TRUCK AT LUBUMBASHI | TRUCK AT LUBUMBASHI | TRUCK AT LUBUMBASHI | TRUCK AT LUBUMBASHI WAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 04-07-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023 | OFFLOADED 04-08-2023
BA2474 | 1 X CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M8D00400 | CAT000D8LM8D00400 | TXJ02468 | FML2306DSI2094 | VESSEL: DIGNITY ACE Voy. 0075A - ETA DURBAN: 09-06-2023 | COD 2022 251254 | ND437412 | ND647660 / ND647016 | 2306DSI2094 | 28-07-2023 | OFFLOADED 22-08-2023 | 14-07-2023 | 20-07-2023 | BV COMPLETED | 09-06-2023 | 31-07-2023 | MIDDELBURG 03-08-2023 | MIDDELBURG 03-08-2023 | 03-08-2023 | 04-08-2023 | 04-08-2023 | 08-08-2023 | 09-08-2023 | 13-08-2023 | 14-08-2023 | 14-08-2023 | 14-08-2023 | 14-08-2023 | 15-08-2023 | 15-08-2023 | 15-08-2023 | 14-08-2023 | 14-08-2023 | MAKOMBO 15-08-2023 | MAKOMBO 17-08-2023 | 18-08-2023 | 18-08-2023 | 19-08-2023 | 22-08-2023 | 22-08-2023 | [95 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | WAITING CONFIRMATION FROM BV RSA ON INSPECTION DATE | WAITING CONFIRMATION FROM BV RSA ON INSPECTION DATE | WAITING CONFIRMATION FROM BV RSA ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 28-07-2023 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 28-07-2023 | BV INSPECTION COMPLETED - ESTIMATED LOADING DATE 28-07-2023 | BV INSPECTION COMPLETED - TRUCK TO LOAD TODAY AND DISPATCH MONDAY THE 31/07/2023 ONCE PERMITS RECEIVED | BV INSPECTION COMPLETED - TRUCK TO LOAD TODAY AND DISPATCH MONDAY THE 31/07/2023 ONCE PERMITS RECEIVED | BV INSPECTION COMPLETED - TRUCK LOADED AND DISPATCH MONDAY THE 31/07/2023 ONCE PERMITS RECEIVED | DISPATCHING DURBAN TODAY | NEW CASTLE ENROUTE JOHANNESBURG | VOLKRUST ENROUTE JOHANNESBURG | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER RSA SIDE UNDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE UNDER CLEARANCE | VEHICLE CURRENLTY AT HURUNGWE ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT KAROI ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT KAPRIR EN ROUTE CHIRUNDU | VEHICLE CURRENLTY EN ROUTE TO MOKAMBO BORDER | VEHICLE CURRENLTY AT MOKAMBO BORDER CLEARING | VEHICLE CURRENLTY AT SAKANIA BORDER EN-ROUTE TO CLIENT | VEHICLE CURRENLTY AT WHISKEY IN QUEUE TO EXIT AN ACCIDENT THAT TOOK PLACE AT WHSIKEY | VEHICLE CURRENLTY AT LUBUMBASHI, WAITING RELEASE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 22-08-2023 | OFFLOADED 22-08-2023
BA2481 | CAT DE450E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH404674 / PWE07276 / F6B12181 | CAT00C13PDH404674 | N/A | FML2306DSI2104 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 244002 | BCD3426ZM | BCD1776ZM | 2306DSI2104 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [30 empty] | BV INSPECTION COMPLETED - LOADING TODAY | BV INSPECTION COMPLETED - LOADING TODAY | BV INSPECTION COMPLETED - LOADING TODAY | BV INSPECTION COMPLETED - LOADING TODAY | [69 empty] | VESSEL: NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | VESSEL: NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | VESSEL: NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | VESSEL: NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | MATHANGWANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2490 | CAT DE400E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DH404673 / PWE07270 / F6B12182 | CAT00C13TDH404673 | N/A | FML2306DSI2104 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 244002 | BCD3426ZM | BCD1776ZM | 2306DSI2104 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | MATHANGWANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENTLY AT KAFUE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2510 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM705732 / ECL06216 / 7K306862 | CAT00C44KECL06216 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246637 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2511 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM705736 / ECL06217 / 7K306860 | CAT00C44JECL06217 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246637 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2512 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM705741 / ECL06218 / 7K306861 | CAT00C44CECL06218 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246637 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2515 | CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM05950 / EC508999 / E3S15910 | CAT00C33CEC508999 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246636 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2516 | CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG05906 / ECS09000 / E3S15915 | CAT00C33CEC509000 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246636 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2517 | CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG05909 / EC509001 / E3S15913 | CAT00C33TEC509001 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246636 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2518 | CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG05908 / EC509002 / E3S15921 | CAT00C33PEC509002 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246636 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2519 | CAT DE65E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG05907 / EC509003 / E3S15899 | CAT00C33KEC509003 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246636 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2520 | CAT DE55E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JMG05910 / EC508995 / E3S15901 | CAT00C33TEC508995 | N/A | FML2306DSI2106 | VESSEL: NAVIOS BAHAMAS Voy. 891W / Transhipment Vessel: COSCO WELLINGTON Voy. 087W - ETA DURBAN 22-07-2023 | COD 2023 246636 | BCD9039ZM | AEB1926ZM | 2306DSI2106 | 02-08-2023 | OFFLOADED 23-08-2023 | 13-07-2023 | 31-07-2023 | BV COMPLETED | 22-07-2023 | 31-07-2023 | 01-08-2023 | 01-08-2023 | GRB 02-08-2023 | GRB 02-08-2023 | MARTINS DRIFT 02-08-2023 | MARTINS DRIFT 02-08-2023 | FRANCISTOWN 03-08-2023 | FRANCISTOWN 03-08-2023 | KAZUNGULA BW 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 07-08-2023 | 08-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 12-08-2023 | 13-08-2023 | 13-08-2023 | 17-08-2023 | 18-08-2023 | 22-08-2023 | 23-08-2023 | [103 empty] | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | NAVIOS BAHAMAS Voy. 891W - ETA DURBAN 19-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-07-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | VESSEL IN AND WORKING, AWAITING TO COLLECT THE CONTAINERS FROM PORT | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | CONTAINER AT OUR FACILITY AND BV BOOKED FOR MONDAY THE 31/07/2023 AS THERE IS NO SPACE TO BOOK BV EARLIER-LOADING DATE TO BE ADVISED ONCE BV IS DONE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - VEHICLE LOADED - TO DISPATCH DURBAN TODAY | GROBLERS BRIDGE BORDER CLEARING | TAMASANE ENROUTE KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | VEHICLE CURRENLTY AT LIVINGSTONE ENROUTE LUSAKA | VEHICLE CURRENLTY AT KABWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT NDOLA ENROUTE CHINGOLA | VEHICLE CURRENLTY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 3 | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE DAY 4 | TRUCK DISPATCHING WHSIKEY EN-ROUTE TO CE SITE | TRUCK ON SITE WAITING TO OFFLOAD | CONNEX LUBUMBASHI WAITING CLEARANCE AND RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 23-08-2023 | OFFLOADED 23-08-2023
BA2399 | 1 X CAT160K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZM20254 | CAT0160KESZM20254 | TX712419 | FML2211DSI1834 | VESSEL: GRAND VENUS Voy. 14 - ETA DURBAN: 09-01-2023 | COD 2023 222659 | B300BOZ | DS74ZFGP | ND63986 | 12-07-2023 | OFFLOADED 29-08-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 09-01-2023 | 11-07-2023 | 14-07-2023 | 20-07-2023 | 21-07-2023 | 22-07-2023 | 28-07-2023 | 31-07-2023 | 03-08-2023 | 03-08-2023 | 03-08-2023 | 03-08-2023 | 04-08-2023 | 08-08-2023 | 08-08-2023 | 09-08-2023 | 09-08-2023 | 09-08-2023 | 10-08-2023 | 10-08-2023 | 19-08-2023 | 19-08-2023 | 26-08-2023 | 26-08-2023 | 29-08-2023 | 29-08-2023 | [80 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 23-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23-06-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 23-06-2023 | AWAITING BV LICENSE AND FIRE SUPPRESSION SYSTEM (CO-LOAD WITH BA2312) | AWAITING BV LICENSE AND FIRE SUPPRESSION SYSTEM (CO-LOAD WITH BA2312) | AWAITING BV LICENSE AND FIRE SUPPRESSION SYSTEM FOR CO-LOAD (BA2312) | AWAITING FIRE SUPPRESSION SYSTEM FOR CO-LOAD (BA2312) | AWAITING FIRE SUPPRESSION SYSTEM FOR CO-LOAD (BA2312) | AWAITING FIRE SUPPRESSION SYSTEM FOR CO-LOAD (BA2312) | AWAITING FIRE SUPPRESSION SYSTEM & BV INSPECTION FOR CO-LOAD (BA2312) | AWAITING FIRE SUPPRESSION SYSTEM & BV INSPECTION FOR CO-LOAD (BA2312) | AWAITING FIRE SUPPRESSION SYSTEM & BV INSPECTION FOR CO-LOAD (BA2312) | LOADING FRIDAY 07-07-2023 | LOADING PLANNED FOR TODAY 07-07-2023 | LOADING FSS - PLANNING TO DISPATCH THIS AFTERNOON | UNIT LOADED - AWAITING PERMIT IN ORDER TO DISPATCH | VEHCILE CURRENTLY AT PIETERMARITZBURG ENROUTE JOHANNESBURG | VEHCILE CURRENTLY AT PIETERMARITZBURG AWAITING PERMIT TO DISPATCH | VEHCILE CURRENTLY AT COLENSO ENROUTE JOHANNESBURG | VEHCILE AT JOHANNESBURG WAITING LIMPOPO PERMIT | VEHCILE AT JOHANNESBURG WAITING LIMPOPO PERMIT | VEHCILE AT JOHANNESBURG STILL WAITING LIMPOPO PERMIT - DELAY WITH PERMIT ISSUING | VEHCILE AT JOHANNESBURG STILL WAITING LIMPOPO PERMIT - DELAY WITH PERMIT ISSUING - SHOULD RECEIVE IT TODAY | VEHICLE DISPATCHED JOHANNESBURG ENROUTE BORDER | VEHICLE AT GROBLERSBRIDGE BORDER CLEARING | HORSE ON BREAKDOWN, NEW HORSE WILL LINK UP WITH THE TRAILER AND DISPATCH TO SITE. AMENDED PRE-ALERT TO FOLLOW | HORSE ON BREAKDOWN, NEW HORSE WILL LINK UP WITH THE TRAILER TODAY AND PROCEED WITH CLEARANCE AT BEITBRIDGE BORDER | NEW HORSE ARRIVED, TRUCK EN-ROUTE TO BEITBRODGE BORDER | TRUCK AT BEITBRIDGE CLEARING | TRUCK AT BEITBRIDGE WAITING RELEASE | TRUCK AT RUTENGA ENROUTE MASVINGO | TRUCK AT GWERU ENROUTE MASVINGO | TRUCK AT KWE KWE ENROUTE MASVINGO | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING VOC TO BE PROCESSED | VEHICLE AT KASUMBALESA DRC SIDE AWAITING VOC TO BE PROCESSED | VEHICLE AT KASUMBALESA DRC SIDE AWAITING VOC TO BE PROCESSED DAY 3 | VEHICLE AT KASUMBALESA DRC SIDE AWAITING VOC TO BE PROCESSED DAY 4 | VEHICLE AT KASUMBALESA DRC SIDE AWAITING VOC TO BE PROCESSED DAY 5 | VEHICLE AT KASUMBALESA DRC SIDE AWAITING VOC TO BE PROCESSED DAY 6 | VEHICLE AT WHISKEY WAITING RELEASE | VEHICLE AT WHISKEY WAITING RELEASE - DAY 2 | WHISKEY WAITING RELEASE - DAY 4 | WHISKEY WAITING RELEASE - DAY 5 | WHISKEY WAITING RELEASE - DAY 6 | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | OFFLOADED 29-08-2023
BA2417 | CAT966GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SGW01005 | CAT00966ASGW01005 | NTB12352 | FML2212DSI1884 | VESSEL: MORNING CHANT Voy. 086 - ETA DURBAN: 05-02-2023 | COD 2023 279557 | ND919953 | ND823540 | 2212DSI1884 | 01-09-2023 | OFFLOADED 22-09-2023 | 29-08-2023 | 31-08-2023 | BV NUMBER RECEIVED | 05-02-2023 | 03-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 04-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 13-09-2023 | 13-09-2023 | 13-09-2023 | MOKAMBO 13-09-2023 | MOKAMOBO 14-09-2023 | 15-09-2023 | 16-09-2023 | 16-09-2023 | 22-09-2023 | 22-09-2023 | [55 empty] | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY 30-08-2023 - LOADING TOMORROW 31-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN ONCE PERMIT IS RECEIVED. | VEHICLE CURRENTLY AT HENDRINA ENROUTE JOHANNESBURG | VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIBOMBO ZAMBIA EN ROUTE TO MOKAMBO BORDER | VEHICLE CURRENTLY AT CHIBOMBO ZAMBIA EN ROUTE TO MOKAMBO BORDER | VEHICLE CURRENTLY AT MOKAMBO BORDER CLEARING | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASI AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASI AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASI AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASI AWAITING RELEASE - DAY 4 PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-09-2023 | OFFLOADED 22-09-2023
BA2413 | 1 X CAT C15 ENGINE | BARTRAC EQUIPMENT . CONGO EQUIPMENT | MCW18128 | N/A | N/A | FML2307DSI2151 | VESSEL: ONE TRITON / Transhipment Vessel: SANTA RITA - ETA DURBAN: 25-08-2023 | COD 2023 247025 | BCE9025ZM | BCD854ZM | 2307DSI2151 | 01-09-2023 | OFFLOADED 27-09-2023 | 18-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 26-08-2023 | 01-09-2023 | 01-09-2023 | 02-09-2023 | 02-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [27 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-08-2023 | VESSEL IN AND WORKING | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHICLE CURRENLTY AT BEITBRIDGE TO DISPATCH FOR HARARE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT CHISAMBA ENROUTE NDOLA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2414 | 1 X CAT C15 ENGINE | BARTRAC EQUIPMENT . CONGO EQUIPMENT | MCW18129 | N/A | N/A | FML2307DSI2151 | VESSEL: ONE TRITON / Transhipment Vessel: SANTA RITA - ETA DURBAN: 25-08-2023 | COD 2023 247025 | BCE9025ZM | BCD854ZM | 2307DSI2151 | 01-09-2023 | OFFLOADED 27-09-2023 | 18-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 26-08-2023 | 01-09-2023 | 01-09-2023 | 02-09-2023 | 02-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [27 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-08-2023 | VESSEL IN AND WORKING | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHICLE CURRENLTY AT BEITBRIDGE TO DISPATCH FOR HARARE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT CHISAMBA ENROUTE NDOLA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2415 | 1 X CAT C18 ENGINE | BARTRAC EQUIPMENT . CONGO EQUIPMENT | WRH15195 | N/A | N/A | FML2307DSI2151 | VESSEL: ONE TRITON / Transhipment Vessel: SANTA RITA - ETA DURBAN: 25-08-2023 | COD 2023 247025 | BCE9025ZM | BCD854ZM | 2307DSI2151 | 01-09-2023 | OFFLOADED 27-09-2023 | 18-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 26-08-2023 | 01-09-2023 | 01-09-2023 | 02-09-2023 | 02-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [27 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023-ESTIMATED BERTHING DATE 25/07/2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 21-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 25-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN PORT 26-08-2023 | VESSEL IN AND WORKING | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHICLE CURRENLTY AT BEITBRIDGE TO DISPATCH FOR HARARE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT CHISAMBA ENROUTE NDOLA | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2482 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | CAT000C9JLX905071 | N/A | FML2307DSI2147 | VESSEL: TS KELANG V. 23004W / Transhipment Vwssel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 266568 | BCF1202ZM | BCD2207ZM | 2307DSI2147 | 01-09-2023 | OFFLOADED 27-09-2023 | 11-08-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [23 empty] | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE CURRENTLY AT GROBLERS BRIDGE AWAIITNG CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIBOMBO ENROUTE NDOLA | VEHICLE CURRENLTY AT KITWE ENROUTE CHILILABOMBWE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2483 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | CAT000C9KLX905070 | N/A | FML2307DSI2147 | VESSEL: TS KELANG V. 23004W / Transhipment Vwssel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 266568 | BCF1202ZM | BCD2207ZM | 2307DSI2147 | 01-09-2023 | OFFLOADED 27-09-2023 | 11-08-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [23 empty] | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE CURRENTLY AT GROBLERS BRIDGE AWAIITNG CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIBOMBO ENROUTE NDOLA | VEHICLE CURRENLTY AT KITWE ENROUTE CHILILABOMBWE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2513 | CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | CAT00C71JECW07460 | N/A | FML2307DSI2147 | VESSEL: TS KELANG V. 23004W / Transhipment Vwssel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 266568 | BCF1202ZM | BCD2207ZM | 2307DSI2147 | 01-09-2023 | OFFLOADED 27-09-2023 | 11-08-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [23 empty] | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 32408-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 34-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE CURRENTLY AT GROBLERS BRIDGE AWAIITNG CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIBOMBO ENROUTE NDOLA | VEHICLE CURRENLTY AT KITWE ENROUTE CHILILABOMBWE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2514 | CAT DE165E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | CAT00C71CECW07461 | N/A | FML2307DSI2147 | VESSEL: TS KELANG V. 23004W / Transhipment Vwssel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 266568 | BCF1202ZM | BCD2207ZM | 2307DSI2147 | 01-09-2023 | OFFLOADED 27-09-2023 | 11-08-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [23 empty] | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | VESSEL: TS KELANG V. 23004W - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE CURRENTLY AT GROBLERS BRIDGE AWAIITNG CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIBOMBO ENROUTE NDOLA | VEHICLE CURRENLTY AT KITWE ENROUTE CHILILABOMBWE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2485 | CAT DE275E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | CAT000C9JLX905054 | N/A | FML2306DSI2124 | VESSEL: EVER EAGLE Voy. 173W / Transhipment Vessel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 278284 | BCD9050ZM | BCE85ZM | 2306DSI2124 | 01-09-2023 | OFFLOADED 27-09-2023 | 28-08-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 05-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 10-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [23 empty] | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE DISPATCHED CHIRUNDU ENROUTE LUSAKA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE AT NDOLA UNDERGOING TRIP CHECK | VEHICLE AT KITWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2486 | CAT DE275E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | CAT000C9CLX905055 | N/A | FML2306DSI2124 | VESSEL: EVER EAGLE Voy. 173W / Transhipment Vessel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 278284 | BCD9050ZM | BCE85ZM | 2306DSI2124 | 01-09-2023 | OFFLOADED 27-09-2023 | 28-08-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 05-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 10-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [23 empty] | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE DISPATCHED CHIRUNDU ENROUTE LUSAKA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE AT NDOLA UNDERGOING TRIP CHECK | VEHICLE AT KITWE EN-ROUTE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2508 | CAT DE110EO GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | N/A | FML2306DSI2124 | VESSEL: EVER EAGLE Voy. 173W / Transhipment Vessel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 278284 | BCD9050ZM | BCE85ZM | 2306DSI2124 | 04-09-2023 | OFFLOADED 27-09-2023 | 28-08-2023 |  | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [23 empty] | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT NDOLA BUSY WITH TRIP CHECK | VEHICLE AT NDOLA UNDERGOING TRIP CHECK | VEHICLE AT CHILILABOMBWE AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA2509 | CAT DE110EO GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | N/A | FML2306DSI2124 | VESSEL: EVER EAGLE Voy. 173W / Transhipment Vessel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 278284 | BCD9050ZM | BCE85ZM | 2306DSI2124 | 04-09-2023 | OFFLOADED 27-09-2023 | 28-08-2023 |  | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 06-09-2023 | 06-09-2023 | 07-09-2023 | 12-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 16-09-2023 | 16-09-2023 | 21-09-2023 | 21-09-2023 | 26-09-2023 | 27-09-2023 | [23 empty] | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT NDOLA BUSY WITH TRIP CHECK | VEHICLE AT NDOLA UNDERGOING TRIP CHECK | VEHICLE AT CHILILABOMBWE AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | ON SITE WAITING TO OFFLOAD | OFFLOADED 27-09-2023
BA1995 | 1 X CAT14-15A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | F5800118 | CAT00014CF5800118 | TXX05083 | FML2305DSI2062 | VESSELl GUANGZHOU HIGHWAY V. 172 - ETA DURBAN: 30-06-2023 | COD 2023 283760 PT02 | ND804122 | ND803726 | 131694 | 12-09-2023 | OFFLOADED 29-09-2023 | 05-09-2023 | 06-09-2023 | BV COMPLETED | 30-06-2023 | 11-09-2023 | MIDDELBURG 14-09-2023 | MIDDELBURG 14-09-2023 | 15-09-2023 | 16-09-2023 | 16-09-2023 | 18-09-2023 | 19-09-2023 | 19-09-2023 | 19-09-2023 | 21-09-2023 | 21-09-2023 | 22-09-2023 | 22-09-2023 | 23-09-202 | 23-09-2023 | 23-09-2023 | 23-09-2023 | MOKAMBO 23-09-2023 | MOKAMBO 26-09-2023 | 26-09-2023 | 26-09-2023 | 26-09-2023 | 29-09-2023 | 29-09-2023 | [63 empty] | BV INSPECTION COMPLETED - LOADING MONDAY | TRUCK TO LOAD AND DISPATCH TODAY | TRUCK AT CATORIDGE AWAITING PERMIT AND UNDERGOING TRIP CHECK | TRUCK AT CATORIDGE AWAITING PERMIT AND UNDERGOING TRIP CHECK | TRUCK AT PIETERMARITSBURG ENROUTE MUSINA | TRUCK AT ROEDTAN ENROUTE MUSINA | VEHICLE ENROUTE HARARE | VEHICLE ENROUTE HARARE | VEHICLE AT CHIRUNDU BORDER CLEARING | VEHICLE AT CHIRUNDU BORDER CLEARING | VEHICLE AT CHIRUNDU BORDER CLEARING | VEHICLE AT MOKAMBO DRC SIDE | VEHICLE AT CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE | VEHICLE AT CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE | VEHICLE AT LIKASI ON BREAKDOWN - BUSY ATTENDING TO IT | OFFLOADED 29-09-2023 | OFFLOADED 29-09-2023
BA2208 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00966 | CAT00352LHLW00966 | P4E05427 | FML2211DSI1816 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | ND436314 | ND646811 / ND644688 | 2211DSI1816-BA2208 | 20-07-2023 | OFFLOADED 07-08-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 20-07-2023 | 20-07-2023 | 24-07-2023 | 24-07-2023 | 24-07-2023 | 25-07-2023 | 28-07-2023 | 29-07-2023 | 09-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 15-09-2023 | 15-09-2023 | 16-09-2023 | 17-09-2023 | 04-08-2023 | 04-08-2023 | 05-08-2023 | 05-08-2023 | 06-08-2023 | 06-08-2023 | 07-08-2023 | 07-08-2023 | 07-08-2023 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2205 - CAT 352-08A) | JOHANNESBURG | MOKOPONG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER SIDE CLEARING | TRUCK AT BEITBRIDGE BORDER SIDE CLEARING | TRUCK AT BEITBRIDGE BORDER SIDE CLEARING | TRUCK AT BEITBRIDGE BORDER CROSSING TODAY | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT CHIRUNDU BORDER CLEARING | TRUCK AT LUSAKA ENROUTE MOKAMBO BORDER | TRUCK AT NDOLA ENROUTE MOKAMBO BORDER | VEHICLE AT LUBUMBASHI AWAITING CLEARANCE | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023 | OFFLOADED 07-08-2023
BA2484 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | F5D05995 LX905052 S9X07158 | CAT000C9PLX905052 | N/A | FML2306DSI2120 | VESSEL: EVER EAGLE Voy. 173W / Transhipment Vessel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 250964 | BCD3140ZM | BCD836ZM | 2306DSI2120 | 01-09-2023 | OFFLOADED 29-09-2023 | 21-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 05-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 17-09-2023 | 17-09-2023 | 22-09-2023 | 22-09-2023 | 28-09-2023 | 29-09-2023 | [23 empty] | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE DISPATCHED CHIRUNDU ENROUTE LUSAKA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE AT NDOLA UNDERGOING TRIP CHECK | KITWE EN-ROUTE TO KASUMBALESA BORDER | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 4 | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 29-09-2023 | OFFLOADED 29-09-2023
BA2487 | CAT DE275E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LX905053 S9X07189 F5D05996 | CAT000C9KLX905053 | N/A | FML2306DSI2120 | VESSEL: EVER EAGLE Voy. 173W / Transhipment Vessel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 250964 | BCD3140ZM | BCD836ZM | 2306DSI2120 | 01-09-2023 | OFFLOADED 29-09-2023 | 21-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 05-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 17-09-2023 | 17-09-2023 | 22-09-2023 | 22-09-2023 | 28-09-2023 | 29-09-2023 | [23 empty] | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE DISPATCHED CHIRUNDU ENROUTE LUSAKA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE AT NDOLA UNDERGOING TRIP CHECK | KITWE EN-ROUTE TO KASUMBALESA BORDER | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 4 | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 29-09-2023 | OFFLOADED 29-09-2023
BA2488 | CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM705753 GTY01816 KRG13852 | CAT00C71VGTY01816 | N/A | FML2306DSI2120 | VESSEL: EVER EAGLE Voy. 173W / Transhipment Vessel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 250964 | BCD3140ZM | BCD836ZM | 2306DSI2120 | 01-09-2023 | OFFLOADED 29-09-2023 | 21-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 05-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 17-09-2023 | 17-09-2023 | 22-09-2023 | 22-09-2023 | 28-09-2023 | 29-09-2023 | [23 empty] | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE DISPATCHED CHIRUNDU ENROUTE LUSAKA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE AT NDOLA UNDERGOING TRIP CHECK | KITWE EN-ROUTE TO KASUMBALESA BORDER | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 4 | VEHICLE AT CONNEX LUBUMBASHI 5AITING RELEASE - DAY 5 | VEHICLE AT CONNEX LUBUMBASHI 5AITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 29-09-2023 | OFFLOADED 29-09-2023
BA2489 | CAT DE150E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM705752 GTY01815 KRG13850 | CAT00C71CGTY01815 | N/A | FML2306DSI2120 | VESSEL: EVER EAGLE Voy. 173W / Transhipment Vessel: SEAMAX STAMFORD Voy. 139W - ETA DURBAN 24-08-2023 | COD 2023 250964 | BCD3140ZM | BCD836ZM | 2306DSI2120 | 01-09-2023 | OFFLOADED 29-09-2023 | 21-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 22-08-2023 | 01-09-2023 | 01-09-2023 | 02-03-2023 | 02-03-2023 | 03-04-2023 | 03-04-2023 | 04-09-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 05-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 13-09-2023 | 17-09-2023 | 17-09-2023 | 22-09-2023 | 22-09-2023 | 28-09-2023 | 29-09-2023 | [23 empty] | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | VESSEL: EVER EAGLE Voy. 173W - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | AT DEPOT - CONTAINER TO BE UNPACKED | CONTAINER UNPACKED - BV INSPECTION BOOKED FOR TODAY 30-08-2023 | BV INSPECTION COMPLETED - LOADING TODAY | DISPATCHING DURBAN TODAY | VEHCILE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE DISPATCHED CHIRUNDU ENROUTE LUSAKA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE AT NDOLA UNDERGOING TRIP CHECK | KITWE EN-ROUTE TO KASUMBALESA BORDER | VEHICLE CURRENLTY AT CHILILABOMBWE IN QUEUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT KASUMBALESA ZAMBIAN SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 4 | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 5 | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 29-09-2023 | OFFLOADED 29-09-2023
BA2320 | 1 X CAT14-15A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | F5800102 | CAT00014KF5800102 | TXX04425 | FML2211DSI1843 | VESSEL: RCC AFRICA V020 - ETA DURBAN: 16-01-2023 | COD 2023 283760 PT01 | CB67PGGP | KH82PCGP | ND64527 | 12-09-2023 | OFFLOADED 11-10-2023 | 05-09-2023 | 06-09-2023 | BV COMPLETED | 16-01-2023 | 13-09-2023 | 13-09-2023 | 20-09-2023 | 20-09-2023 | 21-09-2023 | 21-09-2023 | 24-09-2023 | 24-09-2023 | 27-09-2023 | 27-09-2023 | 28-09-2023 | 28-09-2023 | 29-09-2023 | 30-09-2023 | 01-10-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 03-10-2023 | 04-10-2023 | 04-10-2023 | 06-10-2023 | 07-10-2023 | LIKASI 11-10-2023 | 11-10-2023 | [63 empty] | BV INSPECTION COMPLETED - LOADING TODAY | UNIT LOADED AWAITING PERMIT BEFORE DISPATCH | UNIT LOADED AWAITING PERMIT BEFORE DISPATCH-PERMIT TO BE OUT BY TOMMROW | TRUCK AT VAN REENEN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JOHANNESBURG DOING VEHICLE CHECK BEFORE PROCEEDING TO BEITBRIDGE BORDER | TRUCK AT JOHANNESBURG VEHICLE CHECK COMPLETED - AWAITING LIMPOPO PERMITS | TRUCK AT JOHANNESBURG - AWAITING LIMPOPO PERMITS | TRUCK AT JOHANNESBURG - AWAITING LIMPOPO PERMITS | HAMMANSKRAAL ENROUTE MUSINA | MUSINA CLEARING | BEIT BRIDGE BORDER CLEARING | HARARE | DISPATCHING HARARE THIS MORNING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KABWE ENROUTE KASUMBALESA | CHILILABOMBWE EN ROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | WHISKEY WAITING CLEARANCE & RELEASE | WHISKEY WAITING CLEARANCE & RELEASE - DAY 2 | DISPATCH FORM LUBUMBASHI ENROUTE LIKASI | VEHICLE DUE TO ARRIVE IN LIKASI | OFFLOADED 11-10-2023 | OFFLOADED 11-10-2023
BA2492 | CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816137 / GBY15944 / SM817375 | CAT00C22KGBY15944 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2493 | CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816138 / GBY15945 / SM817378 | CAT00C22GJGBY15945 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2494 | CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816142 / GBY15946 / SM817381 | CAT00C22GBY15946 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2495 | CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816194 / GBY15947 / SM817379 | CAT00C22VGBY15947 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2496 | CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816141 / GBY15948 / SM817382 | CAT00C22AGBY15948 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2497 | CAT DE22E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816139 / GBY15943 / SM817380 | CAT00C22PGBY15943 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2498 | CAT DE13,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816144 / GB904631 / W2205333 | CAT00C15EGB904631 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2499 | CAT DE13,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816145 / GB904629 / W2205331 | CAT00C15CGB904629 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2500 | CAT DE13,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816146 / GB904628 / W2205332 | CAT00C15EGB904628 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 4-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 4-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 4-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2501 | CAT DE13,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JM816143 / GB904630 / W2205334 | CAT00C15HGB904630 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2502 | CAT DE9,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB800613 / NP200637 / TT913681 | CAT00C11KGB800613 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2503 | CAT DE9,5E3 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | GB800612 / NP200636 / TT913680 | CAT00C11PGB800612 | N/A | FML2306DSI2123 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: COSCO SURABAYA Voy. 111W - ETA DURBAN 30-08-2023 | COD 2023 245418 | BCF1076ZM | BCD871ZM | 2306DSI2123 | 01-09-2023 | OFFLOADED 10-10-2023 | 15-07-2023 | 30-08-2023 | BV NUMBER RECEIVED | 30-08-202 | 01-09-2023 | 02-09-2023 | 03-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 09-09-2023 | 10-09-2023 | 10-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 12-09-2023 | 12-09-2023 | 13-09-2023 | 14-09-2023 | 14-09-2023 | 20-09-2023 | 28-09-2023 | 28-09-2023 | 02-10-2023 | 02-10-2023 | 10-10-2023 | 10-10-2023 | [23 empty] | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | VESSEL: MARTINIQUE Voy. 0224E - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-08-2023 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT AND UNPACK AT WAREHOUSE | VESSEL DUE TO ARRIVE PM TODAY | VESSEL DUE TO ARRIVE AM TODAY | LOADING TODAY | WAITING BV INSPECTION | VEHCILE AT MOREOMABELE ENROUTE KAZANGULA | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | VEHICLE CURRENLTY AT DIBENG ENROUTE GRB | VEHICLE CURRENLTY AT CHILILABOMBWE AWAITING RELEASE | VEHICLE CURRENLTY AT LUSAKA EN ROUTE TO NDOLA | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT NDOLA DOING TRIP CHECK | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT CHILILABOMBWE CLEARING | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAMBIAN SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE - DAY 2 | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 2 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 3 | TRUCK AT CONNEX LUBUMBASHI AWAITING FINAL RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 10-10-2023 | OFFLOADED 10-10-2023
BA2206 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00894 | CAT00352KHLW00894 | P4E05363 | FML2211DSI1815 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | KR85BVGP | NT74888 / NT79777 | 2211DSI1815-BA2206 | 15-08-2023 | OFFLOADED 16-10-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 15-08-2023 | 21-08-202 | 24-08-2023 | 28-08-2023 | 30-08-2023 | 30-08-2023 | 02-09-2023 | 07-09-2023 | 09-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 15-09-2023 | 15-09-2023 | 16-09-2023 | 20-09-2023 | 26-09-2023 | 28-09-2023 | 06-10-2023 | 12-10-2023 | 12-10-2023 | 14-10-2023 | 15-10-2023 | 16-10-2023 | 16-10-2023 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNITS AT VOLKSRUST EN-ROUTE TO JOHANNESBURG | UNITS AT STANDERTON ENROUTE MUSINA | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER - DISPATCHING TOMORROW MORNING | DISPATCHING POMONA TODAY | VEHCLE AT PIENAARSREVER WAITING LIMPOPO PERMIT | VEHCLE AT PIETERSBURG ENROUTE BEITH BRIDGE BORDER | VEHCLE AT MUSINA CLEARING | VEHCLE AT MUSINA CLEARING | VEHCLE AT BEIT BRIDGE BORDER CLEARING | VEHCLE AT BEIT BRIDGE RSA SIDE CROSSING OVER TO ZIM SIDE | VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENLTY AT BEATRICE ENROUTE HARARE | VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT HARARE REFUELLING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING RELESAE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING PERMIT - TO DISPATCH THIS AFTERNOON | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE ONLY DISPATCHING KAFUE TODAY | VEHICLE KABWE ENROUTE KASUMBALESA | VEHICLE KAPIRI ENROUTE KASUMBALESA | VEHICLE NDOLA ENROUTE KASUMBALESA | VEHICLE CHINGOLA ENROUTE KASUMBALESA | VEHICLE DISPATCHING CHINGOLA FOR KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUE TO CROSSING INTO DRC | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023
BA2207 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00949 | CAT00352LHLW00949 | P4E05422 | FML2211DSI1816 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | KH29NKGP | DG54VVGP / DG54WHGP | 2211DSI1816-BA2207 | 15-08-2023 | OFFLOADED 16-10-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 15-08-2023 | 21-08-2023 | 28-08-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 09-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 15-09-2023 | 15-09-2023 | 16-09-2023 | 20-09-2023 | 26-09-2023 | 28-09-2023 | 05-10-2023 | 12-10-2023 | 12-10-2023 | 14-10-2023 | 15-10-2023 | 16-10-2023 | 16-10-2023 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNITS AT VOLKSRUST EN-ROUTE TO JOHANNESBURG | UNITS AT STANDERTON ENROUTE MUSINA | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER - DISPATCHING TOMORROW MORNING | POMONA STILL BUSY WITH TRIPCHECK TO DISPATCHING TOMORROW MORNING | POMONA WAITING LIMPOPO PERMIT | MIDRAND ENROUTE BEITH BRIDGE BORDER | WARMBAD ENROUTE BEITH BRIDGE BORDER | PIETERSBURG ENROUTE BEITH BRIDGE BORDER | VIVO ENROUTE BEITH BRIDGE BORDER | VENITIA ENROUTE BEITH BRIDGE BORDER | VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT BEITBRIDGE AWAITING CLEARANCE | VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENLTY AT HARARE REFUELLING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING RELESAE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING PERMIT - TO DISPATCH THIS AFTERNOON | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE ONLY DISPATCHING KAFUE TODAY | VEHICLE KABWE ENROUTE KASUMBALESA | VEHICLE KAPIRI ENROUTE KASUMBALESA | VEHICLE NDOLA ENROUTE KASUMBALESA | VEHICLE CHINGOLA ENROUTE KASUMBALESA | VEHICLE DISPATCHING CHINGOLA FOR KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUE TO CROSSING INTO DRC | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023
BA2506 | 1 X CAT DE330E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LX905074 / S9X07166 / F5D06042 | CAT000C9ALX905074 | N/A | FML2307DSI2148 | VESSEL: TS KELANG V. 23004W / Transhipment Vwssel: DOLPHIN II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 289077 | BAD7326 | AKB2580T | 2307DSI2148 | 20-09-2023 | OFFLOADED 17-10-2023 | 11-09-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | GRB 22-09-2023 | GRB 23-09-2023 | MARTINS DRIFT 23-09-2023 | MARTINS DRIFT 23-09-2023 | FRANCISTOWN 24-09-2023 | FRANCISTOWN 24-09-2023 | KAZUNGULA BW 24-09-2023 | KAZUNGULA BW 26-09-2023 | KAZUNGULA ZM 26-09-2023 | KAZUNGULA ZM 26-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 07-10-2023 | 07-10-2023 | 14-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | [28 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER CLEARING | KAFUE ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | DISPATCHING LUSAKA | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | WHISKEY PREPARING TO DISPATCH | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 17-10-2023
BA2507 | 1 X CAT DE330E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LX905075 / S9X07159 / F5D06043 | CAT000C9LLX905075 | N/A | FML2307DSI2148 | VESSEL: TS KELANG V. 23004W / Transhipment Vwssel: DOLPHIN II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 289077 | BAD7326 | AKB2580T | 2307DSI2148 | 20-09-2023 | OFFLOADED 17-10-2023 | 11-09-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | GRB 22-09-2023 | GRB 23-09-2023 | MARTINS DRIFT 23-09-2023 | MARTINS DRIFT 23-09-2023 | FRANCISTOWN 24-09-2023 | FRANCISTOWN 24-09-2023 | KAZUNGULA BW 24-09-2023 | KAZUNGULA BW 26-09-2023 | KAZUNGULA ZM 26-09-2023 | KAZUNGULA ZM 26-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 07-10-2023 | 07-10-2023 | 14-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | [28 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER CLEARING | KAFUE ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | DISPATCHING LUSAKA | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | WHISKEY PREPARING TO DISPATCH | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 17-10-2023
BA2504 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK05273 | CAT00C18CLXK05273 | N/A | FML2307DSI2167 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: DOLPHINE II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 275102 | AKB2619 | BAD9294T | 2307DSI2167 | 20-09-2023 | OFFLOADED 18-10-2023 | 23-08-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | GRB 22-09-2023 | GRB 23-09-2023 | MARTINS DRIFT 23-09-2023 | MARTINS DRIFT 23-09-2023 | FRANCISTOWN 24-09-2023 | FRANCISTOWN 24-09-2023 | KAZUNGULA BW 24-09-2023 | KAZUNGULA BW 26-09-2023 | KAZUNGULA ZM 26-09-2023 | KAZUNGULA ZM 26-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 07-10-2023 | 07-10-2023 | 14-10-2023 | 16-10-2023 | 17-10-2023 | 18-10-2023 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER CLEARING | PEMBA ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | DISPATCHING LUSAKA | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | WHISKEY PREPARING TO DISPATCH | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023
BA2505 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK05272 | CAT00C18JLXK05272 | N/A | FML2307DSI2167 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: DOLPHINE II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 275102 | AKB2619 | BAD9294T | 2307DSI2167 | 20-09-2023 | OFFLOADED 18-10-2023 | 23-08-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | GRB 22-09-2023 | GRB 23-09-2023 | MARTINS DRIFT 23-09-2023 | MARTINS DRIFT 23-09-2023 | FRANCISTOWN 24-09-2023 | FRANCISTOWN 24-09-2023 | KAZUNGULA BW 24-09-2023 | KAZUNGULA BW 26-09-2023 | KAZUNGULA ZM 26-09-2023 | KAZUNGULA ZM 26-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 07-10-2023 | 07-10-2023 | 14-10-2023 | 16-10-2023 | 17-10-2023 | 18-10-2023 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER CLEARING | PEMBA ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | DISPATCHING LUSAKA | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | WHISKEY PREPARING TO DISPATCH | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023
BA2209 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00958 | CAT00352KHLW00958 | P4E05090 | FML2211DSI1816 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | HK04RGGP | NT82883 / NT78055 | 2211DSI1816-BA2209 | 15-08-2023 | OFFLOADED | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 16-08-2023 | 21-08-2023 | 28-08-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 09-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 15-09-2023 | 15-09-2023 | 16-09-2023 | 20-09-2023 | 26-09-2023 | 28-09-2023 | 05-10-2023 | 12-10-2023 | 12-10-2023 | 20-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 10-08-2023 | ESTIMATED LOADING DATE 14-08-2023 | ESTIMATED LOADING DATE 14-08-2023 | ESTIMATED LOADING DATE 14-08-2023 | ESTIMATED LOADING DATE 14-08-2023 | ESTIMATED LOADING DATE 14-08-2023 | ESTIMATED LOADING DATE 14-08-2023 | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNITS AT COLENSO EN-ROUTE TO JOHANNESBURG | UNITS AT NEWCASTLE ENROUTE JOHANNESBURG | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER - DISPATCHING TOMORROW MORNING | POMONA STILL BUSY WITH TRIPCHECK TO DISPATCHING TOMORROW MORNING | POMONA WAITING LIMPOPO PERMIT | MIDRAND ENROUTE BEITH BRIDGE BORDER | PIENAARSREVIER ENROUTE BEITH BRIDGE BORDER | PIETERSBURG ENROUTE BEITH BRIDGE BORDER | VIVO ENROUTE BEITH BRIDGE BORDER | VENITIA ENROUTE BEITH BRIDGE BORDER | VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT BEITBRIDGE AWAITING CLEARANCE | VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENLTY AT HARARE REFUELLING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING RELESAE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING PERMIT - TO DISPATCH THIS AFTERNOON | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE ONLY DISPATCHING KAFUE TODAY | VEHICLE KABWE ENROUTE KASUMBALESA | VEHICLE KAPIRI ENROUTE KASUMBALESA | VEHICLE NDOLA ENROUTE KASUMBALESA | VEHICLE CHINGOLA ENROUTE KASUMBALESA | VEHICLE DISPATCHING CHINGOLA FOR KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUE TO CROSSING INTO DRC | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | ON SITE WAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2480 | 1 X CAT DE550E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXJ07795 | CAT00C15TLXJ07795 | N/A | FML2307DSI2166 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: DOLPHINE II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 275102 | BAD8793 | BAD8320T | 2307DSI2166 | 20-09-2023 | OFFLOADED | 23-08-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 29-09-2023 | GRB 30-09-2023 | GRB 03-10-2023 | M-DRIFT 04-10-2023 | M-DRIFT 04-10-2023 | FRANCISTOWN 04-10-2023 | FRANCISTOWN 04-10-2023 | KAZUNGULA BW 04-10-2023 | KAZUNGULA BW 05-10-2023 | KAZUNGULA ZM 05-10-2023 | KAZUNGULA ZM 05-10-2023 | 06-10-2023 | 07-10-2023 | 09-10-2023 | 09-10-2023 | 09-10-2023 | 09-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | 23-10-2023 | 23-10-2023 | 25-10-2023 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | JOHANNESBURG DISPATCHING TODAY | ENROUTE GROBLERS BRIDGE BORDER | JOHANNESBURG, WILL DISPATCH TOMORROW MORNING | DISPATCHING JOHANNESBURG | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER CLEARING | FRANCISTOWN ENROUTE KAZUNGULA | KAZUNGULA BORDER CLEARING | KAFUE ENROUTE LUSAKA | KASUMBALESA CLEARING | KASUMBALESA CLEARING | KASUMBALESA CLEARING | KASUMBALESA CLEARING | KASUMBALESA CLEARING | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE CURRENTLY IN QUEUE TO EXIT WHISKEY | AWAITING TO OFFLOAD | AWAITING TO OFFLOAD | OFFLOADED
BA2491 | CAT DE780E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK05269 | CAT00C18JLXK05269 | N/A | FML2307DSI2166 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: DOLPHINE II Voy. 015W - ETA DURBAN 08-09-2023 | COD 2023 275102 | BAD8793 | BAD8320T | 2307DSI2166 | 20-09-2023 | OFFLOADED | 23-08-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 29-09-2023 | GRB 30-09-2023 | GRB 03-10-2023 | M-DRIFT 04-10-2023 | M-DRIFT 04-10-2023 | FRANCISTOWN 04-10-2023 | FRANCISTOWN 04-10-2023 | KAZUNGULA BW 04-10-2023 | KAZUNGULA BW 05-10-2023 | KAZUNGULA ZM 05-10-2023 | KAZUNGULA ZM 05-10-2023 | 06-10-2023 | 07-10-2023 | 09-10-2023 | 09-10-2023 | 09-10-2023 | 09-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | 23-10-2023 | 23-10-2023 | 25-10-2023 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT KAZANGULA / CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT LUSAKA ENROUTE NDOLA | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | JOHANNESBURG DISPATCHING TODAY | ENROUTE GROBLERS BRIDGE BORDER | JOHANNESBURG, WILL DISPATCH TOMORROW MORNING | DISPATCHING JOHANNESBURG | GROBLERS BRIDGE BORDER CLEARING | GROBLERS BRIDGE BORDER CLEARING | FRANCISTOWN ENROUTE KAZUNGULA | KAZUNGULA BORDER CLEARING | KAFUE ENROUTE LUSAKA | KASUMBALESA CLEARING | KASUMBALESA CLEARING | KASUMBALESA CLEARING | KASUMBALESA CLEARING | KASUMBALESA CLEARING | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE CURRENTLY IN QUEUE TO EXIT WHISKEY | AWAITING TO OFFLOAD | AWAITING TO OFFLOAD | OFFLOADED
BA2590 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M8D00435 | CAT000D8TM8D00435 | TXJ02523 | FML2308DSI2183 | VESSEL: FIRMAMENT ACE V. 0132A - ETA DURBAN: 29-08-2023 | COD 2023 295298 | ND433449 | ND231110 / ND427407 | 132022 | 04-10-2023 | OFFLOADED | 20-09-2023 | 22-09-2023 | BV NUMBER RECEIVED | 29-08-2023 | 06-10-2023 | 09-10-2023 | 09-10-2023 | 10-10-2023 | 10-10-2023 | 10-10-2023 | 12-10-2023 | 12-10-2023 | 14-10-2023 | 16-10-2023 | 16-10-2023 | 16-10-2023 | 16-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 25-10-2023 | 25-10-2023 | 25-10-2023 | [68 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED, BV INSPECTION TO BE BOOKED | BV INSPECTION BOOKED FOR TOMORROW 22-09-2023 | BV INSPECTION BOOKED FOR TODAY 22-09-2023 - LOADING WEDNESDAY 27-09-2023 | BV INSPECTION DONE - LOADING WEDNESDAY 27-09-2023 / THURSDAY 28-09-2023 | BV INSPECTION DONE - LOADING FRIDAY 29-09-2023 | BV INSPECTION DONE - LOADING FRIDAY 29-09-2023 | VEHICLE UNDER MAJOR SERVICE, TO LOAD ON WEDNESDAY | VEHICLE UNDER MAJOR SERVICE, TO LOAD ON WEDNESDAY | VEHICLE UNDER MAJOR SERVICE, TO LOAD ON WEDNESDAY | LOADING TODAY | LOADED, WAITING FOR PERMITS BEFORE DISPATCHING DURBAN | DISPATCHED FROM DURBAN ENROUTE BEIT BRIDGE BORDER | VEHICLE AT MODIMOLLE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | VEHICLE AT HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE AT LUSAKA ENROUTE KABWE | VEHICLE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI AWAITING RELEASE DAY 2 | VEHICLE CURRENLTY ON SITE AWAIITNG TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED
BA2504 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK05273 | CAT00C18CLXK05273 | N/A | FML2307DSI2167 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: DOLPHINE II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 275102 | AKB2619 | BAD9294T | 2307DSI2167 | 20-09-2023 | OFFLOADED 18-10-2023 | 23-08-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | GRB 22-09-2023 | GRB 23-09-2023 | MARTINS DRIFT 23-09-2023 | MARTINS DRIFT 23-09-2023 | FRANCISTOWN 24-09-2023 | FRANCISTOWN 24-09-2023 | KAZUNGULA BW 24-09-2023 | KAZUNGULA BW 26-09-2023 | KAZUNGULA ZM 26-09-2023 | KAZUNGULA ZM 26-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 07-10-2023 | 07-10-2023 | 14-10-2023 | 16-10-2023 | 17-10-2023 | 18-10-2023 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER CLEARING | PEMBA ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | DISPATCHING LUSAKA | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | WHISKEY PREPARING TO DISPATCH | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023
BA2505 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LXK05272 | CAT00C18JLXK05272 | N/A | FML2307DSI2167 | VESSEL: MARTINIQUE Voy. 0224E / Transhipment Vessel: DOLPHINE II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 275102 | AKB2619 | BAD9294T | 2307DSI2167 | 20-09-2023 | OFFLOADED 18-10-2023 | 23-08-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | GRB 22-09-2023 | GRB 23-09-2023 | MARTINS DRIFT 23-09-2023 | MARTINS DRIFT 23-09-2023 | FRANCISTOWN 24-09-2023 | FRANCISTOWN 24-09-2023 | KAZUNGULA BW 24-09-2023 | KAZUNGULA BW 26-09-2023 | KAZUNGULA ZM 26-09-2023 | KAZUNGULA ZM 26-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 07-10-2023 | 07-10-2023 | 14-10-2023 | 16-10-2023 | 17-10-2023 | 18-10-2023 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER CLEARING | PEMBA ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | DISPATCHING LUSAKA | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | WHISKEY PREPARING TO DISPATCH | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023 | OFFLOADED 18-10-2023
BA2506 | 1 X CAT DE330E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LX905074 / S9X07166 / F5D06042 | CAT000C9ALX905074 | N/A | FML2307DSI2148 | VESSEL: TS KELANG V. 23004W / Transhipment Vwssel: DOLPHIN II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 289077 | BAD7326 | AKB2580T | 2307DSI2148 | 20-09-2023 | OFFLOADED 17-10-2023 | 11-09-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | GRB 22-09-2023 | GRB 23-09-2023 | MARTINS DRIFT 23-09-2023 | MARTINS DRIFT 23-09-2023 | FRANCISTOWN 24-09-2023 | FRANCISTOWN 24-09-2023 | KAZUNGULA BW 24-09-2023 | KAZUNGULA BW 26-09-2023 | KAZUNGULA ZM 26-09-2023 | KAZUNGULA ZM 26-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 07-10-2023 | 07-10-2023 | 14-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | [28 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER CLEARING | KAFUE ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | DISPATCHING LUSAKA | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | WHISKEY PREPARING TO DISPATCH | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023
BA2507 | 1 X CAT DE330E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | LX905075 / S9X07159 / F5D06043 | CAT000C9LLX905075 | N/A | FML2307DSI2148 | VESSEL: TS KELANG V. 23004W / Transhipment Vwssel: DOLPHIN II Voy. 015W - ETA DURBAN 11-09-2023 | COD 2023 289077 | BAD7326 | AKB2580T | 2307DSI2148 | 20-09-2023 | OFFLOADED 17-10-2023 | 11-09-2023 | 18-09-2023 | BV NUMBER RECEIVED | 11-09-2023 | 20-09-2023 | 21-09-2023 | 22-09-2023 | GRB 22-09-2023 | GRB 23-09-2023 | MARTINS DRIFT 23-09-2023 | MARTINS DRIFT 23-09-2023 | FRANCISTOWN 24-09-2023 | FRANCISTOWN 24-09-2023 | KAZUNGULA BW 24-09-2023 | KAZUNGULA BW 26-09-2023 | KAZUNGULA ZM 26-09-2023 | KAZUNGULA ZM 26-09-2023 | 27-09-2023 | 28-09-2023 | 29-09-2023 | 02-10-2023 | 02-10-2023 | 03-10-2023 | 07-10-2023 | 07-10-2023 | 14-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | [28 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 20-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-08-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-09-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 11-09-2023 | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | VESSEL IS IN AND WORKING AWAITING CONTAINERS TO BE GROUNDED | CONTAINER COLLECTED FROM PORT - TO BE UNPACKED TODAY, BV INSPECTION TO BE BOOKED FOR MONDAY 18-09-2023 | LOADING PLANNED FOR TODAY | LOADING PLANNED FOR TODAY | LOADED - DISPATCHING DURBAN TODAY | MOOIRIVER ENROUTE JOHANNESBURG | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | KAZUNGULA BORDER CLEARING | KAFUE ENROUTE LUSAKA | LUSAKA ENROUTE NDOLA | DISPATCHING LUSAKA | NDOLA ENROUTE KASUMBALESA | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | TRUCK AT KASUMBALESA BORDER CLEARING | WHISKEY PREPARING TO DISPATCH | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | WHISKEY WAITING FOR DUTIES TO BE PAID AND RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING RELEASE | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023 | OFFLOADED 17-10-2023
BA2206 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00894 | CAT00352KHLW00894 | P4E05363 | FML2211DSI1815 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | KR85BVGP | NT74888 / NT79777 | 2211DSI1815-BA2206 | 15-08-2023 | OFFLOADED 16-10-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 15-08-2023 | 21-08-202 | 24-08-2023 | 28-08-2023 | 30-08-2023 | 30-08-2023 | 02-09-2023 | 07-09-2023 | 09-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 15-09-2023 | 15-09-2023 | 16-09-2023 | 20-09-2023 | 26-09-2023 | 28-09-2023 | 06-10-2023 | 12-10-2023 | 12-10-2023 | 14-10-2023 | 15-10-2023 | 16-10-2023 | 16-10-2023 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2203 - CAT 352-08A) | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNITS AT VOLKSRUST EN-ROUTE TO JOHANNESBURG | UNITS AT STANDERTON ENROUTE MUSINA | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER - DISPATCHING TOMORROW MORNING | DISPATCHING POMONA TODAY | VEHCLE AT PIENAARSREVER WAITING LIMPOPO PERMIT | VEHCLE AT PIETERSBURG ENROUTE BEITH BRIDGE BORDER | VEHCLE AT MUSINA CLEARING | VEHCLE AT MUSINA CLEARING | VEHCLE AT BEIT BRIDGE BORDER CLEARING | VEHCLE AT BEIT BRIDGE RSA SIDE CROSSING OVER TO ZIM SIDE | VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENLTY AT BEATRICE ENROUTE HARARE | VEHICLE CURRENLTY AT HARARE ENROUTE CHIRUNDU | VEHICLE CURRENLTY AT HARARE REFUELLING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING RELESAE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING PERMIT - TO DISPATCH THIS AFTERNOON | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE ONLY DISPATCHING KAFUE TODAY | VEHICLE KABWE ENROUTE KASUMBALESA | VEHICLE KAPIRI ENROUTE KASUMBALESA | VEHICLE NDOLA ENROUTE KASUMBALESA | VEHICLE CHINGOLA ENROUTE KASUMBALESA | VEHICLE DISPATCHING CHINGOLA FOR KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUE TO CROSSING INTO DRC | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023
BA2207 | 1 X CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW00949 | CAT00352LHLW00949 | P4E05422 | FML2211DSI1816 | VESSEL: GLOVIS SKY Voy. 033 - ETA DURBAN: 10-12-2022 | COD 2023 222678 | KH29NKGP | DG54VVGP / DG54WHGP | 2211DSI1816-BA2207 | 15-08-2023 | OFFLOADED 16-10-2023 | 14-06-2023 | 20-06-2023 | BV COMPLETED | 10-12-2022 | 15-08-2023 | 21-08-2023 | 28-08-2023 | 04-09-2023 | 04-09-2023 | 05-09-2023 | 06-09-2023 | 07-09-2023 | 09-09-2023 | 11-09-2023 | 11-09-2023 | 11-09-2023 | 15-09-2023 | 15-09-2023 | 16-09-2023 | 20-09-2023 | 26-09-2023 | 28-09-2023 | 05-10-2023 | 12-10-2023 | 12-10-2023 | 14-10-2023 | 15-10-2023 | 16-10-2023 | 16-10-2023 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TEUSDAY 20-06-2023 | BV INSPECTION BOOKED FOR TODAY - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | BV INSPECTION COMPLETE - ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 30-07-2023 | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 10-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | ESTIMATED LOADING DATE 14-08-2023 - WAITING FOR VEHICLES TO RETURN FROM DRC (BA2204 - CAT 352-08A) | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT LOADED AWAITING PERMIT IN ORDER TO DISPATCH TO SITE | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNIT IN JHB UNDER GOING TRIP CHECK AND AWAITING LIMPOP PERMIT BEFORE DISPATCHING | UNITS AT VOLKSRUST EN-ROUTE TO JOHANNESBURG | UNITS AT STANDERTON ENROUTE MUSINA | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER | POMONA BUSY WITH TRIPCHECK BEFORE DISPATCHING FOR MUSINA / BEITH BRIDGE BORDER - DISPATCHING TOMORROW MORNING | POMONA STILL BUSY WITH TRIPCHECK TO DISPATCHING TOMORROW MORNING | POMONA WAITING LIMPOPO PERMIT | MIDRAND ENROUTE BEITH BRIDGE BORDER | WARMBAD ENROUTE BEITH BRIDGE BORDER | PIETERSBURG ENROUTE BEITH BRIDGE BORDER | VIVO ENROUTE BEITH BRIDGE BORDER | VENITIA ENROUTE BEITH BRIDGE BORDER | VEHICLE CURRENLTY AT MUSINA ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT BEITBRIDGE AWAITING CLEARANCE | VEHICLE CURRENLTY AT BUBI ENROUTE HARARE | VEHICLE CURRENLTY AT MASVINGO ENROUTE HARARE | VEHICLE CURRENLTY AT HARARE REFUELLING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU CLEARING | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING RELESAE | VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE WAITING PERMIT - TO DISPATCH THIS AFTERNOON | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE DISPATCHING KAFUE TODAY | VEHICLE ONLY DISPATCHING KAFUE TODAY | VEHICLE KABWE ENROUTE KASUMBALESA | VEHICLE KAPIRI ENROUTE KASUMBALESA | VEHICLE NDOLA ENROUTE KASUMBALESA | VEHICLE CHINGOLA ENROUTE KASUMBALESA | VEHICLE DISPATCHING CHINGOLA FOR KASUMBALESA | VEHICLE AT CHINGOLA IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT CHILILABOMBWE IN THE QUE TO KASUMBALESA | VEHICLE AT KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE IN THE QUE TO CROSSING INTO DRC | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023 | OFFLOADED 16-10-2023
BA2607 | CAT730-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F300733 | CAT00730L3F300733 | TXX04675 | FML2308DSI2179 | VESSEL: RCC CLASSIC V. 032 - ETA DURBAN 08-10-2023 | COD 2023 279560 | ND766591 | ND899773 | 132426 | 11-10-2023 | OFFLOADED 28-10-2023 | 29-08-2023 | 11-10-2023 | BV COMPLETE | 08-10-2023 | 11-10-2023 | 14-10-2023 | 16-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 24-10-2023 | 25-10-2023 | 25-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-10-2023 | COLLECTING FROM PORT TODAY - BV INSPECTION TO BE DONE TOMORROW | BV INSPECTION TO BE DONE TODAY | VAN REENEN ENROUTE BEIT BRIDGE BORDER | LADYSMITH ENROUTE BEIT BRIDGE BORDER | DISPATCHED JOHANNESBURG THIS MORNING ENROUTE POLOKWANE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIVI ENROUTE HARARE | VEHICLE CURRENTLY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENTLY AT KAPIRI EN-ROUTE TO MOKAMBO | VEHICLE CURRENTLY AT MOKAMBO AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI, AWAITING FINAL RELEASE | OFFLOADED 28-10-2023 | OFFLOADED 28-10-2023
BA2608 | CAT730-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F300661 | CAT00730L3F300661 | TXX04183 | FML2308DSI2179 | VESSEL: RCC CLASSIC V. 032 - ETA DURBAN 08-10-2023 | COD 2023 279560 | ND919955 | ND140841 | 132427 | 11-10-2023 | OFFLOADED 28-10-2023 | 29-08-2023 | 11-10-2023 | BV COMPLETE | 08-10-2023 | 11-10-2023 | 14-10-2023 | 16-10-2023 | 16-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 23-10-2023 | 24-10-2023 | 25-10-2023 | 25-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | [55 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-10-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-10-2023 | COLLECTING FROM PORT TODAY - BV INSPECTION TO BE DONE TOMORROW | BV INSPECTION TO BE DONE TODAY | VAN REENEN ENROUTE BEIT BRIDGE BORDER | LADYSMITH ENROUTE BEIT BRIDGE BORDER | DISPATCHED JOHANNESBURG THIS MORNING ENROUTE POLOKWANE | VEHICLE CURRENTLY AT BEITBRIDGE RSA SIDE - AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIVI ENROUTE HARARE | VEHICLE CURRENTLY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENTLY AT KAPIRI EN-ROUTE TO MOKAMBO | VEHICLE CURRENTLY AT MOKAMBO AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI, AWAITING FINAL RELEASE | OFFLOADED 28-10-2023 | OFFLOADED 28-10-2023
BA2317 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201515 | CAT00140KW9201515 | E7A57602 | FML2211DSI1831 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 315700 | KB15KRGP | WCL622GP | ND64581 | 24-10-2023 | OFFLOADED 01-11-2023 | 10-10-2023 | 17-10-2023 | BV COMPLETE | 22-12-2022 | 19-10-2023 | 20-10-2023 | 20-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 25-10-2023 | 25-10-2023 | 25-10-2023 | 25-10-2023 | 26-10-2023 | 26-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 29-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 01-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | VEHICLE CURRENTLY IN JOHANNESBURG UNDERGOING FINAL TRIP CHECK BEFORE DISPATCHING | VEHICLE CURRENTLY AT HARARE EN ROUTE TO CHIRUNDU | VEHICLE CURRENTLY CHIRUNDU ZIM SIDE | VEHICLE CURRENTLY CHIRUNDU ZIM SIDE | VEHICLE CURRENTLY KAFUE EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE CURRENTLY CHINGOLA EN-ROUTE TO KASUMBALESA BORDER | VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | VEHICLE CURRENTLY AT LUBUMBASHI | VEHICLE CURRENTLY AT LUBUMBASHI | OFFLOADED 01-11-2023 | OFFLOADED 01-11-2023
BA2260 | 1 X CAT 374-07B HYDRAULIC EXCAVATOR - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10080 | CAT00374ERGM10080 | E4T00755 | FML2212DSI1861 | VESSEL: RCC AFRICA V020 - ETA DURBAN: 16-01-2023 | COD 2023 312129 | ND760431 | ND760424 / ND760428 | ND64574 | 18-10-2023 | OFFLOADED 04-11-2023 | 11-10-2023 | 19-10-2023 | BV COMPLETE | 16-01-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 22-10-2023 | 23-10-2023 | 24-10-2023 | 25-10-2023 | 25-10-2023 | 26-10-2023 | 26-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 02-11-2023 | 02-11-2023 | 04-11-2023 | 04-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 13-10-2023 | BV INSPECTION TO BE DONE TODAY | LOADING UNIT TODAY | UNIT LOADED - TO DISPATCH DURBAN THIS AFTERNOON | VEHICLE CURRENLTY AT DOORNKOP ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT POLOKWANE ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT MASVINGO | VEHICLE CURRENLTY AT HARARE EN-ROUTE TO CHIRUNDU | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | KAPIRI ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE STILL IN QUE TO THE BORDER | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | CONNEX LUBUMBASHI, WAITING RELEASE | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023
BA2328 | 1 X CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30370 | CAT00345TKEF30370 | NTB12277 | FML2210DAI1789 | VESSEL: DURBAN HIGHWAY V. 105 - ETA DUEBAN: 02-12-2022 | COD 2023 312129 | ZKB404GP | PTW945GP / WDL443GP | ND64576 | 23-10-2023 | OFFLOADED 03-11-2023 | 11-10-2023 | 19-10-2023 | BV COMPLETE | 02-12-2022 | 20-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 24-10-2023 | 24-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 31-10-2023 | 01-11-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED NEXT WEEK | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | VEHICLE DISPATCHING DURBAN ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG UNDERGOING TRIP CHECK | VEHICLE AT JOHANNESBURG DISPATCHING TO BEITBRIDGE BORDER | VEHICLE AT MASVINGO EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT GWERU EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT KAROI EN-ROUTE | CHILILIBOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | LUBUMBASHI | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023
BA2339 | 1 X CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30374 | CAT00345CKEF30374 | NTB12087 | FML2210DAI1789 | VESSEL: DURBAN HIGHWAY V. 105 - ETA DUEBAN: 02-12-2022 | COD 2023 312129 | WMN927GP | BG55CXGP / BG37PLGP | ND64577 | 23-10-2023 | OFFLOADED 03-11-2023 | 11-10-2023 | 19-10-2023 | BV COMPLETE | 02-12-2022 | 20-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 24-10-2023 | 24-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 31-10-2023 | 01-11-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED NEXT WEEK | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK LOADED WAITING PERMIT IN ORDER TO DISPATCH | VEHICLE AT JOHANNESBURG DISPATCHING TO BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE RSA SIDE | VEHICLE AT BEITBRIDGE ZIM SIDE | VEHICLE AT CHIVU EN-ROUTE TO CHIRUNDU | VEHICLE AT KAPIRI ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | LUBUMBASHI | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023
BA2313 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03569 | CAT0226BVDX03569 | CZ209813 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023
BA2357 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201517 | CAT00140CW9201517 | TBA | FML2211DSI1833 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 315700 | TBM395GP | RNN269GP | ND64583 | 23-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 18-10-2023 | BV COMPLETE | 22-12-2022 | 23-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 25-10-2023 | 26-10-2023 | 27-10-2023 | 28-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 04-11-2023 | 04-11-2023 | 05-11-2023 | 05-11-2023 | 05-11-2023 | [72 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB DISPATCHING TODAY | TRUCK AT BBR RSA SIDE | TRUCK AT BBR ZIM SIDE AWAITING RELEASE | TRUCK AT HARARE | CHIRUNDU ZAM SIDE | DISPATCHED CHIRUNDU ZAM SIDE ENROUTE LUSAKA | NDOLA ENROUTE KASUMBULESA | KASUMBALESA ZAM SIDE CLEARING | CONGO EQUIPMENT LUBUMBASHI | CONGO EQUIPMENT LUBUMBASHI | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 08-11-2023
BA2401 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03575 | CAT0226BHDXZ03575 | CZ209781 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023
BA2402 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03573 | CAT0226BADXZ03573 | CZ209804 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023
BA2403 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03574 | CAT0226BLDXZ03574 | CZ209795 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023
BA2316 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201513 | CAT00140TW9201513 | E7A57603 | FML2211DSI1830 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 315700 | ND491242 | ND627367 | ND64584 | 24-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 17-10-2023 | BV COMPLETE | 22-12-2022 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 06-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | [72 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | LOADING TODAY AND UNIT TO DISPATCH ONCE PERMIT IS RECEIVED | TUCK LOADING MONDAY THE 30/10/2023 | TUCK AT HOWICK EN-ROUTE TO JHB | TUCK AT NGUNDU ENROUTE HARARE | HARARE | CHIRUNDU ZAM SIDE | LUSAKA ENOURTE KASUMBALESA | KITWE ENOURTE KASUMBALESA | GOMES DRC SIDE | GOMES DRC SIDE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT CONNEX AWAITING RELEASE | VEHICLE CURRENTLY AT CONNEX AWAITING RELEASE | OFFLOADED 08-11-2023
BA2318 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201514 | CAT00140PW9201514 | E7A57601 | FML2211DSI1832 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 315700 | JV80FPGP | JZ68SNGP | ND64582 | 24-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 17-10-2023 | BV COMPLETE | 22-12-2022 | 23-10-2023 | 23-10-2023 | 25-10-2023 | 27-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 27-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 04-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB TO DISPATCH TODAY | TRUCK IN POLOKWANE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IN RUTENGA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT HARARE | MAKUTI ENROUTE CHIRUNDU | DISPATCHED CHIRUNDU ZAM SIDE ENROUTE LUSAKA | NDOLA ENROUTE KASUMBULESA | KASUMBALESA ZAM SIDE CLEARING | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 08-11-2023
BA2340 | 1 X CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30371 | CAT00354PKEF30371 | NTB12084 | FML2210DAI1789 | VESSEL: DURBAN HIGHWAY V. 105 - ETA DUEBAN: 02-12-2022 | COD 2023 312129 | JP79VKGP | LC63BJGP / ZVM447GP | ND64578 | 23-10-2023 | OFFLOADED 08-11-2023 | 11-10-2023 | 13-10-2023 | BV COMPLETE | 02-12-2022 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 06-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | 08-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 13-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK DISPATCH DURBAN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT WARDEN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT WALLMANSTHAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT LOUIS TRICHARD EN-ROUTE TO BEITBRIDGE BORDER | KAROI ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE | DISPATCHED CHIRUNDU ZAM SIDE ENROUTE LUSAKA | LUSAKA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | OFFLOADED 08-11-2023
BA2357 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201517 | CAT00140CW9201517 | TBA | FML2211DSI1833 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 315700 | TBM395GP | RNN269GP | ND64583 | 23-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 18-10-2023 | BV COMPLETE | 22-12-2022 | 23-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 25-10-2023 | 26-10-2023 | 27-10-2023 | 28-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 04-11-2023 | 04-11-2023 | 05-11-2023 | 05-11-2023 | 05-11-2023 | [72 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB DISPATCHING TODAY | TRUCK AT BBR RSA SIDE | TRUCK AT BBR ZIM SIDE AWAITING RELEASE | TRUCK AT HARARE | CHIRUNDU ZAM SIDE | DISPATCHED CHIRUNDU ZAM SIDE ENROUTE LUSAKA | NDOLA ENROUTE KASUMBULESA | KASUMBALESA ZAM SIDE CLEARING | CONGO EQUIPMENT LUBUMBASHI | CONGO EQUIPMENT LUBUMBASHI | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023
BA2401 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03575 | CAT0226BHDXZ03575 | CZ209781 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023
BA2402 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03573 | CAT0226BADXZ03573 | CZ209804 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023
BA2403 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03574 | CAT0226BLDXZ03574 | CZ209795 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023
BA2416 | 1 X CAT CB34B UTILITY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3B400500 | CATCB34BT3B400506 | CYP04273 | FML2301DSI1910 | VESSEL: MIGNON V. EE235 - ETA DURBAN: 24-02-2023 | COD 2023 312137 | ND491242 | ND627367 | ND64584 | 24-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 17-10-2023 | BV COMPLETE | 22-12-2022 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 06-11-2023 | 07-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED ONE BV IS COMPLETED ON BA2316 (CO-LOAD) | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED ONE BV IS COMPLETED ON BA2316 (CO-LOAD) | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED ONE BV IS COMPLETED ON BA2316 (CO-LOAD) | BV INSPECTION COMPLETED - PLANNED LOADING DATE 20-10-2023 (CO-LOAD BA2316) | BV INSPECTION COMPLETED - PLANNED LOADING DATE 23-10-2023 (CO-LOAD BA2316) | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | TRUCK LOADING TODAY AND WILL DISPATCH ONCE PERMIT RECEIVED | TUCK LOADING MONDAY THE 30/10/2023 | TUCK AT HOWICK EN-ROUTE TO JHB | TUCK AT NGUNDU ENROUTE HARARE | HARARE | CHIRUNDU ZAM SIDE | LUSAKA ENOURTE KASUMBALESA | KITWE ENOURTE KASUMBALESA | GOMES DRC SIDE | GOMES DRC SIDE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT CONNEX AWAITING RELEASE | OFFLOADED 08-11-2023
BA2210 | 1 X CAT352-08A HYDRUALIC EXCAVATOR - 2 PACKAGES | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW01001 | CAT00352VHLW01001 | P4E05450 | FML2211DSI1837 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 312129 | XYP614GP | CV71JLGP / DD10RDGP | ND64570 | 24-10-2023 | OFFLOADED | 11-10-2023 | 13-10-2023 | BV COMPLETE | 22-12-2022 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 06-11-2023 | 06-11-2023 | 06-11-2023 | 07-11-2023 | 08-11-2023 | 09-11-2023 | 09-11-2023 | 09-11-2023 | 10-11-2023 | 14-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 13-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK TO LOAD TODAY AND DISPATCH ONCE BV RECEIVED | TRUCK DISPATCH DURBAN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT WARDEN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE BORDER | HARARE | MAKUTI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE | DEPARTED FROM CHIRUNDU ENROUTE KASUMBALESA | LUSAKA ENROUTE KASUMBALESA | NDOLA ENROUTE KASUMBALESA | NDOLA ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING RELEASE | VEHICLE ON SITE WAITING TO OFFLOAD | VEHICLE AT CONNEX LUBUMBASHI, AWAITING CLEARANCE/OFFLOADING | VEHICLE AT CONNEX LUBUMBASHI, AWAITING CLEARANCE/OFFLOADING | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2211 | 1 X CAT352-08A HYDRUALIC EXCAVATOR - 2 PACKAGES | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW01034 | CAT00352LHLW01034 | P4E05147 | FML2212DSI1860 | VESSEL: RCC AFRICA V020 - ETA DURBAN: 16-01-2023 | COD 2023 312129 | JP51CBGP | CS71TPGP / CS88PXGP | ND64571 | 24-10-2023 | OFFLOADED | 11-10-2023 | 13-10-2023 | BV COMPLETE | 16-01-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 05-11-2023 | 06-11-2023 | 07-11-2023 | 08-11-2023 | 09-11-2023 | 10-11-2023 | 13-11-2023 | 13-11-2023 | 14-11-2023 | 14-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 13-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK TO LOAD TODAY AND DISPATCH ONCE BV RECEIVED | TRUCK DISPATCH DURBAN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT WALLMANSTHAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE BORDER | KAROI ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE | DEPARTED FROM CHIRUNDU ENROUTE KASUMBALESA | LUSAKA ENROUTE KASUMBALESA | NDOLA ENROUTE KASUMBALESA | NDOLA ENROUTE KASUMBALESA | NDOLA ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE AT CONNEX LUBUMBASHI, AWAITING CLEARANCE/OFFLOADING | VEHICLE AT CONNEX LUBUMBASHI, AWAITING CLEARANCE/OFFLOADING | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2260 | 1 X CAT 374-07B HYDRAULIC EXCAVATOR - MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10080 | CAT00374ERGM10080 | E4T00755 | FML2212DSI1861 | VESSEL: RCC AFRICA V020 - ETA DURBAN: 16-01-2023 | COD 2023 312129 | ND760431 | ND760424 / ND760428 | ND64574 | 18-10-2023 | OFFLOADED 04-11-2023 | 11-10-2023 | 19-10-2023 | BV COMPLETE | 16-01-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 22-10-2023 | 23-10-2023 | 24-10-2023 | 25-10-2023 | 25-10-2023 | 26-10-2023 | 26-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 02-11-2023 | 02-11-2023 | 04-11-2023 | 04-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 13-10-2023 | BV INSPECTION TO BE DONE TODAY | LOADING UNIT TODAY | UNIT LOADED - TO DISPATCH DURBAN THIS AFTERNOON | VEHICLE CURRENLTY AT DOORNKOP ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT POLOKWANE ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT MASVINGO | VEHICLE CURRENLTY AT HARARE EN-ROUTE TO CHIRUNDU | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | KAPIRI ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE STILL IN QUE TO THE BORDER | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | CONNEX LUBUMBASHI, WAITING RELEASE | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023 | OFFLOADED 04-11-2023
BA2313 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03569 | CAT0226BVDX03569 | CZ209813 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023
BA2316 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201513 | CAT00140TW9201513 | E7A57603 | FML2211DSI1830 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 315700 | ND491242 | ND627367 | ND64584 | 24-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 17-10-2023 | BV COMPLETE | 22-12-2022 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 06-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | 08-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | LOADING TODAY AND UNIT TO DISPATCH ONCE PERMIT IS RECEIVED | TUCK LOADING MONDAY THE 30/10/2023 | TUCK AT HOWICK EN-ROUTE TO JHB | TUCK AT NGUNDU ENROUTE HARARE | HARARE | CHIRUNDU ZAM SIDE | LUSAKA ENOURTE KASUMBALESA | KITWE ENOURTE KASUMBALESA | GOMES DRC SIDE | GOMES DRC SIDE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT CONNEX AWAITING RELEASE | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023
BA2318 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201514 | CAT00140PW9201514 | E7A57601 | FML2211DSI1832 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 315700 | JV80FPGP | JZ68SNGP | ND64582 | 24-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 17-10-2023 | BV COMPLETE | 22-12-2022 | 23-10-2023 | 23-10-2023 | 25-10-2023 | 27-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 27-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 04-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB TO DISPATCH TODAY | TRUCK IN POLOKWANE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IN RUTENGA EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT HARARE | MAKUTI ENROUTE CHIRUNDU | DISPATCHED CHIRUNDU ZAM SIDE ENROUTE LUSAKA | NDOLA ENROUTE KASUMBULESA | KASUMBALESA ZAM SIDE CLEARING | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023
BA2021 | 1 X CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605655 | CAT00745C3F605655 | TXW07071 | FML2301DSI1936 | VESSEL: RED CEDAR V. 231203 - ETA DURBA: 13-03-2023 | COD 2023 312132 | ND730794 | ND443606 | ND64572 | 24-10-2023 | OFFLOADED 17-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 13-03-2023 | 26-10-2023 | 30-10-2023 | 30-10-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 05-11-2023 | 06-11-2023 | 06-11-2023 | 06-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | 09-11-2023 | 10-11-2023 | 13-11-2023 | 13-11-2023 | 13-11-2023 | 13-11-2023 | 16-11-2023 | 17-11-2023 | 17-11-2023 | 17-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED NEXT WEEK | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | LOADING TODAY AND UNIT TO DISPATCH ONCE PERMIT IS RECEIVED | LOADED, UNIT TO DISPATCH ONCE PERMIT IS RECEIVED | TRUCK AT PINETOWN EN-ROUTE TO JHB | VOLKSRUST ENROUTE JOHANNESBURG | DOORNKOP ENROUTE BEIT BRIDGE | LOUIS TRICHARDT ENROUTE BEIT BRIDGE | BEIT BRIDGE CLEARING | CHIVI ENROUTE HARARE | KADOMA ENROUTE HARARE | KADOMA ENROUTE HARARE | VEHICLE CURRENLTY AT CHIRUNDU ZAM AWAITING PERMIT | VEHICLE CURRENLTY AT CHIRUNDU ZAM AWAITING PERMIT | VEHICLE CURRENLTY AT CHINGOLA ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT WHISKEY AWAIITNG RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAIITNG RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAIITNG RELEASE | VEHICLE CURRENLTY AT KANYAKA AWAITING ESCORT TO PROCEED TO SITE | VEHICLE CURRENLTY AT KANYAKA AWAITING ESCORT TO PROCEED TO SITE | OFFLOADED 17-11-2023
BA2023 | 1 X CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605660 | CAT00745A3F605660 | TXW07169 | FML2301DSI1937 | VESSEL: RED CEDAR V. 231203 - ETA DURBA: 13-03-2023 | COD 2023 312132 | ND760468 | ND476150 | ND64573 | 24-10-2023 | OFFLOADED 17-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 13-03-2023 | 30-10-2023 | MIDDELBURG 01-11-2023 | MIDDELBURG 01-11-2023 | 02-11-2023 | 02-11-2023 | 02-11-2023 | 06-11-2023 | 05-11-2023 | 06-11-2023 | 06-11-2023 | 06-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | 09-11-2023 | 09-11-2023 | 09-11-2023 | 10-11-2023 | 13-11-2023 | 13-11-2023 | 16-11-2023 | 17-11-2023 | 17-11-2023 | 17-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED NEXT WEEK | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | LOADING TODAY AND UNIT TO DISPATCH ONCE PERMIT IS RECEIVED | UNIT TO LOAD AND DISPATCH MONDAY THE 30/10/2023 | UNIT TO LOAD AND DISPATCH MONDAY THE 30/10/2023 | DISPATCHING DURBAN TODAY | DUNDEE ENROUTE JOHANNESBURG | AMMERSFORT ENROUTE BEITH BRIDGE | POLOKWANE ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | BANKET ENROUTE HARARE | BANKET ENROUTE HARARE | VEHICLE CURRENLTY AT CHIRUNDU ZAM AWAITING PERMIT | VEHICLE CURRENLTY AT CHIRUNDU ZAM AWAITING PERMIT | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY AWAIITNG RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAIITNG RELEASE | VEHICLE CURRENLTY AT WHISKEY AWAIITNG RELEASE | VEHICLE CURRENLTY AT KANYAKA AWAITING ESCORT TO PROCEED TO SITE | VEHICLE CURRENLTY AT KANYAKA AWAITING ESCORT TO PROCEED TO SITE | OFFLOADED 17-11-2023
BA2260 | 1 X CAT 374-07B HYDRAULIC EXCAVATOR - SPARE PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10080 | CAT00374ERGM10080 | E4T00755 | FML2212DSI1861 | VESSEL: RCC AFRICA V020 - ETA DURBAN: 16-01-2023 | COD 2023 312129 | BCC1016 | BCC1014 / BCC1015 | ND64574-1 | 18-10-2023 | OFFLOADED 17-11-2023 | 11-10-2023 | 19-10-2023 | BV COMPLETE | 16-01-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 24-10-2023 | 24-10-2023 | 25-10-2023 | 25-10-2023 | 26-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 02-11-2023 | 03-11-2023 | 04-11-2023 | 07-11-2023 | 08-11-2023 | 10-11-2023 | 12-11-2023 | 13-11-2023 | 17-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 13-10-2023 | BV INSPECTION TO BE DONE TODAY | LOADING SPARES TODAY | UNIT LOADED - TO DISPATCH DURBAN THIS AFTERNOON | VEHICLE CURRENLTY AT VAN REENENS PASS ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT POLOKWANE ENROUTE BEITBRIDGE | VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | VEHICLE CURRENLTY AT CHIRUNDU AWAITING CLEARANCE | KABWE ENROUTE KASUMBALESA | KITWE ENROUTE KASUMBALESA | DISPATCHING KITWE FOR KASUMBALESA | ONLY DISPATCHING KITWE FOR KASUMBALESA TODAY | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA ZAM SIDE AWAITING CLEARING | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | OFFLOADED | VEHICLE AT CONNEX LUBUMBASHI, AWAITING CLEARANCE/OFFLOADING | VEHICLE AT CONNEX LUBUMBASHI, AWAITING CLEARANCE/OFFLOADING | VEHICLE AT CONNEX LUBUMBASHI, AWAITING CLEARANCE/OFFLOADING | VEHICLE AT CONNEX LUBUMBASHI, AWAITING CLEARANCE/OFFLOADING | OFFLOADED 17-11-2023 | OFFLOADED 17-11-2023
BA2609 | CAT D7 TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HXA00288 | CAT000D7VHXA00288 | NTB13845 | FML2310DSI2238 | VESSEL: ORCHID ACE Voy. 0133A - ETA DURBAN: 31-10-2023 | COD 2023 329834 | ND919953 | ND823540 | 132910 | 09-11-2023 | OFFLOADED 25-11-2023 | 02-11-2023 | 07-11-2023 | BV NUMBER RECEIVED | 31-10-2023 | 08-11-2023 | 08-11-2023 | 08-11-2023 | 08-11-2023 | 09-11-2023 | 10-11-2023 | 13-11-2023 | 13-11-2023 | 13-11-2023 | 14-11-2023 | 15-11-2023 | 15-11-2023 | 16-11-2023 | 16-11-2023 | 16-11-2023 | 17-11-2023 | 17-11-2023 | 20-11-2023 | 20-11-2023 | 20-11-2023 | 21-11-2023 | 21-11-2023 | 22-11-2023 | KIPUSHI 24-11-2023 | 25-11-2023 | [83 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 30-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 31-10-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 31-10-2023 | VESSEL ARRIVED AND DISCHARGING CARGO | VESSEL STILL DISCHARGING CARGO - UNIT TO BE LOADED ONCE AVAILABLE | UNIT COLLECTED FROM PORT - INSPECTION BOOKED FOR TUESDAY 07-11-2023 - AWAITING VALIDATION OF BV LICENSE | UNIT COLLECTED FROM PORT - INSPECTION BOOKED FOR TUESDAY 07-11-2023 | UNIT COLLECTED FROM PORT - INSPECTION BOOKED FOR TUESDAY 07-11-2023 | BV INSPECTION COMPLETED THIS MORNING - VEHICLE PLANNING TO DISPATCH THIS AFTERNOON | VEHICLE DISPATCHED DURBAN THIS MORNING ENROUTE JOHANNESBURG | VEHICLE CURRENTLY AT BEITBRIDGE RSA AWAITING CLEARANCE | VEHICLE CURRENTLY AT ZVIMBA ZIMBABWE EN-ROUTE TO CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU | VEHICLE CURRENTLY AT CHIRUNDU | TRUCK AT KAFUE EN-ROUTE MOKAMBO | TRUCK AT KAFUE EN-ROUTE MOKAMBO | TRUCK IS AT MUFULIRA ZAMBIA EN-ROUTE MOKAMBO | TRUCK IS AT WHISKEY | VEHICLE AT CONNEX LUBUMBASHI | VEHICLE AT CONNEX LUBUMBASHI | AT CLIENT IN KIPUSHI WAITING TO OFFLOAD | OFFLOADED 25-11-2023 | OFFLOADED 25-11-2023
BA2328 | 1 X CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30370 | CAT00345TKEF30370 | NTB12277 | FML2210DAI1789 | VESSEL: DURBAN HIGHWAY V. 105 - ETA DUEBAN: 02-12-2022 | COD 2023 312129 | ZKB404GP | PTW945GP / WDL443GP | ND64576 | 23-10-2023 | OFFLOADED 03-11-2023 | 11-10-2023 | 19-10-2023 | BV COMPLETE | 02-12-2022 | 20-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 24-10-2023 | 24-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 31-10-2023 | 01-11-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED NEXT WEEK | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | VEHICLE DISPATCHING DURBAN ENROUTE JOHANNESBURG | VEHICLE AT JOHANNESBURG UNDERGOING TRIP CHECK | VEHICLE AT JOHANNESBURG DISPATCHING TO BEITBRIDGE BORDER | VEHICLE AT MASVINGO EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT GWERU EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE AT KAROI EN-ROUTE | CHILILIBOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | LUBUMBASHI | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023
BA2339 | 1 X CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30374 | CAT00345CKEF30374 | NTB12087 | FML2210DAI1789 | VESSEL: DURBAN HIGHWAY V. 105 - ETA DUEBAN: 02-12-2022 | COD 2023 312129 | WMN927GP | BG55CXGP / BG37PLGP | ND64577 | 23-10-2023 | OFFLOADED 03-11-2023 | 11-10-2023 | 19-10-2023 | BV COMPLETE | 02-12-2022 | 20-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 24-10-2023 | 24-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 26-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 31-10-2023 | 01-11-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED NEXT WEEK | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK LOADED WAITING PERMIT IN ORDER TO DISPATCH | VEHICLE AT JOHANNESBURG DISPATCHING TO BEITBRIDGE BORDER | VEHICLE AT BEITBRIDGE RSA SIDE | VEHICLE AT BEITBRIDGE ZIM SIDE | VEHICLE AT CHIVU EN-ROUTE TO CHIRUNDU | VEHICLE AT KAPIRI ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE CLEARING | WHISKEY WAITING RELEASE | WHISKEY WAITING RELEASE | LUBUMBASHI | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023 | OFFLOADED 03-11-2023
BA2340 | 1 X CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30371 | CAT00354PKEF30371 | NTB12084 | FML2210DAI1789 | VESSEL: DURBAN HIGHWAY V. 105 - ETA DUEBAN: 02-12-2022 | COD 2023 312129 | JP79VKGP | LC63BJGP / ZVM447GP | ND64578 | 23-10-2023 | OFFLOADED 08-11-2023 | 11-10-2023 | 13-10-2023 | BV COMPLETE | 02-12-2022 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 06-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | 08-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 13-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 20-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK DISPATCH DURBAN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT WARDEN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT WALLMANSTHAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT LOUIS TRICHARD EN-ROUTE TO BEITBRIDGE BORDER | KAROI ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE | DISPATCHED CHIRUNDU ZAM SIDE ENROUTE LUSAKA | LUSAKA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE | KASUMBALESA DRC SIDE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023
BA2357 | 1 X CAT140GC-01A MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | W9201517 | CAT00140CW9201517 | TBA | FML2211DSI1833 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 315700 | TBM395GP | RNN269GP | ND64583 | 23-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 18-10-2023 | BV COMPLETE | 22-12-2022 | 23-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 25-10-2023 | 26-10-2023 | 27-10-2023 | 28-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 30-10-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 02-11-2023 | 03-11-2023 | 04-11-2023 | 04-11-2023 | 05-11-2023 | 05-11-2023 | 05-11-2023 | [72 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB UNDERGOING TRIP CHECK | TRUCK IN JHB DISPATCHING TODAY | TRUCK AT BBR RSA SIDE | TRUCK AT BBR ZIM SIDE AWAITING RELEASE | TRUCK AT HARARE | CHIRUNDU ZAM SIDE | DISPATCHED CHIRUNDU ZAM SIDE ENROUTE LUSAKA | NDOLA ENROUTE KASUMBULESA | KASUMBALESA ZAM SIDE CLEARING | CONGO EQUIPMENT LUBUMBASHI | CONGO EQUIPMENT LUBUMBASHI | VEHICLE ON SITE WAITING TO OFFLOAD | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023
BA2401 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03575 | CAT0226BHDXZ03575 | CZ209781 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023
BA2402 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03573 | CAT0226BADXZ03573 | CZ209804 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023
BA2403 | 1 X CAT226B3 SKID STEER LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | DXZ03574 | CAT0226BLDXZ03574 | CZ209795 | FML2302DSI1947 | VESSEL: RIO GRANDE Voy. 2308W - ETA DURBAN: 17-03-2023 | COD 2023 312130 | KB 12 WB GP | YLK 221 GP / YLK 214 GP | 2302DSI1947 | 13-10-2023 | OFFLOADED 07-11-2023 | 10-10-2023 | 13-10-2023 | BV COMPLETE | 17-03-2023 | 13-10-2023 | 14-10-2023 | 14-10-2023 | 17-10-2023 | 17-10-2023 | 17-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 18-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 19-10-2023 | 20-10-2023 | 21-10-2023 | 21-10-2023 | 23-10-2023 | 24-10-2023 | 24-10-2023 | 27-10-2023 | 27-10-2023 | 07-11-2023 | 07-11-2023 | [80 empty] | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING TODAY | VEHICLE CURRENLTY AT GROBLERSBRIDGE ENROUTE MUSINA | VEHICLE DISPATCHED MUSINA CURRENLTY ENROUTE KAZUNGULA | VEHICLE ENROUTE LUSAKA | VEHICLE AT NDOLA ENROUTE CHINGOLA | TRUCK IS AT KASUMBALESA AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT WHISKEY AWAITING FINAL CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | LUBUMBASHI, WAITING PERMISSION TO OFFLOAD | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | CONNEX LUBUMBASHI, WAITING PERMISSION TO OFFLOAD / RELEASE - 9 DAYS - PLEASE ASSIST | ON SITE WAITING TO OFFLOAD | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023 | OFFLOADED 07-11-2023
BA2416 | 1 X CAT CB34B UTILITY COMPACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3B400500 | CATCB34BT3B400506 | CYP04273 | FML2301DSI1910 | VESSEL: MIGNON V. EE235 - ETA DURBAN: 24-02-2023 | COD 2023 312137 | ND491242 | ND627367 | ND64584 | 24-10-2023 | OFFLOADED 08-11-2023 | 10-10-2023 | 17-10-2023 | BV COMPLETE | 22-12-2022 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 27-10-2023 | 28-10-2023 | 28-10-2023 | 29-10-2023 | 30-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 31-10-2023 | 01-11-2023 | 01-11-2023 | 02-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 03-11-2023 | 06-11-2023 | 07-11-2023 | 07-11-2023 | 07-11-2023 | 08-11-2023 | 08-11-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR TOMORROW 12-10-2023 | BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED ONE BV IS COMPLETED ON BA2316 (CO-LOAD) | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED ONE BV IS COMPLETED ON BA2316 (CO-LOAD) | BV INSPECTION COMPLETED, LOADING DATE TO BE CONFIRMED ONE BV IS COMPLETED ON BA2316 (CO-LOAD) | BV INSPECTION COMPLETED - PLANNED LOADING DATE 20-10-2023 (CO-LOAD BA2316) | BV INSPECTION COMPLETED - PLANNED LOADING DATE 23-10-2023 (CO-LOAD BA2316) | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | TRUCK LOADING TODAY AND WILL DISPATCH ONCE PERMIT RECEIVED | TUCK LOADING MONDAY THE 30/10/2023 | TUCK AT HOWICK EN-ROUTE TO JHB | TUCK AT NGUNDU ENROUTE HARARE | HARARE | CHIRUNDU ZAM SIDE | LUSAKA ENOURTE KASUMBALESA | KITWE ENOURTE KASUMBALESA | GOMES DRC SIDE | GOMES DRC SIDE | VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | VEHICLE CURRENTLY AT CONNEX AWAITING RELEASE | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023 | OFFLOADED 08-11-2023
BA2319 | 1 X CAT 160K MOTOR GRADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SZM20252 | CAT0160KLSZ20252 | TX712623 | FML2210DSI1790 | VESSEL: DURBAN HIGHWAY V. 105 - ETA DUEBAN: 02-12-2022 | COD 2023 315700 | ND55MTGP | CYB609GP | BD64575 | 24-10-2023 | OFFLOADED 04-12-2023 | 10-10-2023 | 17-10-2023 | BV COMPLETE | 02-12-2022 | 25-10-2023 | 26-10-2023 | 27-10-2023 | 01-11-2023 | 01-11-2023 | 01-11-2023 | 04-11-2023 | 05-11-2023 | 06-11-2023 | 07-11-2023 | 08-11-2023 | 09-11-2023 | 14-11-2023 | 15-11-2023 | 15-11-2023 | 15-11-2023 | 15-11-2023 | 16-11-2023 | 16-11-2023 | 19-11-2023 | 20-11-2023 | 21-11-2023 | 27-11-2023 | 27-11-2023 - CONNEX | 04-12-2023 | [71 empty] | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING INVOICE AND BV NUMBER | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | AWAITING BV NUMBER AND DISPATCH DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 23-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | BV INSPECTION COMPLETE - PLANNING TO LOAD 25-10-2023 | TRUCK DISPATCH DURBAN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT JHB UNDERGOING TRIP CHECK | TRUCK AT BELA BELA EN-ROUTE TO BEITBRIDGE BORDER | CURRENTLY AT LOUIS TRICHARDT ON BREAKDOWN | CURRENTLY AT LOUIS TRICHARDT ON BREAKDOWN - REPLACEMENT VEHICLE TO ARRIVE TODAY | DEPARTED LOUIS TRICHARDT ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CROSSING TO ZIM | HARARE ENROUTE CHIRUNDU | HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZIM AWAITING CLEARANCE | VEHICLE AT CHIRUNDU ZIM AWAITING CLEARANCE | VEHICLE AT CHIRUNDU ZAM SIDE - DISPATCHING FOR LUBUMBASHI | VEHICLE AT CHIRUNDU ZAM SIDE - DISPATCHING FOR LUBUMBASHI | VEHICLE AT CHIRUNDU EN-ROUTE TO KASUMBALESA | VEHICLE AT KABWE EN-ROUTE TO KASUMBALESA | VEHICLE AT KABWE EN-ROUTE TO KASUMBALESA | VEHICLE AT KABWE EN-ROUTE TO KASUMBALESA | VEHICLE AT WHISKEY WAITING RELEASE | VEHICLE DISPATCHING WHISKEY | VEHICLE AT CONNEX LUBUMBASHI | VEHICLE 10KM BEFORE LUBUMBASHI STUCK IN MUD. VEHICLE TO BE TOWED OUT THIS MORNING | VEHICLE 10KM BEFORE LUBUMBASHI STUCK IN MUD. VEHICLE TO BE TOWED OUT THIS MORNING | CONNEX LUBUMBASHI | CONNEX LUBUMBASHI WAITING RELEASE | CONNEX LUBUMBASHI WAITING RELEASE - DAY 3 PLEASE ASSIST | CONNES AFRICA LUBUMBASHI, WAITING TO OFFLOAD | CONNES AFRICA LUBUMBASHI, WAITING TO OFFLOAD | CONNEX AFRICA LUBUMBASHI, WAITING TO OFFLOAD | OFFLOADED 04-12-2023 | OFFLOADED 04-12-2023
BA2259 | 1 X CAT 374-07B HYDRAULIC EXCAVATOR MAIN UNIT | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10079 | CAT00374TRGM10079 | E4T00777 | FML2211DSI1838 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 329835 | ND760431 | ND760424/ND760428 | ND61102 | 20-11-2023 | OFFLOADED 09-12-2023 | 01-11-2023 | 06-11-2023 | BV COMPLETE | 22-12-2022 | 20-11-2023 | MIDDELBURG 21-11-2023 | MIDDELBURG 21-11-2023 | 21-11-2023 | 22-11-2023 | 22-11-2023 | 24-11-2023 | 25-11-2023 | 28-11-2023 | 28-11-2023 | 03-12-2023 | 03-12-2023 | 03-12-2023 | 04-12-2023 | 04-12-2023 | 04-12-2023 | 04-12-2023 | 05-12-2023 | 05-12-2023 | 06-12-2023 | 06-12-2023 | 07-12-2023 | 07-12-2023 | 09-12-2023 | 09-12-2023 | [90 empty] | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | BV NUMBER RECEIVED - INSPECTION BOOKED FOR MONDAY 06-11-2023 | BV NUMBER RECEIVED - INSPECTION BOOKED FOR MONDAY 06-11-2023 - AWAITING VALIDATION OF BV LICENSE | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY 06-11-2023 | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY 06-11-2023 | BV INSPECTION COMPLETED YESTERDAY - UNIT PLANNING TO LOAD 08-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 08-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 14-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 14-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 17-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 20-11-2023 | LOADED AWAITING PERMIT | LOADED AWAITING PERMIT | PIETERMARITZBURG ENROUTE JOHANNESBURG | MIDDELBURG ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | VEHICLE AT HARARE TO DISPATCH FOR CHIRUNDU | VEHICLE DISPATCHING HARARE FOR CHIRUNDU | VEHICLE CHIRUNDU ZIM SIDE | VEHICLE CHIRUNDU ZIM SIDE | CHIRUNDU ZIM SIDE - VEHICLE ON BREAKDOWN | LUSAKA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | DISPATCHING WHISKEY | CONNEX LUBUMBASHI, WAITING CEARANCE AND RELEASE | OFFLOADED 09-12-2023 | OFFLOADED 09-12-2023
BA2638 | 1 X CAT D6R2 TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SSS01743 | CAT00D6RJSSS01743 | TXD26457 | FML2310DSI2237 | VESSEL: PROCYON LEADER:- Transhipment Vessel: LEO LEADER Voy. 105 - ETA DURBAN: 18-11-2023 | COD 2023 329834 | VFK347GP | KM53XDGP | ND61127 | 23-11-2023 | OFFLOADED | 02-11-2023 | 22-11-2023 | BV NUMBER RECEIVED | 20-11-2023 | 22-11-2023 | 23-11-2023 | 25-11-2023 | 25-11-2023 | 26-11-2023 | 26-11-2023 | 28-11-2023 | 28-11-2023 | 29-11-2023 | 29-11-2023 | 30-11-2023 | 30-11-2023 | 04-12-2023 | 04-12-2023 | 04-12-2023 | 04-12-2023 | 05-12-2023 | 05-12-2023 | 05-12-2023 | 07-12-2023 | 07-12-2023 | 10-12-2023 | 11-12-2023 | 13-12-2023 | 14-12-2023 | [90 empty] | AWAITING VESSEL ARRIVAL: ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 27-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | AWAITING VESSEL ARRIVAL: ETA DURBAN 18-11-2023 | VESSEL ARRIVED 19-11-2023 - COLLECTING FROM PORT TODAY - BV INSPECTION BOOKED FOR TODAY | VESSEL ARRIVED 19-11-2023 - COLLECTING FROM PORT TODAY - BV INSPECTION MOVED TO TOMORROW | BV INSPECTION TO BE DONE TODAY | JOHANNESBURG ENROUTE MUSINA | JOHANNESBURG DOING MAINTENANCE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE ZIM SIDE AWAITING RELEASE | HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAFUE ENROUTE KASUMBALESA | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE - AWAITING RELEASE | WHISKEY AWAITING RELEASE | LUBUMBASHI | CONNEX AFRICA AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 PLEASE ASSIST | OFFLOADED | OFFLOADED
BA2259 | 1 X CAT 374-07B HYDRAULIC EXCAVATOR SPARES | BARTRAC EQUIPMENT . CONGO EQUIPMENT | RGM10079 | CAT00374TRGM10079 | E4T00777 | FML2211DSI1838 | VESSEL: MORNING CHAMPION V. 163 - ETA DURBAN: 22-12-2022 | COD 2023 329835 | AGL3037 | BCE5782ZM / BCE5783ZM | ND61101 | 20-11-2023 | OFFLOADED 21-12-2023 | 01-11-2023 | 06-11-2023 | BV COMPLETE | 22-12-2022 | 25-11-2023 | 25-11-2023 | 27-11-2023 | 28-11-2023 | 28-11-2023 | 28-11-2023 | 30-11-2023 | 01-12-2023 | 02-12-2023 | 02-12-2023 | 06-12-2023 | 06-12-2023 | 07-12-2023 | 07-12-2023 | 07-12-2023 | 08-12-2023 | 08-12-2023 | 08-12-2023 | 08-12-2023 | 12-12-2023 | 12-12-2023 | 17-12-2023 | 18-12-2023 | CONNEX 21-12-2023 | 21-12-2023 | [90 empty] | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | BV NUMBER RECEIVED - INSPECTION BOOKED FOR MONDAY 06-11-2023 | BV NUMBER RECEIVED - INSPECTION BOOKED FOR MONDAY 06-11-2023 - AWAITING VALIDATION OF BV LICENSE | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY 06-11-2023 | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY 06-11-2023 | BV INSPECTION COMPLETED YESTERDAY - UNIT PLANNING TO LOAD 08-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 08-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 14-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 14-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 17-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 20-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 20-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 20-11-2023 | BV INSPECTION COMPLETED - PARTS PLANNING TO LOAD 20-11-2023 / 21-11-2023 | BV INSPECTION COMPLETED - PARTS PLANNING TO LOAD 24-11-2023 | BV INSPECTION COMPLETED - PARTS PLANNING TO LOAD 24-11-2023 | BV INSPECTION COMPLETED - PARTS LOADING TOMORROW 24-11-2023 | LOADING TODAY | JOHANNESBURG - DISPATCHING FOR BEIT BRIDGE | POLOKWANE ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE AWAITING RELEASE | BEIT BRIDGE ZIM SIDE AWAITING RELEASE | RUTENGA ENROUTE HARARE | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | LUWANYA ENROUTE KASUMBALESA | KITWE ENROUTE KASUMBALESA | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC TO MOVE TO WHISKEY TODAY | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | ENROUTE SITE TO OFFLOAD | VEHICLE CURRENTLY AT LUBUMBASHI - WAIITNG FINAL RELEASE TO PROCEED TO SITE | CONNEX LUBUMBASHI - ELECTION DAY | CONNEX LUBUMBASHI - AWAITING TO OFFLOAD | OFFLOADED 21-12-2023 | OFFLOADED 21-12-2023
BA2606 | 1 CAT395 BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML2311DSI2288 | VESSEL: MORNING COMPOSER V. EE320 - ETA DURBAN: 04-12-2023 | COD 2023 356364 | SVZ496GP | N/A | 2311DSI2288 | 11-12-2032 | OFFLOADED 22-12-2023 | 06-12-2023 | 08-12-2023 | BV COMPLETE | 04-12-2023 | 11-12-2023 | 12-12-2023 | 12-12-2023 | GRB 12-12-2023 | GRB 13-12-2023 | M/DRIFT 13-12-2023 | M/DRIFT 13-12-2023 | F/TOWN 13-12-2023 | F/TOWN 13-12-2023 | 13-12-2023 | 14-12-2023 | 14-12-2023 | 14-12-2023 | 15-12-2023 | 15-12-2023 | 15-12-2023 | 16-12-2023 | 16-12-2023 | 17-12-2023 | 17-12-2023 | 18-12-2023 | 18-12-2023 | 19-12-2023 | 21-12-2023 | 22-12-2023 | [119 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 04-12-2023 PM | VESSEL IN AND WORKING | BUCKET AT BONDED FACILITY - AWAITING BV NUMBER | BV NUMBER RECEIVED - AWATING VALIDATION OF LICENSE BEFORE THE BV INSPECTION CAN TAKE PLACE. - PLANNIG TO LOAD 11-12-2023 | BV INSPECTION TO BE DONE TODAY - LOADING MONDAY 11-12-2023 | BV COMPLETED - LOADING TODAY | VILLIERS ENROUTE JOHANNESBURG | GROBLERS BRIDGE BORDER IN THE QUEUE TO CROSS TO BOTSWANA SIDE | NATA ENROUTE KAZUNGULA | VEHICLE CURRENTLY AT LUMATA ENROUTE LUBUMBASHI | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - WAITING RELEASE - ELECTION DAY | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI - WAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-12-2023 | OFFLOADED 22-12-2023
BA2634 | 1 X CAT D6R2 TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SSS01756 | CAT00D6RKSSS01756 | TXD26872 | FML2311DSI2305 | VESSEL: APOLLON LEADER V. 101 - ETA DURBAN: 19-12-2023 | COD 2023 364777 | ALC9531 | ACZ7653T | ND61196 | 22-12-2023 | OFFLOADED 11-01-2024 | 18-12-2023 | 21-12-2023 | BV COMPLETED | 19-12-2023 | 23-12-2023 | 23-12-2023 | 26-12-2023 | GRB 27-12-2023 | GRB 27-12-2023 | MARTINS DRIFT 27-12-2023 | MARTINS DRIFT 27-12-2023 | FRANCISTOWN 27-12-2023 | FRANCISTOWN 27-12-2023 | KAZUNGULA BW 28-12-2023 | KAZUNGULA BW 28-12-2023 | KAZUNGULA BW 28-12-2023 | KAZUNGULA BW 29-12-2023 | 30-12-2023 | 31-12-2023 | 31-12-2023 | 02-01-2024 | 02-01-2024 | 02-01-2024 | 04-01-2024 | 04-01-2024 | 08-01-2024 | 08-01-2024 | 10-01-2024 | 11-01-2024 | [119 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-12-2023 | VESSEL CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - TO DISPATCH FROM DURBAN | GROBLES BRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | TRUCK AT CHOMA EN-ROUTE TO KASUMBALESA BORDER | TRUCK AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | TRUCK AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING FINAL RELEASE | TRUCK AT WHISKEY AWAITING FINAL RELEASE | TRUCK AT WHISKEY PAYING FOR PARKING - TO DISPATCHED ONCE DONE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE & RELEASE | CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 11-01-2024
BA2637 | 1 X CAT D6R2 TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | SSS01757 | CAT00D6RJSSS01757 | TXD26679 | FML2311DSI2306 | VESSEL: APOLLON LEADER V. 101 - ETA DURBAN: 19-12-2023 | COD 2023 364777 | ALG1979 | ADD3951T | ND61197 | 22-12-2023 | OFFLOADED 11-01-2024 | 18-12-2023 | 21-12-2023 | BV COMPLETED | 19-12-2023 | 23-12-2023 | 23-12-2023 | 26-12-2023 | GRB 27-12-2023 | GRB 27-12-2023 | MARTINS DRIFT 27-12-2023 | MARTINS DRIFT 27-12-2023 | FRANCISTOWN 27-12-2023 | FRANCISTOWN 27-12-2023 | KAZUNGULA BW 28-12-2023 | 29-12-2023 | 30-12-2023 | 31-12-2023 | 31-12-2023 | 31-12-2023 | 02-01-2024 | 02-01-2024 | 02-01-2024 | 03-01-2024 | 05-01-2024 | 05-01-2024 | 08-01-2024 | 08-01-2024 | 10-01-2024 | 11-01-2024 | [119 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 18-12-2023 | AWAITING VESSEL ARRIVAL - ETA DURBAN: 19-12-2023 | VESSEL CURRENTLY DISCHARGING CARGO | COLLECTED FROM PORT - BV INSPECTION TO BE DONE TODAY | BV INSPECTION COMPLETED - TO DISPATCH FROM DURBAN | GROBLES BRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | TRUCK IS AT KITWE EN-ROUTE TO KASUMBALESA | TRUCK IS AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | TRUCK IS AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING FINAL RELEASE | TRUCK AT WHISKEY PAYING FOR PARKING - TO DISPATCHED ONCE DONE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE & RELEASE | CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 11-01-2024
BA2327 | 1 X CAT 345GC-07D HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KEF30376 | CAT00345AKEF30376 | NTB12158 | FML2210DSI1789 | VESSEL: DURBAN HIGHWAY V. 105 - ETA DUEBAN: 02-12-2022 | COD 2023 329835 | ND568309 | ND566910 / ND564162 | ND61103 | 28-11-2023 | OFFLOADED 15-01-2024 | 01-11-2023 | 06-11-2023 | BV COMPLETED | 02-12-2023 | 08-10-2023 | MIDDELBURG 11-12-2023 | MIDDELBURG 11-12-2023 | 12-12-2023 | 13-12-2023 | 13-12-2023 | 17-12-2023 | 18-12-2023 | 28-12-2023 | 02-01-2023 | 02-01-2023 | 02-01-2023 | 07-01-2024 | 08-01-2024 | 08-01-2024 | 08-01-2024 | 08-01-2024 | 08-01-2024 | SAKANIA 09-01-2024 | SAKANIA 09-01-2024 | 10-01-2023 | 10-01-2024 | 10-01-2024 | 10-01-2024 | 15-01-2024 | [90 empty] | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING INVOICE & BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | AWAITING BV NUMBER TO BOOK INSPECTION | BV NUMBER RECEIVED - INSPECTION BOOKED FOR MONDAY 06-11-2023 | BV NUMBER RECEIVED - INSPECTION BOOKED FOR MONDAY 06-11-2023 - AWAITING VALIDATION OF BV LICENSE | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY 06-11-2023 | BV NUMBER RECEIVED - INSPECTION BOOKED FOR TODAY 06-11-2023 | BV INSPECTION COMPLETED YESTERDAY - UNIT PLANNING TO LOAD 08-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 08-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 14-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 14-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 17-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 20-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 20-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 20-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 27-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 27-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 27-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 27-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 27-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 30-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 30-11-2023 | BV INSPECTION COMPLETED - UNIT PLANNING TO LOAD 30-11-2023 | LOADING TODAY | LOADED - BUSY WITH TRIP CHECKS | TO DISPATCH DURBAN TODAY | AWAITING PERMIT BEFORE DISPATCHING | AWAITING KZN PERMIT BEFORE DISPATCHING | AWAITING KZN PERMIT BEFORE DISPATCHING - PERMIT TO BE RECEIVED MIDDAY TODAY | HOWICK ENROUTE JOHANNESBURG | MIDDELBURG | POLOKWANE ENROUTE BEIT BRIDGE | MUSINA ENROUTE BEIT BRIDGE | BEIT BRIDGE ZIM SIDE | VEHICLE CURRELTY AT HARARE DISPATCHING FOR CHIRUNDU THIS AFTERNOON | VEHICLE CURRELTY AT HARARE DISPATCHING FOR CHIRUNDU THIS AFTERNOON | VEHICLE CURRELTY AT HARARE DISPATCHING FOR CHIRUNDU THIS AFTERNOON - VEHICLE WAS IN THE WORKSHOP BUSY WITH TRIP CHECK | ENROUTE CHIRUNDU BORDER | HARARE - VEHICLE WILL DISPATCH ON WEDNESDAY 27-12-2023 | HARARE - VEHICLE WILL DISPATCH TOMORROW MORNING | DISPATCHED HARARE ENROUTE CHIRUNDU | TRUCK AT CHINHOYI EN ROUTE CHIRUNDU | TRUCK AT CHIRUNDU ZAM UNDERGOING CLEARANCE | TRUCK AT CHIRUNDU ZAM AWAITING PERMITS | TRUCK AT CHIRUNDU ZAM AWAITING PERMITS | TRUCK AT CHIRUNDU PN BREAKDOWN,AWAITING FEEDBACK AS TO WHEN THE TRUCK WILL BE REPAIRED | KAPIRI MPOSHE ENROUTE KASUMBALESA | SAKANIA BORDER ZAM SIDE CLEARING | KANYAKA DRC | CONGO EQUIPMENT WAITING TO OFFLOAD | CONGO EQUIPMENT WAITING ESCORT TO PROCEED TO CONNEX | CONNEX LUBUMBASHI, WAITING TO OFFLOAD | OFFLOADED 15-01-2024 | OFFLOADED 15-01-2024
BA2563 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805296 | CAT00740L3F805296 | TXY07933 | FML2310DSI2244 | VESSEL: LILAC ROLLER Voy. 231223 - ETA DURBA: 27-11-2023 | COD 2024 110678 | JP79VKGP | LC38BJGP | ND64634 | 26-01-2024 | OFFLOADED 08-02-2024 | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 27-11-2023 | 24-01-2024 | 25-01-2024 | 26-01-2024 | 28-01-2024 | 28-01-2024 | 28-01-2024 | 30-01-2024 | 31-01-2024 | 01-02-2024 | 02.02.2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 05.02.2024 | 05.02.2024 | 06-02-2024 | 06-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 08-02-2024 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK TO LOAD TODAY THE 24/01/2024 AND DISPATCH THE 25/01/2024 | TRUCK IS AT VAN REENEN EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT MOKGOPHONG EN-ROUTE TO BEITBRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | HARARE ENROUTE CHIRUNDU | DISPATCHING HARARE FOR CHIRUNDU BORDER | CHIRUNDU ZAM SIDE | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE CURRENTLY AT LUBUMBASHI AWAITING FINAL CLEARANCE | OFFLOADED 08-02-2024
BA2156 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805178 | CAT00740C3F805178 | TXY07780 | FML2305DSI2055 | VESSEL: RED CEDAR Voy. 231209 - ETA DURBAN: 09-06-2023 | COD 2024 110678 | LB59FBGP | CM76CRGP | ND64630 | 26-01-2024 | OFFLOADED 08-02-2024 | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 09-06-2023 | 24-01-2024 | 25-01-2024 | 26-01-2024 | 28-01-2024 | 28-01-2024 | 28-01-2024 | 30-01-2024 | 30-01-2024 | 31-01-2024 | 31-01-2024 | 01-02-2024 | 01-02-2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 05-02-2024 | 05-02-2024 | 06-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK LOADING TODAY TO DISPATCH THE 24/01/2024 | TRUCK IS AT MOOI RIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK IS AT MOKGOPHONG EN-ROUTE TO BEITBRIDGE | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE | KAFUE ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI ENROUTE SITE | VEHICLE AT CONNEX AWIAITNG FINAL CLEARNACE | OFFLOADED 08-02-2024
BA2157 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805179 | CAT00740V3F805179 | TXY07729 | FML2305DSI2069 | VESSEL: BRIGHT SKY Voy. 231210 - eta durban: 22-06-2023 | COD 2024 110678 | LF67PNGP | LM49ZSGP | ND64631 | 26-01-2024 | OFFLOADED 08-02-2024 | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 22-06-2023 | 24-01-2024 | 25-01-2024 | 27-01-2024 | 28-01-2024 | 28-01-2024 | 28-01-2024 | 29-01-2024 | 29-01-2024 | 30-01-2024 | 30-01-2024 | 31-01-2024 | 31-01-2024 | 01-02-2024 | 01-02-2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 05.02.2024 | 05-02-2024 | 05-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK LOADING TODAY TO DISPATCH THE 24/01/2024 | TRUCK IS AT MOOI RIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK IS AT JOHANNESBURG UNDERGOING TRIP CHECK | BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE | LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE AT CONNEX AWIAITNG FINAL CLEARNACE | OFFLOADED 08-02-2024
BA2158 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805194 | CAT00740J3F805194 | TXY07842 | FML2305DSI2088 | VESSEL: GREEN MOUNTAIN Voy. 231211 - ETA DURBAN: 08-07-2023 | COD 2024 110678 | JF47HVGP | HK63LCGP | ND64632 | 26-01-2024 | OFFLOADED 08-02-2024 | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 08-07-2023 | 24-01-2024 | 25-01-2024 | 27-01-2024 | 28-01-2024 | 28-01-2024 | 28-01-2024 | 29-01-2024 | 29-01-2024 | 30-01-2024 | 30-01-2024 | 31-01-2024 | 31-01-2024 | 01-02-2024 | 01-02-2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 05.02.2024 | 05-02-2024 | 05-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK LOADING TODAY TO DISPATCH THE 24/01/2024 | TRUCK IS AT MOOI RIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK IS AT JOHANNESBURG UNDERGOING TRIP CHECK | BEIT BRIDGE ZIM SIDE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE | CHIRUNDU ZAM SIDE | LUSAKA ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE DISPATCHING WHISKEY ENROUTE LUBUMBASHI | VEHICLE AT CONNEX AWIAITNG FINAL CLEARNACE | OFFLOADED 08-02-2024
BA2159 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805195 | CAT00740C3F805195 | TXY07775 | FML2305DSI2089 | VESSEL: GREEN MOUNTAIN Voy. 231211 - ETA DURBAN: 08-07-2023 | COD 2024 110678 | KX54BNGP | LF39FZGP | ND64633 | 26-01-2024 | OFFLOADED 08-02-2024 | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 08-07-2023 | 24-01-2024 | 26-01-2024 | 27-01-2024 | 28-01-2024 | 28-01-2024 | 28-01-2024 | 30-01-2024 | 30-01-2024 | 31-01-2024 | 31-01-2024 | 01-02-2024 | 01-02-2024 | 01-02-2024 | 01-02-2024 | 01-02-2024 | 02-02-2024 | 03.02.2024 | 04.02.2024 | 05-02-2024 | 05-02-2024 | 05-02-2024 | 06-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK TO LOAD TODAY THE 24/01/2024 AND DISPATCH THE 25/01/2024 | TRUCK IS AT MOOI RIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT JOHANNESBURG UNDERGOING TRIP CHECK | BEIT BRIDGE ZIM SIDE | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE | KABWE ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA DRC SIDE AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT LUBUMBASHI ENROUTE SITE | VEHICLE AT CONNEX AWIAITNG FINAL CLEARNACE | OFFLOADED 08-02-2024
BA2020 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605644 | CAT00745L3F605644 | TXW07092 | FML2302DSI1965 | VESSEL: BRIGHT SKY Voy. 231205 - ETA DURBAN: 30-03-2023 | COD 2024 110678 | NS433449 | ND231110 / NS247407 | 2302DSI1965 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 30-03-2023 | 31-01-2024 | MIDDELBURG 01-02-2024 | MIDDELBURG 01-02-2024 | 03.02.2024 | 04.02.2024 | 05.02.2024 | 05-02-2024 | 06-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 09-02-2024 | 09-02-2024 | 09-02-2024 | 10-02-2024 | 11-02-2024 | 11-02-2024 | 12-02-2024 | 12-02-2024 | 13-02-2024 | 15-02-2024 | 15-02-2024 | 15-02-2024 | 15-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK IS AT OUR TRANSPORTERS FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | TRUCK IS AT OUR TRANSPORTERS FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | TRUCK IS AT OUR TRANSPORTERS FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | TRUCK IS AT OUR TRANSPORTERS FACILITY AWAITING TRUCKS TO RETURN FROM DRC IN ORDER TO LOAD AND DISPATCH | DISPATCHING DURBAN TODAY | ENROUTE TO BETHAL | MOTSERERENG ENROUTE MUSIAN | VEHICLE CURRENTLY AT BEITBRIDGE ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT GUTU ENROUTE HARARE | VEHICLE AT HURUNGWE ZIM ENROUTE CHIRUINDU | VEHICLE AT CHIRUINDU ZAM SIDE AWAITING CLEARANCE | VEHICLE AT CHIRUINDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE AT MUFULIRA ZAMBIA | VEHICLE AT WHSIKEY AWAITING CLEARANCE AND RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING CLEARANCE AND RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING CLEARANCE AND RELEASE | OFFLOADED | OFFLOADED
BA2024 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605739 | CAT00745L3F605739 | TXW06782 | FML2304DSI2045 | VESSEL: LIBERTY Voy. EE307 - ETA DURBAN: 05-05-2023 | COD 2024 110678 | ND747407 | ND692809 / ND692831 | 2304DSI2045 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 05-05-2024 | 24-01-2024 | 26-01-2024 | 26-01-2024 | 29-01-2024 | 29-01-2024 | 29-01-2024 | 30-01-2024 | 31-01-2024 | 01-02-2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 05.02.2024 | 06-02-2024 | 07-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 09-02-2024 | 10-02-2024 | 10-02-2024 | 12-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | UNIT WILL BE COLLECTED TODAY FROM OUR BONDED FACILITY AND UNDER GO TRIP CHECK AT TRANSPORTERS YARD BEFORE DISPATCH-PLANNING TO DISPATCH NEXT WEEK | TRUCK IS AT TUGELA EN-ROUTE TO BEITBRIDGE BOPRDER | TRUCK IS AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BOPRDER | LOUIS TRICHARDT ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE CHIRUNDU BORDER | HARARE ENROUTE CHIRUNDU | APPROCHING CHIRUNDU | VEHICLE AT KABWE ENROUTE CHINGOLA | VEHICLE AT KITWE ENROUTE MOKAMBO BORDER | VEHICLE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2025 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605746 | CAT00745T3F605746 | TXW07051 | FML2304DSI2046 | VESSEL: LIBERTY Voy. EE307 - ETA DURBAN: 05-05-2023 | COD 2024 110678 | ND437412 | ND647660 / ND647016 | 2304DSI2046 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 05-05-2024 | 24-01-2024 | 26-01-2024 | 26-01-2024 | 28-01-2024 | 28-01-2024 | 28-01-2024 | 30-01-2024 | 31-01-2024 | 01-02-2024 | 01.02.2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 06-02-2024 | 07-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 09-02-2024 | 10-02-2024 | 14-02-2024 | 14-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | UNIT WILL BE COLLECTED TODAY FROM OUR BONDED FACILITY AND UNDER GO TRIP CHECK AT TRANSPORTERS YARD BEFORE DISPATCH-PLANNING TO DISPATCH NEXT WEEK | TRUCK CURRENTLY AT MOOIRIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK CURRENTLY AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE CHIRUNDU BORDER | HARARE ENROUTE CHIRUNDU | APPROCHING CHIRUNDU | VEHICLE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | VEHICLE AT KITWE ENROUTE MOKAMBO BORDER | VEHICLE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | TRUCK AT CONGO EQUIPMENT AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED
BA2168 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605747 | CAT00745P3F605747 | TXW07135 | FML2307DSI2144 | VESSEL: GOLDEN KAROO Voy. 231214 - ETA DURBAN: 21-08-2023 | COD 2024 110678 | JP51CBGP | CS71TPGP / CS88PXGP | ND64645 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 21-08-2023 | 29-01-2024 | PTA 29-01-2024 | PTA 31-01-2024 | 01-02-2024 | 01-02-2024 | 01-02-2024 | 02-02-2024 | 03.02.2024 | 04.02.2024 | 05.02.2024 | 05-02-2024 | 05-02-2024 | 06-02-2024 | 06-02-2024 | 06-02-2024 | 07-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 10-02-2024 | 10-02-2024 | 12-02-2024 | 13-02-2024 |  |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK LOADING TODAY AND TO DISPATCH MONDAY THE 29-01-2024 | TRUCK LOADING TODAY AND TO DISPATCH MONDAY THE 29/01/2024 | VAN REENEN ENROUTE JOHANNESBURG | PRETORIA BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR THE BORDER | POLOKWANE ENROUTE MUSINA | LOUIS TRICHARDT ENROUTE MUSIAN | MASVINGO ENROUTE HARARE | VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KAPIRI ENROUTE CHINGOLA | VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | TRUCK AT CE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2169 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605755 | CAT00745A3F605755 | TXW07123 | FML2303DSI2011 | VESSEL: BLUE MASTER II Voy. 231207 - ETA DURBAN: 13-05-2023 | COD 2024 110678 | ND431993 | ND923084 | 2303DSI2011 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | Lusaka, Zambia | 13-05-2023 | 24-01-2024 | 26-01-2024 | 26-01-2024 | 28-01-2024 | 28-01-2024 | 28-01-2024 | 30-01-2024 | 31-01-2024 | 01-02-2024 | 01.02.2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 05.02.2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 09-02-2024 | 10-02-2024 | 15-02-2024 | 15-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | UNIT WILL BE COLLECTED TODAY FROM OUR BONDED FACILITY AND UNDER GO TRIP CHECK AT TRANSPORTERS YARD BEFORE DISPATCH-PLANNING TO DISPATCH NEXT WEEK | TRUCK IS AT TUGELA EN-ROUTE TO BEITBRIDGE BOPRDER | TRUCK IS AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BOPRDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE CHIRUNDU BORDER | HARARE ENROUTE CHIRUNDU | APPROCHING CHIRUNDU | VEHCILE AT CHIBOMBO ZAMBIA ENROUTE KASUMBALESA | VEHICLE AT KITWE ENROUTE MOKAMBO BORDER | VEHICLE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | TRUCK AT CE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED
BA2170 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605756 | CAT00745L3F605756 | TXW07130 | FML2303DSI2008 | VESSEL: BLUE MASTER II Voy. 231207 - ETA DURBAN: 13-05-2023 | COD 2024 110678 | ND870909 | ND692828 / ND692813 | 2303DSI2008 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 13-05-2023 | 26-01-2024 | MIDDELBURG 28-01-2024 | MIDDELBURG 29-01-2024 | 29-01-2024 | 29-01-2024 | 29-01-2024 | 01-02-2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 05.02.2024 | 06-02-2024 | 06-02-2024 | 07-02-2024 | 07-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 09-02-2024 | 10-02-2024 | 10-02-2024 | 14-02-2024 | 14-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | UNIT WILL BE COLLECTED TODAY FROM OUR BONDED FACILITY AND UNDER GO TRIP CHECK AT TRANSPORTERS YARD BEFORE DISPATCH-PLANNING TO DISPATCH NEXT WEEK | UNIT WILL BE COLLECTED TODAY FROM OUR BONDED FACILITY AND UNDER GO TRIP CHECK AT TRANSPORTERS YARD BEFORE DISPATCH-PLANNING TO DISPATCH NEXT WEEK | TRUCK IS AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE BORDER | MIDDELBURG | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | CHIRUMANZU ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KAPIRI ENROUTE CHINGOLA | VEHICLE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHCILE CURRENLTY AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | TRUCK AT CE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED
BA2280 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605738 | CAT00745A3F605738 | TXW07207 | FML2303DSI1991 | VESSEL GREEN MOUNTAIN Voy. 231206 - ETA DURBAN: 16-04-2023 | COD 2024 110678 | ND750229 | ND710695 | 2303DSI1991 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 16-04-2023 | 24-01-2024 | MIDDELBURG 27-01-2024 | MIDDELBURG 28-01-2024 | 29-01-2024 | 29-01-2024 | 29-01-2024 | 31-01-2024 | 31-01-2024 | 31-01-2024 | 31-01-2024 | 03.02.2024 | 05.02.2024 | 05-02-2024 | 05-02-2024 | 05-02-2024 | 06-02-2024 | 07-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 09-02-2024 | 10-02-2024 | 13-02-2024 | 13-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | UNIT WILL BE COLLECTED TODAY FROM OUR BONDED FACILITY AND UNDER GO TRIP CHECK AT TRANSPORTERS YARD BEFORE DISPATCH-PLANNING TO DISPATCH NEXT WEEK | TRUCK IS AT MOOI RIVER EN-ROUTE TO BEITBRIDGE BORDER | TRUCK IS AT BETHAL EN-ROUTE TO BEITBRIDGE BORDER | GROBLERSDAL ENROUTE MUSINA | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | CHIRUNDU ZIM SIDE | CHIRUNDU ZIM SIDE | VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE AT KITWE ENROUTE MOKAMBO BORDER | VEHICLE CURRENTLY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | VEHICLE DISPATCHED WHISKEY ENROUTE LUBUMBASHI | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | OFF LAODED | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2332 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605856 | CAT00745E3F605856 | TXW07436 | FML2306DSI2105 | VESSEL: GREY FOX Voy. 231212 - ETA DURBAN: 22-07-2023 | COD 2024 110678 | ND73512 | ND207161 | ND64644 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 22-07-2023 | 29-01-2024 | MIDDELBURG 30-01-2024 | MIDDELBURG 30-01-2024 | 01-02-2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 05.02.2024 | 05.02.2024 | 06-02-2024 | 06-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 08-02-2024 | 09-02-2024 | 12-02-2024 | 12-02-2024 | 13-02-2023 | 14-02-2024 | 15-02-2024 | 15-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK TO LOAD TODAY THE 24/01/2024 AND DISPATCH THE 25/01/2024 | TRUCK TO LOAD TODAY THE 24/01/2024 AND IS AWAITING PERMITS IN ORDER TO DISPATCH | TUCK IS LOADED AWAITING PERMITS IN ORDER TO DISPATCH | DISPATCHING DURBAN | BETHAL ENROUTE MUSINA | POLOKWANE ENROUTE MUSINA | LOUIS TRICHARDT ENROUTE MUSIAN | MUSINA ENROUTE BEIT BRIDGE | VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE TO DISPATCH FROM CHIRUNDU ZAM TODAY | VEHICLE CURRENTLY AT LUSAKA ENROUTE KASUMBALESA | VEHICLE CURRENTLY AT CHILILABOMBWE ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE - AWAITING CLEARANCE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING CLEARANCE AND RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING CLEARANCE AND RELEASE | OFFLOADED | OFFLOADED
BA2565 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805301 | CAT00740L3F805301 | TXY07929 | FML2310DSI2269 | VESSEL: GOLDEN KAROO Voy. 231220 - ETA DURBAN: 19-12-2023 | COD 2024 110678 | LD33CMGP | KN32ZCGP | ND64635 | 26-01-2024 | OFFLOADED | 19-01-2024 | 24-01-2024 | BV INSPECTION COMPLETED | 19-12-2023 | 26-01-2024 | PTA 29-01-2024 | PTA 01-02-2024 | 01-02-2024 | 02.02.2024 | 03.02.2024 | 04.02.2024 | 05.02.2024 | 05-02-2024 | 05-02-2024 | 06-02-2024 | 07-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 08-02-2024 | 08-02-2024 | 08-02-2024 | 09-02-2024 | 10-02-2024 | 12-02-2024 | 12-02-2024 | 12-02-2024 | 13-02-2024 | 14-02-2024 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | LOADING TODAY AND WILL DISPATCH TOMMROW THE 26-01-2024 | TRUCK IS AT CATO RIDGE EN-ROUTE TO JOHANNESBURG | VAN REENEN ENROUTE JOHANNESBURG | PRETORIA BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR THE BORDER | PRETORIA AWAITING PERMIT | DISPATCHING PRETORIA | MUSINA ENROUTE BEIT BRIDGE | VEHICLE AT HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | VEHICLE AT NDOLA ENROUTE CHINGOLA | VEHICLE AT KASUMBALESA DRC SIDE AWAIITNG CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING AND RELEASE | TRUCK AT CE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED | OFFLOADED | OFFLOADED
BA2333 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT - CONGO EQUIPMENT | 3F605857 | CAT00745C3F605857 | TXW07307 | FML2306DSI2121 | VESSEL: BLUE MASTER II Voy. 231213 - ETA DUEBAN: 07-08-2023 | COD 2024 110678 | ND730794 | ND443606 | ND64646 | 26-01-2024 | OFFLOADED 19-02-2024 | 19-01-2024 | 24-01-2024 | BV COMPLETED | 07-08-2023 | 01-02-2024 | 03.02.2024 | 04.02.2024 | 05-04-2024 | 06-02-2024 | 06-02-2024 | 07-02-2024 | 07-02-2024 | 08-02-2024 | 09-02-2024 | 09-02-2024 | 10-02-2024 | 10-02-2024 | 11-02-2024 | 11-02-2024 | 12-02-2024 | 12-02-2024 | 12-02-2024 | 13-02-2024 | 15-02-2024 | 16-02-2024 | 17-02-2024 | 17-02-2024 | CONNEX OFFLOADED 19-02-2024 | 19-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | AWAITING LOADING DATE AND TRUCK DETAILS | TRUCK LOADING TODAY AND TO DISPATCH MONDAY THE 29/01/2024 | LOADED - AWAITING PERMIT | LOADED - AWAITING PERMIT | DISPATCHING DURBAN TODAY | CAMPERDOWN ENROUTE JOHANNESBURG | NEWCASTLE ENROUTE JOHANNESBURG | VEHICLE AT GROBLERSDAL ENROUTE MUSINA | VEHICLE AT BEIT BRIDGE BORDER | VEHICLE AT MASVINGO ENROUTE HARARE | VEHCILE CURRENLTY AT HARARE ENROUTE CHIRUNDU | VEHCILE CURRENLTY AT MAPINGA ENROUTE CHIRUNDU | VEHCILE CURRENLTY AT NDOLA EN-ROUET TO CHIRUNDU | VEHCILE CURRENLTY AT KASUMBALESA ZAM SIDE | VEHCILE CURRENLTY AT KASUMBALESA ZAM SIDE | VEHCILE CURRENLTY AT KASUMBALESA DRC SIDE | VEHCILE CURRENLTY AT WHISKEY AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI AWAITING CLEARANCE | OFFLOADED 19-02-2024 | OFFLOADED 19-02-2024
BA2566 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805302 | CAT00740H3F805302 | TXY07900 | FML2310DSI2245 | VESSEL: LILAC ROLLER Voy. 231223 - ETA DURBA: 27-11-2023 | COD 2024 110678 | ND72757 | ND613163 | ND64636 | 26-01-2024 | OFFLOADED 19-02-2024 | 19-01-2024 | 24-01-2024 | BV COMPLETED | 27-11-2023 | 29-01-2024 | MIDDELBURG 30-01-2024 | MIDDELBURG 30-01-2024 | 01-02-2024 | 02.02.2024 | 02.02.2024 | 03.02.2024 | 03.02.2024 | 03.02.2024 | 04.02.2024 | 04.02.2024 | 04.02.2024 | 05.02.2024 | 05.02.2024 | 05-02-2024 | 05-02-2024 | 05-02-2024 | 06-02-2024 | 07-02-2024 | 08-02-2024 | 12-02-2024 | 13-02-2024 | 14-02-2024 | CONNEX OFFLOADED 19-02-2024 | 19-02-2024 | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | TRUCK TO LOAD TODAY THE 24/01/2024 AND DISPATCH THE 25/01/2024 | TUCK IS LOADED AWAITING PERMITS IN ORDER TO DISPATCH | TUCK IS LOADED AWAITING PERMITS IN ORDER TO DISPATCH | DISPATCHING DURBAN | BETHAL ENROUTE MUSINA | POLOKWANE ENROUTE MUSINA | LOUIS TRICHARDT ENROUTE MUSIAN | MUSINA ENROUTE BEIT BRIDGE | VEHICLE CURRENTLY AT LUSAKA ENROUTE KABWE | VEHICLE AT CHILLABOMBWE ENROUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE - CROSSING TO DRC | VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE - IN QUEUE TO CROSS TO DRC | VEHICLE CURRENTLY AT WHISKEY | VEHICLE CURRENTLY AT WHISKEY | TRUCK AT CONNEX LUBUMBASHI | TRUCK AT CONNEX LUBUMBASHI | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE AND CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING OFFLOADING | OFFLOADED 19-02-2024 | OFFLOADED 19-02-2024
BA2171 | CAT745-04A ARRICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F605763 | CAT00745T3F605763 | TXW07006 | FML2304DSI2048 | VESSEL: LIBERTY Voy. EE307 - ETA DURBAN: 05-05-2023 | COD 2024 110678 | ND673267 | ND837795 | 2304DSI2048 | 26-01-2024 | OFFLOADED 20-02-2024 | 19-01-2024 | 24-01-2024 | BV COMPLETED | 05-05-2023 | 24-01-2024 | MIDDELBURG 28-01-2024 | MIDDELBURG 29-01-2024 | 29-01-2024 | 29-01-2024 | 29-01-2024 | 02-02-2024 | 03.02.2024 | 04.02.2024 | 05.02.2024 | 06-02-2024 | 07-02-2024 | 09-02-2024 | 11-02-2024 | 12-02-2024 | 13-02-2024 | 14-02-2024 | 15-02-2024 | 16-02-2024 | 17-02-2024 | 17-02-2024 | 18-02-2024 | 18-02-2024 | 19-02-2024 | 20-02-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | UNIT WILL BE COLLECTED TODAY FROM OUR BONDED FACILITY AND UNDER GO TRIP CHECK AT TRANSPORTERS YARD BEFORE DISPATCH-PLANNING TO DISPATCH NEXT WEEK | TRUCK IS LOADED AND UNDERGOING TRIP CHECK BEFORE DISPATCH | TRUCK IS AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE BORDER | MIDDELBURG | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | GUTU ZIM ENROUTE HARARE | VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE TO DISPATCH CHIRUNDU EN-ROUTE TO MOKAMBO | VEHICLE AT MASAITI ZAMBIA EN-ROUTE TO MOKAMBO | VEHICLE AT MOKAMBO BORDER AWAITING CLEARANCE | VEHICLE AT CONNEX LUBUMBASHI AWAITING CLEARANCE | ON SITE WAITING TO OFFLOAD | OFFLOADED 20-02-2024 | OFFLOADED 20-02-2024
| BA2438 | CAT 330GC-07E HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT - CONGO EQUIPMENT | FEK40024 | CAT00330CFEK40024 | E7A58081 | FML2301DSI1905 | VESSEL: DE FENG GANG HE SHUN HAO Voy. 2301 - ETA DUEBAN: 10-02-2023 | COD 2024 126363 | ND919947 | ND923085 | 2301DSI1905 | 15-02-2024 | OFFLOADED | 12-02-2024 | 15-02-2024 | BV COMPLETED | 10-02-2023 | 19-02-2024 | MIDDELBURG 22-02-202 | MIDDELBURG 22-02-202 | 22-02-2024 | 22-02-2024 | 23-02-2024 | 24-02-2024 | 24-02-2024 | 25-02-2024 | 25-02-2024 | 25-02-2024 | 25-02-2024 | 28-02-2024 | 28-02-2024 | 28-02-2024 | 29-02-2024 | 29-02-2024 | 01-03-2024 | 01-03-2024 | 02-03-2024 | 02-03-2024 | 03-03-2024 | 03-03-2024 | 06-03-2024 | 06-03-2024 | [26 empty] | AWAITING BV VALIDATION IN ORDER TO BOOK BV AND PLAN FOR LOADING | BV COMPLETED TRUCK TO LOAD AND DISPATCH ON THE 16/02/2024 | BV COMPLETED TRUCK TO LOAD AND DISPATCH ON THE 16/02/2024 | TRUCK LOADED AND DISPATCHING MONDAY THE 19/02/2024 | DISPATCHING TODAY | ENROUTE BEIT BRIDGE BORDER | ERMELO ENROUTE BEIT BRIDGE | MIDDELBURG ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | VEHICLE DISPATCHED CHIRUNDU - CURRENTLY AT CHIKANKANTA | VEHICLE CURRENLTY AT MPONGWE ENROUTE CHINGOLA | VEHICLE CURRENLTY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI | VEHICLE CURRENLTY AT CE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2564 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805339 | CAT00740J3F805339 | TXY07975 | FML2312DSI2349 | VESSEL: GREEN MOUNTAIN Voy. 241202 - ETA DURBAN: 07-02-2024 | COD 2024 110678 | ND705348 | ND926113 | ND64638 | 12-02-2024 | OFFLOADED | 19-01-2024 | 12-02-2024 | BV COMPLETED | 09-02-2024 | 13-02-2024 | 14-02-2024 | 15-02-2024 | 15-02-2024 | 16-02-2024 | 16-02-2024 | 18-02-2024 | 19-02-2024 | 19-02-2024 | 19-02-2024 | 20-02-2024 | 20-02-2024 | 21-02-2024 | 21-02-2024 | 21-02-2024 | 22-02-2024 | 22-02-2024 | 22-02-2024 | 23-02-2024 | 25-02-2024 | 25-02-2024 | 02-03-2024 | 02-03-2024 | 06-03-2024 | 06-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 29-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 29-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 06-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 07-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 07-02-2024 | PLANNING TO COLLECT UNITS FROM PORT TODAY | UNIT AT OUR DEPO AWAITING LOADING DATE-BV BOOKED FOR TOMMROW THE 13/02/2024 | DISPATCHING DURBAN EN-ROUTE TO JHB | TRUCK AT VOLKSRUST EN-ROUTE TO BEITBRIDGE | TRUCK AT LEBOWKGOMO EN-ROUTE TO BEITBRIDGE | TRUCK AT MUSINA EN-ROUTE TO BEITBRIDGE | VEHICLE AT KWEKWE ENROUTE HARARE | CHIRUNDU ZIM SIDE IN THE QUE TO CROSS | CHIRUNDU ZAM SIDE TO DISPATCH FOR KASUMBULESA BORDER | KAPIRI ENROUTE KASUMBULESA BORDER | KASUMBULESA ZAM SIDE BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | WHISKEY AWAITING RELEASE - DAY 5 | CONNEX LUBUMBASHI | CONNEX LUBUMBASHI | CE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2567 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805313 | CAT00740V3F805313 | TXX07942 | FML2312DSI2319 | VESSEL: GREEN MOUNTAIN Voy. 241202 - ETA DURBAN: 06-02-2024 | COD 2024 110678 | ND436314 | ND646811 / ND644688 | 2312DSI2319 | 15-02-2024 | OFFLOADED | 19-01-2024 | 07-02-2024 | BV COMPLETED | 07-02-2024 | 21-02-2024 | MIDDELBURG 22-02-202 | MIDDELBURG 22-02-202 | 22-02-2024 | 23-02-2024 | 23-02-2024 | 24-02-2024 | 24-02-2024 | 24-02-2024 | 26-02-2024 | 27-02-2024 | 27-02-2024 | 28-02-2024 | 28-02-2024 | 28-02-2024 | 29-02-2024 | 29-02-2024 | 01-03-2024 | MOKAMBO 01-03-2024 | MOKAMBO 02-03-2024 | 02-03-2024 | 03-02-2024 | 03-02-2024 | 06-03-2024 | 06-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 16-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 07-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 06-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 07-02-2024 | VESSEL CURRENTLY IN AND WORKING | PLANNING TO COLLECT UNITS FROM PORT TODAY | UNIT AT OUR DEPO AWAITING LOADING DATE-BV BOOKED FOR TOMMROW THE 13/02/2024 | UNIT AT OUR DEPO AWAITING LOADING DATE-BV BOOKED FOR THE 13/02/2024 | TRUCK PLANNING TO LOAD AND DISPATCH ON THE 19/02/2024 | TRUCK PLANNING TO LOAD AND DISPATCH ON THE 19/02/2024 | TRUCK PLANNING TO LOAD AND DISPATCH ON THE 21/02/2024 | TRUCK PLANNING TO LOAD AND DISPATCH ON THE 21/02/2024 | TRUCK PLANNING TO LOAD AND DISPATCH ON THE 21/02/2024 | NEW CASTLE ENROUTE BEIT BRIDGE | MIDDELBURG ENROUTE BEIT BRIDGE | BEIT BRIDGE RSA SIDE CLEARING | MAKONDE ZIM ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | VEHICLE DISPATCHING CHIRUNDU ENROUTE LUSAKA | VEHICLE CURRENTLY AT KAPIRI ENROUTE CHINGOLA | VEHICLE CURRENLTY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI | VEHICLE CURRENLTY AT CE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2568 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT . CONGO EQUIPMENT | 3F805319 | CAT00740T3F805319 | TXY07955 | FML2312DSI2320 | VESSEL: GREEN MOUNTAIN Voy. 241202 - ETA DURBAN: 06-02-2024 | COD 2024 110678 | ND919955 | ND140841 | 2312DSI2320 | 14-02-2024 | OFFLOADED | 19-01-2024 | 07-02-2024 | BV NUMBER RECEIVED | 07-02-2024 | 15-02-2024 | 16-02-2024 | 19-02-2024 | 19-02-2024 | 19-02-2024 | 19-02-2024 | 21-02-2024 | 22-02-2024 | 23-02-2024 | 23-02-2024 | 23-02-2024 | 23-02-2024 | 24-02-2024 | 24-02-2024 | 24-02-2024 | 25-02-2024 | 26-02-2024 | 26-02-2024 | MOKAMBO 26-02-2024 | 28-02-2024 | 29-02-2024 | 03-02-2024 | 03-03-2024 | 06-03-2024 | 06-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 16-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 31-01-2024 - TO BERTH 05-01-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 05-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 07-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 06-02-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN - 07-02-2024 | VESSEL CURRENTLY IN AND WORKING | PLANNING TO COLLECT UNITS FROM PORT TODAY | UNIT AT OUR DEPO AWAITING LOADING DATE-BV BOOKED FOR TOMMROW THE 13/02/2024 | UNIT AT OUR DEPO AWAITING LOADING DATE-BV BOOKED FOR THE 13/02/2024 | TRUCK PLANNING TO LOAD AND DISPATCH ON THE 19/02/2024 | TRUCK AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BETHAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | DISPATCHED BEIT BRIDGE ENROUTE CHIRUNDU BORDER | HURUNGWE ZIM ENROUTE CHIRUNDU BORDER | MAFULIRA ZAMBIA ENORUTE MOKAMBO BORDER | MOKAMBO ZAMBIA SIDE | MOKAMBO ZAMBIA SIDE | VEHICLE CURRENTLY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENTLY AT WHISKEY - AWAITING CLEARANCE | VEHICLE CURRENLTY AT MOKAMBO ENROUTE KASUMBALESA | VEHICLE CURRENLTY AT CONNEX LUBUMBASHI | VEHICLE CURRENLTY AT CE AWAITING TO OFFLOAD | OFFLOADED | OFFLOADED
BA2131 | CAT D6GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | XPC00813 | CAT000D6CXPC00813 | R6J04768 | FML2307DSI2131 | VESSEL: TIANJIN HIGHWAY Voy. 157A - ETA DURBAN: 03-08-2023 | COD 2024 132991 | LB59FBGP | CM76CRGP | ND64689 | 29-02-2024 | OFFLOADED 11-03-2024 | 21-02-2024 | 27-02-2024 | BV COMPLETED | 03-08-2023 | 28-02-2024 | 29-02-2024 | 29-02-2024 | 01-03-2024 | 01-03-2024 | 01-03-2024 | 02-03-2024 | 02-03-2024 | 03-03-2024 | 03-03-2024 | 03-03-2024 | 03-03-2024 | 03-03-2024 | 05-03-2024 | 05-03-2024 | 06-03-2024 | 07-03-2024 | 07-03-2024 | 07-03-2024 | 08-03-2024 | 08-03-2024 | 09-03-2024 | 09-03-2024 | 11-03-2023 | 11-03-2024 |  | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING AMENDMENTS | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | AWAITING NEW BV NUMBER | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | BV BOOKED FOR THE 24/01/2024-AWAITING LOADING DATES ONCE BV IS COMPLETED | UNIT WILL BE COLLECTED TODAY FROM OUR BONDED FACILITY AND UNDER GO TRIP CHECK AT TRANSPORTERS YARD BEFORE DISPATCH-PLANNING TO DISPATCH NEXT WEEK | TRUCK IS LOADED AND UNDERGOING TRIP CHECK BEFORE DISPATCH | TRUCK IS AT PIETERMARITZBURG EN-ROUTE TO BEITBRIDGE BORDER | MIDDELBURG | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | GUTU ZIM ENROUTE HARARE | VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE AT CHIRUNDU ZIM SIDE AWAITING CLEARANCE | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE ATTENDING TO MINOR BREAKDOWN | VEHICLE TO DISPATCH CHIRUNDU EN-ROUTE TO MOKAMBO | VEHICLE AT MASAITI ZAMBIA EN-ROUTE TO MOKAMBO | VEHICLE AT MOKAMBO BORDER AWAITING CLEARANCE | VEHICLE AT CONNEX LUBUMBASHI AWAITING CLEARANCE | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV INSPECTION BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | VEHICLE CURRENTLY AT HOWICK ENROUTE BEITBRIDGE BORDER | VEHICLE CURRENTLY AT JOHANNESBURG ENROUTE BEITBRIDGE BORDER | VEHICLE CURRENTLY AT MUSINA ENROUTE BEITBRIDGE BORDER | VEHICLE CURRENTLY AT CHINYOI ENROUTE KASUBMALESA | VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE | VEHICLE CURRENTLY AT KABWE EN-ROUTE TO BEITBRIDGE BORDER | VEHICLE CURRENTLY AT NDOLA EN-ROUTE TO KASUMBALESA BORDER | VEHICLE CURRENTLY AT KASUMBALESA BORDER DRC SIDE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI -AWAITING RELEASE | OFFLOADED 11-03-2024 | OFFLOADED 11-03-2024
BA2411 | CAT M317DE WHEEL EXCAVATOR | BARTRAC EQUIPMENT - CONGO EQUIPMENT | CA600891 | CATM317DCCA600891 | 3W234182 | FML2212DSI1883 | VESSEL: MORNING CHNAT Voy. 086 - ETA DURBAN 05-02-2023 | COD 2024 136564 | KJ69VKGP | KL77BDGP | ND64688 | 05-03-2024 | OFFLOADED 16-03-2024 | 28-02-2024 | 01-03-2024 | BV COMPLETED | 05-02-2023 | 02-03-2024 | PRETORIA 02-03-2024 | PRETORIA 04-03-2024 | 05/03/2024 | 06-03-2024 | 06-03-2024 | 06-03-2024 | 07-03-2024 | 07-03-2024 | 07-03-2024 | 07-03-2024 | 07-03-2024 | 07-03-2024 | 08-03-2024 | 08-03-2024 | 08-03-2024 | 08-03-2024 | 08-03-2024 | 08-03-2024 | 09-03-2024 | 09-03-2024 | 13-03-2024 | 14-03-2024 | 15-03-2024 | 16-03-2024 | [31 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER - LOADING DATE TO BE CONFIRMED | UNIT LOADING TODAY - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | UNIT LOADING TODAY - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | DISPATCHING PRETORIA TODAY | TRUCK AT LOUIS TRICHARDT EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT KWEKWE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT CHIRUNDU AWAITING CLERAANCE | LUSAKA ENROUTE KASUMBALESA BORDER | VEHICLE CURRENTLY AT WHISKEY - AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY - AWAITING RELEASE | VEHICLE CURRENTLY AT WHISKEY - AWAITING RELEASE | VEHICLE CURRENTLY AT KANYAKA WAITING RELEASE | VEHICLE CURRENTLY AT CONNEX LUBUMBASHI AWAITING RELEASE | OFFLOADED 16-03-2024 | OFFLOADED 16-03-2024 | OFFLOADED 16-03-2024 | OFFLOADED 16-03-2024 | OFFLOADED 16-03-2024
BA2635 | CAT333-07E HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TJT10235 | CAT00333KTJT10235 | E7A60714 | FML2312DSI2312 | VESSEL: TORRENS Voy. 035 - ETA DURBAN: 02-01-2024 | COD 2024 132976 | ND747407 | ND692809 / ND692831 | 2312DSI2312 | 01-03-2024 | OFFLOADED 18-03-2024 | 21-02-2024 | 29-02-2024 | BV COMPLETED | 02-01-2024 | 05/03/2024 | 06-03-2024 | 06-03-2024 | 06-03-2024 | 07-03-2024 | 07-03-2024 | 09-03-2024 | 09-03-2024 | 10-03-2024 | 11-03-2024 | 11-03-2024 | 11-03-2024 | 13-03-2024 | 13-03-2024 | 13-03-2024 | 14-03-2024 | 15-03-2024 | 15-03-2024 | MOKAMBO 15-03-2024 | MOKAMBO 15-03-2024 | 15-03-2024 | 16-03-2024 | 16-03-2024 | 16-03-2024 | 18-03-2024 | [31 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED THURSDAY 29-02-2024 - LOADING PLAN TO BE ADVISED | BV INSPECTION BOOKED FOR 29-02-2024 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 04-03-2024 | DISPATCHING DURBAN TODAY | TRUCK DISPATCHED EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MODIMOLLE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER RSA SIDE | TRUCK AT BEITBRIDGE BORDER ZIM SIDE | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT DISPATCH CHIRUNDU ZAM ENROUTE LUSAKA | TRUCK AT KABWE ENROUTE MOKAMBO BORDER | TRUCK AT KITWE ENROUTE MOKAMBO BORDER | ON SITE AWAITING TO OFFLOAD | OFFLOADED 18-03-2024 | OFFLOADED 18-03-2024 | OFFLOADED 18-03-2024 | OFFLOADED 18-03-2024
BA2636 | CAT333-07E HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TJT10245 | CAT00333ETJT10245 | E7A60710 | FML2312DSI2311 | VESSEL: TORRENS Voy. 035 - ETA DURBAN: 02-01-2024 | COD 2024 132976 | ND919950 | ND820122 | 2312DSI2311 | 01-03-2024 | OFFLOADED 18-03-2024 | 21-02-2024 | 29-02-2024 | BV COMPLETED | 02-01-2024 | 05/03/2024 | 06-03-2024 | 06-03-2024 | 07-03-2024 | 07-03-2024 | 07-03-2024 | 09-03-2024 | 09-03-2024 | 09-03-2024 | 10-03-2024 | 11-03-2024 | 11-03-2024 | 12-03-2024 | 12-03-2024 | 13-03-2024 | 13-03-2024 | 14-03-2024 | 14-03-2024 | MOKAMBO 14-03-2024 | MOKAMBO 14-03-2024 | 14-03-2024 | 16-03-2024 | 16-03-2024 | 16-03-2024 | 18-03-2024 | [31 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR NEXT WEEK | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED THURSDAY 29-02-2024 - LOADING PLAN TO BE ADVISED | BV INSPECTION BOOKED FOR 29-02-2024 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETE - VEHICLE TO DISPATCH MONDAY 04-03-2024 | DISPATCHING DURBAN TODAY | TRUCK DISPATCHED EN-ROUTE TO BEITBRIDGE BORDER | TRUCKAT BETHAL EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MAKHADO EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER ZIM SIDE | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT LUSAKA ENROUTE KASUMBALESA | TRUCK AT KITWE ENROUTE MOKAMBO BORDER | TRUCK AT WHISKEY | ON SITE AWAITING TO OFFLOAD | OFFLOADED 18-03-2024 | OFFLOADED 18-03-2024 | OFFLOADED 18-03-2024 | OFFLOADED 18-03-2024
BA2664 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KGX00500 | CAT000D8PKGX00500 | TXJ02613 | FML2401DSI2353 | VESSEL: SHANGHAI HIGHWAY Voy. 170A - ETA DURBAN: 30-01-2024 | COD 2024 133930 | ND570587 | ND443606 | ND64701 | 02-03-2024 | OFFLOADED 22-03-2024 | 23-02-2024 | 01-03-2024 | BV NUMBER RECEIVED | 30-01-2024 | 05/03/2024 | 05-03-2024 | 05-03-2024 | 05-03-2024 | 06-03-2024 | 07-03-2024 | 08-03-2024 | 08-03-2024 | 10-03-2024 | 11-03-2024 | 12-03-2024 | 12-03-2024 | 13-03-2024 | 13-03-2024 | 13-03-2024 | 14-03-2024 | 15-03-2024 | 15-03-2024 | 15-03-2024 | 16-03-2024 | 16-03-2024 | 19-03-2024 | 20-03-2024 | 22-03-2024 | 22-03-2024 | [34 empty] | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - UNIT LOADING TOMORROW 29-02-2024 | UNIT LOADING TODAY - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | UNIT LOADING TODAY - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | DISPATCHING DURBAN TODAY | TRUCK AT AMMERSFORT EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT POLOKWANE EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT BEITBRIDGE BORDER RSA SIDE | TRUCK DISPATCHED BEITBRIDGE BORDER ZIM | TRUCK AT MAPINGA ENOUTE CHINGOLA | TRUCK AT CHIRUNDU ZIM SIDE CLEARING | TRUCK AT CHIRUNDU ZAM SIDE CLEARING | TRUCK AT KABWE ENROUTE KASUMBALESA | TRUCK AT KITWE ENROUTE KASUMBALESA | TRUCK AT WHISKEY AWAITNG RELEASE | TRUCK DISPATCHING WHISKEY EN-ROUTE TO CONNEX LUBUMBASHI | TRUCK AT CONNEX LUBUMBASHI | TRUCK AT CONNEX LUBUMBASHI | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-03-2024 | OFFLOADED 22-03-2024
BA2612 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JZ401349 | CAT00426LJZ401349 | CC207880 | FML2311DSI2300 | VESSEL: MSC FLORIANA Voy. VIIB350R - ETA DURBAN: 22-12-2023 | COD 2024 132975 | BCF1153ZM | BCD2213ZM | 2311DSI2300 | 01-03-2024 | OFFLOADED 26-03-2024 | 23-02-2024 | 01-03-2024 | BV COMPLETED | 22-12-2023 | 01-03-2024 | 01-03-2024 | 02-03-2024 | GRB 02-03-2024 | GRB 03-03-2024 | M/DRIFT 03-03-2024 | M/DRIFT 04-03-2024 | F/TOWN 04-03-2024 | F/TOWN 04-03-2024 | KAZUNGULA BW 05-03-2024 | KAZUNGULA BW 06-03-2024 | KAZUNGULA ZM 06-03-2024 | KAZUNGULA ZM 07-03-2024 | 08-03-2024 | 09-03-2024 | 09-03-2024 | 13-03-2024 | 13-03-2024 | 13-03-2024 | 18-03-2024 | 19-03-2024 | 23-03-2024 | 23-03-2024 | CONNEX 23-03-2024 | 26-03-2024 | [31 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | UNIT LOADING TOMORROW - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | UNIT LOADING TOMORROW - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | UNIT LOADING TOMORROW - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | VEHICLE AT GROBLERSBRIDGE BORDER CLEARING | VEHICLE AT KASANGULA BORDER CLEARING | VEHICLE AT KASANGULA BORDER CLEARING | VEHICLE AT MONZE EN-ROUTE TO LUSAKA | VEHICLE AT LUSAKA TO DISPATCH FOR KASUMBALESA | VEHICLE AT NDOLA BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR KASUMBALESA | VEHICLE AT NDOLA BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR KASUMBALESA | VEHICLE AT CHILILABOMBWE ERNOUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT DISPATCH WHISKEY | VEHICLE AT CONNEX LUBUMBASHI - AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI - AWAITING RELEASE | OFFLOADED 26-03-2024 | OFFLOADED 26-03-2024
BA2613 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JZ401350 | CAT00426VJZ401350 | CC207861 | FML2311DSI2300 | VESSEL: MSC FLORIANA Voy. VIIB350R - ETA DURBAN: 22-12-2023 | COD 2024 132975 | BCF1153ZM | BCD2213ZM | 2311DSI2300 | 01-03-2024 | OFFLOADED 26-03-2024 | 23-02-2024 | 01-03-2024 | BV COMPLETED | 22-12-2023 | 01-03-2024 | 01-03-2024 | 02-03-2024 | GRB 02-03-2024 | GRB 03-03-2024 | M/DRIFT 03-03-2024 | M/DRIFT 04-03-2024 | F/TOWN 04-03-2024 | F/TOWN 04-03-2024 | KAZUNGULA BW 05-03-2024 | KAZUNGULA BW 06-03-2024 | KAZUNGULA ZM 06-03-2024 | KAZUNGULA ZM 07-03-2024 | 08-03-2024 | 09-03-2024 | 09-03-2024 | 13-03-2024 | 13-03-2024 | 13-03-2024 | 18-03-2024 | 19-03-2024 | 23-03-2024 | 23-03-2024 | CONNEX 23-03-2024 | 26-03-2024 | [31 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | UNIT LOADING TOMORROW - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | UNIT LOADING TOMORROW - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | UNIT LOADING TOMORROW - BV INSPECTION BOOKED FOR FRIDAY 01-03-2024 | VEHICLE AT GROBLERSBRIDGE BORDER CLEARING | VEHICLE AT KASANGULA BORDER CLEARING | VEHICLE AT KASANGULA BORDER CLEARING | VEHICLE AT MONZE EN-ROUTE TO LUSAKA | VEHICLE AT LUSAKA TO DISPATCH FOR KASUMBALESA | VEHICLE AT NDOLA BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR KASUMBALESA | VEHICLE AT NDOLA BUSY WITH TRIP CHECK BEFORE DISPATCHING FOR KASUMBALESA | VEHICLE AT CHILILABOMBWE ERNOUTE KASUMBALESA | VEHICLE AT KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT KASUMBALESA ZAM SIDE CLEARING | VEHICLE AT KASUMBALESA DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT DISPATCH WHISKEY | VEHICLE AT CONNEX LUBUMBASHI - AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI - AWAITING RELEASE | OFFLOADED 26-03-2024 | OFFLOADED 26-03-2024
BA2467 | CAT C27 ENGINE & 1 PKGS PARTS + FORKS FOR BA2612 AND BA2613 | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TWM08416 | TBA | TBA | FML2304DSI2379 | VESSEL: SANTA CRUZ - Transhipment Vessel: SANTA ISABEL Voy. 240S - ETA DURBAN 06-03-2024 | COD 2024 138004 | LP49LTGP | N/A | 2401DSI2379 | 14-03-2024 | OFFLOADED 29-03-2024 | 29-02-2024 | 13-03-2024 | BV NUMBER RECEIVED | 06-03-2024 | 13-03-2024 | 14-03-2024 | 15-03-2024 | 16-03-2024 | 17-03-2024 | 17-03-2024 | 18-03-2024 | 18-03-2024 | 19-03-2024 | 19-03-2024 | 20-03-2024 | 20-03-20214 | 20-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | SAKANIA 22-03-2024 | SAKANIA 24-03-2024 | 24-03-2024 | 24-03-2024 | 25-03-2024 | 29-03-2024 | 29-03-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-03-2024 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED AND CURRENTLY DISCHARGING CONTAINERS | COLLECTED CONTAINER FROM PORT - TO BE UNPACKED TODAY - BV INSPECTION BOOKED FOR TOMORROW 13-03-2024 | BV INSPECTION BOOKED FOR TODAY - LOADING ONCE BV INSPECTION IS COMPLETED | HEIDELBERG ENROUTE JOHANNESBURG | DISPATCHED JOHANNESBURG ENROUTE GROBLERSBRIDGE | MARTINS DRIFT BORDER AWAITING RELEASE | KAZANGULA ZAMBIA SIDE AWAITING FINAL RELEASE | KAZANGULA ZAMBIA SIDE AWAITING FINAL RELEASE | TRUCK AT LUSAKA EN-ROUTE TO SAKANIA BORDER | TRUCK AT NDOLA EN-ROUTE TO SAKANIA BORDER | TRUCK AT CONNEX AFRICA LUBUMBASHI | TRUCK AT CONNEX AFRICA LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX AFRICA LUBUMBASHI AWAITING RELEASE - PLEASE ASSIST WITH THE RELEASE | TRUCK AT CONNEX AFRICA LUBUMBASHI AWAITING RELEASE - PLEASE ASSIST WITH THE RELEASE | OFFLOADED 29-03-2024 | OFFLOADED 29-03-2024
BA2468 | CAT C27 ENGINE & 1 PKGS PARTS | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TWM08417 | TBA | TBA | FML2304DSI2379 | VESSEL: SANTA CRUZ - Transhipment Vessel: SANTA ISABEL Voy. 240S - ETA DURBAN 06-03-2024 | COD 2024 138004 | LP49LTGP | N/A | 2401DSI2379 | 14-03-2024 | OFFLOADED 29-03-2024 | 29-02-2024 | 13-03-2024 | BV NUMBER RECEIVED | 06-03-2024 | 13-03-2024 | 14-03-2024 | 15-03-2024 | 16-03-2024 | 17-03-2024 | 17-03-2024 | 18-03-2024 | 18-03-2024 | 19-03-2024 | 19-03-2024 | 20-03-2024 | 20-03-20214 | 20-03-2024 | 21-03-2024 | 21-03-2024 | 22-03-2024 | 22-03-2024 | 22-03-2024 | SAKANIA 22-03-2024 | SAKANIA 24-03-2024 | 24-03-2024 | 24-03-2024 | 25-03-2024 | 29-03-2024 | 29-03-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 07-03-2024 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CONTAINERS | VESSEL ARRIVED AND CURRENTLY DISCHARGING CONTAINERS | COLLECTED CONTAINER FROM PORT - TO BE UNPACKED TODAY - BV INSPECTION BOOKED FOR TOMORROW 13-03-2024 | BV INSPECTION BOOKED FOR TODAY - LOADING ONCE BV INSPECTION IS COMPLETED | HEIDELBERG ENROUTE JOHANNESBURG | DISPATCHED JOHANNESBURG ENROUTE GROBLERSBRIDGE | MARTINS DRIFT BORDER AWAITING RELEASE | KAZANGULA ZAMBIA SIDE AWAITING FINAL RELEASE | KAZANGULA ZAMBIA SIDE AWAITING FINAL RELEASE | TRUCK AT LUSAKA EN-ROUTE TO SAKANIA BORDER | TRUCK AT NDOLA EN-ROUTE TO SAKANIA BORDER | TRUCK AT CONNEX AFRICA LUBUMBASHI | TRUCK AT CONNEX AFRICA LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX AFRICA LUBUMBASHI AWAITING RELEASE - PLEASE ASSIST WITH THE RELEASE | TRUCK AT CONNEX AFRICA LUBUMBASHI AWAITING RELEASE - PLEASE ASSIST WITH THE RELEASE | OFFLOADED 29-03-2024 | OFFLOADED 29-03-2024
BA2708 | CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCD 3129 ZM | BCD 726 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2717 | CAT DE50E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCD 3129 ZM | BCD 726 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2720 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3129 ZM | BCD 726 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-204 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2721 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3129 ZM | BCD 726 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2731 | CAT DE715E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCD 3129 ZM | BCD 726 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | KITWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2709 | CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCE 8833 ZM | BCF 6174 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT PANDAMATENGA EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT LUBUMBASHI CONNEX AWAITING RELEASE | TRUCK AT LUBUMBASHI CONNEX AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2710 | CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCE 8833 ZM | BCF 6174 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT PANDAMATENGA EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT LUBUMBASHI CONNEX AWAITING RELEASE | TRUCK AT LUBUMBASHI CONNEX AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2725 | CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCE 8833 ZM | BCF 6174 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT PANDAMATENGA EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT LUBUMBASHI CONNEX AWAITING RELEASE | TRUCK AT LUBUMBASHI CONNEX AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2743 | CAT DE220E GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCE 8833 ZM | BCF 6174 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT PANDAMATENGA EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT LUBUMBASHI CONNEX AWAITING RELEASE | TRUCK AT LUBUMBASHI CONNEX AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2715 | CAT DE50E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCC 9364 ZM | BCF 6141 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH ONCE DONE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2716 | CAT DE50E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCC 9364 ZM | BCF 6141 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH ONCE DONE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2718 | CAT DE50E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCC 9364 ZM | BCF 6141 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH ONCE DONE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2735 | CAT DE715E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCC 9364 ZM | BCF 6141 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH ONCE DONE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2733 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCE 4993 ZM | BCD 727 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT KALOMO ENROUTE | TRUCK AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK AT LUSAKA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | BALUBA ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2741 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCE 4993 ZM | BCD 727 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 29-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 29-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT KALOMO ENROUTE | TRUCK AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK AT LUSAKA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | BALUBA ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 29-04-2024 | OFFLOADED 29-04-2024
BA2712 | CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCD 9085 ZM | BCD 723 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT BALUBA ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2713 | CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCD 9085 ZM | BCD 723 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT BALUBA ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2726 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 9085 ZM | BCD 723 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT BALUBA ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2744 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 9085 ZM | BCD 723 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT BALUBA ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2714 | CAT DE50E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCD 3123 ZM | BCD 853 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 12-04-2024 | 12-04-2024 | GRB 12-04-2024 | GRB 14-04-2024 | FRANCISTOWN 14-04-2024 | FRANCISTOWN 14-04-2024 | KAZUNGULA BW 15-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 17-04-2024 | 18-04-2024 | 19-04-2024 | 19-04-2024 | 22-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT KAZUNGULA BW SIDE CLEARING | TRUCK AT KAZUNGULA ZAM SIDE CLEARING | TRUCK DISPATCH FROM KAZUNGULA BORDER ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | KITWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2722 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3123 ZM | BCD 853 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 12-04-2024 | 12-04-2024 | GRB 12-04-2024 | GRB 14-04-2024 | FRANCISTOWN 14-04-2024 | FRANCISTOWN 14-04-2024 | KAZUNGULA BW 15-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 17-04-2024 | 18-04-2024 | 19-04-2024 | 19-04-2024 | 22-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT KAZUNGULA BW SIDE CLEARING | TRUCK AT KAZUNGULA ZAM SIDE CLEARING | TRUCK DISPATCH FROM KAZUNGULA BORDER ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | KITWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2738 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCD 3123 ZM | BCD 853 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 12-04-2024 | 12-04-2024 | GRB 12-04-2024 | GRB 14-04-2024 | FRANCISTOWN 14-04-2024 | FRANCISTOWN 14-04-2024 | KAZUNGULA BW 15-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 17-04-2024 | 18-04-2024 | 19-04-2024 | 19-04-2024 | 22-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT KAZUNGULA BW SIDE CLEARING | TRUCK AT KAZUNGULA ZAM SIDE CLEARING | TRUCK DISPATCH FROM KAZUNGULA BORDER ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | KITWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2723 | CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3159 ZM | BCD 4761 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT KABWE ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2724 | CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3159 ZM | BCD 4761 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT KABWE ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2742 | CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3159 ZM | BCD 4761 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT KABWE ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2712 | CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCD 9085 ZM | BCD 723 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT BALUBA ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2713 | CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCD 9085 ZM | BCD 723 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT BALUBA ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2726 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 9085 ZM | BCD 723 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT BALUBA ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2744 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 9085 ZM | BCD 723 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 24-04-2024 | 24-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LIVINGSTONE ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT BALUBA ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2714 | CAT DE50E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCD 3123 ZM | BCD 853 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 12-04-2024 | 12-04-2024 | GRB 12-04-2024 | GRB 14-04-2024 | FRANCISTOWN 14-04-2024 | FRANCISTOWN 14-04-2024 | KAZUNGULA BW 15-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 17-04-2024 | 18-04-2024 | 19-04-2024 | 19-04-2024 | 22-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT KAZUNGULA BW SIDE CLEARING | TRUCK AT KAZUNGULA ZAM SIDE CLEARING | TRUCK DISPATCH FROM KAZUNGULA BORDER ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | KITWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2722 | CAT DE110E2 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3123 ZM | BCD 853 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 12-04-2024 | 12-04-2024 | GRB 12-04-2024 | GRB 14-04-2024 | FRANCISTOWN 14-04-2024 | FRANCISTOWN 14-04-2024 | KAZUNGULA BW 15-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 17-04-2024 | 18-04-2024 | 19-04-2024 | 19-04-2024 | 22-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT KAZUNGULA BW SIDE CLEARING | TRUCK AT KAZUNGULA ZAM SIDE CLEARING | TRUCK DISPATCH FROM KAZUNGULA BORDER ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | KITWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2738 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCD 3123 ZM | BCD 853 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 12-04-2024 | 12-04-2024 | GRB 12-04-2024 | GRB 14-04-2024 | FRANCISTOWN 14-04-2024 | FRANCISTOWN 14-04-2024 | KAZUNGULA BW 15-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 16-04-2024 | KAZUNGULA BW 17-04-2024 | 18-04-2024 | 19-04-2024 | 19-04-2024 | 22-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 27-04-2024 | 27-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG UNDERGOING TRIP CHECK | TRUCK AT MOOIBULT EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT KAZUNGULA BW SIDE CLEARING | TRUCK AT KAZUNGULA ZAM SIDE CLEARING | TRUCK DISPATCH FROM KAZUNGULA BORDER ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | KITWE ENROUTE KASUMBALESA BORDER | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT KASUMBALESA BORDER AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK IS AT CONNEX LUBUMBASHI AWAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2723 | CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3159 ZM | BCD 4761 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT KABWE ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2724 | CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3159 ZM | BCD 4761 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT KABWE ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2742 | CAT DE200E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCD 3159 ZM | BCD 4761 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 27-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT KABWE ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2736 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCF 1097 ZM | BCF 6236 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | TRUCK IS AT PANDAMATENGA EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT KAPIRI MPOSHI ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH ONCE DONE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2737 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCF 1097 ZM | BCF 6236 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERSBRIDGE BORDER AWAITING CLEARANCE | TRUCK IS AT PANDAMATENGA EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT KAPIRI MPOSHI ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH ONCE DONE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2739 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCD 3457 ZM | BCD 1966 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK JOHANNESBURG EN-ROUTE TO GROBLERS | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2740 | CAT DE850E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCD 3457 ZM | BCD 1966 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 30-04-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 29-04-2024 | 30-04-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK JOHANNESBURG EN-ROUTE TO GROBLERS | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | OFFLOADED 30-04-2024 | OFFLOADED 30-04-2024
BA2711 | CAT DE33E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141226 | BCF 1091 ZM | BCF 6142 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 03-05-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 27-04-2024 | 27-04-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 03-05-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | WHISKEY AWAITING DOCUMENTS AND RELEASE | WHISKEY AWAITING DOCUMENTS AND RELEASE - PLEASE ASSIST | TRUCK IS AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 03-05-2024
BA2719 | CAT DE88E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCF 1091 ZM | BCF 6142 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 03-05-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 27-04-2024 | 27-04-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 03-05-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | WHISKEY AWAITING DOCUMENTS AND RELEASE | WHISKEY AWAITING DOCUMENTS AND RELEASE - PLEASE ASSIST | TRUCK IS AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 03-05-2024
BA2727 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCF 1091 ZM | BCF 6142 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 03-05-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 27-04-2024 | 27-04-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 03-05-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | WHISKEY AWAITING DOCUMENTS AND RELEASE | WHISKEY AWAITING DOCUMENTS AND RELEASE - PLEASE ASSIST | TRUCK IS AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 03-05-2024
BA2728 | CAT DE250E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141219 | BCF 1091 ZM | BCF 6142 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 03-05-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 27-04-2024 | 27-04-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 03-05-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK IS AT GROBLERS BORDER AWAITING CLEARANCE | TRUCK IS AT SERULE EN-ROUTE TO KAZUNGULA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT LUSAKA ENROUTE KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | CHILILABOMBWE ENROUTE KASUMBALESA BORDER | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | WHISKEY AWAITING DOCUMENTS AND RELEASE | WHISKEY AWAITING DOCUMENTS AND RELEASE - PLEASE ASSIST | TRUCK IS AT CONNEX LUBUMBASHI WAITING FINAL CLEARANCE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 03-05-2024
BA2729 | CAT DE500E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCE 8852 ZM | BCE 9922 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 03-05-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 02-05-2024 | 03-05-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT GROBLERSBRIDGE AWAITING CLEARANCE | TRUCK AT KAZUNGULA BW SIDE CLEARING | TRUCK AT KAZUNGULA ZAM SIDE CLEARING | TRUCK DISPATCH FROM KAZUNGULA BORDER ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | NDOLA BUSY WITH MAINTENACE BEFORE DISPATCHING FOR THE BORDER | TRUCK IS AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | TRUCK IS AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | TRUCK AT KASUMBALESA DRC AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | TRUCK ENROUTE TO CONGO EQUIPMENT | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 03-05-2024
BA2730 | CAT DE500E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCE 8852 ZM | BCE 9922 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 03-05-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 10-04-2024 | 10-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 12-04-2024 | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 15-04-2024 | 16-04-2024 | 16-04-2024 | 19-04-20244 | 19-04-2024 | 19-04-2024 | 20-04-2024 | 20-04-2024 | 24-04-2024 | 25-04-2024 | 02-05-2024 | 03-05-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK AT GROBLERSBRIDGE AWAITING CLEARANCE | TRUCK AT KAZUNGULA BW SIDE CLEARING | TRUCK AT KAZUNGULA ZAM SIDE CLEARING | TRUCK DISPATCH FROM KAZUNGULA BORDER ENROUTE NDOLA | TRUCK IS AT LUSAKA ENROUTE NDOLA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | NDOLA BUSY WITH MAINTENACE BEFORE DISPATCHING FOR THE BORDER | TRUCK IS AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | TRUCK IS AT CHILILABOMBWE EN-ROUTE TO KASUMBALESA | TRUCK AT KASUMBALESA DRC AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONGO EQUIPMENT - WAITING TO OFFLOAD | TRUCK ENROUTE TO CONGO EQUIPMENT | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | TRUCK IS AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 03-05-2024
BA2732 | CAT DE715E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCD 9026 ZM | BCD 5337 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 06-05-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 03-05-2024 | 06-05-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH ONCE DONE | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK ENROUTE TO CONGO EQUIPMENT | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 06-05-2024
BA2734 | CAT DE715E0 GENSET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TBA | TBA | TBA | FML2401DSI2380 | VESSEL: MSC ELMA - ETA DURBAN 27-03-2024 | COD 2024 141231 | BCD 9026 ZM | BCD 5337 ZM | 2401DSI2380 | 11/04/2024 | OFFLOADED 06-05-2024 | 05-03-2024 | 09-04-2024 | BV NUMBER RECEIVED | 27-03-2024 | 09-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024 | 11-04-2024(GROBLERS) | 11-04-2024(GROBLERS) | FRANCISTOWN 12-04-2024 | FRANCISTOWN 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA BW 12-04-2024 | KAZUNGULA ZM 12-04-2024 | KAZUNGULA ZM 13-04-2024 | 14-04-2024 | 14-04-2024 | 15-04-2024 | 19-04-2024 | 19-04-2024 | 19-04-2024 | 23-04-2024 | 24-04-2024 | 25-04-2024 | 25-04-2024 | 03-05-2024 | 06-05-2024 | [25 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 08-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 04-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 13-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 22-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 24-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 28-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | AWAITING VESSEL ARRIVAL - VESSEL MOVED OUT - NEW ETA DURBAN 27-03-2024 | VESSEL IN AND WORKING - TRUCK ON STANDBY TO LOAD | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | CONTAINER COLLECTED FROM PORT - AWAITING UNPACK - BV INSPECTION TO BE THIS WEEK | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | LOADED - BV INSPECTION BOOKED FOR TUESDAY 09-04-2024 DUE TO INSPECTOR AVAILABILITY | TRUCK TO DISPATCH DURBAN TODAY THE 09/04/2024 EN-ROUTE TO GROBLERSBRIDGE BORDER | TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERSBRIDGE | TRUCK IS AT TAMASANE EN-ROUTE TO KAZUNGULA | TRUCK IS AT KAFULAFUTA ENROUTE NDOLA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH SHORLTY | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH TODAY FOR KASUMBALESA | TRUCK IS AT NDOLA YARD BUSY WITH TRIP CHECK - TO DISPATCH ONCE DONE | KASUMBALBESA DRC SIDE CLEARING | KASUMBALBESA DRC SIDE CLEARING | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT WHISKEY AWAITING CLEARANCE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK AT CONNEX LUBUMBASHI AWAITING RELEASE | TRUCK ENROUTE TO CONGO EQUIPMENT | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 06-05-2024
BA2669 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | KGX0051 | CAT000D8KKGX00515 | TXJ02660 | FML2402DSI2386 | EX FML BOND STORE | COD 2024 165518 | ND706468 | ND476150 | ND64753 | 17-04-2024 | OFFLOADED 07-05-2024 | 10-04-2024 | 16-04-2024 | BV NUMBER RECEIVED | 02-11-2023 | 16-04-2024 | MIDDELBURG 17-04-2024 | MIDDELBURG 17-04-2024 | 19-04-2024 | 20-04-2024 | 21-04-2024 | 22-04-2024 | 23-04-2024 | 23-04-2024 | 23-04-2024 | 25-04-2024 | 25-04-2024 | 25-04-2024 | 25-04-2024 | 26-04-2024 | 26-04-2024 | 26-04-2024 | 27-04-2024 | 27-04-2024 | 28-04-2024 | 28-04-2024 | 01-05-2024 | 01-05-2024 | 06-05-2024 | 07-05-2024 | [31 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAIITNG BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | AWAITING BV NUMBER IN ORDER TO LOAD AND DISPATCH | AWAITING BV NUMBER IN ORDER TO LOAD AND DISPATCH | AWAITING BV NUMBER IN ORDER TO LOAD AND DISPATCH | AWAITING BV NUMBER IN ORDER TO LOAD AND DISPATCH | AWAITING BV NUMBER IN ORDER TO LOAD AND DISPATCH | BV INSPECTION BOOKED FOR TOMORROW 16-04-2024 - LOADING AFTER BV INSPECITON | BV INSPECTION BOOKED FOR TODAY 16-04-2024 - LOADING AFTER BV INSPECITON | NEWCASTLE ENROUTE BEIT BRIDGE BORDER | MARBELHALL ENROUTE BEIT BRIDGE BORDER | MUSIAN ENROUTE BEIT BRIDGE BORDER | MUSIAN ENROUTE BEIT BRIDGE BORDER | TRUCK IS AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | TRUCK IS AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | TRUCK IS AT CHIRUNDU DISPATCHING TODAY EN-ROUTE TO KASUMBALESA | TRUCK IS AT KAPIRI ENROUTE KASUMBALESA | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE - DAY 2 | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT CONNEX LUBUMBASHI WAITING RELEASE | VEHICLE AT TENKE | OFFLOADED 07-05-2024 | OFFLOADED 07-05-2024
BA2598 | CAT CS74B VIBRATORY COMPACTRO | BARTRAC EQUIPMENT . CONGO EQUIPMENT | B7M00460 | CATCS74BAB7M00460 | E7A60129 | FML2309DSI2227 | VESSEL: TIANJIN HIGHWAY Voy. 158A - ETA DURBAN: 02-11-2023 | COD 2024 132988 | L87NDGP | LL44DPGP | ND64690 | 24-04-2024 | OFFLOADED 21-05-2024 | 23-02-2024 | 24-04-2024 | BV COMPLETED | 02-11-2023 | 25-04-2024 | 27-04-2024 | 30-04-2024 | 01-05-2024 | 01-05-2024 | 02-05-2024 | 04-05-2024 | 05-05-2024 | 06-05-2024 | 06-05-2024 | 06-05-2024 | 06-05-2024 | 08-05-2024 | 08-05-2024 | 08-05-2024 | 08-05-2024 | 09-05-2024 | 09-05-2024 | 09-05-2024 | 11-05-2024 | 11-05-2024 | 16-05-2024 | 16-05-2024 | 20-05-2024 | 21-05-2024 | [31 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR THIS WEEK - LOADING PLAN TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAIITNG BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION AND LOADING DATE TO BE ADVISED AWAITING BA2707 | BV INSPECTION BOOKED FOR TUESDAY 23-04-2024 | BV INSPECTION BOOKED FOR TUESDAY 23-04-2024 | BV INSPECTION BOOKED FOR TODAY AWAITING DISPATCH DATE | TRUCK LOADING TODAY AND DISPATCH TOMMROW THE 25/04/2024 | TRUCK DISPATCHING DURBAN EN-ROUTE TO JOHANNESBURG | TRUCK EN-ROUTE TO JOHANNESBURG | VEHICLE IN JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | VEHICLE IN HAMMANSKRAAL ENROUTE BEIT BRIDGE BORDER | VEHICLE AT BEIT BRIDGE RSA SIDE | VEHICLE AT BEIT BRIDGE RSA SIDE | VEHICLE AT HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT NDOLA ENROUTE KASUMBUBALESA | VEHICLE KASUMBUBALESA ZAM SIDE CLEARING | VEHICLE WHISKEY AWAITING RELEASE | VEHICLE WHISKEY AWAITING RELEASE | VEHICLE WHISKEY AWAITING RELEASE | VEHICLE WHISKEY AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBAHSI WAITING FINAL CLEARANCE AND RELEASE | VEHICLE AT CONNEX LUBUMBAHSI WAITING FINAL CLEARANCE AND RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | OFFLOADED 21-05-2024
BA2707 | CAT966L BUCKET | BARTRAC EQUIPMENT . CONGO EQUIPMENT | N/A | N/A | N/A | FML2402DSI2413 | VESSEL: GREY FOX V. 241207 - ETA DURBAN: 15-04-2024 | COD 2024 166881 | L87NDGP | LL44DPGP | ND64690 | 24-04-2024 | OFFLOADED 21-05-2024 | 11-04-2024 | 24-04-2024 | BV COMPLETED | 17-04-2024 | 25-04-2024 | 27-04-2024 | 30-04-2024 | 01-05-2024 | 01-05-2024 | 04-05-2024 | 04-05-2024 | 05-05-2024 | 06-05-2024 | 06-05-2024 | 06-05-2024 | 06-05-2024 | 08-05-2024 | 08-05-2024 | 08-05-2024 | 08-05-2024 | 09-05-2024 | 09-05-2024 | 09-05-2024 | 11-05-2024 | 11-05-2024 | 16-05-2024 | 16-05-2024 | 20-05-2024 | 21-05-2024 | [44 empty] | AWAITING VESSEL DETAILS AND ETA DURBAN | AWAITING VESSEL DETAILS AND ETA DURBAN | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 14-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 15-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-04-2024 | VESSEL ARRIVED CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED CURRENTLY DISCHARGING CARGO - BV INSPECTION IS BOOKED FOR TUESDAY 23-04-2024 | COLLECTED FROM PORT - BV INSPECTION BOOKED FOR TOMORROW 23-04-2024 | BV INSPECTION BOOKED FOR TODAY AWAITING DISPATCH DATE | TRUCK LOADING TODAY AND DISPATCH TOMMROW THE 25/04/2024 | TRUCK DISPATCHING DURBAN EN-ROUTE TO JOHANNESBURG | TRUCK EN-ROUTE TO JOHANNESBURG | VEHICLE IN JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | VEHICLE IN HAMMANSKRAAL ENROUTE BEIT BRIDGE BORDER | VEHICLE AT BEIT BRIDGE RSA SIDE | VEHICLE AT BEIT BRIDGE RSA SIDE | VEHICLE AT HARARE ENROUTE CHIRUNDU | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT CHIRUNDU ZAM SIDE | VEHICLE AT NDOLA ENROUTE KASUMBUBALESA | VEHICLE KASUMBUBALESA ZAM SIDE CLEARING | VEHICLE WHISKEY AWAITING RELEASE | VEHICLE WHISKEY AWAITING RELEASE | VEHICLE WHISKEY AWAITING RELEASE | VEHICLE WHISKEY AWAITING RELEASE | VEHICLE AT CONNEX LUBUMBAHSI WAITING FINAL CLEARANCE AND RELEASE | VEHICLE AT CONNEX LUBUMBAHSI WAITING FINAL CLEARANCE AND RELEASE - DAY 4 | ON SITE WAITING TO OFFLOAD | OFFLOADED 21-05-2024
BA2679 | CAT350-06C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | WDP20025 | CAT00350CWDP20025 | NTB13577 | FML2401DSI2371 | VESSEL: TOMBARRA Voy. 037 - ETA DURBAN: 09-03-2024 | COD 2024 184844 | BJ60GTZN | ND247407 / ND231110 | 2401DSI2371 | 17-05-2024 | OFFLOADED 31-05-2024 | 10-05-2024 | 15-05-2024 | BV COMPLETED | 09-03-2024 | 15-05-2024 | MIDDELBURG 16-05-2024 | MIDDELBURG 16-05-2024 | 18-05-2024 | 20-05-2024 | 20-05-2024 | 20-05-2024 | 21-05-2024 | 21-05-2024 | 23-05-2024 | 23-05-2024 | 23-05-2024 | 24-05-2024 | 24-05-2024 | 26-05-2024 | 26-05-2024 | 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 30-05-2024 | 30-05-2024 | 31-05-2024 | 31-05-2024 | 31-05-2024 | 31-05-2024 | [83 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS DATE | LOADING TODAY - BV INSPECTION BOOKED FOR TOMORROW | LOADED YESTERDAY - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHED DURBAN | LOSKOMDAM ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ZIM ENROUTE HARARE | ZVIMBA ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | DISPATCHED MIKAMOBO BORDER | WHISKEY AWAITING RELEASE | OFFLOADED 31-05-2024 | OFFLOADED 31-05-2024
BA2213 | CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW01036 | CAT00352EHLW01036 | P4E05551 | FML2212DSI1868 | VESSEL: DALIAN HIGHWAY Voy. 97 - ETA DUEBAN: 29-01-2023 | COD 2024 184841 | BC02BWZN | ND821906 / ND822365 | 2212DSI1868A | 17-05-2024 | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI | 10-05-2024 | 15-05-2024 | BV COMPLETED | 29-01-2023 | 16-05-2024 | MIDDELBURG 16-05-2024 | MIDDELBURG 16-05-2024 | 18-05-2024 | 20-05-2024 | 20-05-2024 | 20-05-2024 | 21-05-2024 | 22-05-2024 | 23-05-2024 | 23-05-2024 | 23-05-2024 | 25-05-2024 | 25-05-2024 | 26-05-2024 | 27-05-2024 | 28-05-2024 | 28-05-2024 | MOKAMBO 28-05-2024 | MOKAMBO 30-05-2024 | 30-05-2024 | 01-06-2024 | 01-06-2024 | CONNEX | 03-06-2024 | [83 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS DATE | LOADING TODAY - BV INSPECTION BOOKED FOR TOMORROW | LOADED YESTERDAY - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHED DURBAN | LOSKOMDAM ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | CHIVI ZIM ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KABWE ERNOUTE MOKAMBO BORDER | MUFULIRA ERNOUTE MOKAMBO BORDER | DISPATCHED MIKAMOBO BORDER | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI
BA2214 | CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW017037 | CAT00352CHLW01037 | P4E05616 | FML2212DSI1868 | VESSEL: DALIAN HIGHWAY Voy. 97 - ETA DUEBAN: 29-01-2023 | COD 2024 184841 | BC01ZHZN | ND18488 / ND715801 | 2212DSI1868B | 17-05-2024 | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI | 10-05-2024 | 15-05-2024 | BV COMPLETED | 29-01-2023 | 16-05-2024 | MIDDELBURG 16-05-2024 | MIDDELBURG 16-05-2024 | 18-05-2024 | 20-05-2024 | 20-05-2024 | 20-05-2024 | 21-05-2024 | 22-05-2024 | 23-05-2024 | 23-05-2024 | 23-05-2024 | 25-05-2024 | 25-05-2024 | 26-05-2024 | 26-05-2024 | 27-05-2024 | 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 30-05-2024 | 30-05-2024 | 01-06-2024 | 01-06-2024 | CONNEX | 03-06-2024 | [83 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS DATE | LOADING TODAY - BV INSPECTION BOOKED FOR TOMORROW | LOADING TODAY DUE TO UNIT NOT STARTING - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHED DURBAN | LOSKOMDAM ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | MVUNGU ZIM ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | DISPATCHED MIKAMOBO BORDER | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI
BA2433 | CAT336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JFW22293 | CAT00336CJFW22293 | E7A57294 | FML2301DSI1933 | VESSEL: BOSPURUS HIGHWAY Voy. 130 - ETA DURBAN: 28-02-2023 | COD 2024 184842 | ND875035 | ND650731 | 2301DSI1933 | 17-05-2024 | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI | 10-05-2024 | 15-05-2024 | BV COMPLETED | 28-02-2023 | 16-05-2024 | MIDDELBURG 16-05-2024 | MIDDELBURG 16-05-2024 | 18-05-2024 | 20-05-2024 | 20-05-2024 | 21-05-2024 | 22-05-2024 | 22-05-2024 | 24-05-2024 | 24-05-2024 | 24-05-2024 | 25-05-2024 | 25-05-2024 | 26-05-2024 | 26-05-2024 | 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 30-05-2024 | 30-05-2024 | 01-06-2024 | 01-06-2024 | CONNEX | 03-06-2024 | [83 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS DATE | LOADING TODAY - BV INSPECTION BOOKED FOR TOMORROW | LOADING TODAY DUE TO UNIT NOT STARTING - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHED DURBAN | LOSKOMDAM ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE | MASVINGO ENROUTE HARARE | MKONDE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | DISPATCHED MIKAMOBO BORDER | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI
BA2434 | CAT336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JFW22291 | CAT00336KJFW22291 | E7A57221 | FML2301DSI1951 | VESSEL: TORINO Voy. 029 - ETA DURBAN: 05-03-2023 | COD 2024 184842 | ND303591 | ND580401 | 2301DSI1951B | 17-05-2024 | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI | 10-05-2024 | 15-05-2024 | BV COMPLETED | 05-03-2023 | 15-05-2024 | MIDDELBURG 16-05-2024 | MIDDELBURG 16-05-2024 | 18-05-2024 | 20-05-2024 | 20-05-2024 | 20-05-2024 | 21-05-2024 | 22-05-2024 | 22-05-2024 | 23-05-2024 | 23-05-2024 | 25-05-2024 | 25-05-2024 | 26-05-2024 | 26-05-2024 | 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 30-05-2024 | 30-05-2024 | 01-06-2024 | 01-06-2024 | CONNEX | 03-06-2024 | [83 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS DATE | LOADING TODAY - BV INSPECTION BOOKED FOR TOMORROW | LOADING TODAY DUE TO UNIT NOT STARTING - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHED DURBAN | LOSKOMDAM ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | CHIVI ZIM ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | DISPATCHED MIKAMOBO BORDER | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI | OFFLOADED 03-06-2024 AT CONNEX LUBUMBASHI
BA2432 | CAT336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | JFW22290 | CAT00336PJFW22290 | E7A57293 | FML2301DSI1951 | VESSEL: TORINO Voy. 029 - ETA DURBAN: 05-03-2023 | COD 2024 184842 | ND673267 | ND710695 | 2301DSI1951A | 17-05-2024 | OFFLOADED 04-06-2024 | 10-05-2024 | 15-05-2024 | BV COMPLETED | 05-03-2023 | 15-05-2024 | MIDDELBURG 16-05-2024 | MIDDELBURG 16-05-2024 | 18-05-2024 | 20-05-2024 | 20-05-2024 | 20-05-2024 | 21-05-2024 | 21-05-2024 | 22-05-2024 | 23-05-2024 | 23-05-2024 | 24-05-2024 | 24-05-2024 | 26-05-2024 | 26-05-2024 | 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 27-05-2024 | MOKAMBO 30-05-2024 | 30-05-2024 | 01-06-2024 | 01-06-2024 | 03-06-2024 | 04-06-2024 | [83 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS DATE | LOADING TODAY - BV INSPECTION BOOKED FOR TOMORROW | LOADED YESTERDAY - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - DISPATCHED DURBAN | LOSKOMDAM ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | CHIVI ZIM ENROUTE HARARE | ZVIMBA ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | DISPATCHED MIKAMOBO BORDER | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 04-06-2024 | OFFLOADED 04-06-2024
BA2212 | CAT352-08A HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | HLW01035 | CAT00352HHLW01035 | P4E05563 | FML2212DSI1880 | VESSEL: MORNING CHANT Voy. 086 - ETA DURBAN: 05-02-2023 | COD 2024 184841 | BJ59WJZN | ND646811 / ND644688 | 2212DSI1880 | 17-05-2024 | OFFLOADED 04-06-2024 | 10-05-2024 | 15-05-2024 | BV COMPLETED | 05-02-2023 | 16-05-2024 | MIDDELBURG 18-05-2024 | MIDDELBURG 19-05-2024 | 20-05-2024 | 20-05-2024 | 20-05-2024 | 21-05-2024 | 22-05-2024 | 23-05-2024 | 23-05-2024 | 24-05-2024 | 24-05-2024 | 25-05-2024 | 25-05-2024 | 26-05-2024 | 26-05-2024 | 28-05-2024 | 28-05-2024 | MOKAMBO 28-05-2024 | MOKAMBO 30-05-2024 | 30-05-2024 | 01-06-2024 | 01-06-2024 | 03-06-2024 | 04-06-2024 | [83 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS DATE | LOADING TODAY - BV INSPECTION BOOKED FOR TOMORROW | LOADED YESTERDAY - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - TO DISPATCH DURBAN | PIETERMARTIZBURG ENROUTE BEIT BRIDGE BORDER | MARBLE HALL ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | CHIRUMANZU ZIM ENROUTE HARARE | DISPATCH HARARE ENROUTE CHIRUNDU | CHIRUNDU ZIM SIDE CLEARING | KAPIRI ENROUTE MOKAMBO BORDER | MUFULIRA ENROUTE MOKAMBO BORDER | DISPATCHED MIKAMOBO BORDER | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD - DAY 2 | OFFLOADED 04-06-2024
BA2321 | CAT950GC-01A WHEEL LOADER | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M5K06407 | CAT00950PM5K06407 | E7A57688 | FML2212DSI1881 | VESSEL: MORNING CHANT Voy. 086 - ETA DURBAN: 05-02-2023 | COD 2024 184929 | ND923885 | ND184465 | ND64772 | 17-05-2024 | OFFLOADED 06-06-2024 | 10-05-2024 | 15-05-2024 | BV COMPLETED | 05-02-2023 | 16-05-2024 | MIDDELBURG 17-05-2024 | MIDDELBURG 18-05-2024 | 21-05-2024 | 21-05-2024 | 21-05-2024 | 22-05-2024 | 22-05-2024 | 24-05-2024 | 24-05-2024 | 25-05-2024 | 25-05-2024 | 26-05-2024 | 26-05-2024 | 26-05-2024 | 26-05-2024 | 27-05-2024 | 27-05-2024 | 28-05-2024 | 30-05-2024 | 30-05-2024 | 04-06-2024 | 04-06-2024 | 06-06-2024 | 06-06-2024 | [83 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW 14-05-2024 | LOADED YESTERDAY - BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - TO DISPATCH DURBAN | DISPATCHING DURBAN | AMERFOORT ENROUTE BEIT BRIDGE BORDER | LOUIS TRICHARDT ENROUTE BEIT BRIDGE BORDER | MUSINA ENROUTE BEIT BRIDGE | MVUMA ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | DISPATCHED HARARE ENROUTE CHIRUNDU | KAPIRI ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER CLEARING | KASUMBALESA ZAM SIDE IN THE QUE TO CROSS TO DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 5 | WHISKEY AWAITING RELEASE - DAY 6 | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 06-06-2024 | OFFLOADED 06-06-2024
BA2747 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TJT20108 | CAT00333LTJT20108 | E7A61629 | FML2404DSI2481 | VESSEL: OREGON HIGHWAY Voy. 146 - ETA DURBAN: 30-04-2024 | COD 2024 191227 | ND570587 | BH 61 YR ZN | ND64775 | 24-05-2024 | OFFLOADED 20-06-2024 | 20-05-2024 | 22-05-2024 | BV COMPLETED | 30-04-2024 | 24-05-2024 | MIDDELBURG 27-05-2024 | MIDDELBURG 30-05-2024 | 31-05-2024 | 01-06-2024 | 01-06-2024 | 03-06-2024 | 05-06-2024 | 05-06-2024 | 06-06-2024 | 06-06-2024 | 06-06-2024 | 09-06-2024 | 10-06-2024 | 10-06-2024 | 10-06-2024 | 11-06-2024 | 11-06-2024 | 12-06-2024 | 13-06-2024 | 13-06-2024 | 14-06-2024 | 14-06-2024 | 20-06-2024 | 20-06-2024 | [89 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY 22-05-2024 | LOADING TODAY | PIETERMARITZBURG ENROUTE BEIT BRIDGE BORDER | ERMELO ENROUTE BEIT BRIDGE BORDER | MIDDELBURG AWAITING LIMPOPO PERMIT | MIDDELBURG AWAITING LIMPOPO PERMIT - PERMITS TO BE RECEIVED MIDDAY TODAY | MUSINA ENROUTE BEIT BRIDGE BORDER FOR CLEARING | BEIT BRIDGE ZIM SIDE | GWERU ENROUTE HARARE | DISPATCHING GWERU FOR HARARE | MAKUTI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | KAPITI ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI, AWAITING RELEASE | CONNEX LUBUMBASHI, AWAITING RELEASE - DAY 2 | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 20-06-2024
BA2748 | CAT333-07F HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | TJT20107 | CAT00333ATJT20107 | E7A61632 | FML2404DSI2481 | VESSEL: OREGON HIGHWAY Voy. 146 - ETA DURBAN: 30-04-2024 | COD 2024 191227 | ND705348 | ND926113 | ND64776 | 24-05-2024 | OFFLOADED 20-06-2024 | 20-05-2024 | 22-05-2024 | BV COMPLETED | 30-04-2024 | 24-05-2024 | MIDDELBURG 27-05-2024 | MIDDELBURG 30-05-2024 | 31-05-2024 | 02-06-2024 | 02-06-2024 | 04-06-2024 | 05-06-2024 | 05-06-2024 | 06-06-2024 | 06-06-2024 | 06-06-2024 | 09-06-2024 | 10-06-2024 | 10-06-2024 | 10-06-2024 | 11-06-2024 | 11-06-2024 | 12-06-2024 | 13-06-2024 | 13-06-2024 | 14-06-2024 | 14-06-2024 | 20-06-2024 | 20-06-2024 | [89 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY 22-05-2024 | LOADING TODAY | PIETERMARITZBURG ENROUTE BEIT BRIDGE BORDER | NEWCASTLE ENROUTE BEIT BRIDGE BORDER | MIDDELBURG AWAITING LIMPOPO PERMIT | MIDDELBURG AWAITING LIMPOPO PERMIT - PERMITS TO BE RECEIVED MIDDAY TODAY | MUSINA ENROUTE BEIT BRIDGE BORDER FOR CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE CLEARING | REDCLIFF ZIM ENROUTE HARARE | MAKUTI ENROUTE CHIRUNDU | CHIRUNDU ZAM SIDE CLEARING | KAPITI ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI, AWAITING RELEASE | CONNEX LUBUMBASHI, AWAITING RELEASE - DAY 2 | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 20-06-2024
BA2680 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M8D00465 | CAT000D8CM8D00465 | TXJ02589 | FML2404DSI2483 | VESSEL: MARGUERITE ACE Voy. 0125A - ETA DURBAN: 26-04-2024 | COD 2024 194056 | ND61605 | ND868372 | ND64774 | 30-05-2024 | OFFLOADED 20-06-2024 | 22-05-2024 | 23-05-2024 | BV COMPLETED | 26-04-2024 | 28-05-2024 | MIDDELBURG 31-05-2024 | MIDDELBURG 31-05-2024 | 01-06-2024 | 02-06-2024 | 02-06-2024 | 03-06-2024 | 05-06-2024 | 05-06-2024 | 07-06-2024 | 08-06-2024 | 08-06-2024 | 10-06-2024 | 11-06-2024 | 11-06-2024 | 11-06-2024 | 12-06-2024 | 12-06-2024 | 12-06-2024 | 13-06-2024 | 13-06-2024 | 14-06-2024 | 14-06-2024 | 20-06-2024 | 20-06-2024 | [89 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY 23-05-2024 | BV INSPECTION COMPLETED - LOADING MONDAY | LOADING TODAY | LOADED TO DISPATCH DURBAN | ENOURTE BEIT BRIDGE BORDER | ERMELO ENOURTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | MVUMA ENROUTE HARARE | DISPATCHING MVUMA FOR HARARE | KAROI ENROUTE CHIRUNDU | MAKUTI ENROUTE CHIRUNDU | DISPATCHED FROM CHIRUNDU BORDER ENROUTE KASUMBALESA BORDER | KAPIRI ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI, AWAITING RELEASE | CONNEX LUBUMBASHI, AWAITING RELEASE - DAY 2 | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 20-06-2024
BA2681 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT . CONGO EQUIPMENT | M8D00466 | CAT000D8TM8D00466 | TXJ02607 | FML2404DSI2483 | VESSEL: MARGUERITE ACE Voy. 0125A - ETA DURBAN: 26-04-2024 | COD 2024 204838 | BJ59ZYZN | ND647660 / ND647016 | 2404DSI2483B | 10-06-2024 | OFFLOADED 21-06-2024 | 05-06-2024 | 07-06-2024 | BV COMPLETED | 26-04-2024 | 10-06-2024 | MIDDELBURG 11-06-2024 | MIDDELBURG 11-06-2024 | 11-06-2024 | 12-06-2024 | 12-06-2024 | 12-06-2024 | 13-06-2024 | 14-06-2024 | 14-06-2024 | 15-06-2024 | 15-06-2024 | 16-06-2024 | 16-06-2024 | 17-06-2024 | 17-06-2024 | 18-06-2024 | 18-06-2024 | MOKAMBO 18-06-2024 | MOKAMBO 19-06-2024 | 19-06-2024 | 20-06-2024 | 20-06-2024 | 20-06-2024 | 21-06-2024 | [100 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - AWAITING LICENSE TO BE VALIDATED IN ORDER TO DO THE INSPECTION | BV INSPECTION BOOKED FOR TODAY | DISPATCHED FROM DURBAN ENROUTE MEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | MWENEZI ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER ZAM SIDE | WHISKEY AWAITING RELEASE | AT CONGO EQUIPMENT WAITING TO OFFLOAD | OFFLOADED 21-06-2024
BA2435 | CAT336GC-07C HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | JFW22289 | CAT00336JJFW22289 | E7A57237 | FML2301DSI1933 | VESSEL: BOSPORUS HIGHWAY Voy. 130 - ETA DURBAN: 28-02-2023 | COD 2024 252379 | ND730794 | ND443606 | ND61879 | 13-08-2024 | OFFLOADED 05-09-2024 | 08-08-2024 | 13-08-2024 | BV COMPLETED | 28-02-2023 | 14-08-2024 | MIDDELBURG 15-08-2024 | MIDDELBURG 16-08-2024 | 17-08-2024 | 18-08-2024 | 18-08-2024 | 19-08-2024 | 20-08-2024 | 22-08-2024 | 22-08-2024 | 23-08-2024 | 23-08-2024 | 23-08-2024 | 24-08-2024 | 25-08-2024 | 25-08-2024 | 27-08-2024 | 27-08-2024 | 27-08-2024 | 31-08-2024 | 31-08-2024 | 03-09-2024 | 03-09-2024 | 04-09-2024 | 05-09-2024 | [19 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR TODAY 12-08-2024 - LOADING PLANNED FOR TOMORROW 13-08-2024 | LOADING TODAY | CATO RIDGE ENROUTE BEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | MIDDELBURG AWAITING LIMPOPO PERMITS | BEIT BRIDGE ZIM SIDE | MVUMA ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU BORDER | DISPATCHING HARARE TODAY FOR CHIRUNDU BORDER | CHIRUNDU BORDER CLEARNING | KAPIRI MPOSHI ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY TO DISPATCH TODAY | AT CONNEX LUBUMBAHSI - AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 05-09-2024
BA2752 | CAT D8GC TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | M8D00468 | CAT000D8KM8D00468 | TXJ02595 | FML2404DSI2483 | VESSEL: MARGUERITE ACE Voy. 0125A - ETA DURBAN: 26-04-2024 | COD 2024 252314 | ND923885 | ND184465 | ND61880 | 13-08-2024 | OFFLOADED 05-09-2024 | 08-08-2024 | 13-08-2024 | BV COMPLETED | 26-04-2024 | 14-08-2024 | MIDDELBURG 15-08-2024 | MIDDELBURG 16-08-2024 | 17-08-2024 | 18-08-2024 | 18-08-2024 | 19-08-2024 | 20-08-2024 | 22-08-2024 | 23-08-2024 | 23-08-2024 | 23-08-2024 | 24-08-2024 | 24-08-2024 | 25-08-2024 | 25-08-2024 | 27-08-2024 | 27-08-2027 | 27-08-2024 | 31-08-2024 | 31-08-2024 | 03-09-2024 | 03-09-2024 | 04-09-2024 | 05-09-2024 | [20 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR TODAY 12-08-2024 - LOADING PLANNED FOR TOMORROW 13-08-2024 | LOADING TODAY | CATO RIDGE ENROUTE BEIT BRIDGE BORDER | MIDDELBURG ENROUTE BEIT BRIDGE BORDER | MIDDELBURG AWAITING LIMPOPO PERMITS | BEIT BRIDGE ZIM SIDE | MVUMA ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU BORDER | DISPATCHING HARARE TODAY FOR CHIRUNDU BORDER | KAROI ENROUTE CHIRUNDU BORDER | KAPIRI MPOSHI ENROUTE KASUMBALESA BORDER | CHINGOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY TO DISPATCH TODAY | AT CONNEX LUBUMBAHSI - AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 05-09-2024
BA2684 TO BA2705 | 22 LIGHTING TOWERS & 8 PKGS PARTS | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TBA | TBA | TBA | FML2405DSI2549 | VESSEL: EVER UNITED V. 199W - ETA DURBAN: 30-07-2024 | COD 2024 241975 / COD 2024 241664 | BCE5028ZM | ATB2573T | 2405DSI2549 | 08-08-2024 | OFFLOADED 06-09-2024 | 25-07-2024 | 02-08-2024 | BV COMPLETED | 30-07-2024 | 09-08-2024 | 10-08-2024 | 11-08-2024 | GRB BORDER 11-08-2024 | GRB 12-08-2024 | MARTINS DRIFT 12-08-2024 | MARTINS DRIFT 12-08-2024 | FRANCISTOWN 13-08-2024 | FRANCISTOWN 13-08-2024 | KAZUNGULA BW 13-08-2024 | KAZUNGULA BW 15-08-2024 | KAZUNGULA ZM 15-08-2024 | KAZUNGULA ZM 18-08-2024 | 19-08-2024 | 19-08-2024 | 19-08-2024 | 24-08-2024 | 24-08-2024 | 25-08-2024 | 30-08-2024 | 30-08-2024 | 31-08-2024 | 31-08-2024 | 04-09-2024 | 06-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 24-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 26-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 28-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-07-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-07-2024 | AWAITING VESSEL ARRIVAL - VESSEL DUE TO ARRIVE TODAY | VESSEL IN AND DISCHARDING CONTAINERS | CONTAINER TO BE COLLECTED FROM PORT | BV INSPECTION BOOKED FOR TODAY 02-08-2024 | BV INSPECTION DONE - LOADING WEDNESDAY 07-08-2024 | BV INSPECTION DONE - LOADING THURSDAY 08-08-2024 | BV INSPECTION DONE - LOADING MONDAY 12-08-2024 - (AWAITING PARTS TO BE BV INSPECTED) | LOADING MONDAY | LOADED YESTERDAY - DISPATCHING FOR THE BORDER | CURRENTLY AT GROBERSBRIDGE BORDER CLEARING | SERULE BW ENROUTE KAZUNGULA BORDER | KAZUMGULA BORDER CLEARING | KAZUMGULA BORDER CLEARING | KAZUNGULA BORDER FINALIZING CLEARING | KAPIRI ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE CHECK | NDOLA UNDER ROUTINE MAINTENANCE CHECK | NDOLA FINALIZING MAINTENANCE CHECK | DISPATCHING NDOLA FOR KASUMBALESA BORDER | KASUMBALESA BORDER CLEARING | KASUMBALESA BORDER - DRC SIDE CLEARING | KASUMBALESA BORDER - DRC SIDE CLEARING | VEHICLE AT WHISKEY AWAITING RELEASE | VEHICLE AT WHISKEY AWAITING RELEASE | ON SITE AWAITING TO OFFLOAD | ON SITE AWAITING TO OFFLOAD | AT CONNEX LUBUMBAHSI - AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | ON SITE WAITING TO OFFLOAD | OFFLOADED 06-09-2024
BA2678 | CAT C15 ENGINE | BARTRAC EQUIPMENT / CONGO EQUIPMNET | MCW19394 | N/A | N/A | FML2405DSI2537 | VESSEL: ONE TRITON V. 105E - Transhipment Vessel: SANTA RITA V. 241S - ETA DURBAN: 29-06-2024 | COD 2024 253969 PT01 | BCE4038ZM | BCE5493ZM | 2405DSI2537 | 19-08-2024 | OFFLOADED 13-09-2024 | 12-08-2024 | 13-08-2024 | BV COMPLETED | 29-06-2024 | 20-08-2024 | 21-08-2024 | 21-08-2024 | GRB BORDER 21-08-2024 | GRB 24-08-2024 | MARTINS DRIFT 24-08-2024 | MARTINS DRIFT 24-08-2024 | FRANCISTOWN 24-08-2024 | FRANCISTOWN 25-08-2024 | KAZUNGULA BW 25-08-2024 | KAZUNGULA BW 26-08-2024 | KAZUNGULA ZM 26-08-2024 | KAZUNGULA ZM 28-08-2024 | 30-08-2024 | 30-08-2024 | 31-08-2024 | 31-08-2024 | 31-08-2024 | 31-08-2024 | 09-09-2024 | 09-09-2024 | 11-09-2024 | 11-09-2024 | 13-09-2024 | 13-09-2024 | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | AT BONDED FACILITY - AWATING BA2668 TO ARRIVE IN DURBAN IN AUGUST | BV INSPECTION BOOKED FOR MONDAY 12-08-2024 | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR TODAY 13-08-2024 | BV INSPECTION COMPLETED - LOADING THURSDAY | LOADING TOMORROW | LOADING TODAY | VEHICLE WAS DELAYED - TO LOAD THIS AFTERNOON | LOADED | ENROUTE GROBLERSBRIDGE BORDER | GROBLERSBRIDGE BORDER CLEARING | GROBLERSBRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | DISPATCHING KAZUNGULA BORDER | PEMBA ENROUTE LUSAKA | MASAITI ENROUTE KASUMBALESA | KASUMBALESA BORDER CLEARING AWAITING RELEASE | KASUMBALESA ZAM SIDE TO CROSS TO DRC SIDE | KASUMBALESA ZAM SIDE WAITING TO CROSS TO DRC SIDE | KASUMBALESA ZAM SIDE WAITING TO CROSS TO DRC SIDE | KASUMBALESA ZAM SIDE WAITING TO CROSS TO DRC SIDE - SHOULD CROSS TODAY | KASUMBALESA DRC SIDE AWAITING CLEARANCE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE | OFFLOADED 13-09-2024
BA2668 | CAT C27 ENGINE | BARTRAC EQUIPMENT / CONGO EQUIPMNET | TWM08609 | N/A | N/A | FML2406DSI2551 | VESSEL: COLUMBINE MAERSK V. 425E - Transipment Vessel: MSC ROSARIA V. UZ426S - ETA DURBAN: 05-08-2024 | COD 2024 253983 PT01 | BCE4038ZM | BCE5493ZM | 2405DSI2537 | 19-08-2024 | OFFLOADED 13-09-2024 | 12-08-2024 | 13-08-2024 | BV COMPLETED | 05-08-2024 | 20-08-2024 | 21-08-2024 | 21-08-2024 | GRB BORDER 21-08-2024 | GRB 24-08-2024 | MARTINS DRIFT 24-08-2024 | MARTINS DRIFT 24-08-2024 | FRANCISTOWN 24-08-2024 | FRANCISTOWN 25-08-2024 | KAZUNGULA BW 25-08-2024 | KAZUNGULA BW 26-08-2024 | KAZUNGULA ZM 26-08-2024 | KAZUNGULA ZM 28-08-2024 | 30-08-2024 | 30-08-2024 | 31-08-2024 | 31-08-2024 | 31-08-2024 | 31-08-2024 | 09-09-2024 | 09-09-2024 | 11-09-2024 | 11-09-2024 | 13-09-2024 | 13-09-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 09-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 06-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 03-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 05-08-2024 | BV INSPECTION BOOKED FOR MONDAY 12-08-2024 | AWAITING BV NUMBER | BV INSPECITON BOOKED FOR TODAY 13-08-2024 | BV INSPECTION COMPLETED - LOADING THURSDAY | LOADING TOMORROW | LOADING TODAY | VEHICLE WAS DELAYED - TO LOAD THIS AFTERNOON | LOADING THIS MORNING | ENROUTE GROBLERSBRIDGE BORDER | GROBLERSBRIDGE BORDER CLEARING | GROBLERSBRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER ZAMBIAN SIDE CLEARING | DISPATCHING KAZUNGULA BORDER | PEMBA ENROUTE LUSAKA | MASAITI ENROUTE KASUMBALESA | KASUMBALESA BORDER CLEARING AWAITING RELEASE | KASUMBALESA ZAM SIDE TO CROSS TO DRC SIDE | KASUMBALESA ZAM SIDE WAITING TO CROSS TO DRC SIDE | KASUMBALESA ZAM SIDE WAITING TO CROSS TO DRC SIDE | KASUMBALESA ZAM SIDE WAITING TO CROSS TO DRC SIDE - SHOULD CROSS TODAY | KASUMBALESA DRC SIDE AWAITING CLEARANCE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE | CONNEX LUBUMBASHI - AWAITING FINAL CLEARANCE | OFFLOADED 13-09-2024
BA2802 | CAT966GC BUCKET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N/A | N/A | N/A | 2407DSI2561 | VESSEL: SILVER SOUL Voy. 24SS08 - ETA DURBAN: 18-08-2024 | COD 2024 261350 | KV66PYGP | FL25PLGP / FL25WCGP | POR5775 | 02-09-2024 | OFFLOADED 30-09-2024 | 26-08-2024 | 28-08-2024 | BV COMPLETED | 18-08-2024 | 28-08-2024 | 29-08-2024 | 31-08-2024 | GRB 31-08-2024 | GRB 01-09-2024 | MARTINS DRIFT 01-09-2024 | MARTINS DRIFT 02-09-2024 | FRANCISTOWN 02-09-2024 | FRANCISTOWN 03-09-2024 | KAZUNGULA BW 03-09-2024 | KAZUNGULA BW 04-09-2024 | KAZUNGULA ZM 04-09-2024 | KAZUNGULA ZM 05-09-2024 | 06-09-2024 | 08-09-2024 | 09-09-2024 | 09-09-2024 | 09-09-2024 | 09-09-2024 | 11-09-2024 | 11-09-2024 | 21-09-2024 | 22-09-2024 | 30-09-2024 | 30-09-2024 | [15 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 21-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 18-08-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-08-2024 | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | VESSEL ARRIVED AND CURRENTLY DISCHARGING CARGO | BUCKET TO BE COLLECTED FROM PORT | BUCKET TO BE COLLECTED FROM PORT TODAY | BUCKET AT FML BONDED FACILITY - AWAITING CONSOLIDATION LOAD | BV INSPECTION BOOKED 27-08-2024 | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - BUCKET COLLECTED AND ENROUTE TO JOHANNESBURG FOR CONSOLIDATION | BV INSPECTION COMPLETED - BUCKET ENROUTE TO JOHANNESBURG FOR CONSOLIDATION | BUCKET LOADED ON COLSOL VEHICLE TO DISPATCH NEXT WEEK | DISPATCHING JOHANNESBURG SHORLTY | DISPATCHED FRANCISTOWN ENROUTE KAZUNGULA BORDER | KAZUNGULA ZAM SIDE CLEARING | LIVINBSTONE ENROUTE KASUMBALESA | KALOMO ENROUTE KASUMBALESA | ENROUTE KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | GOMES AWAITING RELEASE | WHIESKEY AWAITING RELEASE | WHIESKEY AWAITING RELEASE | WHIESKEY AWAITING RELEASE | WHIESKEY AWAITING RELEASE | WHIESKEY AWAITING RELEASE | WHISKEY AWAITING SEGUSE | WHISKEY AWAITING SEGUSE | CONSOLIDATION VEHICLE IN LUBUMBASHI AT OFFLOADING POINT 1 | CONSOLIDATION VEHICLE IN LUBUMBASHI AT OFFLOADING POINT 1 - DRC CUSTOMS OFFLINE WHICH ARE DELAYING THE OFFLOADING PORCESS | CONSOLIDATION VEHICLE IN LUBUMBASHI AT OFFLOADING POINT 2 - | CONSOLIDATION VEHICLE IN LUBUMBASHI AT OFFLOADING POINT 2 - AWAITING RELEASE TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | OFFLOADED 30-09-2024
BA2022 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F605657 | CAT00745A3F605657 | TXW07072 | 2301DSI1903 | VESSEL: GOLDEN KAROO Voy. 231202 - ETA DURBAN: 20-02-2023 | COD 2024 291367 | ND730794 | ND443606 | ND61033 | 08-10-2024 | OFFLOADED 22-10-2024 | 30-09-2024 | 01-10-2024 | BV COMPLETED | 20-02-2023 | 03-10-2024 | MIDDELBURG 03-10-2024 | MIDDELBURG 03-10-2024 | 05-10-2024 | 06-10-2024 | 07-10-2024 | 08-10-2024 | 09-10-2024 | 10-10-2024 | 11-10-2024 | 12-10-2024 | 12-10-2024 | 13-10-2024 | 13-10-2024 | 13-10-2024 | 14-10-2024 | 14-10-2024 | 14-10-2024 | 14-10-2024 | 15-10-2024 | 15-10-2042 | 18-10-2024 | 19-10-2024 | 22-10-2024 | 22-10-2024 | [54 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS | BV INSPECTION BOOKED FOR TODAY - LOADING THIS WEEK | BV INSPECTION COMPLETED - LOADING TODAY | LOADED YESTERDAY - CURRENTLY AT PIETERMARITZBURG ENROUTE BEIT BRIGDE BORDER | GROBLERSDAL ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER CLEARING | BEIT BRIDGE BORDER ZIM SIDE CLEARING | MVUMA ENROUTE HARARE | HARARE TO DISPATCH FOR CHIRUNDU BORDER | MAPINGA ENROUTE CHIRUDNU BORDER | KITWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE TO CROSS TO DRC SIDE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 2 - PLEASE ASSIST | WHISKEY AWAITING RELEASE - DAY 3 - PLEASE ASSIST | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-10-2024
BA2166 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F605732 | CAT00745T3F605732 | TXW07121 | 2303DSI1989 | VESSEL: GREEN MOUNTAIN Voy. 231206 - ETA DURBAN: 16-04-2023 | COD 2024 291459 | BL01BKZN | ND580401 | MFSTD002974 | 08-10-2024 | OFFLOADED 22-10-2024 | 30-09-2024 | 01-10-2024 | BV COMPLETED | 16-04-2023 | 07-10-2024 | 07-10-2024 | 08-10-2024 | 08-10-2024 | 08-10-2024 | 08-10-2024 | 11-10-2024 | 11-10-2024 | 12-10-2024 | 12-10-2024 | 12-10-2024 | 12-10-2024 | 15-10-2024 | 15-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 18-10-2024 | 19-10-2024 | 19-10-2024 | 20-10-2024 | 20-10-2024 | 22-10-2024 | 22-10-2024 | [54 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS | BV INSPECTION BOOKED FOR TODAY - LOADING THIS WEEK | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | LOADED, AWAITING PERMITS | DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE AWAITING RELEASE | CHIVI ZIM ENROUTE HARARE | CHIRUNDU ZAMBIAN SIDE CLEARING | DISPATCH CHIRUNDU ENROUTE MOKAMBO BORDER | CHIBOMBO ZAMBIA ENROUTE MOKAMBO BORDER | NDOLA ENROUTE MOKAMBO BORDER | NDOLA TO DISPATCH FOR MOKAMBO BORDER | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-10-2024
BA2167 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F605733 | CAT00745P3F605733 | TXW06634 | 2303DSI1990 | VESSEL: GREEN MOUNTAIN Voy. 231206 - ETA DURBAN: 16-04-2023 | COD 2024 291459 | BJ30DXZN | ND650731 | MFSTD002976 | 08-10-2024 | OFFLOADED 22-10-2024 | 30-09-2024 | 01-10-2024 | BV COMPLETED | 16-04-2023 | 07-10-2024 | 07-10-2024 | 08-10-2024 | 08-10-2024 | 08-10-2024 | 08-10-2024 | 11-10-2024 | 11-10-2024 | 12-10-2024 | 12-10-2024 | 12-10-2024 | 12-10-2024 | 15-10-2024 | 15-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 17-10-2024 | 19-10-2024 | 19-10-2024 | 20-10-2024 | 20-10-2024 | 22-10-2024 | 22-10-2024 | [54 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS | BV INSPECTION BOOKED FOR TODAY - LOADING THIS WEEK | BV INSPECTION COMPLETED - LOADING TOMORROW | LOADING TODAY | LOADED, AWAITING PERMITS | DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE AWAITING RELEASE | CHIVI ZIM ENROUTE HARARE | CHIRUNDU ZAMBIAN SIDE CLEARING | DISPATCH CHIRUNDU ENROUTE MOKAMBO BORDER | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-10-2024
BA2570 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F805331 | CAT00740A3F805331 | TXY07964 | 2312DSI2344 | VESSEL: BLUE MASTER II - ETA DURBAN: 16-02-2024 | COD 2024 291458 | ND875035 | BL01BYZN | MFSTD002972 | 08-10-2024 | OFFLOADED 22-10-2024 | 30-09-2024 | 01-10-2024 | BV COMPLETED | 16-02-2024 | 08-10-2024 | 09-10-2024 | 09-10-2024 | 10-10-2024 | 10-10-2024 | 10-10-2024 | 12-10-2024 | 12-10-2024 | 13-10-2024 | 13-10-2024 | 14-10-2024 | 14-10-2024 | 15-10-2024 | 15-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 17-10-2024 | 19-10-2024 | 19-10-2024 | 20-10-2024 | 20-10-2024 | 22-10-2024 | 22-10-2024 | [54 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS | BV INSPECTION BOOKED FOR TODAY - LOADING THIS WEEK | BV INSPECTION COMPLETED - LOADING FRIDAY | LOADING TOMORROW | VEHICLE DELAYED - LOADING MONDAY | LOADING TODAY | VAN REENEN ENROUTE JOHANNESBURG | VAN REENEN AWAITING PERMITS | POLOKWANE ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE ZIM SIDE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-10-2024
BA2571 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F805332 | CAT00740L3F805332 | TXY07968 | 2312DSI2343 | VESSEL: BLUE MASTER II - ETA DURBAN: 16-02-2024 | COD 2024 291458 | ND673267 | ND710695 | MFSTD002973 | 08-10-2024 | OFFLOADED 22-10-2024 | 30-09-2024 | 01-10-2024 | BV COMPLETED | 16-02-2024 | 03-10-2024 | 04-10-2024 | 07-10-2024 | 07-10-2042 | 08-10-2024 | 08-10-2024 | 09-10-2024 | 10-10-2024 | 11-10-2024 | 12-10-2024 | 12-10-2024 | 12-10-2024 | 15-10-2024 | 15-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 17-10-2024 | 19-10-2024 | 19-10-2024 | 20-10-2024 | 20-10-2024 | 22-10-2024 | 22-10-2024 | [54 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS | BV INSPECTION BOOKED FOR TODAY - LOADING THIS WEEK | BV INSPECTION COMPLETED - LOADING TODAY | LOADING TODAY | VAN REENEN ENROUTE BEIT BRIDGE BORDER | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | MUSINA ENROUTE BEIT BRIDGE BORDER TO CLEAR | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE CLEARING | CHIRUNDU ZAMBIAN SIDE CLEARING | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-10-2024
BA2572 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F805336 | CAT00740T3F805336 | TXY07982 | 2312DSI2342 | VESSEL: BLUE MASTER II - ETA DURBAN: 16-02-2024 | COD 2024 291458 | BJ59XNZN | BL01DGZN | MFSTD002977 | 08-10-2024 | OFFLOADED 22-10-2024 | 30-09-2024 | 01-10-2024 | BV COMPLETED | 16-02-2024 | 03-10-2024 | 04-10-2024 | 07-10-2024 | 08-10-2024 | 08-10-2024 | 08-10-2024 | 09-10-2024 | 10-10-2024 | 11-10-2024 | 12-10-2024 | 12-10-2024 | 12-10-2024 | 15-10-2024 | 15-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 17-10-2024 | 19-10-2024 | 19-10-2024 | 20-10-2024 | 20-10-2024 | 22-10-2024 | 22-10-2024 | [54 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS | BV INSPECTION BOOKED FOR TODAY - LOADING THIS WEEK | BV INSPECTION COMPLETED - LOADING TODAY | LOADING TODAY | VAN REENEN ENROUTE BEIT BRIDGE BORDER | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | MUSINA ENROUTE BEIT BRIDGE BORDER TO CLEAR | BEIT BRIDGE RSA SIDE CLEARING | MASVINGO ENROUTE HARARE | HARARE ENROUTE CHIRUNDU | CHIRUNDU ZAMBIAN SIDE CLEARING | DISPATCH CHIRUNDU ENROUTE MOKAMBO BORDER | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 22-10-2024
BA2451 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F605971 | CAT00745E3F605971 | TXW07531 | 2309DSI2201 | VESSEL: GREY FOX Voy. 231218 - ETA DURBAN: 15-10-2023 | COD 2024 291361 | ND681744 | BV08NFZN | MFSTD002975 | 08-10-2024 | OFFLOADED 24-10-2024 | 30-09-2024 | 01-10-2024 | BV COMPLETED | 15-10-2023 | 07-10-2024 | 07-10-2024 | 08-10-2024 | 08-10-2024 | 08-10-2024 | 08-10-2024 | 11-10-2024 | 11-10-2024 | 12-10-2024 | 12-10-2024 | 12-10-2024 | 12-10-2024 | 15-10-2024 | 15-10-2024 | 16-10-2024 | 16-10-2024 | 17-10-2024 | 17-10-2024 | 17-10-2024 | 19-10-2024 | 19-10-2024 | 20-10-2024 | 20-10-2024 | 23-10-2024 | 24-10-2024 | [54 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION DATE TO BE CONFIRMED ONCE BV RSA CONFIRMS | BV INSPECTION BOOKED FOR TODAY - LOADING THIS WEEK | BV INSPECTION COMPLETED - LOADING FRIDAY | LOADING TODAY | LOADED, AWAITING PERMITS | DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE AWAITING RELEASE | CHIVI ZIM ENROUTE HARARE | CHIRUNDU ZAMBIAN SIDE CLEARING | DISPATCH CHIRUNDU ENROUTE MOKAMBO BORDER | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | CONNEX LUBUMBASHI AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE | ON SITE WAITING TO OFFLOAD | OFFLOADED 24-10-2024
BA2591 | CAT D6GC TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | XPC00869 | CAT00D6LXPC00869 | R6J04838 | 2309DSI2197 | VESSEL: GUANGZHOU HIGHWAY Voy. 173A - ETA DRUBAN: 26-09-2023 | COD 2024 323103 | BS34MSZN | BV93SGZN | 2309DSI2197 | 13-11-2024 | OFFLOADED 28-11-2024 | 11-11-2024 | 12-11-2024 | BV COMPLETED | 26-09-2023 | 14-11-2024 | 15-11-2024 | 16-11-2024 | 16-11-2024 | 17-11-2024 | 17-11-2024 | 19-11-2024 | 20-11-2024 | 20-11-2024 | 21-11-2024 | 23-11-2024 | 23-11-2024 | 24-11-2024 | 24-11-2024 | 24-11-2024 | 25-11-2024 | 25-11-2024 | 25-11-2024 | MOKAMBO 25-11-2024 | MOKAMBO 27-11-2024 | 27-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | 28-11-2024 | [77 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION COMPLETED - LOADING TODAY | CURRENTLY LOADING FROM BONDED FACILITY | LOADED - ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE CLEARING | BEIT BRIDGE BORDER ZIM SIDE | MVUMA ENROUTE HARARE | KAROI ENROUTE CHIRUNDU | CHIRUNDU BORDER CLEARING | KAPIRI MPOSHI ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | MOKAMBO BORDER DRC SIDE | WHISKEY AWAITING RELEASE | OFFLOADED 28-11-2024 | OFFLOADED 28-11-2024
BA2592 | CAT CB34B UTILITY COMPACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3B400523 | CATCB34BT3B400523 | CYP04308 | 2309DSI2207 | VESSEL: TREASURE Voy. EE316 - ETA DURBAN: 13-10-2023 | COD 2024 319494 | BCG8256ZM | AEB2973ZM / AEB2981ZM | 2309DSI2207 | 13-11-2024 | OFFLOADED 13-12-2024 | 05-11-2024 | 07-11-2024 | BV COMPLETED | 13-10-2023 | 13-11-2024 | 13-11-2024 | 14-11-2024 | GRB 14-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 19-11-2024 | KAZUNGULA ZM 19-11-2024 | KAZUNGULA ZM 20-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 02-12-2024 | 02-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 13-12-2024 | [77 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TOMORROW 07-11-2024 | BV INSPECTION BOOKED FOR TODAY 07-11-2024 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING PLANNED FOR THIS WEEK | LOADING PLANNED FOR TOMORROW | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | GROBLERSBRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | CHOMA ENROUTE NDOLA | LUSAKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | OFFLOADED 13-12-2024
BA2666 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | JZ401525 | CAT00426CJZ401525 | CC208095 | 2401DSI2354 | VESSEL: MSC SHAY Voy. ZF352A - ETA DURBAN: 21-02-2024 | COD 2024 319444 | BCG8256ZM | AEB2973ZM / AEB2981ZM | 2309DSI2207 | 13-11-2024 | OFFLOADED 13-12-2024 | 05-11-2024 | 07-11-2024 | BV COMPLETED | 21-02-2024 | 13-11-2024 | 13-11-2024 | 14-11-2024 | GRB 14-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 19-11-2024 | KAZUNGULA ZM 19-11-2024 | KAZUNGULA ZM 20-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 02-12-2024 | 02-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 13-12-2024 | [77 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TOMORROW 07-11-2024 | BV INSPECTION BOOKED FOR TODAY 07-11-2024 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING PLANNED FOR THIS WEEK | LOADING PLANNED FOR TOMORROW | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | GROBLERSBRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | CHOMA ENROUTE NDOLA | LUSAKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | OFFLOADED 13-12-2024
BA2667 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | JZ401527 | CAT00426AJZ401527 | CC208032 | 2401DSI2354 | VESSEL: MSC SHAY Voy. ZF352A - ETA DURBAN: 21-02-2024 | COD 2024 319444 | BCG8256ZM | AEB2973ZM / AEB2981ZM | 2309DSI2207 | 13-11-2024 | OFFLOADED 13-12-2024 | 05-11-2024 | 07-11-2024 | BV COMPLETED | 21-02-2024 | 13-11-2024 | 13-11-2024 | 14-11-2024 | GRB 14-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 19-11-2024 | KAZUNGULA ZM 19-11-2024 | KAZUNGULA ZM 20-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 02-12-2024 | 02-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 13-12-2024 | [77 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TOMORROW 07-11-2024 | BV INSPECTION BOOKED FOR TODAY 07-11-2024 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING PLANNED FOR THIS WEEK | LOADING PLANNED FOR TOMORROW | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | GROBLERSBRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | CHOMA ENROUTE NDOLA | LUSAKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | OFFLOADED 13-12-2024
BA2809 | CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | EC903851 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 314929 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2810 | CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | EC903848 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 314929 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2811 | CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7C00692 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 312143 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2812 | CAT DE150GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7F00414 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 312095 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2813 | CAT DE150E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GTY01790 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 310321 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2814 | CAT DE150E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GTY01719 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 310236 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2815 | CAT DE150E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | GTY01726 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 310236 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2818 | CAT DE110GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7E00862 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 314950 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2819 | CAT DE65GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | N7300791 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 312087 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2820 | CAT DE165E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | ECW07272 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 311035 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2821 | CAT DE165E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | ECW07809 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 311035 | BCG8131ZM | ACZ3745T / ACZ3734T | 2409DSI2590-1 | 15-11-2024 | OFFLOADED 16-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 20-11-2024 | KAZUNGULA ZM 20-11-2024 | KAZUNGULA ZM 22-11-2024 | 22-11-2024 | 23-11-2024 | 23-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 13-12-2024 | 16-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER TO BE COLLECTED FROM PORT | CONTAINER TO BE UNPACKED TODAY | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | MAZABUKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | ON SITE WAITING TO OFFLOAD - DAY 3 | OFFLOADED 16-12-2024 | OFFLOADED 16-12-2024
BA2816 | CAT DE500E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | LXJ07894 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 310240 | BCE8816ZM | BCD1777ZM | 2409DSI2590-2 | 15-11-2024 | OFFLOADED 17-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 18-11-2024 | KAZUNGULA BW 19-11-2024 | KAZUNGULA ZM 19-11-2024 | KAZUNGULA ZM 20-11-2024 | 22-11-2024 | 25-11-2024 | 25-11-2021 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 16-12-2024 | 17-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER RECEIVED FOR UNPACK | BV INSPECTION TO BE DONE NEXT WEEK | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | LIVINGSTONE ENROUTE KASUMBALESA BORDER | KALOMO ENROUTE KASUMBALESA BORDER | KALOMO ENROUTE KASUMBALESA BORDER | LUSAKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA DISPATCHED FOR KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE - DAY 11 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-12-2024 | OFFLOADED 17-12-2024
BA2817 | CAT DE500E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 2S300213 |  |  | 2409DSI2590 | VESSEL: SPIRIT OF SINGAPORE Voy. 2438S - TRANSHIPMENT VESSEL: AS CARLOTTA Voy 2434E - ETA DURBAN: 04-11-2024 | COD 2024 310240 | BCE8816ZM | BCD1777ZM | 2409DSI2590-2 | 15-11-2024 | OFFLOADED 17-12-2024 | 25-10-2024 | 12-11-2024 | BV COMPLETED | 04-11-2024 | 14-11-2024 | 14-11-20204 | 15-11-2024 | GRB 15-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 18-11-2024 | KAZUNGULA BW 19-11-2024 | KAZUNGULA ZM 19-11-2024 | KAZUNGULA ZM 20-11-2024 | 22-11-2024 | 25-11-2024 | 25-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 01-12-2024 | 01-12-2024 | 05-12-2024 | 05-12-2024 | 16-12-2024 | 17-12-2024 | [63 empty] | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 19-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 22-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 30-10-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 01-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | AWAITING VESSEL ARRIVAL - ETA DURBAN 02-11-2024 | VESSEL DUE TO ARRIVE TODAY 04-11-2024 | VESSEL IN AND WORKING | VESSEL IN AND WORKING | CONTAINER RECEIVED FOR UNPACK | BV INSPECTION TO BE DONE NEXT WEEK | BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TODAY | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERSBRIDE BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KALOMO ENROUTE KASUMBALESA BORDER | KALOMO ENROUTE KASUMBALESA BORDER | LUSAKA ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA DISPATCHED FOR KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 4 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | ON SITE WAITING TO OFFLAOD | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE - DAY 11 | ON SITE WAITING TO OFFLOAD | OFFLOADED 17-12-2024 | OFFLOADED 17-12-2024
BA2750 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | JZ401900 | CAT00426CJZ401900 | CC208449 | 2404DSI2500 | VESSEL: MSC BRIDEPORT Voy. ZF419R - ETA DURBAN: 26-05-2024 | COD 2024 320588 | BCD9084ZM | BCD4878ZM | 2404DSI2500 | 13-11-2024 | OFFLOADED 18-12-2024 | 05-11-2024 | 07-11-2024 | BV COMPLETED | 24-05-2024 | 13-11-2024 | 13-11-2024 | 14-11-2024 | GRB 14-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 18-11-2024 | KAZUNGULA ZM 18-11-2024 | KAZUNGULA BW 20-11-2024 | 20-11-2024 | 20-11-2024 | 21-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 02-12-2024 | 02-12-2024 | 05-12-2024 | 05-12-2024 | 18-12-2024 | 18-12-2024 | [77 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TOMORROW 07-11-2024 | BV INSPECTION BOOKED FOR TODAY 07-11-2024 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING PLANNED FOR THIS WEEK | LOADING PLANNED FOR TOMORROW | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | GROBLERSBRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KALOMO ENROUTE KASUMBALESA BORDER | KABWE ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA DISPATCHED FOR KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | LUBUMBASHI TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADNG | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE - DAY 11 | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE - DAY 12 | ON SITE WAITING TO OFFLOAD | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024
BA2751 | CAT426-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | JZ401901 | CAT00426VJZ401901 | CC208445 | 2404DSI2500 | VESSEL: MSC BRIDEPORT Voy. ZF419R - ETA DURBAN: 26-05-2024 | COD 2024 320588 | BCD9084ZM | BCD4878ZM | 2404DSI2500 | 13-11-2024 | OFFLOADED 18-12-2024 | 05-11-2024 | 07-11-2024 | BV COMPLETED | 24-05-2024 | 13-11-2024 | 13-11-2024 | 14-11-2024 | GRB 14-11-2024 | GRB 17-11-2024 | MARTINS DRIFT 17-11-2024 | MARTINS DRIFT 17-11-2024 | FRANCISTOWN 17-11-2024 | FRANCISTOWN 17-11-2024 | KAZUNGULA BW 17-11-2024 | KAZUNGULA BW 18-11-2024 | KAZUNGULA ZM 18-11-2024 | KAZUNGULA BW 20-11-2024 | 20-11-2024 | 20-11-2024 | 21-11-2024 | 27-11-2024 | 27-11-2024 | 27-11-2024 | 02-12-2024 | 02-12-2024 | 05-12-2024 | 05-12-2024 | 18-12-2024 | 18-12-2024 | [77 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV NUMBER RECEIVED - BV INSPECTION TO BE BOOKED FOR TOMORROW | BV INSPECTION BOOKED FOR TOMORROW 07-11-2024 | BV INSPECTION BOOKED FOR TODAY 07-11-2024 | BV INSPECTION COMPLETED - LOADING NEXT WEEK | BV INSPECTION COMPLETED - LOADING PLANNED FOR THIS WEEK | LOADING PLANNED FOR TOMORROW | LOADING TODAY | LOADED YESTERDAY - DISPATCHING DURBAN TODAY | GROBLERSBRIDGE BORDER CLEARING | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER CLEARING | KALOMO ENROUTE KASUMBALESA BORDER | KABWE ENROUTE NDOLA | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA UNDER ROUTINE MAINTENANCE | NDOLA DISPATCHED FOR KASUMBALESA BORDER | KASUMBALESA ZAM SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE | WHISKEY AWAITING RELEASE - DAY 3 | LUBUMBASHI ENROUTE CONNEX FOR FINAL CLEARANCE | LUBUMBASHI TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADNG | CONNEX LUBUMBAHSI - AWAITING RELEASE | CONNEX LUBUMBAHSI - TO PROCEED TO CONGO EQUIPMENT FOR OFFLOADING | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE - DAY 11 | CONNEX LUBUMBAHSI - STILL AWAITING FINAL CLEARANCE AND RELEASE - DAY 12 | ON SITE WAITING TO OFFLOAD | OFFLOADED 18-12-2024 | OFFLOADED 18-12-2024
BA2555 | CAT745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F606179 | CAT00745E3F606179 | TXW07766 | 2312DSI2346 | VESSEL: BLUE MASTER II Voy. 241203 - ETA DURBAN: 16-02-2024 | COD 2024 343933 | ND681744 | BV08NFZN | MFST002566 | 06-12-2024 | OFFLOADED 26-12-2024 | 03-12-2024 | 05-12-2024 | BV COMPLETED | 16-02-2024 | 09-12-2024 | 10-12-2024 | 11-12-2024 | 11-12-2024 | 12-12-2024 | 12-12-2024 | 13-12-2024 | 14-12-2024 | 16-12-2024 | 16-12-2024 | 18-12-2024 | 18-12-2024 | 20-12-2024 | 20-12-2024 | 21-12-2024 | 22-12-2024 | 23-12-2024 | 23-12-2024 | MOKAMBO 23-12-2024 | MOKAMBO 24-12-2024 | 24-12-2024 | 24-12-2024 | 25-12-204 | 25-12-2024 | 26-12-2024 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | LISENCE RECEIVED - AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR THIS WEEK | BV INSPECTION REQUEST SENT TO BV RSA - AWAITING CONFIRMATION ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING MONDAY | LOADING TODAY | DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE BORDER RSA SIDE | HARARE | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZIM SIDE CLEARING | CHIRUNDU ZAM SIDE CLEARING | DISPATCHING CHIRUNDU TODAY FOR MOKAMBO BORDER | KITWE ENROUTE MOKAMBO BORDER | MOKAMBO ZAMBIA SIDE CLEARING | ON SITE WAITING TO OFFLOAD | OFFLOADED 26-12-2024
BA2706 | CAT D6GC TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | XPC00951 | CAT00D6VXPC00951 | R6J04941 | 2403DSI2456 | VESSEL: AMERICAN HIGHWAY Voy. 212 - ETA DURBAN: 01-04-2024 | COD 2024 343129 | BL64MKZN | ND702944 | ND61090 | 06-12-2024 | OFFLOADED 27-12-2024 | 03-12-2024 | 05-12-2024 | BV COMPLETED | 01-04-2024 | 06-12-2024 | 07-12-2024 | 08-12-2024 | 08-12-2024 | 09-12-2024 | 09-12-2024 | 11-12-2024 | 12-12-2024 | 13-12-2024 | 13-12-2024 | 14-12-2024 | 14-12-2024 | 14-12-2024 | 14-12-2024 | 15-12-2024 | 15-12-2024 | 16-12-2024 | 16-12-2024 | 16-12-2024 | 18-12-2024 | 19-12-2024 | 21-12-2024 | 21-12-2024 | 27-12-2024 | 27-12-2024 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | LISENCE RECEIVED - AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR THIS WEEK | BV INSPECTION REQUEST SENT TO BV RSA - AWAITING CONFIRMATION ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADED 05-12-2024 - DISPATCHED DURBAN ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | NGUNDU ENROUTE HARARE | MVUMA ENROUTE HARARE | CHINGOLA ENROUTE KASUMBALESA | KASUMBALESA ZAMBIAN SIDE CLEARING | KASUMBALESA DRC SIDE CLEARING | WHISKEY AWAITING RELEASE - DAY 1 | WHISKEY AWAITING RELEASE - DAY 2 | CONNEX LUBUMBAHSI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBAHSI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBAHSI AWAITING FINAL CLEARANCE AND RELEASE - DAY 4 | OFFLOADED 27-12-2024
BA2675 | CAT428-07A BACKHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMNET | L7D01758 | CAT00428CL7D01758 | C4Z14587 | 2402DSI2395 | VESSEL: HOEGH TOKYO Voy. 111 - ETA DURBAN: 03-03-2024 | COD 2024 343925 | SRL32 ZM | ACP7021T | 2402DSI2395 | 06-12-2024 | OFFLOADED 06-01-2025 | 03-12-2024 | 05-12-2024 | BV COMPLETED | 03-03-2024 | 11-12-2024 | 11-12-2024 | 12-12-2024 | GRB 12-12-2024 | GRB 15-12-2024 | MARTINS DRIFT 15-12-2024 | MARTINS DRIFT 16-12-2024 | FRANCISTOWN 16-12-2024 | FRANCISTOWN 16-12-2024 | KAZUNGULA BW 16-12-2024 | KAZUNGULA BW 17-12-2024 | KAZUNGULA ZM 17-12-2024 | KAZUNGULA ZM 18-12-2024 | 19-12-2024 | 19-12-2024 | 19-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 25-12-2024 | 25-12-2024 | 28-12-2024 | 28-12-2024 | 03-01-2025 | 06-01-2025 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | LISENCE RECEIVED - AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR THIS WEEK | BV INSPECTION REQUEST SENT TO BV RSA - AWAITING CONFIRMATION ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING MONDAY | BV INSPECTION DONE - LOADING TOMORROW | LOADING TODAY | DISPATCHING DURBAN TODAY | JOHANNESBURG ENROUTE GROBLERS BRIDGE BORDER | MARTINS DRIFT BORDER TO DISPATCH FOR KAZUNGULA BORDER | KAZUNGULA BORDER CLEARING | KAZUNGULA BORDER ZAM SIDE AWAITING RELEASE | KAPIRI ENROUTE KASUMBALESA | NDOLA | CHILILABOMBWE ENROUTE KASUMBALESA | KASUMBALESA ZAM SIDE, WAITING TO CROSS TO DRC SIDE | WHISKEY AWAITING RELEASE | LUBUMBASHI ENROUTE SITE | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 5 - PLEASE ASSIST | CONGO EQUIPMENT - WAITING TO OFFLOAD | CONGO EQUIPMENT - WAITING TO OFFLOAD - DAY 4 | OFFLOADED 06-01-2025
BA2573 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F805337 | CAT00740P3F805337 | TXY07967 | 2312DSI2348 | VESSEL: BLUE MASTER II Voy. 241203 - ETA DURBAN: 16-02-2024 | COD 2024 349143 | BC01ZHZN - PH217 | BW88SYZN | MFST002581 | 12-12-2024 | OFFLOADED 08-01-2025 | 09-12-2024 | 11-12-2024 | BV COMPLETED | 16-02-2024 | 12-12-2024 | 12-12-20204 | 17-12-2024 | 17-12-2024 | 17-12-2024 | 17-12-2024 | 20-12-2024 | 21-12-2024 | 23-12-2024 | 24-12-2024 | 24-12-2024 | 24-12-2024 | 25-12-2024 | 27-12-2024 | 28-12-2024 | 28-12-2024 | 29-12-2024 | 29-12-2024 | MOKAMBO 29-12-2024 | MOKAMBO 31-12-2024 | 31-12-2024 | 31-12-2024 | 01-01-2025 | 07-01-2025 | 08-01-2025 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW | BV INSPECTION TO BE DONE TODAY | MOOI RIVER ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG - TO DISPATCH ON TUESDAY DUE TO ROAD EMBARGO THAT STARTED FOR THE LONG WEEKEND | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | HARARE ENROUTE CHIRUNDU BORDER | HURUNGWE ENROUTE CHIRUDNU BORDER | KAFUE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | CONNEX LUBUMBASHI AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 5 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 08-01-2025
BA2575 | CAT740GC-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMNET | 3F805333 | CAT00740H3F805333 | TXY07956 | 2312DSI2341 | VESSEL: BLUE MASTER II Voy. 241203 - ETA DURBAN: 16-02-2024 | COD 2024 349143 | BJ30DXZN - PH223 | ND650731 | MFST002580 | 12-12-2024 | OFFLOADED 08-01-2025 | 09-12-2024 | 11-12-2024 | BV COMPLETED | 16-02-2024 | 12-12-2024 | 12-12-2024 | 17-12-2024 | 17-12-2024 | 17-12-2024 | 17-12-2024 | 20-12-2024 | 21-12-2024 | 23-12-2024 | 24-12-2024 | 24-12-2024 | 24-12-2024 | 25-12-2024 | 27-12-2024 | 28-12-2024 | 28-12-2024 | 29-12-2024 | 29-12-2024 | MOKAMBO 29-12-2024 | MOKAMBO 31-12-2024 | 31-12-2024 | 31-12-2024 | 01-01-2025 | 07-01-2025 | 08-01-2025 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | BV INSPECTION BOOKED FOR TOMORROW | BV INSPECTION TO BE DONE TODAY | MOOI RIVER ENROUTE BEIT BRIDGE BORDER | JOHANNESBURG - TO DISPATCH ON TUESDAY DUE TO ROAD EMBARGO THAT STARTED FOR THE LONG WEEKEND | DISPATCHED JOHANNESBURG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | HARARE ENROUTE CHIRUNDU BORDER | HURUNGWE ENROUTE CHIRUDNU BORDER | KAFUE ENROUTE MOKAMBO BORDER | MOKAMBO BORDER CLEARING | CONNEX LUBUMBASHI AWAITING RELEASE | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 2 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 5 | CONNEX LUBUMBASHI AWAITING RELEASE - DAY 6 | ON SITE WAITING TO OFFLOAD | OFFLOADED 08-01-2025
BA2677 | CAT D6GC TRACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMNET | XPC00941 | CAT000D6EXPC00941 | R6J04937 | 2402DSI2386 | VESSEL: BALTIMORE HIGHWAY Voy. 148A - ETA DURBAN: 28-02-2024 | COD 2024 343129 | ND61605 | ND868372 | ND61089 | 06-12-2024 | OFFLOADED 16-01-2025 | 03-12-2024 | 05-12-2024 | BV COMPLETED | 28-02-2024 | 16-12-2024 | 17-12-2024 | 18-12-2024 | 18-12-2024 | 18-12-2024 | 18-12-2024 | 23-12-2024 | 23-12-2024 | 23-12-2024 | 24-12-2024 | 26-12-2024 | 26-12-2024 | 01-01-2025 | 01-01-2025 | 01-01-2025 | 01-01-2025 | 03-01-2025 | 03-01-2025 | 03-01-2025 | 08-01-2025 | 08-01-2025 | 11-01-2025 | 11-01-2025 | 15-01-2025 | 16-01-2025 | [102 empty] | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | AWAITING BV NUMBER | LISENCE RECEIVED - AWAITING BV NUMBER | BV NUMBER RECEIVED - INSPECTION TO BE BOOKED FOR THIS WEEK | BV INSPECTION REQUEST SENT TO BV RSA - AWAITING CONFIRMATION ON INSPECTION DATE | BV INSPECTION BOOKED FOR TODAY | BV INSPECTION DONE - LOADING NEXT WEEK | BV INSPECTION DONE - LOADING THIS WEEK - DATE TO BE CONFIMRED | BV INSPECTION DONE - LOADING THIS WEEK - DATE TO BE CONFIMRED | LOADING TOMORROW 12-11-2024 | LOADING TODAY | LOADED - TO DISPATCH ON TUESDAY DUE TO ROAD EMBARGO THAT STARTED FOR THE LONG WEEKEND | VAN REENEN ENROUTE JOHANNESBURG | HEIDELBERG ENROUTE BEIT BRIDGE BORDER | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE RSA SIDE CLEARING | BEIT BRIDGE ZIM SIDE TO DISPATCH FOR HARARE | CHIRUNDU ZIM SIDE CLEARING | DISPATCHING CHIRUNDU ZAMBIA | CHIRUNDU ZAMBIA - AWATIING PERMITS BEFORE DISPATCHING | KAPIRI MPOSHE ENROUTE KASUMBALESA BORDER | NDOLA ENROUTE KASUMBALESA BORDER | KASUMBALESA BORDER ZAM SIDE | KASUMBALESA BORDER DRC SIDE AWAITING RELEASE | KASUMBALESA BORDER DRC SIDE AWAITING RELEASE - DAY 2 | WHISKEY AWAITING RELEASE - DAY 1 | DISPATCHING WHISHEY TODAY | CONNEX LUBUMBAHSI AWAITING FINAL CLEARANCE AND RELEASE | CONNEX LUBUMBAHSI AWAITING FINAL CLEARANCE AND RELEASE - DAY 2 | CONNEX LUBUMBAHSI AWAITING FINAL CLEARANCE AND RELEASE - DAY 3 | ON SITE WAITING TO OFFLOAD | OFFLOADED 16-01-2025

## 1 X H150 PUMP SET - BA1759 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | OFFLOADED | COMMENTS 26.10.2021 | COMMENTS 27.10.2021 | COMMENTS 29.10.2021 | COMMENTS 02.11.2021 | COMMENTS 03.11.2021 | COMMENTS 04.11.2021 | COMMENTS 05.11.2021 | COMMENTS 08.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 06.12.2021 | COMMENTS 07.12.2021 | COMMENTS 08.12.2021 | COMMENTS 09.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 22.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1759 | 1 X 40FT CONTAINER STC 1 X H150 PUMP SET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | XH150-PR-0013 | N/A | FML2112DSI1357 | COD 2021 340 190 | AJB9959 | N/A | ZP071091 | 20.01.2022 | * VEHICLE DISPATCHED KASUMBALES THIS MORNING ENROUTE WHISKEY | 07.01.2022 | 11.01.2022 | 12.01.2022 | 13.01.2022 | 14.01.2022 | 15.01.2022 | 16.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 25.01.2022 | 26.01.2022 |  |  |  | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 09/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 30/11/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07/12/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07/12/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 07/12/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04/12/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04/12/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04/12/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04/12/2021 | AWAIITNG VESSEL EX JEAN MERMOZ TO ARRIVE DURBAN PORT-ETA 04/12/2021 | * PUMPSET TO BE LOADED 05.12.2021 - VESSEL ETD 12.12.2021 | * PUMPSET TO BE LOADED 05.12.2021 - VESSEL ETD 12.12.2021 | * PUMPSET TO BE LOADED 05.12.2021 - VESSEL ETD 12.12.2021 | * PUMPSET TO BE LOADED 08.12.2021 - VESSEL ETD 12.12.2021 | * PUMPSET TO BE LOADED 08.12.2021 - VESSEL ETD 12.12.2021 | * CONTAINER IS LOADED - VESSEL ETD 12.12.2021 | * CONTAINER IS LOADED - VESSEL ETD 12.12.2021 | * CONTAINER IS LOADED - VESSEL ETD 12.12.2021 | * CONTAINER LOADED - AWAITING VESSEL DISPATCH | * VESSEL SAILED 11.12.2021 - CURRENT ETA 29.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 29.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 29.12.2021 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 07.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 07.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 07.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 07.01.2022 | * VESSEL SAILED 11.12.2021 - CURRENT ETA 06.01.2022-AWAITING VESSEL TO BERTH | * AWAITING VESSEL DISCHARGE IN ORDER TO COLLECT THE CONTAINER | * UNIT IN BONDED FACILITY. BV INSPECTION TO BE BOOKED FOR TOMORROW 11.01.2022 | * BV INSPECTION COMPLETE - VEHICLE TO DISPATCH FOR POLOKWANE THIS MORNING | * VEHICLE CURRENLTY AT JOHANNESBURG ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT MOKOPANE EN-ROUTE TO GROBLERS BRIDGE | * VEHICLE CURRENLTY AT GROBLERS BRIDGE AWAITING FINAL RELEASE | * VEHICLE CURRENLTY AT LUSAKA EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KITWE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE DISPATCHED KASUMBALES THIS MORNING ENROUTE WHISKEY

## 1 X CAT 307 - BA1792 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 02.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1792 | 1 X CAT 307 EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | ZGC03002 | CAT00307HZGC03002 | TBA | FML2112DSI1362 | COD 2021 351 497 | ABJ9958 | N/A | ZP071092 | 20.01.2022 | * VEHICLE DISPATCHED KASUMBALES THIS MORNING ENROUTE WHISKEY | 04.01.2022 | 13.01.2022 | 14.01.2022 | 14.01.2022 | 15.01.2022 | 16.01.2022 | 16.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2022 | 26.01.2022 |  |  |  |  | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL LIBERTY ACE TO ARRIVE ON THE 08.01.2022 | * AWAITING VESSEL GENUINE ACE TO ARRIVE ON THE 29.12.2021 | * AWAITING VESSEL GENUINE ACE TO ARRIVE ON THE 29.12.2021 | * AWAITING VESSEL GENUINE ACE TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL GENUINE ACE TO ARRIVE ON THE 04.01.2022 | *MACHINE AT OUR FACILITY AWAITING BV LICENCE TO BE VALIDATED | *MACHINE AT OUR FACILITY AWAITING BV LICENCE TO BE VALIDATED IN ORDER TO BOOK BV INSPECTION | *MACHINE AT OUR FACILITY AWAITING BV LICENCE TO BE VALIDATED IN ORDER TO BOOK BV INSPECTION | *MACHINE AT OUR FACILITY AWAITING BV LICENSE TO BE VALIDATED IN ORDER TO BOOK BV INSPECTION | *MACHINE AT OUR FACILITY AWAITING BV LICENSE TO BE VALIDATED IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION BOOKED FOR TODAY | * TRUCK DISPATCHED EN-ROUTE TO JOHANNESBURG | * TRUCK AT JOHANNESBURG EN-ROUTE TO GROBLERS BRIDGE | * VEHICLE CURRENLTY AT LIVINGSTONE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KABWE EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE AWAITING T1 AND TR8 | * VEHICLE DISPATCHED KASUMBALES THIS MORNING ENROUTE WHISKEY

## 1 X CAT 336-BA1898 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 11.11.2021 | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 07.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 21.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022
BA1898 | 1 X NEW CAT 336 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12108 | CAT00336TGDY12108 | NTB05475 | FML2111DSI1325 | COD 2021 340189 | ND834401 | ND854241 | ND60200 | 17.12.2021 | * OFFLOADED 24.01.2022 | 12.12.2021 | 06.01.2022 | 08.01.2022 | 10.01.2022 | 13.01.2022 | 14.01.2022 | 15.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2022 | 20.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 24.01.2022 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 10/12/2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 12/12/2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * BV INSPECTION BOOKED FOR FRIDAY 17.12.2021 | * BV INSPECTION BOOKED FOR TODAY 17.01.2021 | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * TRUCK TO DISPATCH TOMORROW THE 06/01/2022 | * TRUCK AT HOWICK EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT MASVINGO EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT SIAVONGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITNG RELEASE | * VEHILCE ON SITE WAITING TO OFFLIOAD | * OFFLOADED 24.01.2022

## 1 X CAT CS74B-BA1862 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | KAMOA SITE | OFFLOADED | COMMENTS 12.11.2021 | COMMENTS 15.11.2021 | COMMENTS 16.11.2021 | COMMENTS 17.11.2021 | COMMENTS 18.11.2021 | COMMENTS 24.11.2021 | COMMENTS 25.11.2021 | COMMENTS 26.11.2021 | COMMENTS 29.11.2021 | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 03.12.2021 | COMMENTS 07.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 21.12.2021 | COMMENTS 22.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 03.01.2022 | COMMENTS 04.01.2022 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 20.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022
BA1862 | 1 X NEW CAT CS74B VIBRATORY COMPACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | B7M00373 | CATCS74BJB7M00373 | E7A47739 | FML2111DSI1324 | COD 2021 360 144 | JR76FMGP | KH82PCGP | ND60722 | 13.12.2021 | * OFFLOADED 24.01.2022 | 12.12.2021 | 22.12.2021 | 23.12.2021 | 24.12.2021 | 27.12.2021 | 28.12.2021 | 30.12.2022 | 02.01.2022 | 03.01.2022 | 04.01.2022 | 05.01.2022 | 09.01.2022 | 10.01.2022 | 18.01.2022 | 18.01.2022 | 21.01.2022 | 24.01.2022 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * AWAITING FINAL INVOICES-VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 06/12/2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 10/12/2021 | * VESSEL GLOVIS SPLENDOR DUE TO ARRIVE ON THE 12/12/2021 | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENLTY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY - AWAIITNG BV NUMBER TO BOOK BV INSPECTION | * UNIT IN BONDED FACILITY - AWAIITNG BV NUMBER TO BOOK BV INSPECTION | * TRUCK TO DISPATCH TODAY-EN-ROUTE TO BEITBRIDGE | * TRUCK AT JOHANNEBSURG AWAITING DISPATCH | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE DISPATCHED HARARE ENROUTE CHIRUNDU | * VEHICLE AT KAFUE EN-ROUTE TO KASUMBALESA | * VEHICLE AT NDOLA EN-ROUTE TO KASUMBALESA | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE KASUMBALESA ZAM SIDE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE BY BOLLORE | * VEHICLE CURRENTLY AT WHISKEY AWAITING CLEARANCE BY BOLLORE FOR THE HANDRAIL DAY 4 | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY ON SITE AWAITING TO OFFLOAD | * VEHICLE CURRENTLY AT LIKASI EN-ROUTE TO SITE | * VEHICLE CURRENTLY AT KOLWEZI EN-ROUTE TO SITE | OFFLOADED 21/01/2022 | * ON SITE WAITING TO OFFLOAD | * OFFLOADED 24.01.2022

## 2 X CAT 745 - BA1730-1731 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 02.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 17.12.2021 | COMMENTS 20.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 24.01.2022
BA1730 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMENT | 3F601870 | CAT00745L3F601870 | TXW06293 | 2111DSI1349 | COD 2021 360996 | ND754967 | ND654346/ND526680 | ND60719 | 04.01.2022 | * OFFLOADED 24.01.2022 | 20.12.2021 | 06.01.2022 | 08.01.2022 | 10.01.2022 | 13.01.2022 | 14.01.2022 | 15.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2022 | 20.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 24.01.2022 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * COLLECTING MACHINE FROM PORT TODAY THE 20.12.2021 | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * TRUCK TO DISPATCH TOMORROW THE 06/01/2022 | * TRUCK AT HOWICK EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT MASVINGO EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT SIAVONGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITNG RELEASE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 24.01.2022
BA1731 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMENT | 3F601872 | CAT00745E3F601872 | TXW06279 | 2111DSI1350 | COD 2021 360996 | ND730794 | ND443606 | ND60720 | 04.01.2022 | * OFFLOADED 24.01.2022 | 20.12.2021 | 06.01.2022 | 08.01.2022 | 10.01.2022 | 13.01.2022 | 14.01.2022 | 15.01.2022 | 17.01.2022 | 18.01.2022 | 18.01.2022 | 19.01.2022 | 20.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 24.01.2022 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 15.12.2021 | * AWAITING VESSEL TORINO TO ARRIVE ON THE 18.12.2021 | * COLLECTING MACHINE FROM PORT TODAY THE 20.12.2021 | * VEHICLE IS AT OUR FACILITY AND TRUCK TO DISPATCH IN THE NEW YEAR DUE TO PERMIT OFFICE CLOSER | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * BV DONE TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * TRUCK TO DISPATCH TOMORROW THE 06/01/2022 | * TRUCK AT HOWICK EN-ROUTE TO BEITBRIDGE BORDER | * TRUCK AT MIDDELBURG EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT MASVINGO EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT HARARE EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT SIAVONGO EN-ROUTE TO CHIRUNDU | * VEHICLE CURRENLTY AT KAPIRI EN-ROUTE TO KASUMBALESA | * VEHICLE CURRENLTY AT KASUMBALESA ZAM SIDE | * VEHICLE CURRENLTY AT KASUMBALESA DRC SIDE | * VEHICLE CURRENLTY AT WHISKEY AWAITNG RELEASE | * VEHICLE ON SITE WAITING TO OFFLOAD | * OFFLOADED 24.01.2022

## 1 X CAT 745-BA1698 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 04.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1698 | 1 X CAT 745-04A ARTICULATED TRUCK | BARTRAC EQUIPMENT / CONGO EQUIPMENT | 3F6018 | CAT00745P3F601875 | NR80037 | FML2111DSI1359 | COD 2021 364 155 | ND705348 | ND476150 | ND60726 | 07.01.2022 | * VEHICLE CURRENTLY AT KASUMBLAESA DRC SIDE AWAITING CLEARANCE | 28.01.2022 | 10.01.2022 | 12.01.2022 | 15.01.2022 | 17.01.2022 | 18.01.2022 | 21.01.2022 | 22.01.2022 | 23.01.2022 | 23.01.2022 | 24.01.2022 | [5 empty] | * AWAITING VESSEL TITUS TO ARRIVE ON THE 22.12.2021 | * AWAITING VESSEL TITUS TO ARRIVE ON THE 22.12.2021 | * AWAITING VESSEL TITUS TO ARRIVE ON THE 22.12.2021 | * AWAITING VESSEL TITUS TO ARRIVE ON THE 22.12.2021 | * AWAITING VESSEL TITUS TO ARRIVE ON THE 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * UNIT IN BONDED FACILITY - TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * UNIT IN BONDED FACILITY - TRUCK TO DISPATCH IN THE NEW YEAR DUE TO CLOSURE OF PERMIT OFFICE. | * AWAITING BV TO BE DONE,PLANNING TO DISPATCH THE TRUCK UPON RECEIVAL OF ABNORMAL PERMIT ON THE 05/01/2022 | * TRUCK TO DISPATCH MONDAY THE 10/01/2022 | * VEHICLE CURRENLTY AT MOOI RIVER ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT HARRISMITH ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT WARDEN ENROUTE POLOKWANE | * VEHICLE CURRENLTY AT MARBLE HALL EN ROUTE POLOKWANE | * VEHICLE CURRENLTY AT DENDRON EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE RSA SIDE AWAITING CUSTOM FORMALITIES | * VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE AWAITING RELEASE | * VEHICLE CURRENLTY AT BEITBRIDGE ZIM SIDE TO DISPATCH TODAY | * VEHICLE CURRENLTY AT CHEGUTU EN-ROUTE TO HARARE | * VEHICLE CURRENLTY AT CHIRUNDU ZAM SIDE | * VEHICLE CURRENTLY AT KASUMBLAESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBLAESA ZAM SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT KASUMBLAESA DRC SIDE AWAITING CLEARANCE

## 1 X CAT 140GC-BA1839 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 24.12.2021 | COMMENTS 24.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 04.01.2022 | COMMENTS 05.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 12.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1839 | 1 X CAT 140GC 01A MOTOR GRADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | W9201005 | CAT00140LW9201005 | E7A48161 | 2112DSI1365 | COD 2021 367 761 | ND66858 | ND700343 | ND60735 | 06.01.2022 | * VEHICLE ON SITE WAITING TO OFFLOAD | 30.12.2021 | 06.01.2022 | 08.01.2022 | 10.01.2022 | 11.01.2022 | 12.01.2022 | 13.01.2022 | 14.01.2022 | 15.01.2022 | 16.01.2022 | 18.01.2022 | 20.01.2022 | 21.01.2022 | 26.01.2022 | 26.01.2022 |  | * AWAITING VESSEL MORNING COURIER 155 TO ARRIVE ON THE 29.12.2021 | * AWAITING VESSEL MORNING COURIER 155 TO ARRIVE ON THE 29.12.2021 | * AWAITING VESSEL MORNING COURIER 155 TO ARRIVE ON THE 30.12.2021 | * AWAITING VESSEL MORNING COURIER 155 TO ARRIVE ON THE 30.12.2021 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD | BV BOOKED FOR TODAY, AWAITING DISPATCH | TRUCK TO DISPATCH TOMMROW THE 06/01/2022 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK AT MOOIRIVER EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEANCE | * VEHICLE CURRENTLY AT HARARE ENROUTE CHIRUNDU | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE UNDERGOING CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT CHIRUNDU ZIM SIDE UNDERGOING CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT KITWE EN-ROUTE KASUMBALESA | * VEHICLE CURRENTLY AT KASUMBALESA ZAM SIDE AWAITNG CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITNG CUSTOM FORMALITIES | * VEHICLE CURRENTLY AT KASUMBALESA DRC SIDE AWAITNG RELEASE DAY 2 | * VEHICLE CURRENTLY AT WHISKEY AWAITING RELEASE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE CURRENLTY AT WHISKEY AWAITING CLEARANCE | * VEHICLE ON SITE WAITING TO OFFLOAD

## 14 X GENSETS - BA1909-1922 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PART NUMBER | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 03.01.2022 | COMMENTS 05.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 13.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1909 | 1 X CAT DE550 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | CE500290 H5G01381 LWL03769 | 4895092 4662629 5029783 | CAT00C15PCE500290 | FML2112DSI1354 | TBA | TBA | TBA | TBA | TBA | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION
BA1910 | 1 X CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A00106 E3S09672 N7H00196 | 6052967 5010890 5992354 | CAT0DE33JN7A00106 | FML2112DSI1354 | COD 2021 901 728 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1911 | 1 X CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A00111 E3S09728 N7H00192 | 6052967 5010890 5992354 | CAT0DE33VN7A00111 | FML2112DSI1354 | COD 2021 901 728 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1912 | 1 X CAT DE33GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7A00109 E3S09719 N7H00199 | 6052967 5010890 5992354 | CAT0DE33AN7A00109 | FML2112DSI1354 | COD 2021 901 728 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1913 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7200105 E3S09747 N7H00216 | 6052972 5011555 5992356 | CAT0DE55PN7200105 | FML2112DSI1354 | TBA | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1914 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7200100 E3S09576 N7H00215 | 6052972 5011555 5992356 | CAT0DE55LN7200100 | FML2112DSI1354 | TBA | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1915 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7200114 E3S10353 N7H00826 | 6052972 5011555 5992356 | CAT0DE55LN7200114 | FML2112DSI1354 | TBA | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1916 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7200101 E3S09626 N7H00214 | 6052972 5011555 5992356 | CAT0DE55HN7200101 | FML2112DSI1354 | TBA | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1917 | 1 X CAT DE55GC GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | N7200104 E3S09749 N7H00217 | 6052972 5011555 5992356 | CAT0DE55TN7200104 | FML2112DSI1354 | TBA | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1918 | 1 X CAT DE22E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GBY11771 SM811725 TT902479 | 4512485 4489035 5849908 | CAT00C22AGBY11771 | FML2112DSI1354 | TBA | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | 27.12.2021 | [15 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE - WAITING BV TO BE DONE ON BA1909 IN ORDER TO DISPATCH (CO-LOAD)
BA1919 | 1 X CAT DE22E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GBY11772 SM811721 TT902486 | 4512485 4489035 5849908 | CAT00C22LGBY11772 | FML2112DSI1354 | COD 2021 901 729 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 27.12.2021 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1920 | 1 X CAT DE22EO GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GBY11830 SM811809 TT902531 | 4512485 4489035 5849908 | CAT00C22PGBY11830 | FML2112DSI1354 | COD 2021 901 729 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 27.12.2021 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1921 | 1 X CAT DE22EO GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GBY11828 SM811817 TT902518 | 4512485 4489035 5849908 | CAT00C22KGBY11828 | FML2112DSI1354 | COD 2021 901 729 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 27.12.2021 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1922 | 1 X CAT DE22EO GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | FML2112DSI1354 | COD 2021 901 729 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 27.12.2021 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - MSC VITA NZ145A - CURRENT ETA 24.12.2021 | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * VESSEL CURRENTLY WORKING - VEHICLES PLACED ALONGSIDE TO LOAD | * COLLECTING CONTAINERS FROM PORT TODAY, BV BOOKED FOR 05.01.2022 | * CONTAINER AT OUR FACILITY, AWAITING UNPACK AND BV INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | * UNITS ARE AT OUR FACILITY AWAITING BV NUMBERS TO BOOK INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | BV NUMBER RECEIVED AND NOT VALIDATED AWAITING BV VALIDATION IN ORDER TO BOOK BV INSPECTION | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE

## 7 X GENSETS - BA1820-1825-1830 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PART NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 30.11.2021 | COMMENTS 01.12.2021 | COMMENTS 02.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 04.01.2022 | COMMENTS 06.01.2022 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1820 | 1 X CAT D13.5E3 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GB903931 W2203899 TT904820 | 4512481 4488966 5849904 | N/A | FML2111DSI1351 | COD 2021 365 065 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 06.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING, AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18/01/2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1821 | 1 X CAT D13.5E3 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GB903930 W2203900 TT904819 | 4512481 4488966 5849904 | N/A | FML2111DSI1351 | COD 2021 365 065 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 06.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING, AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18/01/2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1822 | 1 X CAT D13.5E3 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GB903929 W2203901 TT904821 | 4512481 4488966 5849904 | N/A | FML2111DSI1351 | COD 2021 365 065 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 06.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING, AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18/01/2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1823 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GBY12582 SM812755 TT800314 | 4512485 4489035 5849908 | N/A | FML2111DSI1351 | COD 2021 366 245 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 06.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING, AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18/01/2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1824 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GBY12581 SM812756 TT800315 | 4512485 4489035 5849908 | N/A | FML2111DSI1351 | COD 2021 366 245 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 06.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING, AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18/01/2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1825 | 1 X CAT DE22E3 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GBY12580 SM812754 TT800299 | 4512485 4489035 5849908 | N/A | FML2111DSI1351 | COD 2021 366 245 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 06.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING, AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18/01/2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE
BA1830 | 1 X CAT C13 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | DH403696 PWE05873 LWL04851 | 4215066 3932805 5029779 | N/A | FML2111DSI1351 | COD 2021 351 494 | AEZ5599 | AEG7122 | AEG7106 | 21.01.2022 | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE | 06.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | 26.01.2022 | 26.01.2022 | [9 empty] | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 20.12.2021 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * AWAIITNG VESSEL ARRIVAL - CMA CGM PUGET - CURRENT ETA 04.01.2022 | * VESSEL IS IN AND WORKING, AWAITING TO COLLECT CONTAINER FROM THE PORT | * COLLECTING CONTAINER FROM THE PORT TODAY | * UNIT IN OUR BONDED FACILITY - BV INSPECTION TO BE BOOKED FOR 11.01.2021 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE. VEHICLE PLANNING TO DISPATCH THIS WEEK | BV COMPLETE AND TRUCK TO DISPATCH TEUSDAY THE 18/01/2022 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK TEUSDAY THE 18/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | BV COMPLETE AND PLANNING TO DISPATCH THE TRUCK WEDNESDAY THE 19/01/2022 UPON RECEIVAL OF BV NUMBER FOR BA1909-BA1922 | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | TRUCK TO DISPATCH TODAY EN-ROUTE TO BEITBRIDGE BORDER | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENTLY AT CHIRUNDU ZAM SIDE AWAITING CLEARANCE

## 4 X C15 - BA1934-36-39-41 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 02.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 13.01.2022 | COMMENTS 17.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1934 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | CAT00C15LLXJ06530 | N/A | N/A | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | [16 empty] | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022
BA1936 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | CAT00C15LLXJ06534 | N/A | N/A | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | [16 empty] | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022
BA1939 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | CAT00C15LLXJ06529 | N/A | N/A | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | [16 empty] | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022
BA1941 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | CAT00C15LLXJ06535 | N/A | N/A | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | [16 empty] | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 04.01.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 01.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022 | * AWAITING VESSEL APL PUSAN TO ARRIVE ON THE 14.02.2022

## 4 X C15 - BA1935-37-40-42 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | PART NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 02.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 31.12.2021 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 20.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1935 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FTH15978 LXJ06507 F6B11004 | CAT00C15CLXJ06507 | 4607411 5854458 5500728 | FML2112DSI1379 | COD 2021 361369 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948, BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | 14.01.2022 | [15 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER FROM THE PORT AS WELL AS BV LICENCE NUMBER | LOADING THE CONTAINER FROM THE PORT,AWAITING BV LICENCE NUMBER TO BOOK INSPECTION | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR TUESDAY 25 JAN 2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948, BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD)
BA1937 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FTH15897 LXJ06505 F6B10998 | CAT00C15KLXJ06505 | 4607411 5854458 5500728 | FML2112DSI1369 | COD 2021 361369 | AFJ2620 | AEG2860 / AEG2852 | ND60754 | 25.01.2022 | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | 14.01.2022 | 26.01.2022 | [14 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER FROM THE PORT AS WELL AS BV LICENCE NUMBER | LOADING THE CONTAINER FROM THE PORT,AWAITING BV LICENCE NUMBER TO BOOK INSPECTION | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR TUESDAY 25 JAN 2022 | * BV INSPECTION BOOKED FOR TODAY | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE
BA1940 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FTH15891 LXJ06508 F6B11006 | CAT00C15VLXJ06508 | 4607411 5854458 5500728 | FML2112DSI1379 | COD 2021 361369 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948, BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD) | 14.01.2022 | [15 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER FROM THE PORT AS WELL AS BV LICENCE NUMBER | LOADING THE CONTAINER FROM THE PORT,AWAITING BV LICENCE NUMBER TO BOOK INSPECTION | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR TUESDAY 25 JAN 2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1948, BA1949 & BA1950 TO ARRANGE FOR INSPETION & DISPATCH (CO-LOAD)
BA1942 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FTH15940 LXJ06506 F6B11000 | CAT00C15JLXJ06506 | 4607411 5854458 5500728 | FML2112DSI1369 | COD 2021 361369 | AFJ2620 | AEG2860 / AEG2852 | ND60754 | 25.01.2022 | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | 14.01.2022 | 26.01.2022 | [14 empty] | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 07.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | * AWAITING VESSEL DAPHNE TO ARRIVE - ETA 16.01.2022 | VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER FROM THE PORT AS WELL AS BV LICENCE NUMBER | LOADING THE CONTAINER FROM THE PORT,AWAITING BV LICENCE NUMBER TO BOOK INSPECTION | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | VESSEL IS IN AND WORKING, AWAITNG TO LOAD THE CONTAINER FROM PORT ONCE AVAILABLE. AWAITING BV NUMBER | * BV INSPECTION BOOKED FOR TUESDAY 25 JAN 2022 | * BV INSPECTION BOOKED FOR TODAY | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE

## 4 X C15 BA1931-32-33-38 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | PART NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 02.12.2021 | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 13.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 24.01.2022 | COMMENTS 26.01.2022
BA1931 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FTH15964 LXJ06502 P6B11005 | CAT00C15CLXJ06502 | 4607411 5854458 5500728 | FML2112DSI1361 | COD 2021 361369 | AFJ2620 | AEG2860 / AEG2852 | ND60754 | 25.01.2022 | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE | 11.01.2022 | 26.01.2022 | [14 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | COLLECTING CONTAINER FROM PORT TODAY, AWAITING BV NUMBER | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * BV INSPECTION COMPLETE, WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * BV INSPECTION COMPLETE, WAITING FOR BV ON BA1937 & BA1942 ON TUESDAY 25 JAN 2022 BEFORE DISPATCH (CO-LOAD) | * VEHICLE CURRENTLY AT HOWICK ENROUTE POLOKWANE
BA1932 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FTH15894 LXJ06503 F6B11002 | CAT00C15TLXJ06503 | 4607411 5854458 5500728 | FML2112DSI1360 | COD 2021 361369 | AEU7881 | AEG7120 | AEG7080 | 22.01.2022 | * VEHICLE CURRENLTY AT KAROI ENROUTE HARARE | 11.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | [11 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | COLLECTING CONTAINER FROM PORT TODAY, AWAITING BV NUMBER | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | LOADING CARGO TODAY AND TRUCK WILL DISPATCH ONCE DONE LOADING | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KAROI ENROUTE HARARE
BA1933 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FTH15873 LXJ06501 F6B11001 | CAT00C15ELXJ06501 | 4607411 5854458 5500728 | FML2112DSI1361 | COD 2021 361369 | AEU7881 | AEG7120 | AEG7080 | 22.01.2022 | * VEHICLE CURRENLTY AT KAROI ENROUTE HARARE | 11.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | [11 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | COLLECTING CONTAINER FROM PORT TODAY, AWAITING BV NUMBER | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | LOADING CARGO TODAY AND TRUCK WILL DISPATCH ONCE DONE LOADING | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KAROI ENROUTE HARARE
BA1938 | 1 X CAT C15 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | FTH15979 LXJ06504 F6B10999 | CAT00C15PLXJ06504 | 4607411 5854458 5500728 | FML2112DSI1360 | COD 2021 361369 | AEU7881 | AEG7120 | AEG7080 | 22.01.2022 | * VEHICLE CURRENLTY AT KAROI ENROUTE HARARE | 11.01.2022 | 21.01.2022 | 22.01.2022 | 24.01.2022 | 25.01.2022 | [11 empty] | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * AWAITING VESSEL MAERSK HUACHO TO ARRIVE - ETA 11.01.2022 | * VESSEL IN & WORKING. VEHICLES PLACED ALONGSIDE TO LOAD ONCE UNIT IS AVAILABLE | COLLECTING CONTAINER FROM PORT TODAY, AWAITING BV NUMBER | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | CARGO IS AT OUR FACILITY, AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | LOADING CARGO TODAY AND TRUCK WILL DISPATCH ONCE DONE LOADING | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT BEITBRIDGE SA SIDE AWAITING CLEARANCE | * VEHICLE CURRENLTY AT KAROI ENROUTE HARARE

## 3 X CAT GENSETS-BA1948-49-50 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | PART NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1948 | 1 X CAT DE220E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | F5D03974 ECW05649 KRG10551 | CAT00C71HECW05649 | 5043765 4512509 4507503 | FML 2112DSI1370 | TBA | TBA | TBA | TBA | TBA | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | 17.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR DEPO AWAITING UNPACK | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION
BA1949 | 1 X CAT DE220E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | F5D03963 ECW05648 KRG10518 | CAT00C71LECW05648 | 5043765 4512509 4507503 | FML 2112DSI1370 | TBA | TBA | TBA | TBA | TBA | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | 17.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR DEPO AWAITING UNPACK | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION
BA1950 | 1 X CAT DE220E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | F5D03964 ECW05647 KRG10517 | CAT00C71AECW05647 | 5043765 4512509 4507503 | FML 2112DSI1370 | TBA | TBA | TBA | TBA | TBA | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | 17.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR DEPO AWAITING UNPACK | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION

## 6 X CAT GENSETS-BA1951-52-53-54 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | PART NO | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 10.12.2021 | COMMENTS 13.12.2021 | COMMENTS 14.12.2021 | COMMENTS 15.12.2021 | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 14.01.2022 | COMMENTS 17.01.2022 | COMMENTS 18.01.2022 | COMMENTS 19.01.2022 | COMMENTS 21.01.2022 | COMMENTS 21.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1951 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JM704559 ECW05639 KRG10561 | CAT00C71PECW05639 | 4594459 4594468 4551479 | FML 2112DSI1372 | COD 2021 366 334 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | 18.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24/01/2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD)
BA1952 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JM704557 ECW05626 KRG10521 | CAT00C71KECW05626 | 4594459 4594468 4551479 | FML 2112DSI1372 | COD 2021 366 334 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | 18.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24/01/2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD)
BA1953 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JM704556 ECW05627 KRG10520 | CAT00C71JECW05627 | 4594459 4594468 4551479 | FML 2112DSI1372 | COD 2021 366 334 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | 18.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24/01/2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD)
BA1954 | 1 X CAT DE165E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JM704558 ECW05625 KRG10522 | CAT00C71PECW05625 | 4594459 4594468 4551479 | FML 2112DSI1372 | COD 2021 366 334 | TBA | TBA | TBA | TBA | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD) | 18.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24/01/2022 | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION BOOKED FOR TODAY | * BV INSPECTION COMPLETE - AWAITING BV NUMBER ON BA1955 & BA1957 (CO-LOAD)
BA1955 | 1 X CAT DE110E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | ECL04894 7K304957 JM704455 | CAT00C44HECL04894 | 4512504 4484798 4484946 | TBA | TBA | TBA | TBA | TBA | TBA | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | 18.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24/01/2022 | * CONTAINER IS AT OUR FACILITY AWAITING BV NUMBER | * CONTAINER IS AT OUR FACILITY AWAITING BV NUMBER | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION
BA1957 | 1 X CAT DE110E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JM704446 ECL04895 7K304956 | CAT00C44EECL04895 | 4484946 4512504 4484798 | TBA | TBA | TBA | TBA | TBA | TBA | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION | 18.01.2022 | [15 empty] | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL FINAL BILL AND VESSEL DETAILS | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * AWAITING VESSEL MAERSK HONG KONG TO ARRIVE ON THE 17.01.2022 | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * THE VESSEL IS IN AND WORKING, AWAITING TO LOAD THE CONTAINER | * CONTAINER IS AT OUR FACILITY AWAITING BV TO BE DONE ON MONDAY THE 24/01/2022 | * CONTAINER IS AT OUR FACILITY AWAITING BV NUMBER | * CONTAINER IS AT OUR FACILITY AWAITING BV NUMBER | * UNIT AT OUR FACILITY AWAITING BV NUMBER IN ORDER TO BOOK INSPECTION

## 2 X CAT 428-BA1659-BA1660 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 24.12.2021 | COMMENTS 28.12.2021 | COMMENTS 29.12.2021 | COMMENTS 30.12.2021 | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1660 | 1 X CAT 428 BACHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | L7D00901 | CAT00428HL7D00901 | TBA | TBA | TBA | TBA | TBA | TBA | TBA | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 02.02.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING INVOICE FOR BA1659-VESSEL ETA 01/02/2022 | AWAITING INVOICE FOR BA1659-VESSEL ETA 01/02/2022 | VESSEL ETA 01.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 02.02.2022
BA1659 | 1 X CAT 428 BACHOE LOADER | BARTRAC EQUIPMENT / CONGO EQUIPMENT | L7D00902 | CAT00428EL7D00902 | TBA | TBA | TBA | TBA | TBA | TBA | TBA | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 02.02.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING INVOICE FOR BA1659-VESSEL ETA 01/02/2022 | AWAITING INVOICE FOR BA1659-VESSEL ETA 01/02/2022 | AWAITING INVOICE FOR BA1659-VESSEL ETA 01.02.2022 | WAITING VESSEL MSC CHLOE ARRIVAL - CURRENT ETA 02.02.2022

## 1 X NEW CAT 374-BA1803 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1803 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RGM00284 | CAT00374JRGM00284 | E4T00423 | FML2201DSI1387 | TBA | TBA | TBA | TBA | TBA | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETD-26.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETD-26.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022 | AWAITING BARTRAC INVOICE-VESSEL ADRIATIC HIGHWAY ETA- 27.01.2022

## 4 X CAT 374-BA1850-51-48-49 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 25.01.2022
BA1748 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RGM00280 | CAT00374CRGM00280 | E4T00391 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022
BA1749 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RGM00282 | CAT00374PRGM00282 | E4T00390 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022
BA1850 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RGM00281 | CAT00374TRGM00281 | E4T00427 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022
BA1851 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RGM00283 | CAT00374KRGM00283 | E4T00382 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 31.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022

## 1 X CAT M317D (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1859 | 1 X CAT M317D2 WHEEL EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | CA600785 | CATM317DVCA600785 | 2W230458 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 28/01/2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022 | AWAITING VESSEL RCC AFRICA 013 TO ARRIVE ON THE 30.01.2022

## 2 X CAT CS11-BA1860-BA1861 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1860 | 1 X CAT CS11GC VIBRATORY COMPACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RK801244 | CAT0CS11CRK801244 | MFX11928 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 12/02/2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 10/02/2022 | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 10/02/2022 | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 10/02/2022 | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 12/02/2022
BA1861 | 1 X CAT CS11GC VIBRATORY COMPACTOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RK801246 | CAT0CS11PRK801246 | MFX11938 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 12/02/2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 10/02/2022 | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 10/02/2022 | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 10/02/2022 | AWAITING VESSEL MSC VIDHI ZF201A TO ARRIVE ON THE 12/02/2022

## 1 X CAT 336GC-BA1892 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1892 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JFW20941 | CAT00336EJFW20941 | E7A43821 | TBA | TBA | TBA | TBA | TBA | TBA | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL DUE TO ARRIVE ON THE 31/01/2022 | VESSEL DUE TO ARRIVE ON THE 31/01/2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022

## 3 X CAT 336GC-BA1896-97-91 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1891 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JFW20940 | CAT00336HJFW20940 | E7A43844 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022
BA1896 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JFW20946 | CAT00336JJFW20946 | E7A43868 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022
BA1897 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JFW20945 | CAT00336KJFW20945 | E7A43876 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022

## 4 X CAT 336GC-BA1899-BA1902 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1899 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12127 | CAT00336KGDY12127 | NTB05819 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022
BA1900 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12128 | CAT00336JGDY12128 | NTB05825 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022
BA1901 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12126 | CAT00336PGDY12126 | NTB05800 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022
BA1902 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12124 | CAT00336CGDY12124 | NTB05839 | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING FINAL BARTRAC INVOICES-VESSEL ADRIATIC HIGHWAY ETA-26.01.2022 | AWAITING VESSEL ARRIVAL - ADRIATIC HIGHWAY ETA-27.01.2022

## 1 X CAT 336GC-BA1905 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1905 | 1 X CAT 336GC HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | GDY12133 | CAT00336VGDY12133 | GDY12133 | TBA | TBA | TBA | TBA | TBA | TBA | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | [16 empty] | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL ETA-31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022

## 1 X CAT 374-BA2032 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 07.01.2022 | COMMENTS 10.01.2022 | COMMENTS 11.01.2022 | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA2032 | 1 X CAT 374 HYDRAULIC EXCAVATOR | BARTRAC EQUIPMENT / CONGO EQUIPMENT | RGM00291 | CAT00374LRGM00291 | TBA | TBA | TBA | TBA | TBA | TBA | TBA | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022 | [16 empty] | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | AWAITING FINAL BILL AND INVOICES | VESSEL ETA-31/01/2022 | VESSEL ETA-31/01/2022 | VESSEL ETA-31.01.2022 | VESSEL GRAND PRAVO DUE TO ARRIVE 01.02.2022

## 10 X GENSETS-BA1963-BA1973 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1963 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04964 | CAT00C33JEC507446 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1964 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | KMC04963 | CAT00C33HEC507440 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1965 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04959 | CAT00C33CEC507439 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1966 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04962 | CAT00C33TEC507443 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1967 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMC04960 | CAT00C33CEC507442 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1968 | 1 X CAT DE65E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMC04961 | CAT00C33KEC507445 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1969 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04973 | CAT00C33PEC507444 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1970 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04957 | CAT00C33EEC507455 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1971 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04974 | CAT00C33EEC507441 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022
BA1973 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04972 | CAT00C33CE507456 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | [16 empty] | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022 | AWAITING VESSEL MAERSK HANGZHOU TO ARRIVE ON THE 14/02/2022

## 11 X GENSETS-BA1975-BA1986 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1975 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04976 | CAT00C33JEC305657 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1976 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04965 | CAT00C33AEC305646 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1977 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04966 | CAT00C33LEC305650 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1978 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04970 | CAT00C33HEC305648 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1979 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04968 | CAT00C33PEC305655 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1980 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04979 | CAT00C33LEC305647 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1981 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04975 | CAT00C33CEC305658 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1982 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04980 | CAT00C33VEC305659 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1983 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04978 | CAT00C33EEC305649 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1984 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04969 | CAT00C33KEC305656 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1986 | 1 X CAT DE33E0 | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04967 | CAT00C33VEC305645 | N/A | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS

## 17 X CAT 745 BA1697-2025 (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PIN NUMBER | ENGINE | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1697 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1732 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1786 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1863 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA1864 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2014 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2015 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2016 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2017 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2018 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2019 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2020 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2021 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2022 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2023 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2024 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS
BA2025 | 1 X CAT 745-04A | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | AWAITING FINAL BILL AND VESSEL DETAILS | [16 empty] | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS | AWAITING FINAL BILL AND VESSEL DETAILS

## 9 X GENSETS BA1956-58-60-61-62- (hidden)
CLIENT PO | CARGO DETAILS | CLIENT | SERIAL NUMBER | PART NUMBER | PIN NUMBER | FML REF | BV No. | HORSE REG NO | TRAILER REG NO | MANIFEST NO. | Final Documents Submitted | ACTUAL STATUS | DBN ARR | DBN DISP | POLOKWANE | BBR ARR | BBR DSP | HARARE | CHIRUNDU | LUSAKA | KABWE | KITWE | KASUMBALESA ARR | KASUMBALESA DSP | WHISKY | LUBUMBASHI | ON SITE / CONGO EQUIPMENT | OFFLOADED | COMMENTS 21.01.2022 | COMMENTS 24.01.2022 | COMMENTS 25.01.2022 | COMMENTS 26.01.2022
BA1925 | 1 X CAT DE450E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | DH403810 PWE06229 LWL05151 | 4515066 3932805 5029779 | CAT00C13ADH403810 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1928 | 1 X CAT DE450E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | DH403809 PWE06222 LWL05152 | 4215066 3932805 5029779 | CAT00C13HDH403809 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1956 | 1 X CAT DE110E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | ECL04932 7K305026 JM704588 | 4512504 4484798 4484946 | CAT00C44CECL04932 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1958 | 1 X CAT DE110E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JM704589 ECL04933 7K305047 | 4484946 4512504 4484798 | CAT00C44TECL04933 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1959 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | TBA | TBA | CAT00C44LEC902949 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1960 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JM704584 EC902953 ZRE02959 | 4484943 4512502 4508025 | CAT00C44HEC902953 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1961 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | EC902951 ZRE02958 JM704594 | 4512502 4508025 4484943 | CAT00C44AEC902951 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1962 | 1 X CAT DE88E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JM704593 EC902952 ZRE02957 | 4484943 4512502 4508025 | CAT00C44LEC902952 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1972 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMG04971 EC507457 E3S11959 | 4594403 4985384 5011555 | CAT00C33TEC507457 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1974 | 1 X CAT DE55E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | EC507458 E3S11968 JMG04958 | 4985384 5011555 4594403 | CAT00C33PEC507458 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022
BA1985 | 1 X CAT DE33E0 GENSET | BARTRAC EQUIPMENT / CONGO EQUIPMENT | JMC04977 EC305660 E3S11907 | 4594399 4985380 5010890 | CAT00C33JEC305660 | TBA | TBA | TBA | TBA | TBA | TBA | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022 | * AWAITING VESSEL CMA CGM SAVANNAH ARRIVAL - ETA 21.02.2022